## LegalSizeRegionLoc
ETS Planned Outages - April 1, 2002 Through July 31, 2002
Total Bushton Universe ESD's April / May - Sorted By Start Date / Region
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted February 27, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | EstStart | EstComp | Duration | Region | Location | Units | Title | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
Mullinville South Lean Side ESD's
1 | 18523 | 2002-04-29 08:00 | 2002-04-30 16:00 | 1.3 | AMA | SPEARMAN | ESD & A LINE | ESD & A LINE LEAKS |  | OPS |  | 48 | 64 | Annual ESD. Need to repair several A Line leaks. ESD and back on with 25 mmcf in 4 hours. |  |  |  | 0 | P | N | N
2 | 18522 | 2002-04-30 08:00 | 2002-04-30 12:00 | 0.2 | AMA | BEAVER PLANT | ESD | ESD |  | OPS |  | 600 | 100 | Annual ESD. |  |  |  | 0 | P | N | N
3 | 18524 | 2002-04-30 08:00 | 2002-04-30 16:00 | 0.3 | AMA | NORTHRUP | ALL | ESD |  | OPS |  | 10 | 3.3 | Annual ESD. |  |  |  | 0 | P | N | N
4 | 18525 | 2002-04-30 08:00 | 2002-04-30 16:00 | 0.3 | AMA | PERRYTON BARLOW | ALL | ESD |  | OPS |  | 7 | 2.3 | Annual ESD. |  |  |  | 0 | P | N | N
5 | 18528 | 2002-04-30 08:00 | 2002-04-30 20:00 | 0.5 | AMA | BEAVER 2 | ALL | ESD |  | OPS |  | 10 | 5 | Annual ESD. |  |  |  | 0 | P | N | N
6 | 18526 | 2002-04-30 08:00 | 2002-04-30 20:00 | 0.5 | AMA | SUNRAY | ALL | ESD |  | OPS |  | 144 | 72 | Annual ESD. |  |  |  | 0 | P | N | N
7 | 18465 | 2002-04-30 08:00 | 2002-04-30 20:00 | 0.5 | LIB | BEAVER 1 | ALL | ESD |  | OPS |  | 14 | 7 | Annual ESD. |  |  |  | 0 | P | N | N
8 | 18467 | 2002-04-30 08:00 | 2002-04-30 20:00 | 0.5 | LIB | CLARK 1 | ALL | ESD |  | OPS |  | 6.5 | 3.3 | Annual ESD. |  |  |  | 0 | P | N | N
9 | 18469 | 2002-04-30 08:00 | 2002-04-30 20:00 | 0.5 | LIB | CLARK 2 | ALL | ESD |  | OPS |  | 6 | 3 | Annual ESD. |  |  |  | 0 | P | N | N
10 | 18494 | 2002-04-30 08:00 | 2002-04-30 20:00 | 0.5 | LIB | MULLINVILLE | ALL | ESD |  | OPS |  | 400 | 200 | Annual ESD. |  |  |  | 0 | P | N | N
Holcomb & Field ESD's
1 | 18511 | 2002-05-02 07:30 | 2002-05-02 16:00 | 0.4 | LIB | FINNEY 1 2 3 4 | ALL | ANNUAL ESD |  | OPS |  | 0 | 0 | Annual ESD's for the Finney Co. Stations. 1 2 3 and 4. |  |  |  | 0 | P | N | N
2 | 18408 | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 | LIB | BURDETT | ALL | ANNUAL ESD |  | OPS |  | 0 | 0 | Annual ESD will shut down during the same time as Holcomb's ESD. |  |  |  | 0 | P | N | N
3 | 17839 | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 | LIB | HOLCOMB | ESD | ANNUAL ESD |  | OPS |  | 135 | 22.5 | Annual ESD and maintenance. |  |  |  | 0 | P | N | N
4 | 17840 | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 | LIB | HOLCOMB | HOLCOMB SOUTH | ESD |  | OPS |  | 8 | 1.3 | Outage coordinated with Holcomb's Annual ESD. |  |  |  | 0 | P | N | N
5 | 17757 | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 | LIB | TATE | ALL | ESD |  | OPS |  | 14 | 2.3 | Annual ESD test. |  |  |  | 0 | P | N | N
Hugoton & Field ESD's
6 | 18073 | 2002-05-07 07:30 | 2002-05-07 10:30 | 0.1 | LIB | STEVENS 1 | ALL | ANNUAL ESD |  | OPS |  | 30 | 3.8 | Annual ESD. |  |  |  | 0 | P | N | N
7 | 18493 | 2002-05-07 07:30 | 2002-05-07 10:30 | 0.1 | LIB | STEVENS 3 | ALL | ESD |  | OPS |  | 6 | 0.8 | Annual ESD. |  |  |  | 0 | P | N | N
8 | 17622 | 2002-05-07 07:30 | 2002-05-07 13:00 | 0.3 | LIB | MORTON 1 | ALL | ANNUAL ESD |  | OPS |  | 18 | 4.5 | Annual ESD. |  |  |  | 0 | P | N | N
9 | 17623 | 2002-05-07 07:30 | 2002-05-07 13:00 | 0.3 | LIB | MORTON 6 | ALL | ANNUAL ESD |  | OPS |  | 8 | 2 | Annual ESD. |  |  |  | 0 | P | N | N
10 | 18527 | 2002-05-07 07:30 | 2002-05-07 20:00 | 0.5 | BEA | BUSHTON | ALL | ESD |  | OPS |  | 400 | 216.7 | Annual ESD. We should be able to bypass some volumes through the station using Clifton H.P. |  |  |  | 0 | P | N | N
11 | 17624 | 2002-05-07 07:30 | 2002-05-08 14:00 | 1.3 | LIB | TEXAS 1 | ALL | ANNUAL ESD |  | OPS |  | 10 | 12.9 | Annual ESD. |  |  |  | 0 | P | N | N
12 | 17625 | 2002-05-07 07:30 | 2002-05-08 14:00 | 1.3 | LIB | TEXAS 2 | ALL | ANNUAL ESD |  | OPS |  | 15 | 19.4 | Annual ESD. |  |  |  | 0 | P | N | N
13 | 18089 | 2002-05-07 07:30 | 2002-05-09 16:00 | 2.4 | LIB | HUGOTON | ALL | ESD |  | OPS |  | 80 | 190 | Planned ESD. (Actual completion time depends on contractors). |  |  |  | 0 | P | N | N
14 | 17842 | 2002-05-07 08:00 | 2002-05-07 10:30 | 0.1 | LIB | STEVENS 2 | ALL | ANNUAL ESD |  | OPS |  | 19 | 1.6 | Annual ESD |  |  |  | 0 | P | N | N
15 | 18472 | 2002-05-07 08:00 | 2002-05-07 10:30 | 0.1 | LIB | STEVENS 7 | ALL | ESD |  | OPS |  | 30 | 2.5 | Annual ESD. |  |  |  | 0 | P | N | N
16 | 18473 | 2002-05-07 08:00 | 2002-05-07 14:00 | 0.3 | LIB | SUBLETTE | ALL | ESD |  | OPS |  | 0 | 0 | Annual ESD. (Flow affects are in Hugoton's outage). |  |  |  | 0 | P | N | N
17 | 17895 | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 | LIB | STEVENS 4 | ALL | ANNUAL ESD |  | OPS |  | 18 | 42 | Annual ESD. (Station will be back up when Hugoton comes back on). |  |  |  | 0 | P | N | N
18 | 18471 | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 | LIB | STEVENS 6 | ALL | ESD |  | OPS |  | 18 | 42 | Annual ESD. (The station will be back on line when the Hugoton plant comes back on). |  |  |  | 0 | P | N | N
Beaver Gathering ESD's
1 | 18459 | 2002-05-07 09:00 | 2002-05-07 11:00 | 0.1 | AMA | ELLIS 1 | ALL | ANNUAL ESD |  | OPS |  | 21 | 1.8 | Annual ESD. Will blind flange and not blow the station down. |  |  |  | 0 | P | N | N
2 | 18460 | 2002-05-08 10:00 | 2002-05-08 12:00 | 0.1 | AMA | BEAVER 6 | ALL | ANNUAL ESD |  | OPS |  | 10.5 | 0.9 | Annual ESD. Will blind flange and not blow the station down. |  |  |  | 0 | P | N | N
3 | 18513 | 2002-05-15 09:00 | 2002-05-15 11:00 | 0.1 | AMA | ELLIS 2 | ALL | ESD |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
4 | 18514 | 2002-06-12 09:00 | 2002-06-12 11:00 | 0.1 | AMA | WOODWARD 1 | ALL | ESD |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
5 | 18516 | 2002-06-19 09:00 | 2002-06-19 11:00 | 0.1 | AMA | WOODWARD 3 | ALL | ESD |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
6 | 18515 | 2002-07-17 09:00 | 2002-07-17 11:00 | 0.1 | AMA | WOODWARD 2 | ALL | ESD |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned Outages - April 1, 2002 Through July 31, 2002
Total Bushton Universe ESD's April / May - Sorted By Start Date / Region
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted February 27, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | EstStart | EstComp | Duration | Region | Location | Units | Title | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
Mullinville South Lean Side ESD's
1 | 18523 | 2002-04-29 08:00 | 2002-04-30 16:00 | 1.3 | AMA | SPEARMAN | ESD & A LINE | ESD & A LINE LEAKS |  | OPS |  | 48 | 64 | Annual ESD. Need to repair several A Line leaks. ESD and back on with 25 mmcf in 4 hours. |  |  |  | 0 | P | N | N
2 | 18522 | 2002-04-30 08:00 | 2002-04-30 12:00 | 0.2 | AMA | BEAVER PLANT | ESD | ESD |  | OPS |  | 600 | 100 | Annual ESD. |  |  |  | 0 | P | N | N
3 | 18524 | 2002-04-30 08:00 | 2002-04-30 16:00 | 0.3 | AMA | NORTHRUP | ALL | ESD |  | OPS |  | 10 | 3.3 | Annual ESD. |  |  |  | 0 | P | N | N
4 | 18525 | 2002-04-30 08:00 | 2002-04-30 16:00 | 0.3 | AMA | PERRYTON BARLOW | ALL | ESD |  | OPS |  | 7 | 2.3 | Annual ESD. |  |  |  | 0 | P | N | N
5 | 18528 | 2002-04-30 08:00 | 2002-04-30 20:00 | 0.5 | AMA | BEAVER 2 | ALL | ESD |  | OPS |  | 10 | 5 | Annual ESD. |  |  |  | 0 | P | N | N
6 | 18526 | 2002-04-30 08:00 | 2002-04-30 20:00 | 0.5 | AMA | SUNRAY | ALL | ESD |  | OPS |  | 144 | 72 | Annual ESD. |  |  |  | 0 | P | N | N
7 | 18465 | 2002-04-30 08:00 | 2002-04-30 20:00 | 0.5 | LIB | BEAVER 1 | ALL | ESD |  | OPS |  | 14 | 7 | Annual ESD. |  |  |  | 0 | P | N | N
8 | 18467 | 2002-04-30 08:00 | 2002-04-30 20:00 | 0.5 | LIB | CLARK 1 | ALL | ESD |  | OPS |  | 6.5 | 3.3 | Annual ESD. |  |  |  | 0 | P | N | N
9 | 18469 | 2002-04-30 08:00 | 2002-04-30 20:00 | 0.5 | LIB | CLARK 2 | ALL | ESD |  | OPS |  | 6 | 3 | Annual ESD. |  |  |  | 0 | P | N | N
10 | 18494 | 2002-04-30 08:00 | 2002-04-30 20:00 | 0.5 | LIB | MULLINVILLE | ALL | ESD |  | OPS |  | 400 | 200 | Annual ESD. |  |  |  | 0 | P | N | N
Holcomb & Field ESD's
1 | 18511 | 2002-05-02 07:30 | 2002-05-02 16:00 | 0.4 | LIB | FINNEY 1 2 3 4 | ALL | ANNUAL ESD |  | OPS |  | 0 | 0 | Annual ESD's for the Finney Co. Stations. 1 2 3 and 4. |  |  |  | 0 | P | N | N
2 | 18408 | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 | LIB | BURDETT | ALL | ANNUAL ESD |  | OPS |  | 0 | 0 | Annual ESD will shut down during the same time as Holcomb's ESD. |  |  |  | 0 | P | N | N
3 | 17839 | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 | LIB | HOLCOMB | ESD | ANNUAL ESD |  | OPS |  | 135 | 22.5 | Annual ESD and maintenance. |  |  |  | 0 | P | N | N
4 | 17840 | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 | LIB | HOLCOMB | HOLCOMB SOUTH | ESD |  | OPS |  | 8 | 1.3 | Outage coordinated with Holcomb's Annual ESD. |  |  |  | 0 | P | N | N
5 | 17757 | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 | LIB | TATE | ALL | ESD |  | OPS |  | 14 | 2.3 | Annual ESD test. |  |  |  | 0 | P | N | N
Hugoton & Field ESD's
6 | 18073 | 2002-05-07 07:30 | 2002-05-07 10:30 | 0.1 | LIB | STEVENS 1 | ALL | ANNUAL ESD |  | OPS |  | 30 | 3.8 | Annual ESD. |  |  |  | 0 | P | N | N
7 | 18493 | 2002-05-07 07:30 | 2002-05-07 10:30 | 0.1 | LIB | STEVENS 3 | ALL | ESD |  | OPS |  | 6 | 0.8 | Annual ESD. |  |  |  | 0 | P | N | N
8 | 17622 | 2002-05-07 07:30 | 2002-05-07 13:00 | 0.3 | LIB | MORTON 1 | ALL | ANNUAL ESD |  | OPS |  | 18 | 4.5 | Annual ESD. |  |  |  | 0 | P | N | N
9 | 17623 | 2002-05-07 07:30 | 2002-05-07 13:00 | 0.3 | LIB | MORTON 6 | ALL | ANNUAL ESD |  | OPS |  | 8 | 2 | Annual ESD. |  |  |  | 0 | P | N | N
10 | 18527 | 2002-05-07 07:30 | 2002-05-07 20:00 | 0.5 | BEA | BUSHTON | ALL | ESD |  | OPS |  | 400 | 216.7 | Annual ESD. We should be able to bypass some volumes through the station using Clifton H.P. |  |  |  | 0 | P | N | N
11 | 17624 | 2002-05-07 07:30 | 2002-05-08 14:00 | 1.3 | LIB | TEXAS 1 | ALL | ANNUAL ESD |  | OPS |  | 10 | 12.9 | Annual ESD. |  |  |  | 0 | P | N | N
12 | 17625 | 2002-05-07 07:30 | 2002-05-08 14:00 | 1.3 | LIB | TEXAS 2 | ALL | ANNUAL ESD |  | OPS |  | 15 | 19.4 | Annual ESD. |  |  |  | 0 | P | N | N
13 | 18089 | 2002-05-07 07:30 | 2002-05-09 16:00 | 2.4 | LIB | HUGOTON | ALL | ESD |  | OPS |  | 80 | 190 | Planned ESD. (Actual completion time depends on contractors). |  |  |  | 0 | P | N | N
14 | 17842 | 2002-05-07 08:00 | 2002-05-07 10:30 | 0.1 | LIB | STEVENS 2 | ALL | ANNUAL ESD |  | OPS |  | 19 | 1.6 | Annual ESD |  |  |  | 0 | P | N | N
15 | 18472 | 2002-05-07 08:00 | 2002-05-07 10:30 | 0.1 | LIB | STEVENS 7 | ALL | ESD |  | OPS |  | 30 | 2.5 | Annual ESD. |  |  |  | 0 | P | N | N
16 | 18473 | 2002-05-07 08:00 | 2002-05-07 14:00 | 0.3 | LIB | SUBLETTE | ALL | ESD |  | OPS |  | 0 | 0 | Annual ESD. (Flow affects are in Hugoton's outage). |  |  |  | 0 | P | N | N
17 | 17895 | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 | LIB | STEVENS 4 | ALL | ANNUAL ESD |  | OPS |  | 18 | 42 | Annual ESD. (Station will be back up when Hugoton comes back on). |  |  |  | 0 | P | N | N
18 | 18471 | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 | LIB | STEVENS 6 | ALL | ESD |  | OPS |  | 18 | 42 | Annual ESD. (The station will be back on line when the Hugoton plant comes back on). |  |  |  | 0 | P | N | N
Beaver Gathering ESD's
1 | 18459 | 2002-05-07 09:00 | 2002-05-07 11:00 | 0.1 | AMA | ELLIS 1 | ALL | ANNUAL ESD |  | OPS |  | 21 | 1.8 | Annual ESD. Will blind flange and not blow the station down. |  |  |  | 0 | P | N | N
2 | 18460 | 2002-05-08 10:00 | 2002-05-08 12:00 | 0.1 | AMA | BEAVER 6 | ALL | ANNUAL ESD |  | OPS |  | 10.5 | 0.9 | Annual ESD. Will blind flange and not blow the station down. |  |  |  | 0 | P | N | N
3 | 18513 | 2002-05-15 09:00 | 2002-05-15 11:00 | 0.1 | AMA | ELLIS 2 | ALL | ESD |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
4 | 18514 | 2002-06-12 09:00 | 2002-06-12 11:00 | 0.1 | AMA | WOODWARD 1 | ALL | ESD |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
5 | 18516 | 2002-06-19 09:00 | 2002-06-19 11:00 | 0.1 | AMA | WOODWARD 3 | ALL | ESD |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
6 | 18515 | 2002-07-17 09:00 | 2002-07-17 11:00 | 0.1 | AMA | WOODWARD 2 | ALL | ESD |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N