## Power Projects
Project Name | Enron Business Unit | Project Type I | Project Type/Description | Originator(s) | Responsible EA Tech Services | Technical Support | Location | $$ Exposure | Assessment of Risk | Updated | Update/Comments | EBU | PT1
AMPS | North America - Principal Investing |  | Generation Technology - mobile power units | Michael Miller, Kyle Kitagawa | Bob Virgo | Grigory Zelondzhev | Various |  |  | 2001-06-14 | Working on the marketing questions/issues.
Austin | North America - East |  | Development/Construction - Simple Cycle Project (~180 MW) | Jeff Keenan | Bob Virgo | Eric Booth | Austin, TX |  |  | 2001-05-15 | Construction nearly complete. Estimated completion = May 31, 2001.
Electrobolt | South America | Greenfield | Development/Construction - Simple Cycle Project (386 MW) | Brett Wiggs | Rod Blackham | EEOS | Rio de Janeiro, Brazil |  |  | 2001-05-15 | Site is under development - initial foundations and temporary facilities. 2 of 6 gas turbines to be shipped today to construction site. EEOS/NEPCO are primary parties in construction. Target Operation date = November 1, 2001.
Fort Pierce | North America - East |  | Repower Steam Plant | Dave Fairley | Bob Virgo, Mike Coleman | Darrell Stovall | Ft. Pierce, FL |  |  | 2001-06-28 | Dave Duran to talk with TCO about a potential TCO/Enron joint venture arrangement
Las Vegas Cogen | North America - West |  | Development/Construction - 4x2 LM6000's combined cycle plant | Ed Clark | Wayne Mays | Bob Williams, Bob Chmielewski, Ed Dannhaus | Las Vegas, NV |  |  | 2001-06-14 | Agreement signed with Modern Continental; expecting to finalize on 08/31. Noise mitigation still needs discussion. Sound walls and transmission hardware concerns need to be run to ground.
Longview | North America - West |  | Development/Construction - 4 @2x1 LM6000's combined cycle plant | Jake Thomas | Wayne Mays | Don Hammond, Mark Mullen, Bill Williams | Port of Longview, WA |  |  | 2001-05-15 | Modern Continental South agreed to be EPC for a full project wrap on LED. They will manage four (4) sub-contracters. Scott Co, RCI will be mechanical and civil, respectively. Amec-Simons will be design engineer. Electric is YTBD. Draw down schedule is being prepared. LNTP expected July 1 with FNTP sometime in October if not sooner. Water becoming an issue. Major equipment identified. E-next will be needed.
Roseville | North America - West |  | Site acquisition underway. Seeking to secure emission credits | Mike McDonald | Wayne Mays | Don Hammond | No. California - near Sacramento |  |  | 2001-05-15 | Working on 100% of emissions reduction credits on the 700 MW plant. In discussion with WAPA about transmission topics. Engineering is on the long-term horizon.
TexMex | North America - East |  | Development/Construction - Installation of AC/DC tie, power export to Mexico | Ozzie Pagan | Bob Virgo | Walter Coffer, Scott Laidlaw | Brownsville, TX |  |  | 2001-04-23 | Interface with Brownsville public utility and ABB Engineering. Currently on hold.
Vitro | Mexico | Greenfield | Development/Construction - Combined Cycle Cogen Project (245 MW) | Steve Irvin, Marc Sabine, Max Yzaguirre | Bob Virgo | Ed Elam | Monterrey, Mexico |  |  | 2001-06-18 | Const Mob 03/26/01. Sell down in progress. Contractor's change request under discussion. Applying for co-generation customes exeption.
Midway | North America - East |  | Development - up to 3 x 7FA simple cycle plant | Kreg Krause, Raimund Grube | Bob Virgo |  | St. Lucie Co., FL |  |  | 2001-07-02 | Discussions are underway with TECO regarding a potential TECO/ENRON joint venture arrangement. Further discussions may be pursued with other potential counterparties interested in a 2002/3 COD.
Rio Gen |  |  |  |  | Rod Blackham
Westinghouse (W) 501 D5A Turbines |  |  |  |  | Mike Coleman |  |  |  |  | 2001-06-28 | Enron has one in storage (Ben Jacoby). Team inspecting it today. W201D5A has a generator issue.
Mitsubishi (MHI) 501F Turbines | [9 empty] | 2001-06-28 | Mike Coleman in Japan with Mitsubishi. Three MHI 501F turbines available (Ft. Pierce, Electrobolt II, unassigned).
Ukranian Turbines |  |  |  |  | Bob Virgo
EPC Negotiation Team | Enron Americas | Greenfield | Lead EPC and turbine purchase contract discussions | Lisa Bills, Ron Tapscott, Chip Schneider, John Schwartzenburg | Bob Virgo | Mike Coleman | ENA |  |  | 2001-05-15

## Gas Projects
Project Name | Enron Business Unit | Project Type I | Project Type/Description | Originator(s) | Responsible EA Tech Services | Technical Support | Location | $$ Exposure | Assessment of Risk | Updated | Update/Comments | EBU | PT1
Napoleonville | North America
Crawfish | North America
Crescendo | North America | Greenfield
Oakhill | North America |  | Replacement/Upgrade of two (2) 3,500 hp compressors | Mark Knippa | David Owen |  | Carthage, TX |  |  | 2001-05-14 | Executable pricing still not available. Notional value updated & Hanover's packaging & installation costs received. Meeting with customer on the week of 6/4.
Iroquois | North America |  | Greenfield installation of compresors. Either 17,500 hp or 25,500 hp depending on load | Andrew Miles | David Owen |  | Brookfield, CT |  |  | 2001-06-28 | Iroquois waiting for FERC approval on two (2) potential expansions. One expansion on Eastchester project, another to eastern Long Island, NY to serve new power plant load - will know by end of summer. Either expansion will trigger projects.
Nicor | North America |  | 80,000 - 100,00 HP replacement | Ned Higgins | David Owen |  | Troy Grove, IL |  |  | 2001-05-22 | Preliminary proposal (project specifications and cost estimate) given to commercial originator. Meeting scheduled for 6/12 to present first proposal. Waiting on follow-up technical meeting and additional data.
Anadarko | North America |  | Replacement/Upgrade - 12,500 hp | Ned Higgins | David Owen |  | Panola, TX |  |  | 2001-05-17 | ENA Facility Planning prepared a "ist pass" scoping document and cost estimate. A meeting is scheduled for Monday 6/4 to present a proposed term sheet.
Questar | North America |  | Base gas monetization | Paul Bieniawski, Eva Rainer | Gary Wilson | Walter Coffer, Scott Laidlaw | Utah |  |  | 2001-04-18 | Early stage. Evaluating regulatory issues with ENA Regulatory Affairs.