## Sundevil by Task by Month
|  |  |  | PROJECT SUNDEVIL TASK LIST AND CASH FLOW ESTIMATE FOR ENVIRONMENTAL PROGRAMS | [15 empty] | PROJECT SUNDEVIL TASK LIST AND CASH FLOW ESTIMATE FOR ENVIRONMENTAL PROGRAMS
6792-162 | [14 empty] | 6792-162
| TOTAL | 2001 |  |  |  | 2002 | [11 empty] | 2003
| COSTS | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Task
Data Collection & Review | TOTAL COSTS: 30000; 2001 SEP: 5000; 2001 OCT: 20000; 2001 NOV: 5000
Agency Consultation | 60000 | 5000 | 10000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
Route Selection | TOTAL COSTS: 30000; 2001 SEP: 5000; 2001 OCT: 20000; 2001 NOV: 5000
Habitat/Land Use Surveys | TOTAL COSTS: 30000; 2001 OCT: 15000; 2001 NOV: 15000
T&E Species Surveys | TOTAL COSTS: 160000; 2002 MAR: 32000; 2002 APR: 32000; 2002 MAY: 32000; 2002 JUN: 32000; 2002 JUL: 32000
Wetland Delineation & Report | TOTAL COSTS: 120000; 2002 MAR: 10000; 2002 APR: 20000; 2002 MAY: 60000; 2002 JUN: 30000
Cult. Res. Survey/Report | TOTAL COSTS: 750000; 2001 OCT: 25000; 2001 NOV: 200000; 2001 DEC: 200000; 2002 JAN: 50000; 2002 FEB: 50000; 2002 MAR: 25000; 2002 APR: 25000; 2002 MAY: 25000; 2002 JUN: 25000; 2002 JUL: 25000; 2002 AUG: 25000; 2002 SEP: 25000; 2002 OCT: 25000; 2002 NOV: 25000
Cult. Res. Testing/Mitigation | TOTAL COSTS: 1250000; 2002 MAY: 100000; 2002 JUN: 200000; 2002 JUL: 200000; 2002 AUG: 200000; 2002 SEP: 200000; 2002 OCT: 200000; 2002 NOV: 150000
Cultural Resources Mgt. | 135000 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500
FERC Resource Reports | TOTAL COSTS: 100000; 2001 SEP: 5000; 2001 OCT: 16000; 2001 NOV: 16000; 2001 DEC: 16000; 2002 JAN: 16000; 2002 FEB: 16000; 2002 MAR: 15000
FERC Data Requests | TOTAL COSTS: 20000; 2002 MAY: 10000; 2002 JUN: 10000
Biological Assessment | TOTAL COSTS: 30000; 2001 OCT: 5000; 2001 NOV: 5000; 2001 DEC: 5000; 2002 JAN: 5000; 2002 FEB: 5000; 2002 MAR: 5000
Map/Alig. Sheet Review | TOTAL COSTS: 15000; 2001 OCT: 2500; 2001 NOV: 2500; 2001 DEC: 2500; 2002 JAN: 2500; 2002 FEB: 2500; 2002 MAR: 2500
Section 404 Permits | TOTAL COSTS: 25000; 2002 JUN: 5000; 2002 JUL: 5000; 2002 AUG: 10000; 2002 SEP: 5000
404 Conditions Follow-up | TOTAL COSTS: 11000; 2002 OCT: 1000; 2002 NOV: 5000; 2002 DEC: 5000
Air Quality Permits | TOTAL COSTS: 40000; 2002 JAN: 5000; 2002 FEB: 5000; 2002 MAR: 5000; 2002 APR: 5000; 2002 MAY: 5000; 2002 JUN: 5000; 2002 JUL: 5000; 2002 AUG: 5000
Withdrawal/Discharge Permits | TOTAL COSTS: 25000; 2002 APR: 5000; 2002 MAY: 5000; 2002 JUN: 5000; 2002 JUL: 5000; 2002 AUG: 5000
Agency/Public Meetings | TOTAL COSTS: 140000; 2001 SEP: 10000; 2001 OCT: 20000; 2001 NOV: 20000; 2001 DEC: 10000; 2002 JAN: 10000; 2002 FEB: 10000; 2002 MAR: 10000; 2002 JUN: 10000; 2002 JUL: 10000; 2003 MAY: 10000; 2003 JUL: 10000; 2003 SEP: 10000
Coordination Meetings | 180000 | 10000 | 10000 | 10000 | 10000 | 10000 |  | 10000 | 10000 | 10000 |  | 10000 |  | 10000 |  | 10000 | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 10000
Project Management | 350000 | 10000 | 20000 | 20000 | 20000 | 16250 | 16250 | 16250 | 16250 | 16250 | 11250 | 6250 | 6250 | 6250 | 6250 | 6250 | 6250 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500
GIS Web Page Mgt. | 70000 | 2500 | 5000 | 7500 | 5000 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
Env. Compliance Plan Prep. | TOTAL COSTS: 50000; 2002 OCT: 10000; 2002 NOV: 20000; 2002 DEC: 20000
EIS Review and Input | TOTAL COSTS: 10000; 2002 NOV: 5000; 2002 DEC: 5000
Implementation Plan Prep. | TOTAL COSTS: 10000; 2002 NOV: 5000; 2002 DEC: 5000
Permit Book Preparation | TOTAL COSTS: 15000; 2002 NOV: 5000; 2002 DEC: 5000; 2003 JAN: 5000
Permit Compliance Tracking | TOTAL COSTS: 35000; 2002 NOV: 2500; 2002 DEC: 2500; 2003 JAN: 2500; 2003 FEB: 2500; 2003 MAR: 2500; 2003 APR: 2500; 2003 MAY: 2500; 2003 JUN: 2500; 2003 JUL: 2500; 2003 AUG: 2500; 2003 SEP: 2500; 2003 OCT: 2500; 2003 NOV: 2500; 2003 DEC: 2500
Env. Inspector Mgt. | TOTAL COSTS: 60000; 2003 JAN: 5000; 2003 FEB: 5000; 2003 MAR: 5000; 2003 APR: 5000; 2003 MAY: 5000; 2003 JUN: 5000; 2003 JUL: 5000; 2003 AUG: 5000; 2003 SEP: 5000; 2003 OCT: 5000; 2003 NOV: 5000; 2003 DEC: 5000
Env. Inspector Subcontract | TOTAL COSTS: 3168000; 2002 DEC: 132000; 2003 JAN: 264000; 2003 FEB: 264000; 2003 MAR: 264000; 2003 APR: 264000; 2003 MAY: 264000; 2003 JUN: 264000; 2003 JUL: 264000; 2003 AUG: 264000; 2003 SEP: 264000; 2003 OCT: 264000; 2003 NOV: 264000; 2003 DEC: 132000
Discharge Water Analysis | TOTAL COSTS: 15000; 2003 OCT: 5000; 2003 NOV: 5000; 2003 DEC: 5000
Env. Training Support | TOTAL COSTS: 15000; 2002 NOV: 4000; 2002 DEC: 4000; 2003 JAN: 4000; 2003 FEB: 2000; 2003 MAR: 1000
Field Support | TOTAL COSTS: 35000; 2002 NOV: 2500; 2002 DEC: 2500; 2003 JAN: 2500; 2003 FEB: 2500; 2003 MAR: 2500; 2003 APR: 2500; 2003 MAY: 2500; 2003 JUN: 2500; 2003 JUL: 2500; 2003 AUG: 2500; 2003 SEP: 2500; 2003 OCT: 2500; 2003 NOV: 2500; 2003 DEC: 2500
Restoration Support | TOTAL COSTS: 15000; 2003 SEP: 2500; 2003 OCT: 2500; 2003 NOV: 5000; 2003 DEC: 5000
Third Party Contractor | 550000 |  | 10000 | 28000 | 28000 | 28000 | 28000 | 28000 | 32000 | 38000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 25000 | 25000
Total For Month |  | 60000 | 186000 | 344500 | 307000 | 155750 | 145750 | 171750 | 158250 | 314250 | 386250 | 351250 | 304250 | 299250 | 294250 | 292250 | 249250 | 332000 | 335000 | 291500 | 298500 | 298500 | 298500 | 298500 | 298500 | 301000 | 306000 | 296500 | 174500
Grand Total to Date |  | 60000 | 246000 | 590500 | 897500 | 1053250 | 1199000 | 1370750 | 1529000 | 1843250 | 2229500 | 2580750 | 2885000 | 3184250 | 3478500 | 3770750 | 4020000 | 4352000 | 4687000 | 4978500 | 5277000 | 5575500 | 5874000 | 6172500 | 6471000 | 6772000 | 7078000 | 7374500 | 7549000
Grand Total | TOTAL COSTS: 7549000; 2002 AUG: Revised 09/25/01; 2003 NOV: Revised 09/25/01