## EOL Countries
|  | ENRONONLINE WORLDWIDE PRESENCE STATUS |  |  |  | as of: | 2000-08-24
Note: "New American Countries" information has not been updated since August 15th.
THE AMERICAS
# | Available at: |  |  | In the works: | Business Unit | Responsibility | Scheduled for: | Comments:
1 | Canada |  | 1 | Argentina | Enron Argentina | M. Taylor | 2000-09-01 | 08/15 Draft of legal Documents later this week.
2 | United States |  | 2 | Bermuda |  | M. Taylor | to be determined | 08/15 No date yet. Mark Taylor is checking and will get back to us.
3 | Mexico |  | 3 | Brazil | Enron Brazil | M. Taylor | to be determined | 08/15 No date yet.
4 |  |  | 4 | Chile | MG | M. Taylor | 2000-08-01 | 08/15 More info Wed.
5 |  |  | 5 | Colombia | Enron Coal / MG | M. Taylor | 2000-09-01 | 08/15 Mark Taylor is restarting process.
6 |  |  | 6 | Peru | MG | M. Taylor | 2000-08-01 | 08/15 More info Wed.
7 |  |  | 7
8 |  |  | 8
9 |  |  | 9
AFRICA
# | Available at: |  |  | In the works: | Business Unit | Responsibility | Scheduled for: | Comments:
1 |  |  | 1 | South Africa | Enron Coal | Edmund | to be determined | 08/15 No date yet. 8/22 Issue: South Africans can not make payments to non-residents without approval of Reserve Bank. Reserve Bank gives no approvals to South Africans in respect of commodity or derivative transactions with foreign counterparties.
2 |  |  | 2
ASIA / AUSTRALIA
# | Available at: |  |  | In the works: | Business Unit | Responsibility | Scheduled for: | Comments:
1 | Australia |  | 1 | China | MG | Edmund | to be determined | 8/22 Commodity derivatives trading within China is not promoted unless it takes place on a domestic futures exchange.
2 | Japan |  | 2 | Hong Kong | MG | Edmund | to be determined | 8/15 Initial and follow up advice received. Further clarification still needed.
3 | Singapore |  | 3 | Israel | Seafreight | Edmund | to be determined | 8/15 Initial outside legal responses received. Issues need clarification. 8/22 Advise outstanding: due at end of August.
4 |  |  | 4 | South Korea | ? | ? | to be determined | 8/15 Need to confirm status.
5 |  |  | 5
6 |  |  | 6
7 |  |  | 7
8 |  |  | 8
9 |  |  | 9
EUROPE
# | Available at: |  |  | In the works: | Business Unit | Responsibility | Scheduled for: | Comments:
1 | Austria |  | 1 | Russia | MG | Edmund | to be determined | 8/15 Initial and follow up advice received. Further clarification still needed. 8/22 Issues; A) Risk of non-deliverable transactions not unforeseeable. B) Payments in foreign currency might require case-by-case consent from Central Bank. C) Every trade with a Russian counterparty needs to be documented in writing.
2 | Belgium |  | 2 | Greece | Seafreight | Edmund | 2000-07-31 | 8/15 Initial outside legal responses received. Issues need clarification. 8/22 There are significant restrictions on trading in gas and power. In addition, only companies possessing a license issued by the Ministry of Development can trade oil. No License needed only permission from Capital Mkt.. Committee.
3 | Croatia |  | 3 | Turkey | Seafreight | Edmund | 2000-07-31 | 8/15 Initial outside legal responses received. 8/22 For enforceability a hard copy of an umbrella agreement should be signed. Follow up advice awaited!!!
4 | Czech Republic |  | 4
5 | Denmark |  | 5
6 | Finland |  | 6
7 | France |  | 7
8 | Germany |  | 8
9 | Ireland |  | 9
10 | Italy |  | 10
11 | Netherlands |  | 11
12 | Norway |  | 12
13 | Poland |  | 13
14 | Portugal |  | 14
10 | Romania |  | 15
16 | Slovenia
17 | Spain
18 | Sweden
19 | Switzerland
20 | United Kingdom

## EOL New Products
|  | ENRONONLINE NEW PRODUCTS STATUS |  |  |  | as of: | 2000-08-24
Note: Due to the Launch of Phase II all new products types and auctions development has been postponed.
TRANSACTIONAL PRODUCTS
# | Commodity | Product | Country | Business Unit | Responsibility | Status | Scheduled for | Comments
1 | Power | PHY Fwd | Argentina | Enron Argentina | Dale Neuner | In Test | 2000-09-01 | 08/16 Products is on test. Argentina is a post Phase II Launch. Legal issues being resolved.
2 | Power | FIN Swap | Argentina | Enron Argentina | Dale Neuner | In Test | 2000-09-01 | 08/16 Products is on test. Argentina is a post Phase II Launch. Legal issues being resolved.
3 | Gas | PHY Fwd | Argentina | Enron Argentina | Dale Neuner | In Test | 2000-09-01 | 08/16 Two products are on test. Argentina is a post Phase II Launch.
4 | Gas | Fin Options | US | Gas | Dale Neuner | Pending | TBD | 08/23 On hold due to Phase II
5 | AUS and JPN Weather | Weather Options | US | Weather | Dale Neuner | Pending | TBD | 08/23 On hold due to Phase II
6 | Advertising Blocks? | Advertisement Market | US | EBS | Dale Neuner | Pending | TBD | 08/23 EBS is reviewing legal issues.
7 | Gas | Transportation | US | EPG | Savita Puthigai | Draft | 2000-09-01 | 08/23 Working on descriptions and GTC.
8 | Gas | Fin Spread | US | Gas | Dale Neuner | Draft | TBD | 08/23 Product for internal use only to hedge between Nymex and HeHub.
9 | Paper | Phy Paper OCC Ex-works | US | Pulp and Paper | Dale Neuner | Initial Review | TBD | 08/23 Desk is working on logistics and legal issues.
10 | Singapore FX | Singapore FX | London will manage | FX desk | Anna | On hold | TBD | 08/23 On hold by request of commercial group
11 | Brent | Brent/Dubai Spread | London will manage | Crudes | Anna / Arfan | Draft | TBD | 08/23 On hold due to Phase II
12 | Tanker Freight | Tanker Freight | London | Oil | Caroline/ Anna | Draft | 2000-09-01 | 08/23 On hold due to Phase II. Legal reviewing.
13 | Marine Bunkers | Marine Bunkers | London | Oil | Caroline/ Anna | Draft | 2000-09-01 | 08/23 On hold due to Phase II
14 | Metals | Metals LME x5 | London | MG | Lara/Arfan | Draft | 2000-09-01 | 08/23 On hold due to Phase II
15 | Power | German Power Options | Germany | Power | Anna / Imelda | Draft | TBD | 08/23 On hold due to Phase II
16
17
18
19
20
AUCTION PRODUCTS
# | Commodity | Product | Country | Business Unit | Responsibility | Status | Scheduled for | Comments
1 | Power | Capacity Generation | US | Power Desk | David Portz | Text in Draft | 2000-09-01 | 8/16 Making changes to text draft. The launch will be post Phase II
2 | Gas | Transportation Cap. | US | NGPL | Steve Hotte | Text in Draft | 2000-09-01 | 8/16 Making changes to text draft. The launch will be post Phase II
3 | Gas | Transportation Cap. | US | FGT | Steve Hotte | Text in Draft | 2000-09-01 | 8/16 Making changes to text draft. The launch will be post Phase II
4 | Coal | Coal Auction | US | Coal | John Massey | Text in Draft | TBD | 8/21 Coal group working on text draft
5
6
7
8
9
10