## EOL New Countries
|  | ENRONONLINE WORLDWIDE PRESENCE |  |  |  |  | as of: | 2000-11-27
Notes:
THE AMERICAS
# | Available at: |  |  | In the works: | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 11/17/00 | Status as of 11/24/00 | Scheduled for: | Comments:
1 | Canada |  |  | Brazil | Enron Brazil | Remy Collognes | Leonardo Pacheco | M. Taylor | Draft | Draft | TBD | 08/15 No date yet. 8/31 No update. 10/20 Brent Hendry is reviewing preliminary drafts from outside counsel.
2 | United States |  |  | Colombia | Enron Coal / Enron Metals | Waiting on Info | Mark Taylor/ Amita Gosalia | M. Taylor | Draft | Draft | TBD | 08/15 Mark Taylor is restarting process. 8/31 M. Taylor to obtain ETA. Brent working on.10/20 Brent Hendry is reviewing preliminary drafts from outside counsel
3 | Mexico
4 | Chile
5 | Bermuda
6 | Peru
7 | Argentina
AFRICA
# | Available at: |  |  | In the works: | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 11/17/00 | Status as of 11/24/00 | Scheduled for: | Comments:
1 | South Africa
ASIA / AUSTRALIA
# | Available at: |  |  | In the works: | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 11/17/00 | Status as of 11/24/00 | Scheduled for: | Comments:
1 | Australia |  |  | South Korea | Enron Metals | David Lilley | Amita Gosalia | Matt Lee | Draft | Draft | TBD | 8/15 Need to confirm status. 8/31 Matt Lee will update. 10/5 Derivative trades need Central bank's approval. Korean law may require amendments to ETA-awaiting legal advice. 11/3 The only possible amendment to the ETA would be to recite that LME Contracts are conducted through Enron Metals Limited (Korean Branch), the local futures broker. LME Contracts qualify as "overseas futures" under the Korean futures law, and accordingly must be conducted through a local futures broker. Enron Metals Limited (Korean Branch) is a local futures broker and we are intending to approach the regulator (the FSS) for a ruling that we can effect LME Contracts via EOL "through" Enron Metals Limited (Korean Branch). No issues for physical metals trades.
2 | Japan |  |  | China | Enron Metals | Bruce Garner | Amita Gosalia | Justin Boyd | Approved | Approved | TBD | 8/22 Commodity derivatives trading within China is not promoted unless it takes place on a domestic futures exchange. 9/22 Gas and power cannot be traded, waiting for metal, coal and oil. 10/5 Approved to trade OTC forwards from overseas base. Await info re: other derivatives and physical metal, coal and oil. 11/3 Commodity derivatives: cannot trade these as there is no express legal basis under PRC law. Other legal restrictions also apply. LME Contracts: (i) physical marketing in PRC should be avoided and marketing should be restricted to PRC counterparties with an established trading record, and (ii) PRC counterparties are required to obtain business permit and other governmental licences to conduct overseas commodity futures trading (this will involve Enron Metals Limited and the LME being designated as approved bodies). Generally free to buy/sell physical copper for delivery in-warehouse in PRC. Natural gas/electric power: cannot trade, foreign participation prohibited. Await advice in relation to physical trading of coal and oil.
3 | Singapore
4 | Hong Kong
5 | Taiwan
6 | Israel
EUROPE
# | Available at: |  |  | In the works: | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 11/17/00 | Status as of 11/24/00 | Scheduled for: | Comments:
1 | Austria |  | 1 | Greece | Seafreight | David Lilley | Amita Gosalia | Justin Boyd | Draft | Completed | 2000-09-01 | 8/15 Initial outside legal responses received. Issues need clarification. 8/22 There are significant restrictions on trading in gas and power. In addition, only companies possessing a license issued by the Ministry of Development can trade oil. No License required only permission from Capital Mkt. Committee. 9/22 waiting on legal advice on metal, coal, and oil. 10/5 Free to trade commodity derivatives but need permission to solicit within Greece. Physical trading of electricity and gas not permitted. Awaiting legal advice on physical trades in metal, coal and oil. 10/20 Physical trading of coal and metals permitted. Seeking clarity re physical trading of crude, electricity and gas. 11/6 Free to trade commodity derivatives but need permission to solicit within Greece. The costs of such approval will be limited to nominal administrative costs and legal expenses – it is difficult to determine the time it would take to obtain such approval, given the infrequency of the procedure being used. Physical trading of crude, electricity and gas not permitted without a licence - this only relates to trading activities within Greece. Physical trading of coal and metal is permitted. 11/24 Completed
2 | Belgium |  | 2 | Turkey | Seafreight | David Lilley | Amita Gosalia | Justin Boyd | Draft | Draft | 2000-09-01 | 8/15 Initial outside legal responses received. 8/22 For enforceability a hard copy of an umbrella agreement should be signed. Follow up advice awaited!!! 9/22 ETA and PA needs to be adapted for Turkish law. 10/5 Free to trade commodity derivatives. Await advice in relation to physical trading. Law may require changing the ETA and PA. 10/20 ETA and PA amended. Trading and marketing of commodity derivatives requires prior approval of Turkish Capital Markets Board. 11/3 After further discussions with Counsel, it seems that the prior approval of the Turkish Capital Markets Board is only required for marketing (including via the Internet) to the public at large; no approval would therefore apply to our trading activities. A further adaptation of the ETA is required to take into account Turkish currency law matters. 11/17 Time required for the approval from Turkish Capital Markets Board is estimated at 3 months.
3 | Croatia |  | 3 | Monaco | Enron Metals | Tim Jones | Amita Gosalia | Justin Boyd | Review | Completed | TBD | 11/3 New due diligence surveys have been sent to Counsel in this jurisdiction. 11/17 Trading of physical metals and metals derivatives is permitted. It is important, for regulatory purposes, that trades are negotiated and concluded by the applicable Enron trading entity without any physical presence in Monaco. 11/24 Completed for metals only
4 | Czech Republic |  | 4 | Slovakia | Cont Power | Guther Tuhy | Amita Gosalia | Justin Boyd |  | Review | TBD | 11/3 New due diligence surveys have been sent to Counsel in this jurisdiction.
5 | Denmark |  | 5 | India | Enron Metals | Eric Gadd | Amita Gosalia | Justin Boyd |  |  | TBD | 11/24 New due diligence surveys have been sent to Counsel in this jurisdiction.
6 | Finland
7 | France
8 | Germany
9 | Ireland
10 | Italy
11 | Latavia
12 | Netherlands
13 | Norway
14 | Poland
15 | Portugal
16 | Romania
17 | Russia
18 | Slovenia
19 | Spain
20 | Sweden
21 | Switzerland
22 | United Kingdom
Print Report

## EOL New NA Products
|  | ENRONONLINE NEW PRODUCTS STATUS Managed by US office |  |  |  | as of: | 2000-11-27
TRANSACTION PRODUCTS
# | Commodity | Product | Country/Location | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 11/17/00 | Status as of 11/24/00 | Scheduled for | Comments
1 | Advertising Blocks (Nielsen Ratings) | Advertisement Market | US | EBS | Stephen Barth | Leonardo Pacheco | Dale Neuner | Pending | Pending | TBD | 08/23 EBS is reviewing legal issues. 09/07 Met with S. Barth (EBS) to discuss. They will work on defining the products and then get back to us.
2 | Bandwidth | US Bandwidth STM-1 | US | EBS | Jay Hawthorn | Robert Cass | Robert Cass | Draft | Approved | 2000-11-01 | 11/03 Need product in test. Test site is unavailable until 11/6. 11/10 Product is pending legal review. 11/17 Product scheduled for release on 11/20. 11/24 Product missed upload but now scheduled for 11/28
3 | Crude | US WTI Fin Swap (Basis) | US | Petchems | Rob Fuller | Robert Cass | Robert Cass | Draft | Draft | 2000-11-01 | 11/03 Need product in test. Test site is unavailable until 11/6. 11/10 Product in Test
4 | FX | Internal FX Forward Swap | US | FX | William Stuart | Robert Cass | Robert Cass | Reviewing | Reviewing | TBD | 10/13 Japanese and European Currency Swaps. Pending tax and legal updates.
5 | Gas | Fin Options | US | Gas | Pete Keavey | Dale Neuner | Dale Neuner | Test | Test | TBD | 08/23 On hold due to Phase. II 9/22 Savita and Dale finalizing language for delivery to Legal. 10/20 Product description under review by David Forster 11/03 Product is being developed in Test, circulated for comments from legal et al.
6 | Gas | Fin Spread | US | Gas | Pete Keavey | Dale Neuner | Dale Neuner | Draft | Draft | TBD | 08/23 Product for internal use only to hedge between Nymex and HeHub. 9/14 products will bridge similar to other basis products. 9/22 Forster provided suggested language, Neuner will modify and send to Peter
7 | Gas | Transportation | US | EPG | Steve Hotte | Savita Puthigai | Legal and Commercial | Draft | Draft | 2000-10-01 | 08/23 Working on descriptions and GTC. 8/31 Product Descriptions and Legal being reviewed. "Chinese Wall" type concerns being reviewed by Legal. 9/07 Reviewing issues related to GPG and ENA information (comply with regulation) 9/14 need to segregate marketing affiliates using Chinese Walls- Preparing list of Proprietary system issues; may include HPL products. 9/22 Meeting held with PCH Managers-Torrey to follow up with Scott Mills-Sitara issues, Torrey will write questions to IT regarding segregation of mktg affiliates
8 | Gas | Secondary Capacity - Pipeline | US | Gas | Colleen Sullivan | Carlos Alatorre | Carlos Alatorre | Test | Approved | 2000-11-01 | 11/10 Product scheduled for release on 11/15. 11/24 Done
9 | Mixed Xylene | US Mixed Xylene Fin Swap | US | Petchems | John Nowlan | Robert Cass | Melba Lozano | Draft | Approved | 2000-11-01 | 11/03 Need product in test. Test site is unavailable until 11/6. 11/10 Product schedule for release on 11/20. 11/17 Product scheduled for release on 11/20. 11/24 Product released
10 | Nitrate Toluene | US Nitrate Toluene Fin Swap | US | Petchems | John Nowlan | Robert Cass | Melba Lozano | Draft | Approved | 2000-11-01 | 11/03 Need product in test. Test site is unavailable until 11/6. 11/10 Product scheduled for release on 11/20. 11/17 Product scheduled for release on 11/20. 11/24 Product released
11 | Paper | Phy Paper OCC Ex-works | US | Pulp and Paper | Jeff Harbert | Robert Cass | Robert Cass | Reviewing | Reviewing | TBD | 08/23 Desk is working on logistics and legal issues. 9/28 16 created products for ClickPaper.com, awaiting set-up on EOL pending Commercial and Technical issues.
12 | Power | Hourly Power | Us | Power | Rudy Acevedo | Robert Cass | Melba Lozano | Test | Test | TBD | 9/22 Dale is trying to tie the Loadshape to the Date/Time Stamp in the Transaction Results screen, then language will go to Legal. 10/20 Product is in test
13 | Power | FIN Swap | Us | Enron Argentina | Patrick Hansen | Carlos Alatorre | Dale Neuner | Reviewing | Reviewing | 2000-09-01 | 08/16 Two products are on test. Argentina is a post Phase II Launch. 8/31 GTC reviewed and sent to Legal. 09/06 Pending until after Version 2.0 Launch. 9/14 PA and ETA received from ARG, legal description approved by Houston legal and forwarded to ARG Legal, set for testing during ARG visit. 11/17 Reviewing regulatory issues.
14 | Power | PHY Fwd | Us | Enron Argentina | Patrick Hansen | Carlos Alatorre | Dale Neuner | Reviewing | Reviewing | 2000-09-01 | 08/16 Two products are on test. Argentina is a post Phase II Launch. 8/31 GTC reviewed and sent to Legal. 09/06 Pending until after Version 2.0 Launch. 9/14 PA and ETA received from ARG, legal description approved by Houston legal and forwarded to ARG Legal, set for testing during ARG visit. 11/17 Reviewing regulatory issues.
15 | Power (Canadian) | Alberta Power Fin Swap - | Canada | Canada Power | Bill Greenizan | Robert Cass | Melba Lozano | Reviewing | Test | TBD | 11/17 Product request being reviewed - 3 descriptions (1 Product Type) On Peak Power; Off Peak Power, Flat Power. 11/24 In Test
16 | Power (weather desk) | US Power Fin Swap | US | Weather | Kevin Presto | Robert Cass | Robert Cass | Approved | Approved | 2000-11-01 | 11/03 Product to be released
17 | Pulp and Paper | US Lumber Phy | US | Pulp and Paper | Jeff Harbert | Robert Cass | Robert Cass | Test | Test | TBD | 9/28 in Draft.10/05 Products created in test, commercial team will only use Clickpaper until comfortable with running position on both websites.11/03 Nine new lumber products and one revised product
18 | Pulp and Paper | US Pulp Phy | US | Pulp and Paper | Jeff Harbert | Robert Cass | Robert Cass | Test | Test | TBD | 9/28 in Draft.10/05 Products created in test, commercial team will only use Clickpaper until comfortable with running position on both websites.
19 | Weather | Hong Kong Weather | Hong Kong | Australia | Paul Quilkey | Justin Timothy | Justin / Robert | Draft | Draft | 2000-11-01 | 11/03 Australia product being finalized in USA (backup team). Product needs GTC's before it can be released. Early release is requested by Australia. 11/10: Update this item has been revised to allow Hong Kong locations for current Australia product. As such it is not a new product. Australia Product will be amended with a new GTC from Legal to cover Hong Kong reference locations. History of entry: Australia product being finalized in USA (backup team). Product needs GTC's before it can be released. Early release is requested by Australia. 11/17 Creation of a world weather product is being reviewed that would accommodate this Australian Product with Hong Kong location.
AUCTION PRODUCTS
# | Commodity | Product | Country/Location | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 11/17/00 | Status as of 11/24/00 | Scheduled for | Comments
1 | Coal | Coal Auction | US | Coal | John Massey | Leonardo Pacheco | John Massey | Text in Draft | Text in Draft | TBD | 8/21 Coal group working on text draft
2 | Gas | Transportation Cap. | US | FGT | Steve Hotte | Leonardo Pacheco | Steve Hotte | Text in Draft | Text in Draft | 2000-09-01 | 8/16 Making changes to text draft. The launch will be post Phase II 09/07 On hold for Phase II. 10/05 Auction being reviewed
3 | Gas | Transportation Cap. | US | NGPL | Steve Hotte | Leonardo Pacheco | Steve Hotte | Text in Draft | Text in Draft | 2000-09-01 | 8/16 Making changes to text draft. The launch will be post Phase II 09/07 On hold for Phase II. 10/05 Auction being reviewed
4 | Power | Capacity Generation | US | Power Desk | Ed Baughman | Leonardo Pacheco | David Portz | Text in Draft | Text in Draft | TBD | 8/16 Making changes to text draft. The launch will be post Phase II 09/07 On hold for Phase II. 10/05 Auction being reviewed
5
6
7
8
9
10

## EOL New London Products
|  | ENRONONLINE NEW PRODUCTS STATUS Managed by London Office |  |  |  |  | as of: | 2000-11-27
TRANSACTION PRODUCTS
# | Commodity | Product | Country/Location | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 11/17/00 | Status as of 11/24/00 | Scheduled for | Comments
| Belgian Gas | Belgian Gas | London | Gas | Carsten Sterz | Amita Gosalia | Arfan | On hold | On hold | 2000-10-02 | 9/14 On hold
| Broadband | Bandwidth Co-location space | London | Broadband | Nick Brewer | Amita Gosalia | Imelda |  |  |  | 11/10 Awaiting commercial sponsor and information
| Bullion | Gold and Silver | London | Metals | Peter Shluter | Amita Gosalia | Caroline / Lara |  | Reviewing | TBD | 11/3 Meeting with trader to be set up. 11/10 Due dilligence commenced. Long descriptions being drafted
| Coal | Seafreight Average Time Charter - amend existing product | London | Coal | Pierre Aury | Amita Gosalia | Marie | Draft | Draft |  | 11/17 Awaiting new Sigma factor
| Coal | Seafreight Average Time Charter | London | Coal | Pierre Aury | Amita Gosalia | Anna | Reviewing | Reviewing |  | 11/17 Expected to go live Dec 4th
| Crude | Brent/Dubai Spread | London | Crudes | John Crismar | Amita Gosalia | Marie | Approved | Approved | 2000-10-01 | 08/23 On hold. 9/22 Long Description received from Singapore 10/5 Approved, should be Active on 9th 10/20 Awaiting approval from Chrismar
| Dutch Gas | Dutch Gas NLG/M3 | London | Gas | Carsten Sterz | Amita Gosalia | Arfan | Approved | Approved | 2000-10-01 | 9/14 On Draft. 9/22 Available to launch 10/20 Mark D to contact Dave F, 11/03 Awaiting response from Dave F. 11/17 Go live Nov 20th 11/24 Go live postponed as traders wish to show prices to 2 decimal places - not poss due to conversion using FX Mgr.
| Fuel Oil | SG East-West Fuel Oil Swap Diff. | London | Global Liquids | Chris Mahoney | Amita Gosalia | Marie / Anna | On Hold | On Hold | 2000-10-01 | 09/08 Reviewing language. 9/22 On Hold
| FX | Internal FX Product | London | FX desk | Shane Dallman | Amita Gosalia | Anna/ Imedla | Review | Review | TBD | 10/5 Request received from trader. 10/20 Houston PCG
| Gasoil | Daily Average x2 | London | Global Liquids | Chris Mahoney | Amita Gosalia | Arfan / Anna | Reviewing | Reviewing | TBD | 09/08 Reviewing language. 9/22 On hold
| Marine Bunkers | Marine Bunkers | London | Oil | Scott Moncrieff | Amita Gosalia | Caroline/ Anna | On Hold | On Hold | 2000-09-01 | 08/23 On hold due to Phase II 09/07 On hold. 09/22 On hold - Scott Moncrieff wants to launch tanker freight before proceeding with this.
| Metals | Copper x 8 Phys - Europe | London | Metals | David Lilley | Amita Gosalia | Marie | Draft | Test | 2000-10-01 | 09/08 On Draft. 9/14 Product description sent for approval, PA and ETA prepared for Chile, Peru, China, Russia, Taiwan, South Africa,. 10/5 Working on long description with traders and legal. Tentative to go live on Oct 19th. 10/20 Awaiting approval from David Lilley. 11/03 Meeting with Trader on 13th Nov. 11/24 Product to launch on Dec 4th
| Metals | Copper Arb | London | Metals | Craig Young | Amita Gosalia | Caroline | Review | Review |  | 11/10 Awaiting commercial sponsor and information
| Oil | Singapore/Dubai time spread | Singapore | Oil | Pat Markey | Amita Gosalia | Caroline | Draft | Draft |  | 11/17 Draft long description
| Paper | Paper/pulp x57 | London | Clickpaper | Martin Holmes | Amita Gosalia | Anna/Lara | Review | Review |  | 11/10 Trader to provide info. 11/24 Long description is under review.
| Power | UK Phy Power | London | Power | Simon Hastings | Amita Gosalia | Arfan/ Caroline | On Hold | On Hold | TBD | 9/14 On Draft. 9/22 On Hold until Q1 2001
| Power | UK Power - LOLP | London | Power | Neil Jackson | Amita Gosalia | Arfan/Philippa/Alan | Review | Review |  | 11/10 Long description received from trader
| Sea Freight | Sea Freight Physical | London | Oil | Pierre Aury | Amita Gosalia | Anna/Amita/Marie | Legal | Legal | TBD | 9/14 On Draft. 9/22 Investigating auctions functionality for this product. 10/20 Meeting with trader on Nov 1. 11/03 Meeting with Trader on Nov 8th. 11/10 Trader and legal to agree to contract terms
| Singapore FX | Singapore FX | London | FX desk | Pat Markey | Amita Gosalia | Anna | On hold | On hold | TBD | 08/23 On hold by request of commercial group 9/22 No further Update
| Softs | Coffee, Sugar, Cocoa | London | Softs | Darren Maloney | Amita Gosalia | Anna | Legal | Legal | TBD | 11/3 Awaiting info from commercial group. 11/10 Long descripions to be approved by commercial prior to legal review.
| Warehouse Space | Warehouse Space | London | Metals | Ed Dablin | Amita Gosalia | Marie/Arfan | Reviewing | Reviewing | TBD | 11/3 Awaiting info from commercial group
| Weather | Weather - Average Swaps | London | Weather | Thor Lien | Amita Gosalia | Arfan/Marie | Legal | Legal | TBD | 10/5 Request received from trader. 10/20 Meeting with trader on Oct 24th. 11/03 Awaiting info from Trader 11/10 Waitng on GTC from Legal
| Weather Options | Weather Options | London | Weather | Thor Lien | Amita Gosalia | Arfan/ Marie | Legal | Legal | TBD | 9/14 GTC in legal. 9/22 Trader Reviewing 10/5 Legal to provide GTC and Long Descriptions. 10/20 Meeting with Trader on 24 Oct. 11/03 Awaiting info from Trader 11/10 Awaiting GTCs from legal

## Activated Countries
|  |  |  | ACTIVATED COUNTRIES |  | as of: | 2000-11-27
THE AMERICAS
# | Available at: | Date Changed | Activated Country | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 11/17/00 | Status as of 11/24/00 | Scheduled for: | Comments:
|  | 2000-10-05 | Bermuda | Weather | Waiting on Info | Leonardo Pacheco | M. Taylor | Approved | Approved | 2000-09-01 | 08/15 No date yet. Mark Taylor is checking and will get back to us. 8/31 M. Taylor will get ETA. Brent is working on country. 10/5 Bermuda's legal forms are the same as North America's. Done
|  | 2000-10-05 | Chile | MG | Bruce Garner | Amita Gosalia | M. Taylor | Approved | Approved | 2000-09-01 | 08/15 More info Wed. 8/31 May need an agent for service of process in the U.S. (Brent is checking). 10/5 Chile can use NA's ETA and PA. Enron entity must not be present in Chile and EOL agreements should not be subject to local law. Done
|  | 2000-10-05 | Peru | MG | Bruce Garner | Amita Gosalia | M. Taylor | Approved | Approved | 2000-09-01 | 08/15 More info Wed. 8/31 May need an agent for service of process in the U.S. (Brent is checking). 10/5 Chile can use NA's ETA and PA. Enron entity must not be present in Chile and EOL agreements should not be subject to local law. Done
|  | 2000-10-20 | Argentina | Enron Argentina | Patrick Hansen | Carlos Alatorre | M. Taylor | Approved | Approved | 2000-10-01 | 08/15 Draft of legal Documents later this week. 8/31 Draft has not been forthcoming. 09/07 Pending! 10/13 Waiting on approval for legal documents.10/20 Legal approval for PA, ETA, GTC-phy gas, and Phy Gas prod Description. To be launched on Oct 23rd. Done
AFRICA
# | Available at: | Date Changed | Activated Country | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 11/17/00 | Status as of 11/24/00 | Scheduled for: | Comments:
|  | 2000-10-05 | South Africa | Enron Coal | Peter Bradley | Amita Gosalia | Justin Boyd | Approved | Approved | TBD | 08/15 No date yet. 8/22 Issue: South Africans can not make payments to non-residents without approval of Reserve Bank. Reserve Bank gives no approvals to South Africans in respect of commodity or derivative transactions with foreign counterparties. 9/22 Allowed to trade commodities but must provide evidence of exchange control approval. 5 Oct - Approved to trade LME Contracts, commodity and weather derivatives, physical non-ferrous metals and coal. South African ctprty to provide evidence of exchange control approval in advance.
ASIA / AUSTRALIA
# | Available at: | Date Changed | Activated Country | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 11/17/00 | Status as of 11/24/00 | Scheduled for: | Comments:
|  | 2000-10-05 | China | MG | Bruce Garner | Amita Gosalia | Justin Boyd | Approved | Approved | TBD | 8/22 Commodity derivatives trading within China is not promoted unless it takes place on a domestic futures exchange. 9/22 Gas and power cannot be traded, waiting for metal, coal and oil. 10/05 Approved to trade OTC forwards from overseas base. Await info re: other derivatives and physical metal, coal and oil.
|  | 2000-10-05 | Hong Kong | MG | Bruce Garner | Amita Gosalia | Justin Boyd | Approved | Approved | 2000-10-01 | 8/15 Initial and follow up advice received. Further clarification still needed. 9/22 Legal review. 10/05 - Approved to trade LME Contracts, OTC commodity derivatives and physical commodities.
|  | 2000-10-20 | Taiwan | Enron Metals | David Lilley | Amita Gosalia | Matt Lee | Draft | Completed | TBD | 8/15 Need to confirm status. 8/31 Matt Lee will update. 9/22 - Some due diligence completed, Justin forwarded additional instructions. 10/05 Free to trade Physical/derivatives for oil and metals. Many import hurdles and maybe some withholding tax impact on derivative income (up to 20%) 10/20 The execution and marketing of LME Contracts will require a local licence if Enron is deemed to engage in futures in Taiwan. The mere availability and use of the website EOL does not give rise to this. however, any other direct solicitation or marketing into Taiwan will give rise to a licence. Completed
|  | 2000-11-03 | Israel | Seafreight | Pierre Aury | Amita Gosalia | Robert Quick | Completed | Completed | 2000-10-01 | 8/15 Initial outside legal responses received. Issues need clarification. 8/22 Advice outstanding: due at end of August. 10/5 - Free to trade LME Contracts and commodity derivatives. Insurance companies, pension funds and municipalities to be excluded. Israeli ctprtys to provide evidence of exchange control approval prior to transaction. Awaiting additional advice re physical trading. 11/3 The physical trading of all commodity products for delivery outside Israel is generally permitted. Completed
EUROPE
|  | Date Changed | Activated Country | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 11/17/00 | Status as of 11/24/00 | Scheduled for: | Comments:
# | Available at: | 2000-10-20 | Latavia | MG | Bruce Garner/ David Lilley | Amita Gosalia | Robert Quick | Draft | Completed | 2000-10-01 | 9/22 can trade commodity derivatives. 10/5 - Free to trade commodity derivatives. Banks and insurance companies should be excluded. 10/20 Completed
|  | 2000-10-20 | Russia | MG | Bruce Garner/ David Lilley | Amita Gosalia | Robert Quick | Draft | Completed | 2000-11-01 | 8/15 Initial and follow up advice received. Further clarification still needed. 8/22 Issues; A) Risk of non-deliverable transactions not unforeseeable. B) Payments in foreign currency might require case-by-case consent from Central Bank. C) Every trade with a Russian counterparty needs to be documented in writing. 10/5 Free to trade LME contracts and in commodities and commodity derivatives. There are licensing requirements for power, metal and gas. Cash settled derivatives could be regarded as unenforceable gaming contracts under Russian law. Central Bank license needed for exchange control purposes. 10/20 Completed

## Activated Products
|  | ACTIVATED PRODUCTS |  |  |  | as of: | 2000-11-27
US TRANSACTION PRODUCTS
Date Changed | Commodity | Product | Country/Location | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 11/17/00 | Status as of 11/24/00 | Scheduled for | Comments
2000-09-07 | AUS and JPN Weather | Weather Options | US | Weather |  |  | Dale Neuner | Active | Active | 2000-09-01 | 08/23 On hold due to Phase II . 8/29 To be launched this week. 09/07 Launched yesterday. Done
2000-09-14 | Power | East Cinergy Peak Splits | US | Power |  |  | Dale Neuner | Active | Active | 2000-09-01 | 09/07 Testing products. 9/14 Done
2000-10-20 | Gas | Phy 3/5/10 day swing | US | Gas | Scott Hendrickson | Dale Neuner | Dale Neuner | Active | Active | TBD | 9/22 Legal language drafted and sent to commercial 10/05 In testing Stage 10/13 To be released on Oct 16th 10/20 To be released on 10/20
2000-10-20 | Gas | PHY Fwd | US | Enron Argentina | Patrick Hansen | Carlos Alatorre | Dale Neuner | Active | Active | 2000-09-01 | 08/16 Two products are on test. Argentina is a post Phase II Launch. 8/31 GTC reviewed and sent to Legal. 09/06 Pending until after Version 2.0 Launch. 10/13 PA and ETA received from ARG, legal description approved by Houston legal and forwarded to ARG Legal, set for testing during ARG visit. 10/20 Product completed, to be activated on 10/23
2000-10-20 | Isobutane | Fin Swap | US | Petchems | Wade Hicks | Dale Neuner | Robert Cass | Active | Active | TBD | 08/31 Working on initial draft. 09/06 Draft in progress. 9/14 product types in legal awaiting approval. 10/05 Approved for release, waiting to be uploaded.10/20 uploaded 10/06 | ~
2000-10-20 | Isobutane | Phy FOB | US | Petchems | Wade Hicks | Dale Neuner | Robert Cass | Active | Active | TBD | 08/31 Working on initial draft. 09/06 Draft in progress. 9/14 product types in legal awaiting approval. 10/05 Approved for release, waiting to be uploaded.10/20 uploaded 10/06
2000-10-27 | Gas | Phys Index non-x <= 1Mo (Restricted) | US | Gas | Tori Kuykendahl | Dale Neuner | Dale Neuner | Active | Active | TBD | 9/22 reviewing Counterparty access 10/05 In testing stage 10/13 to be released on Oct 16th. 10/20 To be released on 10/20. 10/27 Done
2000-10-27 | NNG Capacity | US Pipeline Capacity | US | Gas | Steve Kirk | Robert Cass | Carl Carter/Naveed Ahmed | Active | Active | 2000-10-01 | 10/20 Product in Test. 10/27 To be Launched on 10/30
2000-10-27 | Polymers | PGC3 (Polymer Grade Propylene Fin Swap) | US | Petchems | Lee Jackson | Robert Cass | Robert Cass | Active | Active | TBD | 9/28 in Draft 10/20 To be released on 10/23. 10/27 Done
2000-11-03 | E/P Mix | Fin Swap | US | Petchems | Adam Gross | Dale Neuner | Dale Neuner | Active | Active | TBD | 08/31 Working on initial draft. 09/06 Draft in progress. 9/14 product types in legal awaiting approval. 10/27 Product to be released. 11/03 Product Released
2000-11-03 | E/P Mix | Phy FOB | US | Petchems | Adam Gross | Dale Neuner | Dale Neuner | Active | Active | TBD | 08/31 Working on initial draft. 09/06 Draft in progress. 9/14 product types in legal awaiting approval. 10/27 Product to be released. 11/03 Product Released
2000-11-03 | Heating Oil | US Heating Oil2 Fin Spread | US | Petchems | John Nowlan | Robert Cass | Robert Cass | Active | Active | 2000-10-01 | 10/20 To be released on 10/23. 11/03 released on 10/23
2000-11-03 | Jet Kerosene | US Jet Kerosene Fin Spread | US | Petchems | John Nowlan | Robert Cass | Robert Cass | Active | Active | 2000-10-01 | 10/20 To be released on 10/23. 11/03 released on 10/24
2000-11-03 | Polymers | US LLDPE-Ethylene Fin Spread | US | Petchems | Lee Jackson | Robert Cass | Robert Cass | Active | Active | 2000-10-01 | 10/20 To be released on 10/23. 11/03 released on 10/25
2000-11-03 | Steel | Physical Steel | US |  | Jason Seigal/ Shawn Keenan | Carl Carter/Naveed Ahmed | Robert Cass | Active | Active | TBD | 8/16 No legal documents for this commodity, In legal review. 9/22 Harry Collins in legal is developing documents. 10/05 Financial products will roll out first followed by Physical. 10/13 GTCs for physical created. 10/20 Three steel product types have been created for financial in test. 10/27 Steel financial products to be released (Hot rolled/Cold rolled/ Galvanized) 11/03 Financial products released
2000-11-03 | Unleaded Gasoline | US Unleaded Gas Fin Spread | US | Petchems | John Nowlan | Robert Cass | Robert Cass | Active | Active | 2000-10-01 | 10/20 To be released on 10/23. 11/03 released on 10/26
2000-11-10 | Gas | 3 Products for MultiMonth Gas Flex | US | Gas | Tori Kuykendahl | Robert Cass | Melba Lozano | Approved | Approved | 2000-11-01 | 11/9 Product released on 11/9
2000-10-27 | Polymers | Polypropylene Fin Spread | US | Petchems | Lee Jackson | Robert Cass | Robert Cass | Active | Active | TBD | 9/28 in Draft 10/20 To be released on 10/23. 10/27 Done
NON-US TRANSACTION PRODUCTS
Date Changed | Commodity | Product | Country/Location | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 11/17/00 | Status as of 11/24/00 | Scheduled for | Comments
2000-09-07 | Metals | Metals LME x5 | London | MG |  |  | Lara/Arfan | Active | Active | 2000-09-01 | 08/23 On hold due to Phase II 09/07 Done!
2000-09-22 | Power | German Power Options | London | Power |  | Amita Gosalia | Anna / Imelda | Active | Active | 2000-09-01 | 08/23 On hold due to Phase II . Legal reviewing. 9/22 Done
2000-10-05 | Gasoil | SG East-West Swap Diff. | London | Global Liquids | Chris Mahoney | Amita Gosalia | Marie / Anna | Active | Active | 2000-10-01 | 09/08 Reviewing language. 9/22 - awaiting legal approval of PT and CP upload. 10/5 Done
2000-10-05 | Metals | LME x4 | London | MG | Tim Jones | Amita Gosalia | Lara/Arfan | Active | Active | 2000-09-01 | 08/23 On hold due to Phase II 09/07 On Draft. 10/5 Done
2000-10-20 | Coal | Phy Options | London | Coal | Peter Bradley | Amita Gosalia | Imelda/ Lara | Active | Active | 2000-10-01 | 9/14 On Draft 9/22 - Sent to legal for review. 10/5 Awaiting profile from legal, expecting to go live Oct-16th. 10/20 Done
2000-10-20 | Metals | LME Contracts Fin x3 (lead etc) | London | Metals | Tim Jones | Amita Gosalia | Lara/Imelda | Active | Active | 2000-10-02 | 09/08 On Draft. 9/14 Product description sent for approval, PA and ETA prepared for Chile, Peru, China, Russia, Taiwan, South Africa,. 10/5 - Long disc being reviewed by legal. Tentative go live on 16 Oct. 10/20 Done
2000-10-20 | Sea Freight | Sea Freight x4 | London | Crude | Pierre Aury | Amita Gosalia | Marie | Active | Active | 2000-09-01 | 9/14 On Draft. 9/22 - Awaiting CP Profile upload. 10/5 Awaiting launch. 10/20 Done
2000-11-03 | Crude | Nordic Product Split | London | Crude | Waiting on Info | Amita Gosalia | Arfan/ Caroline/Diana | Active | Active | 2000-10-01 | 9/14 On Draft. 9/22 Marc D to Commence 10/5 Arfan to Commence. 10/20 GTCs to be agreed with Thor, Martin and Paul. 11/03 Done
2000-11-03 | Petchems x 8 | Petchems | London | Petchems | Stuart Bland | Amita Gosalia | Caroline / Diana | Active | Active | 2000-10-01 | 9/14 On Draft. 10/5 On Hold. 10/20 To go live on Oct 23rd. 11/03 Done
2000-11-03 | Propane | Propane - new locations x 2 | London | Global Liquids | Chris Mahoney | Amita Gosalia | Marie | Active | Active | TBD | 11/3 Done
2000-10-20 | Tanker Freight | Tanker Freight | London | Crude | Scott Moncrieff | Amita Gosalia | Caroline/ Anna | Active | Active | 2000-10-01 | 09/08 On hold due to Phase II. Legal reviewing. 9/22 Approved by legal. 10/5 Tentative launch on 10th. 10/20 Done

## Cancelled Requests
|  | CANCELLED PRODUCT REQUESTS |  |  |  | as of: | 2000-11-27
TRANSACTION PRODUCTS
# | Commodity | Product | Country/Location | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 11/17/00 | Status as of 11/24/00 | Scheduled for | Comments
| Propane | Phy Index Purity | US | Petchems |  | Dale Neuner | Dale Neuner | Cancelled | Cancelled | TBD | 08/31 Working on initial draft. 09/06 Draft in progress. 9/22 Cancelled
| Nat-Gasoline | Phy Index | US | Petchems |  | Dale Neuner | Dale Neuner | Cancelled | Cancelled | TBD | 08/31 Working on initial draft. 9/22 Cancelled
| Isobutane | Phy Index | US | Petchems |  | Dale Neuner | Dale Neuner | Cancelled | Cancelled | N/A | 08/31 Working on initial draft. 09/06 Draft in progress. 9/14 Cancelled
AUCTION PRODUCTS
# | Commodity | Product | Country/Location | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 11/17/00 | Status as of 11/24/00 | Scheduled for | Comments