## Sheet1
Proposed Power Plants in the Western States Coordinating Council States
Last Update: October 16, 2001
Trans western | Facility | Location | Technology | Fuel Type | # of Units | Output (MW) | Est Online Date | Est Offline Date | Company | Notes | Source | Status | Est Cost (in Millions) | County | N/S Path 15 (CA only) | Region | Last Updated
| Springerville Generation I | Arizona |  | Coal | 1 | 380 | 2004-06-01 |  | Unisource/Bechtel |  | PMW | 3 |  | Apache |  | Southwest | 2001-09-04
| Springerville Generation II | Arizona |  | Coal | 1 | 380 | 2005-12-01 |  | Unisource/Bechtel |  | PMW | 3 |  | Apache |  | Southwest | 2001-09-04
| Winchester | Arizona | Combined | Gas |  | 750 | 2007-06-01 |  | Independent Power Tech |  | ACC | 5 | 0 | Cochise |  | Southwest | 2001-10-12
| Apache Station GT #4 | Arizona | GT | Gas/FO | 11 | 40 | 2002-08-01 |  | Arizona Elec Power Co-op |  | Owner | 3 | 30 | Cochise |  | Southwest | 2001-10-16
| Bowie I | Arizona | Combined | Gas | 2-2-1 | 500 | 2004-06-30 |  | SW Power Group II |  | ACC | 3 | 300 | Cochise |  | Southwest | 2001-10-12
| Bowie II | Arizona | Combined | Gas | 2-2-1 | 500 | 2005-12-31 |  | SW Power Group II |  | ACC | 3 | 300 | Cochise |  | Southwest | 2001-10-12
| Safford | Arizona |  | Gas |  | 220 | 2011-01-01 |  | Powergen LLC |  | ACC | 5 |  | Graham |  | Southwest | 2001-06-12
| La Paz II | Arizona | Combined | Gas |  | 540 | 2005-04-01 |  | Allegheny |  | Allegheny website | 3 | 270 | La Paz |  | Southwest | 2001-10-12
| La Paz I | Arizona | Combined | Gas |  | 540 | 2004-11-01 |  | Allegheny |  | Allegheny website | 3 | 270 | La Paz |  | Southwest | 2001-10-12
| Harquahala Generating Station | Arizona | Combined | Gas | 4-1-1 | 1040 | 2003-09-01 |  | PG&E NEG | Merchant | Maricopa County | 1 | 398 | Maricopa |  | Southwest | 2001-06-12
| Santan | Arizona | Combined | Gas | 3-3-1 | 825 | 2005-12-01 |  | SRP | ACC Sited Pending Maricopa County siting | www.santanfacts.org | 3 |  | Maricopa |  | Southwest | 2001-06-12
| Gila Bend | Arizona | Combined | Gas | 3-2-1 | 845 | 2004-06-01 |  | Power Dev Ent | ACC Sited Pending Maricopa County siting | AZ Republic | 3 | 400 | Maricopa |  | Southwest | 2001-06-12
| Gila River I | Arizona | Combined | Gas | 4-2-1 | 520 | 2003-04-01 |  | Panda Energy/TECO |  | Maricopa County | 1 | 250 | Maricopa |  | Southwest | 2001-08-29
| Arlington Valley I | Arizona | Combined | Gas | 1-2-1 | 580 | 2002-08-01 |  | Duke | Under Construction | CEM | 1 | 250 | Maricopa |  | Southwest | 2001-06-12
| Arlington Valley II | Arizona | Combined | Gas |  | 600 | 2003-07-01 |  | Duke |  | CEM | 3 |  | Maricopa |  | Southwest | 2001-09-04
| Tonopah | Arizona | Combined | Gas |  | 1100 | 2003-06-01 |  | PG&E NEG/Shaw |  | Power Marketing Ass. | 5 |  | Maricopa |  | Southwest | 2001-05-25
| Redhawk 4 | Arizona | Combined | Gas | 1-2-1 | 530 | 2007-12-01 |  | APS | Merchant | PMW | 2 |  | Maricopa |  | Southwest | 2001-06-12
| Redhawk 3 | Arizona | Combined | Gas | 1-2-1 | 530 | 2006-06-01 |  | APS | Merchant | PMW | 2 | 250 | Maricopa |  | Southwest | 2001-06-12
| Redhawk 2 | Arizona | Combined | Gas | 1-2-1 | 530 | 2003-01-01 |  | APS/Reliant | Merchant/Est Groundbreaking 12/19/00 | PMW/ACC | 1 | 250 | Maricopa |  | Southwest | 2001-06-12
| Redhawk 1 | Arizona | Combined | Gas | 1-2-1 | 530 | 2003-01-01 |  | APS/Reliant | Merchant/Est Groundbreaking 12/19/00 | PMW/ACC | 1 |  | Maricopa |  | Southwest | 2001-06-12
| West Phoenix (Phase 2) | Arizona | Combined | Gas |  | 500 | 2002-09-01 |  | APS/Calpine |  | Website/ACC | 1 | 250 | Maricopa |  | Southwest | 2001-06-12
| West Phoenix (Phase 1) | Arizona | Combined | Gas |  | 120 | 2001-08-01 |  | APS/Calpine | Complete | WEU/PMW/CEM | 1 | 60 | Maricopa |  | Southwest | 2001-09-06
| Kyrene (Oasis) | Arizona | Combined | Gas | 1-2-1 | 250 | 2002-04-01 |  | Oasis LLC |  | http://www.kyrenefacts.org/ | 1 |  | Maricopa |  | Southwest | 2001-09-06
| Gila River II | Arizona | Combined | Gas | 4-2-1 | 520 | 2003-04-01 |  | Panda Energy/TECO |  | Maricopa County | 1 | 250 | Maricopa |  | Southwest | 2001-08-29
| Gila River III | Arizona | Combined | Gas | 4-2-1 | 520 | 2003-09-01 |  | Panda Energy/TECO |  | Maricopa County | 2 | 250 | Maricopa |  | Southwest | 2001-08-31
| Gila River IV | Arizona | Combined | Gas | 4-2-1 | 520 | 2003-09-01 |  | Panda Energy/TECO |  | Maricopa County | 2 | 250 | Maricopa |  | Southwest | 2001-08-31
| West Phoenix Temporary | Arizona | GT | Gas | 5 | 99 | 2001-07-01 | 2001-11-01 | Arizona Public Service |  | ACC | 1 |  | Maricopa |  | Southwest | 2001-06-13
| Saguaro Temporary | Arizona | GT | Gas | 5 | 99 | 2001-07-01 | 2001-11-01 | Arizona Public Service |  | ACC | 1 |  | Maricopa |  | Southwest | 2001-06-13
| APS Upgrades and Reactivate | Arizona |  | Gas |  | 203 | 2001-07-01 |  | Arizona Public Service |  | ACC | 1 |  | Maricopa |  | Southwest | 2001-06-13
| Mesquite Power | Arizona | Combined | Gas |  | 1265 | 2003-03-01 |  | Sempra Energy Resources |  | Maricopa County Web | 1 |  | Maricopa |  | Southwest | 2001-06-12
| White Tank Mountain | Arizona | Pump Storage | Hydro | 5 | 1250 | 2011-01-01 |  | Arizona Independent Pwr |  | CEM | 5 |  | Maricopa |  | Southwest | 2001-06-12
XX | South Point | Arizona |  | Gas |  | 540 | 2001-06-01 |  | Calpine | complete | WEU | 1 | 275 | Mohave |  | Southwest | 2001-06-12
XX | Griffith Energy Project | Arizona | Combined | Gas | 2-2-1 | 650 | 2001-09-15 |  | Griffith Energy (PPL & Duke) |  | mohave news | 1 |  | Mohave |  | Southwest | 2001-09-06
| Littlefield (Beaver Dam) | Arizona | Combined | Gas |  | 500 | 2003-06-01 |  | Williams Energy |  | ACC | 5 |  | Mohave |  | Southwest | 2001-06-12
XX | Caithness Big Sandy (Phase I) | Arizona | Combined | Gas | 1-2-1 | 500 | 2003-08-01 |  | Caithness | ACC Docket # L-00000R-00-0100 | ACC Website | 3 |  | Mohave |  | Southwest | 2001-09-06
XX | Caithness Big Sandy (Phase II) | Arizona | Combined | Gas | 1-1-1 | 220 | 2004-12-01 |  | Caithness | ACC Docket # L-00000R-00-0100 | ACC Website | 3 |  | Mohave |  | Southwest | 2001-09-06
| Vail Generating (Rita Ranch) | Arizona |  | Gas | 2 | 150 | 2003-12-01 |  | Tucson Electric |  | Power Marketing | 3 |  | Pima |  | Southwest | 2001-09-04
| Tucson CT1 | Arizona |  | Gas | 1 | 75 | 2001-06-01 |  | Tucson Electric Power | complete | ACC | 1 |  | Pima |  | Southwest | 2001-09-06
| Tucson CT2 | Arizona |  | Gas | 1 | 21 | 2001-08-01 |  | Tucson Electric Power | Complete | ACC | 1 |  | Pima |  | Southwest | 2001-09-06
| Desert Basin Generating | Arizona |  | Gas |  | 520 | 2001-06-01 |  | Reliant | complete. Under 10 year contract with SRP | WEU/CEM | 1 | 263 | Pinal |  | Southwest | 2001-09-06
| Sundance Energy Project 2 | Arizona |  | Gas |  | 90 | 2002-09-01 |  | PPL Global | ACC Docket # L-00000W-00-0107 | EPA Federal Register | 2 |  | Pinal |  | Southwest | 2001-08-31
| Toltec Power Station II | Arizona | Combined | Gas | 2-2-1 | 1000 | 2005-03-31 |  | SW Power Group II | ACC Docket # L-00000YR-01-0112 | PMA/ACC | 3 | 500 | Pinal |  | Southwest | 2001-06-12
| Signal Peak I | Arizona | Combined | Gas |  | 580 | 2004-04-01 |  | Reliant | Air cooled condensers | Corp Press Release | 5 | 430 | Pinal |  | Southwest | 2001-09-06
| Signal Peak II | Arizona | Combined | Gas |  | 580 | 2009-01-01 |  | Reliant | Air cooled condensers | Corp Press Release | 5 | 310 | Pinal |  | Southwest | 2001-09-06
| Sundance Energy Project 1 | Arizona |  | Gas |  | 450 | 2002-06-01 |  | PPL Global | ACC Docket # L-00000W-00-0107 | EPA Federal Register | 2 |  | Pinal |  | Southwest | 2001-08-31
| Toltec Power Station I | Arizona | Combined | Gas | 2-2-1 | 1000 | 2003-09-30 |  | SW Power Group II | ACC Docket # L-00000YR-01-0112 | PMA/ACC | 3 | 500 | Pinal |  | Southwest | 2001-06-12
| Ambos Nogales Generating | Arizona |  | Gas |  | 500 | 2007-01-10 |  | Maestros Group |  | ACC | 5 | 430 | Santa Cruz |  | Southwest | 2001-10-12
| Welton-Mohawk(Yuma Energy) | Arizona | Combined | Gas |  | 500 | 2003-06-01 |  | Welton-Mohawk |  | ACC | 3 | 250 | Yuma |  | Southwest | 2001-10-12
| CEC Renewables Estimate II | California |  | Various |  | 306 | 2001-12-31 |  | Summary Listing |  |  | 1 |  |  |  | Cal - Mex | 2001-09-13
| CEC Renewables Estimate I | California |  | Various |  | 25 | 2001-05-30 |  | Summary Listing | complete |  | 1 |  |  |  | Cal - Mex | 2001-09-13
| Arco Watson | California | Peaker | Gas |  | 80 | 2002-08-31 |  | BP |  | CEC | 4 |  |  | S | Cal - Mex | 2001-09-13
| CEC Renewables Estimate III | California |  | Various |  | 458 | 2002-10-01 |  | Summary Listing |  |  | 2 |  |  |  | Cal - Mex | 2001-09-13
| Sunol CC | California | Combined | Gas |  | 600 | 2011-01-01 |  | Calpine |  | CEC | 4 |  | Alameda | N | Cal - Mex | 2001-05-10
| FPL Tesla | California | Combined | Gas |  | 1120 | 2005-02-01 |  | FPL |  | CEC Website | 4 |  | Alameda | N | Cal - Mex | 2001-09-13
| East Altamont | California |  | Gas |  | 1100 | 2004-05-01 |  | Calpine | CEC Docket # 01-AFC-4 | CEC Website | 3 |  | Alameda | N | Cal - Mex | 2001-06-13
| Russell City Energy Center | California | Combined | Gas |  | 600 | 2004-02-01 |  | Calpine/Bechtel |  | CEC | 3 |  | Alameda | N | Cal - Mex | 2001-09-13
| Maxwell (Colusa) | California |  | Gas |  | 600 | 2004-07-01 |  | Reliant |  | CEC Website | 3 |  | Colusa | N | Cal - Mex | 2001-09-13
| Evergreen Concord | California |  | Gas |  | 300 | 2011-01-01 |  |  |  | CEC Website | 4 |  | Contra Costa | N | Cal - Mex | 2001-09-13
| Potrero | California | Combustion | Gas | 2 | 540 | 2003-11-01 |  | Mirant | CEC Docket # 00-AFC-4 | CEC Website | 3 | 250 | Contra Costa | N | Cal - Mex | 2001-06-13
| Los Medanos (Pittsburg) Facility | California | Combined | Gas | 2-2-2 | 555 | 2001-07-01 |  | Calpine | Complete | CEC Website | 1 | 300 | Contra Costa | N | Cal - Mex | 2001-06-13
| Delta Energy Center | California | Combined | Gas | 3-3-1 | 880 | 2002-04-01 |  | Calpine & Bechtel | CEC Docket # 98-AFC-3 65% complete | CEC Website | 1 | 375 | Contra Costa | N | Cal - Mex | 2001-09-13
| Contra Costa | California | Combined | Gas | 2-2-1 | 530 | 2003-08-01 |  | Mirant | CEC Docket # 00-AFC-1; 1% complete | CEC Website | 1 | 250 | Contra Costa | N | Cal - Mex | 2001-09-13
| Fresno Cogen | California | Cogeneration | Gas |  | 23 | 2001-08-16 |  | Wellhead | Complete | CEC | 1 |  | Fresno | S | Cal - Mex | 2001-09-14
| Fresno CC | California | Combined | Gas |  | 1100 | 2004-10-01 |  | Calpine |  | CEC | 4 |  | Fresno | S | Cal - Mex | 2001-05-10
| Panoche-Los Banos | California | Peaker | Gas |  | 49 | 2001-10-30 |  | Wellhead |  | CEC | 1 |  | Fresno | S | Cal - Mex | 2001-10-16
| Gates | California | Peaker | Gas |  | 45 | 2001-11-15 |  | Wellhead |  | CEC | 2 |  | Fresno | S | Cal - Mex | 2001-10-16
| Salton Sea VI | California |  | Geo |  | 300 | 2003-12-01 |  | Cal Energy |  | CEC Website | 4 |  | Imperial | S | Cal - Mex | 2001-06-13
| Antelope | California | Combined | Gas |  | 1000 | 2004-10-01 |  | Enron | CEC Docket # 98-SIT-8; up to 1000MW | CEC Website | 4 | 500 | Kern | S | Cal - Mex | 2001-06-13
| Kern Power Plant Restart | California |  | Gas |  | 160 | 2002-04-01 |  | N. American Power | Repair & modify plant | CEC | 4 |  | Kern | S | Cal - Mex | 2001-09-13
| La Paloma Phase I | California | Combined | Gas | 2-2-1 | 521 | 2002-05-01 |  | PG&E NEG | CEC Docket # 98-AFC-2 75% complete | CEC Website | 1 | 500 | Kern | S | Cal - Mex | 2001-09-13
| South Star I | California |  |  | 2 | 100 | 2002-07-01 |  | Texaco |  | CEC | 3 |  | Kern | S | Cal - Mex | 2001-09-13
| Midway Buttonwillow | California | Peaker | Gas |  | 49 | 2002-01-01 |  | Calpeak |  | CEC | 3 |  | Kern | S | Cal - Mex | 2001-09-14
| Taft | California | Cogen | Gas |  | 100 | 2002-07-31 |  | Berry Petroleum |  | CEC | 4 |  | Kern | S | Cal - Mex | 2001-09-14
| Elk Hills GT | California | Simple | Gas | 2-2-1 | 350 | 2002-04-01 | 2003-04-01 | Sempra/OXY | CEC Docket # 99-AFC-1 9% complete | CEC & Sempra Webs | 1 |  | Kern | S | Cal - Mex | 2001-10-16
| Sunrise Power Phase I | California | Simple | Gas | 2-2-0 | 320 | 2001-08-01 |  | Edison International | Complete | CEC Website | 1 | 200 | Kern | S | Cal - Mex | 2001-06-14
| La Paloma Phase II | California | Combined | Gas | 2-2-1 | 522 | 2002-06-01 |  | PG&E NEG | CEC Docket # 98-AFC-2 65% complete | CEC Website | 1 | 500 | Kern | S | Cal - Mex | 2001-09-13
| Midway-Sunset | California | Combined | Gas | 2-2-1 | 500 | 2004-07-01 |  | ARCO Western Energy | awaiting turbine delivery; | CEC Website | 2 | 250 | Kern | S | Cal - Mex | 2001-09-13
| Elk Hills CC | California | Combined | Gas | 2-2-1 | 570 | 2003-04-01 |  | Sempra/OXY | CEC # 99-AFC-1; convert Elk Hills GT to CC | CEC & Sempra Webs | 1 | 300 | Kern | S | Cal - Mex | 2001-09-17
| Sunrise Power Phase II | California | Combined | Gas |  | 260 | 2003-06-01 |  | Edison International | Convert Sunrise I to a 560MW Combined | Edison Press Release | 4 |  | Kern | S | Cal - Mex | 2001-06-13
| Pastoria | California | Combined | Gas | 3-3-2 | 750 | 2003-01-01 |  | Calpine | CEC Docket # 99-AFC-7; 1% complete | CEC Website | 1 | 400 | Kern | S | Cal - Mex | 2001-09-13
| South Star II | California |  |  |  | 100 | 2003-02-01 |  | Texaco |  | CEC | 3 |  | Kern | S | Cal - Mex | 2001-09-13
| Lemoore (Henrietta) | California | Peaker | Gas |  | 91 | 2002-06-01 |  | GWF |  | CEC | 3 |  | Kings | S | Cal - Mex | 2001-09-13
| Avenal | California | Combined | Gas |  | 600 | 2004-09-01 |  | Duke |  | CEC Website | 4 |  | Kings | S | Cal - Mex | 2001-09-13
| Hanford Peaker | California | Peaker | Gas | 1-1-1 | 95 | 2001-08-01 |  | GWF Power Sys | Complete | CEC Website | 1 |  | Kings | S | Cal - Mex | 2001-09-13
| LADWP Harbor CT Project | California |  | Gas | 5 | 188 | 2001-11-21 |  | LADWP |  | LADWP | 1 |  | Los Angeles | S | Cal - Mex | 2001-10-16
| Long Beach District | California |  | Gas |  | 500 | 2004-10-01 |  | Enron | AFC expected 2000 | CEC Website | 5 | 300 | Los Angeles | S | Cal - Mex | 2001-06-13
| LADWP Valley CT Project | California |  | Gas | 1 | 47 | 2001-11-21 |  | LADWP |  | LADWP | 1 |  | Los Angeles | S | Cal - Mex | 2001-10-16
| Redondo Beach | California |  | Gas |  | 1000 | 2011-01-01 |  | AES | AFC expected | CEC Website | 4 |  | Los Angeles | S | Cal - Mex | 2001-06-13
| Lancaster Hanover | California | Peaker | Gas |  | 86 | 2002-03-01 |  | Electricity Provider Inc |  | CEC | 5 |  | Los Angeles | S | Cal - Mex | 2001-06-13
| Magnolia Modernization | California |  | Gas |  | 250 | 2004-03-01 |  | City of Burbank |  | CEC | 3 | 180 | Los Angelos | S | Cal - Mex | 2001-09-13
| Harbor Cogen | California | Cogeneration | Gas |  | 18 | 2001-06-14 |  |  | Complete | CEC | 1 |  | Los Angelos | S | Cal - Mex | 2001-09-14
| Placerita | California | Cogen | Gas |  | 50 | 2002-06-30 |  | Berry Petroleum |  | CEC | 4 |  | Los Angelos | S | Cal - Mex | 2001-09-14
| Haynes | California | Combined | Gas |  | 50 | 2011-01-01 |  | LADWP | Upgrades to existing plant | LADWP Press Release | 5 |  | Los Angelos | S | Cal - Mex
| Scattergood | California | Combined | Gas |  | 50 | 2011-01-01 |  | LADWP | Upgrades to existing plant | LADWP Press Release | 5 |  | Los Angelos | S | Cal - Mex
| El Segundo | California |  | Gas |  | 630 | 2003-11-01 |  | NRG & Dynergy | CEC Docket # 00-AFC-14 Net 280MW | CEC | 3 |  | Los Angelos | S | Cal - Mex | 2001-09-13
| Valley | California | Combined | Gas |  | 250 | 2003-12-01 |  | LADWP | Upgrades to existing plant | LADWP Press Release | 5 |  | Los Angelos | S | Cal - Mex
| Chowchilla II | California | Peaker | Gas |  | 49 | 2001-06-14 |  | NEO | Complete | CEC | 1 |  | Madera | N | Cal - Mex | 2001-09-14
| Calpine King City | California | Peaker | Gas |  | 50 | 2001-12-28 |  | Calpine | 15% complete. | CEC Website | 1 |  | Monterey | N | Cal - Mex | 2001-09-13
| Moss Landing | California | Combined | Gas | 2-2-1 | 1060 | 2002-06-01 |  | Duke | CEC Docket # 99-AFC-4 52% complete | CEC Website | 1 | 475 | Monterey | N | Cal - Mex | 2001-10-16
| Huntington Beach Modern. | California |  | Gas |  | 450 | 2001-11-30 |  | AES | 90% complete. Delayed for mech probs | CEC | 1 |  | Orange | S | Cal - Mex | 2001-09-13
| Roseville | California |  | Gas |  | 750 | 2004-08-01 |  | Enron |  | CEC | 3 |  | Placer | N | Cal - Mex | 2001-09-13
| Indigo 1&2 | California | Peaker | Gas |  | 90 | 2001-07-05 |  | Wildflower LLP | Complete | CEC | 1 |  | Riverside | S | Cal - Mex | 2001-09-13
| Indigo 3 | California | Peaker | Gas |  | 45 | 2001-09-15 |  | Wildflower LLP | Complete | CEC | 1 |  | Riverside | S | Cal - Mex | 2001-10-16
| Blythe II | California | Combined | Gas |  | 560 | 2004-05-01 |  | Summit Energy Group |  | CEC Website | 4 |  | Riverside | S | Cal - Mex | 2001-09-13
| Inland Empire | California | Combined | Gas |  | 600 | 2004-07-01 |  | Calpine |  | CEC | 3 |  | Riverside | S | Cal - Mex | 2001-05-31
| Ocotillo Power II | California | Combined | Gas |  | 260 | 2002-12-01 |  | InterGen | Upgrade Peaker to Combined Cycle Unit | CEC | 4 |  | Riverside | S | Cal - Mex | 2001-09-13
| Ocotillo Power I | California | Peaker | Gas |  | 450 | 2002-08-01 |  | InterGen |  | CEC | 3 |  | Riverside | S | Cal - Mex | 2001-09-13
| SeaWest Wind Projects | California | Wind | Wind | 84 | 57 | 2001-09-30 |  | Seawest, Inc | Complete | CEC | 1 |  | Riverside | S | Cal - Mex | 2001-09-13
| Blythe | California | Combined | Gas | 2-2-1 | 520 | 2003-04-01 |  | Summit Energy Group | CEC Docket # 99-AFC-8 13% complete | CEC Website | 1 | 250 | Riverside | S | Cal - Mex | 2001-10-16
| Teayawa Energy Center | California |  | Gas |  | 600 | 2004-04-01 |  | Calpine | Located on Torres Martinez Desert Cahuilla | Company Website | 5 | 275 | Riverside | S | Cal - Mex | 2001-09-13
| SMUD Combined Cycle | California | Combined | Gas |  | 1000 | 2004-10-01 |  | SMUD |  | CEC | 4 |  | Sacramento | N | Cal - Mex | 2001-06-13
| Procter & Gamble | California |  | Gas |  | 44 | 2001-04-01 |  | Sacramento Municipal | Complete. | CEC | 1 |  | Sacramento | N | Cal - Mex | 2001-05-10
| Air Products | California | Peaker | Gas |  | 180 | 2002-11-01 |  | Air Products |  | CEC | 4 |  | Sacramento | N | Cal - Mex | 2001-09-13
| Rio Linda/Elverta | California | Combined | Gas |  | 560 | 2004-05-01 |  | Florida Power | CEC Docket # 01-AFC-01 | CEC | 3 |  | Sacramento | N | Cal - Mex | 2001-06-13
| SMUD McClellan Upgrade | California |  | Gas |  | 22 | 2001-05-01 |  | SMUD | Complete |  | 1 |  | Sacramento | N | Cal - Mex | 2001-07-30
| Drews | California | Peaker | Gas |  | 40 | 2001-08-15 |  | Alliance Colton LLC | Complete | CEC | 1 |  | San Bernadino | S | Cal - Mex | 2001-09-13
| Century | California | Peaker | Gas |  | 40 | 2001-09-11 |  | Alliance Colton LLC | Complete. | CEC | 1 |  | San Bernadino | S | Cal - Mex | 2001-09-13
| Mountainview | California |  | Gas |  | 1056 | 2003-06-01 |  | Thermo Ecotek | CEC Docket # 00-AFC-2; 1% complete | CEC Website | 1 | 550 | San Bernardino | S | Cal - Mex | 2001-09-13
| High Desert 2 | California | Combined | Gas |  | 450 | 2002-07-01 |  |  |  | CEC Website | 4 |  | San Bernardino | S | Cal - Mex | 2001-09-13
| Pegasus Energy | California | Peaker | Gas | 4 | 180 | 2002-06-01 |  | Pegasus Power Partners | Construction Halted; Possible sale to CPA | CEC | 1 |  | San Bernardino | S | Cal - Mex | 2001-10-16
| High Desert | California | Combined | Gas | 3-3-3 | 720 | 2003-07-01 |  | Inland Group & Constellation | CEC Docket # 97-AFC-1; 14% complete | CEC Website | 1 | 350 | San Bernardino | S | Cal - Mex | 2001-10-16
| Larkspur | California | Peaker | Gas |  | 90 | 2001-07-01 |  | Wildflower LLP | Complete | CEC | 1 |  | San Diego | S | Cal - Mex | 2001-04-23
| Escondido Industrial Park | California |  | Gas |  | 500 | 2004-08-01 |  | Sempra |  | CEC | 4 |  | San Diego | S | Cal - Mex | 2001-06-13
| Otay Mesa | California | Combined | Gas | 2-2-2 | 510 | 2003-07-01 |  | Calpine | CEC Docket # 99-AFC-5; 1% Complete | CEC Website | 1 | 350 | San Diego | S | Cal - Mex | 2001-10-16
| CalPeak Enterprise | California | Peaker | Gas |  | 49 | 2001-10-15 |  | CalPeak | Complete | CEC | 1 |  | San Diego | S | Cal - Mex | 2001-10-16
| San Diego Mission | California | Peaker | Gas |  | 50 | 2001-12-31 |  | Calpeak |  | CEC | 2 |  | San Diego | S | Cal - Mex | 2001-10-16
| El Cajon | California | Peaker | Gas |  | 50 | 2001-12-20 |  | Calpeak |  | CEC | 2 |  | San Diego | S | Cal - Mex | 2001-09-14
| CalPeak Border | California | Peaker | Gas |  | 49 | 2001-10-24 |  | CalPeak | 90% complete | CEC | 1 |  | San Diego | S | Cal - Mex | 2001-10-16
| Tracy | California | Peaker | Gas |  | 169 | 2002-07-01 |  | GWF |  | CEC | 3 |  | San Joaquin | N | Cal - Mex | 2001-09-13
| Morro Bay | California | Combined | Gas | 2-2-1 | 1200 | 2004-01-01 |  | Duke | CEC Docket # 00-AFC-12 450MW net | CEC Website | 3 |  | San Luis Obispo | S | Cal - Mex | 2001-06-13
| United Golden Gate Peaking | California | Peaker | Gas |  | 51 | 2011-01-01 |  | El Paso Merchant Energy | CEC Docket # 00-AFC-5 Decision 3/7/01 | CEC Website | 2 |  | San Mateo | N | Cal - Mex | 2001-09-13
| South City | California | Combined | Gas |  | 550 | 2004-04-01 |  | AES | AFC expected 2000 | CEC Website | 4 |  | San Mateo | N | Cal - Mex | 2001-06-13
| Metcalf Energy Center | California | Combined | Gas | 2-2-1 | 600 | 2003-07-01 |  | Calpine & Bechtel | CEC Docket # 99-AFC-3 | CEC Website | 2 | 350 | Santa Clara | N | Cal - Mex | 2001-10-12
| Spartan Peaker | California | Peaker | Gas |  | 96 | 2002-06-01 |  | Spartan Power |  | CEC | 3 |  | Santa Clara | N | Cal - Mex | 2001-09-13
| Gilroy 1&2 | California | Peaker | Gas | 3 | 90 | 2011-10-24 |  | Calpine | CEC Docket # 01-EP-8 | CEC Website | 1 |  | Santa Clara | N | Cal - Mex | 2001-09-13
| Gilroy 3 | California | Peaker | Gas | 3 | 45 | 2001-11-15 |  | Calpine | CEC Docket # 01-EP-8 | CEC Website | 1 |  | Santa Clara | N | Cal - Mex | 2001-09-13
| Los Esteros (US Dataport) Exp | California |  | Gas |  | 70 | 2002-12-01 |  | Calpine |  | CEC | 5 |  | Santa Clara | N | Cal - Mex | 2001-06-13
| GilroyPhase II | California | Peaker | Gas |  | 135 | 2002-08-01 |  | Calpine |  | CEC Website | 3 |  | Santa Clara | N | Cal - Mex | 2001-09-13
| Los Esteros (US Dataport) | California | Peaker | Gas |  | 180 | 2002-05-31 |  | Calpine |  | CEC | 3 |  | Santa Clara | N | Cal - Mex | 2001-06-13
| Watsonville | California | Peaker | Gas |  | 135 | 2002-07-31 |  | Calpine |  | CEC | 3 |  | Santa Cruz | N | Cal - Mex | 2001-09-13
| Three Mountain | California | Combined | Gas | 2-2-1 | 500 | 2003-12-01 |  | Covanta | CEC Docket # 99-AFC-2 | CEC Website | 2 | 300 | Shasta | N | Cal - Mex | 2001-10-16
| Fourmile Hill | California |  | Geol |  | 50 | 2003-12-01 |  | Calpine |  | BLM Website | 2 |  | Siskiyou/Modoc | N | Cal - Mex | 2001-09-13
| Valero Cogeneration | California |  |  |  | 102 | 2002-04-01 |  | Valero Oil |  | CEC Website | 3 |  | Solano | N | Cal - Mex | 2001-05-30
| Vaca-Dixon | California | Peaker | Gas |  | 49 | 2001-12-01 |  | Calpeak |  | CEC | 1 |  | Solano | N | Cal - Mex | 2001-10-16
| Suisun 1-3 | California | Peaker | Gas |  | 141 | 2002-06-30 |  | Panda West |  | CEC | 2 |  | Solano | N | Cal - Mex | 2001-10-16
| Woodland Generation Station | California | Combined | Gas |  | 80 | 2003-10-01 |  | Modesto Irrigation | Filed SPPE Application | CEC | 2 | 60 | Stanislaus | N | Cal - Mex | 2001-10-16
| Sutter Power | California | Combined | Gas | 2-2-1 | 540 | 2001-07-01 |  | Calpine | Complete | CEC Website | 1 | 275 | Sutter | N | Cal - Mex | 2001-06-14
| Red Bluff | California | Peaker | Gas |  | 47 | 2001-08-02 |  | NEO | Complete | CEC | 1 |  | Tehama | N | Cal - Mex | 2001-09-14
| Port of Sacramento CC | California | Combined | Gas |  | 60 | 2002-12-01 |  | Ameresco | Convert to a CC | CEC | 4 |  | Yolo | N | Cal - Mex | 2001-09-13
| Port of Sacramento | California | Peaker | Gas |  | 140 | 2002-07-01 |  | Ameresco |  | CEC | 4 |  | Yolo | N | Cal - Mex | 2001-09-13
| Muskeg River | Canada - Alberta | Cogeneration | Gas | 2-2-0 | 170 | 2002-12-01 |  | ATCO | Part of Athabasca Oil Sands Project | Atco Website | 1 | 200 |  |  | Northwest | 2001-09-05
| Poplar Creek Ph 2 | Canada - Alberta | Combined | Gas | 0-0-2 | 70 | 2001-01-01 |  | TransAlta | Complete | Website | 1 |  |  |  | Northwest
| Drywood Expansion | Canada - Alberta |  | Gas |  | 7 | 2001-09-01 |  | Canadian Gas & Electric |  | Alberta Resource Dev | 1 |  |  |  | Northwest | 2001-09-05
| Brooks | Canada - Alberta |  | Coal |  | 400 | 2005-07-01 |  | ENMAX/Fording |  | Alberta Resource Dev | 3 | 400 |  |  | Northwest | 2001-09-05
| Bear Creek Cogeneration | Canada - Alberta |  | Gas |  | 80 | 2002-12-01 |  | TransCanada |  | PMW | 3 | 80 |  |  | Northwest | 2001-09-05
| AES Calgary I | Canada - Alberta |  | Gas |  | 350 | 2002-11-01 |  | AES Corp |  | Alberta Resource Dev | 3 | 300 |  |  | Northwest | 2001-09-05
| Vision Quest II | Canada - Alberta | Wind | Wind | 36 | 24 | 2001-12-01 |  | TransAlta |  | Corp Press Release | 1 | 20 |  |  | Northwest | 2001-09-04
| Redwater Cogeneration | Canada - Alberta |  | Gas |  | 40 | 2001-12-01 |  | TransCanada |  | Corporate Website | 1 | 37 |  |  | Northwest | 2001-09-05
| Carseland Cogeneration | Canada - Alberta |  | Gas |  | 80 | 2001-09-01 |  | TransCanada |  | Corporate Website | 1 | 78 |  |  | Northwest | 2001-09-05
| Cancarb Cogen (Medicine Hat) | Canada - Alberta |  |  |  | 47 | 2001-03-01 |  | TransCanada | Complete | Corporate Website | 1 |  |  |  | Northwest
| MacKay River | Canada - Alberta | Cogeneration | Gas |  | 165 | 2004-01-01 |  | TransCanada | 60MW LT K; 90 MW Alberta pool; | Corp Website | 3 | 135 |  |  | Northwest | 2001-09-05
| Calgary Energy Centre | Canada - Alberta | Combined | Gas |  | 250 | 2002-12-01 |  | Calpine | Under Construction | Reuters | 1 | 215 |  |  | Northwest | 2001-09-05
| Vision Quest I | Canada - Alberta | Wind | Wind | 4 | 3 | 2001-07-01 |  | TransAlta | complete | Corp Press Release | 1 |  |  |  | Northwest | 2001-09-04
| Pincher Creek | Canada - Alberta | Wind | Wind |  | 52 | 2001-12-01 |  | Benign Energy |  | Alberta Resource Dev | 3 | 15 |  |  | Northwest | 2001-09-05
| Keephills | Canada - Alberta |  | Coal |  | 900 | 2005-06-01 |  | TransAlta |  | Alberta Resource Dev | 3 | 1800 |  |  | Northwest | 2001-09-04
| Genesee Phase 3 | Canada - Alberta |  | Coal |  | 400 | 2005-07-01 |  | Epcor |  | Alberta Resource Dev | 3 | 550 |  |  | Northwest | 2001-09-05
| Cowley Ridge Expansion | Canada - Alberta | Wind | Wind |  | 25 | 2001-10-01 |  | Canadian Hydro |  | Corporate Website | 1 | 20 |  |  | Northwest | 2001-09-05
| Edmonton Cogen | Canada - Alberta | Cogeneration | Gas |  | 25 | 2001-04-01 |  | Univ of Alberta | Complete | Alberta Resource Dev | 1 |  |  |  | Northwest | 2001-04-26
| Sundance Upgrade I | Canada - Alberta |  | Coal |  | 50 | 2001-12-01 |  | TransAlta |  | Alberta Resource Dev | 3 | 48 |  |  | Northwest | 2001-09-05
| Sundance Upgrade II | Canada - Alberta |  | Coal |  | 100 | 2002-12-01 |  | TransAlta |  | Alberta Resource Dev | 3 | 95 |  |  | Northwest | 2001-09-05
| Sundance Upgrade III | Canada - Alberta |  | Coal |  | 60 | 2003-12-01 |  | TransAlta |  | Alberta Resource Dev | 3 | 57 |  |  | Northwest | 2001-09-05
| Fort Macleod | Canada - Alberta | Cogeneration | Gas |  | 45 | 2002-10-01 |  | Altec Power |  | Alberta Resource Dev | 3 | 40 |  |  | Northwest | 2001-09-05
| Fort McMurray Cogen | Canada - Alberta | Cogeneration | Gas |  | 400 | 2006-06-01 |  | OPTI Canada |  | Alberta Resource Dev | 3 |  |  |  | Northwest | 2001-09-05
| AES Calgary II | Canada - Alberta |  | Gas |  | 175 | 2003-11-01 |  | AES Corp |  | Alberta Resource Dev | 3 | 150 |  |  | Northwest | 2001-09-05
| Sturgeon (Valley View) | Canada - Alberta |  | Gas |  | 46 | 2001-12-01 |  | ATCO |  | Corp Press Release | 1 | 35 |  |  | Northwest | 2001-09-05
| Dunvegan | Canada - Alberta | Hydro | Hydro |  | 80 | 2004-01-01 |  | Glacier Power |  | Alberta Resource | 3 | 80 |  |  | Northwest | 2001-09-05
| Scotford | Canada - Alberta | Cogeneration | Gas |  | 150 | 2002-10-01 |  | ATCO |  | Atco Website | 1 | 140 |  |  | Northwest | 2001-09-05
| Cavalier | Canada - Alberta |  | Gas |  | 106 | 2001-09-01 |  | PanCanadian | 85 MW online | Alberta Resource Dev | 1 | 100 |  |  | Northwest | 2001-09-04
| Balzac | Canada - Alberta |  | Gas |  | 106 | 2001-12-01 |  | PanCanadian/CanOxy | www.resdev.gov.ab.ca/electric/rgeneral | Alberta Resource Dev | 1 | 100 |  |  | Northwest | 2001-09-05
| Grande Prairie | Canada - Alberta |  | Waste |  | 20 | 2002-12-01 |  | Canadian Gas & Elec | www.resdev.gov.ab.ca/electric/rgeneral | Alberta Resource Dev | 3 | 40 |  |  | Northwest | 2001-09-05
| CFL Cogeneration | Canada - Alberta | Cogeneration | Gas |  | 85 | 2004-09-01 |  | PanCanadian |  | Alberta Economic Dev | 5 | 90 |  |  | Northwest | 2001-09-05
| Oldman | Canada - Alberta | Hydro | Hydro |  | 32 | 2002-03-01 |  | Atco Energen |  | Alberta Resource | 1 | 33 |  |  | Northwest | 2001-09-05
| Edmonton | Canada - Alberta | Cogeneration | Gas |  | 30 | 2003-09-01 |  | Confidential | www.resdev.gov.ab.ca/electric/rgeneral | Alberta Resource Dev | 3 |  |  |  | Northwest | 2001-09-05
| Syncrude - Ft McMurray | Canada - Alberta | Cogeneration | Gas |  | 238 | 2005-07-01 |  | Syncrude Aurora | www.resdev.gov.ab.ca/electric/rgeneral | Alberta Resource Dev | 3 |  |  |  | Northwest | 2001-09-05
| Rossdale Unit 11 Repower | Canada - Alberta | Combined | Gas |  | 170 | 2003-07-01 |  | Epcor | *Will use existing steam turbine | Epcor Website | 2 | 115 |  |  | Northwest | 2001-09-05
| Cold Lake | Canada - Alberta | Cogeneration | Gas |  | 170 | 2003-09-01 |  | Imperial Oil/? |  | Alberta Resource | 3 |  |  |  | Northwest | 2001-09-05
| Rainbow Lake | Canada - Alberta |  | Gas |  | 46 | 2002-01-01 |  | ATCO |  | Corp Press Release | 1 | 35 |  |  | Northwest | 2001-09-05
| Pincher Creek 2 | Canada - Alberta | Wind | Wind | 56 | 100 | 2002-12-01 |  | Wind Power, Inc |  | Alberta Resource Dev | 3 |  |  |  | Northwest | 2001-06-14
| Lytton | Canada - British Columbia |  | Waste |  | 25 | 2011-01-01 |  | Lytton power Inc | RFP for BC Hydro | BC Hydro Website | 3 |  |  |  | Northwest
| Pingston | Canada - British Columbia | Hydro | Hydro |  | 30 | 2002-07-01 |  | Canadian Hydro | Joint with Great Lakes Power | Canadian Hydro Website | 1 |  |  |  | Northwest | 2001-09-05
| Ashlu | Canada - British Columbia | Hydro | Hydro |  | 54 | 2011-01-01 |  | Canadian Hydro |  | Canadian Hydro Website | 4 |  |  |  | Northwest
| Mamquam | Canada - British Columbia | Hydro | Hydro |  | 25 | 2011-01-01 |  | Canadian Hydro |  | Canadian Hydro Website | 4 |  |  |  | Northwest
| Island Cogeneration | Canada - British Columbia | Combined | Gas |  | 250 | 2001-06-01 |  | Calpine |  | Website | 1 |  |  |  | Northwest | 2001-06-14
| Brilliant Upgrade | Canada - British Columbia | Hydro | Hydro | 4 | 20 | 2004-06-01 |  | Columbia Power Corp | 5 MW each year 2001-2004 | Corp Website | 1 | 0 |  |  | Northwest | 2001-09-05
| Miller Creek | Canada - British Columbia | Hydro | Hydro |  | 25 | 2003-04-01 |  | Miller Creek Power Ltd | RFP for BC Hydro | BC Hydro Website | 3 |  |  |  | Northwest
| Cascade Heritage | Canada - British Columbia | Hydro | Hydro | 2 | 25 | 2004-01-01 |  | Powerhouse Energy |  | BC EAO | 3 | 24 |  |  | Northwest
| Kwoiek Creek | Canada - British Columbia | Hydro | Hydro |  | 80 | 2004-08-01 |  | Kanaka Bar Indian band | Run of river | BC EAO | 3 | 90 |  |  | Northwest | 2001-09-05
| Brilliant Expansion | Canada - British Columbia | Hydro | Hydro |  | 100 | 2005-01-01 |  | Columbia Power Corp |  | BC EAO | 3 | 150 |  |  | Northwest
| Arrow Lakes | Canada - British Columbia | Hydro | Hydro | 2 | 170 | 2002-04-01 |  | Columbia Power Corp |  | Corp Website | 1 | 250 |  |  | Northwest | 2001-09-05
| Port Alberni | Canada - British Columbia | Combined | Gas |  | 260 | 2003-10-01 |  | BC Hydro/Calpine |  | BC Hydro Website | 3 | 250 |  |  | Northwest | 2001-09-05
| Brighton Generating Station | Colorado |  | Gas |  | 140 | 2002-04-01 |  | Tri-State | Under Construction | Corp Website | 1 |  | Adams |  | Rocky Mountain | 2001-09-06
| Powhaton Peaker | Colorado |  | Gas | 4 | 280 | 2002-05-01 |  | North American Power | 4 GE PG7121EA Simple Cycle Turbines | Colorado CDPHE | 2 |  | Adams |  | Rocky Mountain
| Kiowa Energy Park I | Colorado | Combined | Gas | 2-2-1 | 475 | 2004-07-01 |  | North American Power | Est Construction start 2/2002. | Colorado CDPHE | 2 |  | Arapahoe |  | Rocky Mountain
| Kiowa Energy Park II | Colorado | Combined | Gas | 2-2-1 | 475 | 2011-01-01 |  | North American Power | Requires increased transmission capacity | Colorado CDPHE | 3 |  | Arapahoe |  | Rocky Mountain
| Colorado Energy Center | Colorado |  | Gas | 2 | 336 | 2003-05-01 |  | Calpine | Peaker unit using GE Frame 7 turbines | Corp Website | 5 | 100 | Arapahoe |  | Rocky Mountain | 2001-06-01
| Tri-State | Colorado |  | Coal |  | 1200 | 2005-01-01 |  | Tristate Generation |  | Corp Website | 5 | 1200 | Bent |  | Rocky Mountain | 2001-09-06
| Valmont Expansion | Colorado |  | Gas |  | 40 | 2001-06-01 |  | Black Hills | Complete | Corp Website | 1 |  | Boulder |  | Rocky Mountain | 2001-06-01
| Arapahoe Expansion | Colorado |  | Gas |  | 50 | 2002-06-01 |  | Black Hills |  | Corp Website | 2 |  | Cheyenne |  | Rocky Mountain
| Ray D. Nixon (Phase 2) | Colorado | Combined | Gas |  | 400 | 2003-03-01 |  | Coastal/CSU | Turbines purchased | Website | 3 | 400 | El Paso |  | Rocky Mountain | 2001-09-06
| Fountain Valley (Pueblo) | Colorado | Simple | Gas | 6 | 240 | 2001-08-15 |  | Black Hills | Complete | Corp Website | 1 | 100 | El Paso |  | Rocky Mountain | 2001-09-06
| Plains End | Colorado |  | Gas |  | 108 | 2002-05-01 |  | Xcel |  | Denver Post | 1 |  | Jefferson |  | Rocky Mountain | 2001-05-25
| Rawhide | Colorado |  | Gas | 3 | 210 | 2003-06-01 |  | Platte River Power Auth |  | Colorado CDPHE | 3 |  | Larimer |  | Rocky Mountain
| Limon Generating Station | Colorado |  | Gas |  | 140 | 2001-12-01 |  | Tri-State | Under Construction | Corp Website | 1 |  | Lincoln |  | Rocky Mountain | 2001-09-06
| Manchief Upgrade | Colorado |  | Gas |  | 48 | 2001-07-01 |  | Fulton | Complete |  | 1 |  | Morgan |  | Rocky Mountain | 2001-06-01
| Deserado (Rangely) | Colorado |  | Coal |  | 80 | 2004-12-01 |  | Deseret Generation & Trans |  | Power Marketers | 4 | 130 | Rio Blanco |  | Rocky Mountain | 2001-06-13
| Rocky Mountain | Colorado | Combined | Gas |  | 455 | 2004-05-01 |  | Calpine |  | Website | 5 | 360 | Weld |  | Rocky Mountain | 2001-06-01
| Fort St. Vrain (Phase 3) | Colorado |  | Gas | 1-1-0 | 235 | 2001-05-01 |  | PSC CO | Complete | fsv.homestead.com | 1 |  | Weld |  | Rocky Mountain | 2001-06-01
| Idaho Power Ics | Idaho | Recip Eng | FO2 | 35 | 40 | 2001-06-30 | 2001-12-01 | Idaho Power |  | NWPPC | 1 |  | Ada |  | Northwest | 2001-06-12
| Garnet Energy Facility | Idaho | Combined | Gas | 1-1-1 | 250 | 2004-06-01 |  | Ida-West | Proposed to meet RFP from Idaho Power | www.ida-west.com/projects.htm | 3 | 200 | Canyon |  | Northwest | 2001-09-10
| Mountain Home | Idaho | GT | Gas |  | 90 | 2001-10-01 |  | Idaho Power Company |  | NWPPC | 1 | 45 | Elmore |  | Northwest | 2001-09-10
| Oneida narrows | Idaho | Hydro | Hydro |  | 128 | 2011-01-01 |  | Symbiotics |  |  | 5 |  | Franklin |  | Northwest | 2001-06-13
| Kootenai | Idaho | Combined | Gas |  | 1300 | 2004-06-01 |  | Newport Generation |  | PMW | 5 | 550 | Kootenai |  | Northwest | 2001-04-24
| Rathdrum | Idaho |  | Gas | 1 | 270 | 2001-09-01 |  | Avista | Complete | WEU | 1 | 150 | Kootenai |  | Northwest | 2001-09-10
| Presidente Juarez (Rosarito 8&9) | Mexico - Baja California | Combined | Gas |  | 488 | 2001-07-01 |  | Alstrom Power | complete | CFE | 1 | 300 |  |  | Cal - Mex | 2001-09-10
| Thermoelectrica de Mexicali | Mexico - Baja California |  | Gas |  | 600 | 2003-06-01 |  | Sempra | Imperial Valley 1 | CPUC Testimony | 2 | 350 |  |  | Cal - Mex | 2001-09-10
| La Rosita (Rosarito 10 & 11) | Mexico - Baja California | Combined | Gas |  | 750 | 2003-04-01 |  | Intergen | 1/3 available for sale in US | Corp Press Rel | 1 | 335 |  |  | Cal - Mex | 2001-09-14
| Imperial Valley 2 | Mexico - Baja California |  | Gas |  | 600 | 2005-05-31 |  | Sempra |  | CPUC Testimony | 4 |  |  |  | Cal - Mex | 2001-06-13
| Intergen 2 | Mexico - Baja California | Combined | Gas |  | 600 | 2003-04-01 |  | Intergen | 160 MW available for sale in US | CPUC Testimony | 3 |  |  |  | Cal - Mex | 2001-06-13
| Ensenada | Mexico - Baja California |  |  | 2 | 40 | 2011-01-01 |  |  | Expansion of existing plant | San Diego Union | 5 |  |  |  | Cal - Mex
| Mexicali | Mexico - Baja California |  | Gas |  | 500 | 2003-04-01 |  | AEP |  | CPUC Testimony | 3 | 131 |  |  | Cal - Mex | 2001-09-10
| Montana First Megawatts III | Montana | Combined | Gas |  | 80 | 2002-12-01 |  | Northwestern Corp | Converts 1 & 2 to CC | PMW | 2 | 47 |  |  | Rocky Mountain | 2001-09-17
| Montana First Megawatts I | Montana | Simple | Gas |  | 80 | 2002-07-01 |  | Northwestern Corp |  | PMW | 2 | 47 |  |  | Rocky Mountain | 2001-09-17
| Montana First Megawatts II | Montana | Simple | Gas |  | 80 | 2002-07-01 |  | Northwestern Corp |  | PMW | 2 | 47 |  |  | Rocky Mountain | 2001-09-17
| Blackfeet | Montana |  | Gas |  | 160 | 2011-01-01 |  | Adair | Delayed due to results of feasibility study | PMW | 5 | 150 | Glacier |  | Rocky Mountain | 2001-09-10
| Blackfeet I Wind | Montana | Wind | Wind |  | 50 | 2002-10-01 |  | Seawest Wind |  | NWPPC | 3 |  | Glacier |  | Rocky Mountain | 2001-09-10
| Continental Energy Silver Bow | Montana | Combined | Gas | 2-2-1 | 500 | 2004-01-01 |  | BBI Power | www.deq.state.mt.us/pcd/emb/fs/ | MT DEQ | 3 | 300 | Silver Bow |  | Rocky Mountain | 2001-09-10
| Exxon I | Montana | GT | gas |  | 20 | 2001-04-01 | 2003-03-31 | Exxon | complete | NWPPC | 1 |  | Yellowstone |  | Rocky Mountain | 2001-06-12
| Cenex Cogen | Montana | Cogeneration | FO2 |  | 20 |  |  | Cenex Refinery |  | NWPPC | 3 |  | Yellowstone |  | Rocky Mountain | 2001-09-10
| Conoco | Montana | Recip Eng | FO2 |  | 19 | 2001-04-01 | 2003-03-31 | Conoco | complete | NWPPC | 1 |  | Yellowstone |  | Rocky Mountain | 2001-06-12
| Moapa Energy Facility | Nevada | Combined | Gas |  | 1200 | 2003-05-01 |  | Duke Energy NA | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 3 |  | Clark |  | Southwest | 2001-09-10
| Crystal Generating Station | Nevada | Combined | Gas |  | 760 | 2003-06-01 |  | Calpine | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 3 |  | Clark |  | Southwest | 2001-09-10
| Copper Mountain (El Dorado II) | Nevada | Combined | Gas |  | 600 | 2003-12-01 |  | Sempra/Reliant | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 3 |  | Clark |  | Southwest | 2001-09-10
| Apex Industrial II | Nevada | Combined | Gas |  | 550 | 2004-05-01 |  | Mirant | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 1 |  | Clark |  | Southwest | 2001-09-10
| Red Rock Canyon | Nevada | Pump Store | Hydro |  | 400 | 2004-12-01 |  | Blue Diamond Power | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 3 | 320 | Clark |  | Southwest | 2001-09-10
| Arrow Canyon | Nevada | Combined | Gas |  | 500 | 2003-06-01 |  | Reliant | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 3 |  | Clark |  | Southwest | 2001-09-10
| Meadow Valley | Nevada | Combined | Gas |  | 1100 | 2004-03-01 |  | PG&E NEG | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 3 |  | Clark |  | Southwest | 2001-09-10
| Bighorn CC | Nevada | Combined | Gas |  | 580 | 2003-06-01 |  | Reliant | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 3 |  | Clark |  | Southwest | 2001-09-10
| Silver Hawk | Nevada | Combined | Gas |  | 570 | 2004-05-01 |  | Pinnacle West | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 3 |  | Clark |  | Southwest | 2001-09-10
| Table Mountain Wind Project | Nevada |  | Wind |  | 120 | 2002-12-01 |  | M&N Wind Power | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 3 |  | Clark |  | Southwest | 2001-09-10
| Tortoise Power Plant | Nevada | Peaker | Gas |  | 100 | 2002-03-01 |  | Overton Power District | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 3 |  | Clark |  | Southwest | 2001-09-10
| Las Vegas Cogen II | Nevada | Combined | Gas |  | 230 | 2002-09-01 |  | Enron | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 1 |  | Clark |  | Southwest | 2001-09-10
| Apex Industrial I | Nevada | Combined | Gas |  | 550 | 2003-03-01 |  | Mirant | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 1 |  | Clark |  | Southwest | 2001-09-10
| Boulder Valley | Nevada | Combined | Gas |  | 480 | 2003-12-01 |  | El Paso Merchant | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 3 |  | Eureka |  | Northwest | 2001-09-10
| Toquop Energy | Nevada | Combined | Gas |  | 1100 | 2004-10-01 |  | Cogentrix | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 3 |  | Lincoln |  | Southwest | 2001-09-10
| Shoshone Mountain Wind II | Nevada |  | Wind |  | 175 | 2003-07-01 |  | M&N Wind Power | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 3 |  | Nye |  | Southwest | 2001-09-10
| Shoshone Mountain Wind I | Nevada |  | Wind |  | 85 | 2002-10-01 |  | M&N Wind Power | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 3 |  | Nye |  | Southwest | 2001-09-10
| Rye Patch | Nevada | Geothermal | Geo |  | 12 | 2001-10-01 |  | Mt Wheeler power | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 1 |  | Pershing |  | Northwest | 2001-09-10
| EOPT TRI | Nevada | Peaker |  |  | 30 | 2001-09-01 |  | EOPT | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 3 |  | Storey |  | Northwest | 2001-05-31
| TRI-Center Power Plant | Nevada |  | Gas |  | 360 | 2001-06-01 |  | Naniwa Energy | complete | PUC NV press release | 1 |  | Storey |  | Northwest | 2001-09-10
| Steamboat Springs | Nevada | Geothermal | Geo |  | 30 | 2002-07-01 |  | SB Geo | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 3 |  | Washoe |  | Northwest | 2001-09-10
| Washoe Power Plant | Nevada | Combined | Gas |  | 540 | 2003-05-01 |  | Duke Energy NA | http://puc.state.nv.us/electric/propgen.htm | NV PUC | 3 |  | Washoe |  | Northwest | 2001-09-10
| Clovis II | New Mexico | Combined | Gas |  | 600 | 2004-12-01 |  | Duke Energy NA | Application expected in October | NM PRC | 4 |  | Curry |  | Southwest | 2001-10-16
| Clovis I | New Mexico | Combined | Gas |  | 600 | 2004-12-01 |  | Duke Energy NA | Application expected in October | NM PRC | 4 |  | Curry |  | Southwest | 2001-10-16
| Aston II | New Mexico |  | Gas |  | 85 | 2003-12-01 |  | PSC NM |  |  | 5 |  | Dona Ana |  | Southwest | 2001-09-05
| Aston I | New Mexico |  | Gas |  | 135 | 2002-10-01 |  | PSC NM |  | CA Energy Market 6/22 | 5 |  | Dona Ana |  | Southwest | 2001-09-05
| Tristate Lordsburg | New Mexico |  | Gas |  | 160 | 2003-06-01 |  | Tri-State |  | PMW | 3 |  | Hidalgo |  | Southwest | 2001-09-05
| Deming | New Mexico |  | Gas |  | 600 | 2002-12-01 |  | Duke Energy Luna LLC |  | NM PRC Utility Division | 1 | 250 | Luna |  | Southwest | 2001-09-05
XX | Belen (Rio Puerco) | New Mexico |  | Gas |  | 156 | 2004-01-01 |  | Cobisa | On hold pending zoning change | www.cobisa.com/projects.htm | 2 |  | Valencia |  | Southwest | 2001-09-05
| West Linn Paper | Oregon | Combined | Gas |  | 94 | 2011-01-01 |  | West Linn Paper |  | OR Siting Webpage | 3 |  | Clackamas |  | Northwest | 2001-10-16
| Columbia River Energy | Oregon | GT | Gas |  | 44 | 2002-01-01 | 2004-01-01 | Columbia River Energy |  | OR Siting | 2 |  | Columbia |  | Northwest | 2001-10-16
| Port Westward | Oregon | Combined | Gas |  | 650 | 2005-01-01 |  | Portland General Electric |  | OR Siting Webpage | 3 |  | Columbia |  | Northwest | 2001-10-16
| Beaver GT | Oregon | GT | Gas |  | 24 | 2001-07-01 |  | Portland General Electric | complete | NWPPC | 1 |  | Columbia |  | Northwest | 2001-09-10
| Summit/Westward | Oregon | Combined | Gas |  | 520 | 2004-04-01 |  | Westward Energy LLC |  | OR Siting Webpage | 3 |  | Columbia |  | Northwest | 2001-10-16
| St Helens Cogen | Oregon | Combined | Gas |  | 141 | 2011-01-01 |  | Oregon Energy Company |  | OR Siting Webpage | 2 |  | Columbia |  | Northwest | 2001-10-16
| Condon Wind | Oregon | Wind | Wind |  | 25 | 2002-01-01 |  | Seawest, Inc |  | NPPC | 3 |  | Gilliam |  | Northwest | 2001-09-10
| Condon Wind 2 | Oregon | Wind | Wind |  | 25 | 2002-06-01 |  | Seawest, Inc |  | NPPC | 3 |  | Gilliam |  | Northwest | 2001-09-10
| Grizzly Power Project | Oregon | Combined | Gas | 4-4-2 | 980 | 2004-07-01 |  | Cogentrix |  | Oregon Reg | 4 |  | Jefferson |  | Northwest | 2001-10-16
| Klamath FallsII | Oregon | Combined | Gas |  | 500 | 2011-01-01 |  | PacifiCorp |  | Press Release | 5 |  | Klamath |  | Northwest | 2001-10-16
| Klamath Falls Cogeneration | Oregon | Combined | Gas |  | 500 | 2001-07-01 |  | PacifiCorp | complete | www.klamathcogen.com/ | 1 | 300 | Klamath |  | Northwest | 2001-09-10
| Klamath Falls Expansion | Oregon | GT | Gas |  | 100 | 2001-11-01 | 2003-11-01 | Pacific Klamath energy | Under Construction | NWPPC | 1 |  | Klamath |  | Northwest | 2001-10-16
| Springfield Ics | Oregon | Recip Eng | FO2 |  | 27 | 2001-04-01 | 2001-09-30 | Springfield Utility Board | complete. | NWPPC | 1 |  | Lane |  | Northwest | 2001-06-12
| Coburg | Oregon | Combined | Gas |  | 605 | 2011-01-01 |  | Coburg Power | Enron withdrew from partnership. | OR Siting Webpage | 5 |  | Lane |  | Northwest | 2001-10-16
| Pope & Talbot Cogeneration | Oregon | GT | Gas | 2 | 93 | 2011-01-01 |  | Oregon Energy |  | NWPPC | 4 |  | Linn |  | Northwest | 2001-10-16
| Turner | Oregon | Combined | Gas |  | 620 | 2004-07-01 |  | Calpine | Approved for expedited siting uder HB3788 | OR Siting Webpage | 4 |  | Marion |  | Northwest | 2001-10-16
| Morrow | Oregon | Combined | Gas |  | 550 | 2011-01-01 |  | PG&E Natl Energy |  | OR Siting Webpage | 3 |  | Morrow |  | Northwest | 2001-10-16
| Coyote Springs II | Oregon | Combined | Gas |  | 280 | 2002-06-01 |  | Avista | Baseload Utility Plant | Oregon Reg | 1 |  | Morrow |  | Northwest | 2001-09-10
| Umatilla | Oregon |  | Gas |  | 500 | 2003-12-01 |  | PG&E Natl Energy | Adjacent to existing Hermiston plant | Oregon Reg | 2 |  | Umatilla |  | Northwest | 2001-10-16
| State Line Project | Oregon | Wind | Wind |  | 99 | 2001-12-01 |  | FPL Energy | 1st MWs were sold in Jul 01 | Oregon Reg | 1 |  | Umatilla |  | Northwest | 2001-09-10
| Confederated Tribes of Umatilla | Oregon |  | Gas |  | 500 | 2011-01-01 |  | Eugene Water & Elec | Joint with tribes of Up to 1000MW | PMW | 5 |  | Umatilla |  | Northwest | 2001-09-10
| Hermiston | Oregon | Combined | Gas |  | 546 | 2002-06-01 |  | Calpine | Purchased from Ida Corp & Trans Alta | Oregon Reg | 1 |  | Umatilla |  | Northwest | 2001-09-10
| SP Newsprint Cogen | Oregon | Combined | Gas |  | 119 | 2011-01-01 |  | SP Newsprint | In DEQ Siting | OR Siting Webpage | 3 |  | Yamhill |  | Northwest | 2001-10-16
| Mona | Utah |  | Gas |  | 1100 | 2011-01-01 |  | Panda |  | Deseret News 7/19/01 | 5 | 600 | Juab |  | Northwest | 2001-10-16
| Intermountain 3 | Utah |  | Coal |  | 900 | 2007-06-01 |  | Intermountain Power |  | Las Vegas Review-Journal | 5 |  | Millard |  | Northwest | 2001-09-12
| Murray City | Utah | Peaker | Gas | 3 | 39 | 2001-12-01 |  | City of Murray | First 13MW unit online. Others near comp | Murray City website | 1 |  | Salt Lake |  | Northwest | 2001-09-10
| West Ridge | Utah |  | Gas | 4 | 160 | 2001-11-01 |  | Pacificorp |  | Salt Lake Tribune | 1 |  | Salt Lake |  | Northwest | 2001-09-10
| Gadsby 4 | Utah |  |  | 5 | 100 | 2001-05-15 | 2001-10-01 | Pacificorp | Summer Peaker Units. Online | Pacificorp website | 1 |  | Salt Lake |  | Northwest | 2001-09-10
| Desert Power | Utah |  | Gas |  | 70 | 2001-10-01 |  | DQ Holdings, LLC |  | Salt Lake Tribune | 4 |  | Tooele |  | Northwest | 2001-05-02
| Maiden Wind | Washington | Wind | Wind |  | 150 | 2002-12-01 |  | BPA/ WA Winds |  | BPA Press Release | 4 |  | Benton |  | Northwest | 2001-05-25
| Nine Canyon | Washington | Wind | Wind |  | 25 | 2002-06-01 |  | Energy Northwest |  | NWPPC | 3 |  | Benton |  | Northwest | 2001-06-12
| Mercer Ranch | Washington | Combined | Gas | 3-3-2 | 850 | 2011-01-01 |  | Cogentrix |  | http://www.efsec.wa.gov/Default.htm | 4 |  | Benton |  | Northwest
| Chelan County PUD Ics | Washington | Recip Eng | FO2 | 21 | 34 | 2001-05-01 | 2002-04-30 | Chelan PUD | Complete | NWPPC | 1 |  | Chelan |  | Northwest | 2001-06-05
| Clark County Ics | Washington | Recip Eng | Gas |  | 50 | 2001-07-01 | 2002-05-01 | Clark PUD | Complete | NWPPC | 1 |  | Clark |  | Northwest | 2001-09-12
| Starbuck | Washington | Combined | Gas |  | 1200 | 2004-01-01 |  | PPL Global | http://www.efsec.wa.gov/starbuck.html | WA State Web | 3 | 535 | Columbia |  | Northwest | 2001-10-16
| Longview Power Station | Washington | Combined | Gas |  | 245 | 2004-01-01 |  | Enron |  | NWPPC | 2 |  | Cowlitz |  | Northwest | 2001-06-05
| Mint Farm Industrial Park | Washington | Combined | Gas |  | 249 | 2003-07-01 |  | Mirant | Purchased from Avista | NWPPC | 2 |  | Cowlitz |  | Northwest | 2001-09-12
| Cowlitz County Ics | Washington | Recip Eng | Gas |  | 35 | 2001-09-01 | 2002-08-30 | Cowlitz County PUD | 6MW online | NWPPC | 1 |  | Cowlitz |  | Northwest | 2001-09-12
| Cowlitz Cogeneration project | Washington | Combined | Gas | 2-2-1 | 395 | 2004-02-01 |  | Weyerhauser |  | WA State Web | 2 | 250 | Cowlitz |  | Northwest
| Franklin/Grays Harbor GTs | Washington | GT | Gas | 4 | 44 | 2001-12-01 |  | Franklin/Grays Harbor PUD |  | NWPPC | 3 |  | Franklin |  | Northwest | 2001-06-12
| Georgia Pacific Bellingham | Washington | Recip eng | Gas | 2 | 20 | 2001-12-01 |  | Georgia-Pacific |  | NWPPC | 3 |  | Franklin |  | Northwest | 2001-06-12
| Wheeler (Valley Electric) | Washington | Recip Eng | FO2/Gas |  | 38 | 2001-08-01 |  | Moses Lake Generation | Complete | NWPPC | 1 |  | Grant |  | Northwest | 2001-10-16
| B&G Farms | Washington | Recip Eng | FO2 | 15 | 33 | 2001-06-30 | 2002-06-30 | B&G Farms | Three projects. Complete. | NWPPC | 1 |  | Grant |  | Northwest | 2001-09-12
| Grant County Ics | Washington | Recip Eng | FO2 | 20 | 32 | 2001-06-15 | 2002-06-14 | Grant County PUD | Complete | NWPPC | 1 |  | Grant |  | Northwest | 2001-09-12
| Titan | Washington | Recip Eng | FO2 |  | 15 | 2001-08-01 | 2002-08-30 | Titan | Complete | NWPPC | 1 |  | Grant |  | Northwest | 2001-10-16
| John Day | Washington | Recip Eng | FO2 |  | 12 | 2001-03-01 | 2002-02-28 | Northwest Regional Power | Complete | NWPPC | 1 |  | Klickitat |  | Northwest | 2001-06-05
| John Day 2 | Washington | Recip Eng | FO2 |  | 20 | 2001-06-30 | 2002-06-30 | Northwest Regional Power | complete | NWPPC | 1 |  | Klickitat |  | Northwest | 2001-09-12
| Goldendale NW Aluminum GTs | Washington | GT | Gas | 4 | 190 | 2002-02-01 |  | Golendale NW Alum |  | NWPPC | 3 |  | Klickitat |  | Northwest | 2001-06-05
| Roosevelt Landfill | Washington | Recip Eng | FO2 |  | 16 | 2001-03-01 | 2002-02-28 | Northwest Regional Power | Complete | NWPPC | 1 |  | Klickitat |  | Northwest | 2001-06-05
| NW Hill Expansion | Washington | Recip eng | Gas | 2 | 10 | 2001-09-01 |  | Klickitat County PUD | Will convert to landfill gas complete | NWPPC | 1 |  | Klickitat |  | Northwest | 2001-09-12
| Goldendale | Washington | Combined | Gas | 1-1-1 | 248 | 2002-07-01 |  | Calpine |  | PMW | 1 | 135 | Klickitat |  | Northwest
| Chehalis Generation | Washington | Combined | Gas | 2-2-2 | 520 | 2002-12-01 |  | Tractebel |  | WA State Web | 2 | 220 | Lewis |  | Northwest
| Big Hanaford (Centralia) | Washington |  | Gas |  | 248 | 2002-07-01 |  | TransAlta |  | Corp Press Release | 1 | 210 | Lewis |  | Northwest | 2001-09-12
| NW Regional Power (Creston) | Washington | Combined | Gas | 4-4-2 | 838 | 2011-01-01 |  | Northwest Power Ent | Reg approval 9/96. Needs miles of gas pipe | WA Website | 2 |  | Lincoln |  | Northwest
| Satsop | Washington | Combined | Gas |  | 630 | 2004-06-01 |  | Duke | Rqs 40 miles of gas pipeline. Under Constr | Corp Website | 1 | 250 | Mason |  | Northwest | 2001-10-16
| Okanogan PUD | Washington | Recip Eng | FO2 | 16 | 26 | 2001-09-01 |  | Okanogan PUD | Complete | NWPPC | 1 |  | Okanogan |  | Northwest | 2001-10-16
| Tacoma Power Ics | Washington | Recip Eng | FO2 |  | 58 | 2001-06-01 | 2001-10-31 | Tacoma Light & Power | Complete | NWPPC | 1 |  | Pierce |  | Northwest | 2001-06-05
| Pierce Power | Washington | GT | Gas | 7 | 154 | 2001-09-01 | 2003-05-01 | TransAlta |  | NWPPC | 3 |  | Pierce |  | Northwest | 2001-09-12
| Port Frederickson Industrial | Washington |  | Gas |  | 324 | 2011-01-01 |  | Morgan Stanley |  | Yahoo News | 5 | 100 | Pierce |  | Northwest | 2001-06-13
| Frederickson 2 | Washington |  | Gas |  | 285 | 2011-01-01 |  | Frederickson Power | Joint venture EPCOR and Westcoast energy | PMA | 5 | 180 | Pierce |  | Northwest | 2001-09-12
| Frederickson | Washington |  | Gas |  | 249 | 2002-06-01 |  | Frederickson Power | Joint venture EPCOR & Westcoast energy | PMA | 1 | 160 | Pierce |  | Northwest | 2001-09-12
| Equilon GTs | Washington | GT | Gas | 7 | 35 | 2001-12-01 |  | Equilon Enterprises | Will replace Equilon Ics | NWPPC | 1 |  | Skagit |  | Northwest | 2001-06-12
| Fredonia Addition | Washington | GT | Gas |  | 106 | 2001-08-01 |  | Puget Sound Energy |  | NWPPC | 1 |  | Skagit |  | Northwest | 2001-06-05
| Tesoro Phase II | Washington | Recip Eng | Gas |  | 24 | 2001-09-01 | 2002-08-31 | Tesoro |  | NWPPC | 1 |  | Skagit |  | Northwest | 2001-06-05
| Equilon Ics | Washington | Recip Eng | FO2 |  | 38 | 2001-03-01 | 2002-02-28 | Equilon Enterprises | Complete | NWPPC | 1 |  | Skagit |  | Northwest | 2001-06-05
| Sedro-Wooley | Washington | GT | NG | 2 | 83 | 2001-06-30 |  | Tollhouse Energy |  | NWPPC/NWAPA | 1 |  | Skagit |  | Northwest | 2001-06-12
| Benton PUD | Washington | GT | NG | 1 | 27 | 2001-11-01 |  | Benton PUD |  | NWPPC | 1 |  | Skagit |  | Northwest | 2001-06-12
| Everett Delta | Washington |  | Gas |  | 248 | 2002-12-01 |  | FPL Energy | Purchased rights from NW Power | NWPPC | 2 |  | Snohomish |  | Northwest | 2001-09-12
| Everett Delta II | Washington |  | Gas |  | 248 | 2002-12-01 |  | Wasserstein Perella | Acquired through foreclosure | NWPPC | 2 |  | Snohomish |  | Northwest | 2001-09-12
| State Line Project | Washington | Wind | Wind |  | 200 | 2001-12-01 |  | FPL Energy | See Oregon Stateline project | FPL Website | 1 |  | Walla Walla |  | Northwest | 2001-10-16
| Wallula | Washington |  | Gas |  | 1350 | 2005-01-01 |  | Newport Generation |  | http://www.efsec.wa.gov/Default.htm | 3 | 550 | Walla Walla |  | Northwest | 2001-10-16
| BP Cherry Point GTs | Washington | GT | Gas | 14 | 73 | 2001-09-01 |  | Cherry Point Refinery | Complete | NWPPC | 1 |  | Whatcom |  | Northwest | 2001-09-12
| Georgia Pacific Ics | Washington | Recip Eng | FO2 |  | 19 | 2001-01-01 | 2001-12-31 | Georgia Pacific | Complete | NWPPC | 1 |  | Whatcom |  | Northwest | 2001-06-05
| Sumas 2 Generating Facility | Washington | Combined | Gas | 2-2-2 | 660 | 2003-12-01 |  | National Energy | EFSEC recommended denial of app | WEU/State Reg | 2 | 400 | Whatcom |  | Northwest | 2001-09-12
| BP Cherry Island | Washington | Combined | Gas | 3-3-2 | 750 | 2011-01-01 |  | Cherry Point Refinery |  | http://www.efsec.wa.gov/Default.htm | 4 |  | Whatcom |  | Northwest
| Cherry Point | Washington |  | Coal |  | 249 | 2004-04-01 |  | US Electric Power |  | PMW | 4 |  | Whatcom |  | Northwest
| Wygen I | Wyoming |  | Coal |  | 90 | 2003-06-01 |  | Black Hills | Under Construction | Corp Website | 1 |  | Campbell |  | Rocky Mountain
| Gillette Upgrade | Wyoming |  | Gas |  | 40 | 2001-06-01 |  | Black Hills |  | Corp Website/EIA | 1 |  | Campbell |  | Rocky Mountain
| Two Elk | Wyoming |  | Coal |  | 282 | 2003-04-01 |  | North American Power | Construction est to start in Spring 2001 | WY Air Quality | 2 |  | Campbell |  | Rocky Mountain
| Gillette Coal | Wyoming |  | Coal |  | 500 | 2005-07-01 |  | Black Hills |  | Corp Press Release | 4 |  | Campbell |  | Rocky Mountain
| Rock River | Wyoming | Wind | Wind |  | 50 | 2001-10-01 |  | Seawest |  |  | 1 |  | Carbon |  | Rocky Mountain | 2001-06-13
| Simpson Ridge | Wyoming | Wind | Wind |  | 10 | 2000-12-01 |  | Terra Moya | Complete | Energy Insight | 1 |  | Carbon |  | Rocky Mountain