## Sheet1
CONFIDENTIAL - ENA WEST DEVELOPMENT OPPORTUNITIES Date Revised: 05/04/00
PROJECT | LEAD BUSINESS DEV'MT | LEAD PROJECT DEV'MT | PROJECT SUPPORT | EQUIPMENT | TURBINES COMMITTED? | CONFIG | COMMENTS / ISSUES | NEAR TERM ACTION ITEMS | MAJOR REVENUE ENHANCEMENT / COST REDUCTION ITEMS, etc | MAJOR REVENUE DETRACTORS / COST INCREASE ITEMS, etc
I. YEAR 2000 TARGET COMPLETION OF DEVELOPMENT
Coyote Springs II | Thomas | Williams | Mullen | 1x7FA (250MW) | Yes | Combined Cycle (CC) | 1. Development underway 2. Nepco & ENA signed a limited notice to proceed on 4/13/00 3. Expected to execute turbine delivery contract on 05/11/00 for delivery in 06/01 | 1. Close sale of project with AVISTA (expected June 2000); 2. Complete GE Contract 3. EPC contract negotiations, and PGE/Avista discussions, ongoing | 1. Potential sale of project 2. Have permit | 1. Sharing with PGE
LV Cogen - Expansion ("Project Prescilla") | Clark / Gilbert |  | Williams | 4xLM6000 | Yes | CC | 1. Enron controls LV Cogen LM6000 plant, which is being evaluated for contract restructuring with Nevada Power 2. Air permits submitted (application for air permit deemed incomplete by APCD) 3. Enron has received the draft design basis scope | 1. Complete request for interconnection study with Nevada Power; 2. Meet on 05/08/00 or 05/09/00 to go over the design basis scope 3. Negotiate option and lease agreement 4. Provide response to APCD notification of incomplete air permit application by 5/19/00 | 1. LV load expansion 2. SP15 (California) | 1. Project is small size
Pastoria 2000 | Parquet | Wehn | Cheng, Browner, Hackett, Russell | 3x7FA (750MW) | Yes | CC | 1. Target CEC final approval date is 11/08/00 | 1. Developing solutions for three major issues: air/offsets, water contract and biology 2. Complete development and appeal period by 12/00 | 1. SP-15; 2. Border price gas; | 1. Offsets
PSCo RFP - Colorado Springs Site | Thome | TBD | Mullen | 6 x LM6000 (up to 200MW). 2x7FA if RFP response un- successful? | No | Single Cycle (SC) (or CC if RFP not successful?) | 1. Responded to PSCo RFP on 04/24/00. Won't hear from PSCo until 05/21/00 or 05/22/00. 2. 70 acre Site would cost $210K, transmission interconnection at Midway (colorado) substation to cost <$4M, 5-mile gas line needed, water available. 3. Entered into LOI for site on 4/24/00. 4. Project will help to balance the desk book | 1. Determine whether to proceed with the development even if RFP unsuccessful 2. Determine cost of gas interconnection 3. Await outcome of RFP process | 1. Desk book | 1. Small market
Tri Valley (Pleasanton) | Kates | UAE* | UAE* | 1 x LM6000 | Maybe | SC | 1. *Joint venture with UAE 2. Supportive local community 3. ISO board met 04/26/00 PG&E transmission alternative was selected | 1. Discuss RMR with ISO and UAE 2. UAE to begin air permit 3. Develop a DASH | 1. RMR? 2. UAE is a low cost developer | 1. Project is small size 2. Share returns with UAE
II. YEAR 2001 TARGET COMPLETION OF DEVELOPMENT
AES/El Paso Hunters Point Note - THIS IS STILL CONFIDENTIAL | Kates | TBD | Hackett, McCubbin | 1x7FA (Possible 501G) | No | CC | 1. Project has CEC permit subject to PG&E settlement of BRPU (submitted to CPUC for approval) and securing site control (will require Mayor Willie Brown intervention) 2. Project jointly owned by AES and El Paso 3. Hetch Hetchy is leaning towards a less formal process (than an RFP) (could have positive or negative effect) | 1. Meet with steam host 2. Chase AES and El Paso for response to acquisition proposal 3. Work with Hetch Hetchy to develop proposal. | 1. NP-15 2. Probable RMR 3. Possible CT expansion | 1. Only 1x7FA 2. Probable high political payments
Antelope Valley Note - THIS IS STILL CONFIDENTIAL | Kates | Russell, Hackett | TBD | 2 to 4 x 7FAs | No | CC | 1. On 3/28/00, ENA paid to have Antelope withdraw its queue position for Pastoria's benefit (net saving to Pastoria of $25 million) and purchased an option to acquire the Antelope project 2. Possible strategic play with Pastoria 2002 to save $40 million in transmission costs 3. Proceeding with parallel offset creation strategy 4. Transmission studies are continuing. | 1. Due diligence on the Antelope project 2. Final Phase 1 environmental study due 05/04/00 3. Execute transmission work order 4. Continue spring surveys 5. Await outcome of AQMD ruling on offset transfers (due 05/04/00) 6. Determine whether site access problem exists 7. Complete first draft of definitive agreement 8. Strike on option | 1. SP15 2. Border gas prices | 1. Offsets are likely to be expensive and hard to find 2. Transmission line and transmission mitigation will be major expenses.
Enner Connect (Partners on Cactus) have three development sites in NV: Mesquite, Searchlite, and Henderson | Vickers | Cheng | TBD | Various | No | TBD | 1. Enner Connect has opportunities at each of three sites. | 1. Determine if Enron wishes to pursue development of any or all of the sites (site visits to be scheduled in May) | 1. LV area | 1. Unknown, but partner would be involved
Humbolt | Kates | TBD | TBD | 2 to 4 x LM6000 | Maybe | TBD | 1. PG&E executive solicited Enron's interest in the opportunity 2. One site identified; another site is possible | 1. Determine project size (100 - 200MW) and value proposition 2. Meet and greet the city 3. Conduct formal site investigation | 1. NP-15 2. Probable RMR | 1. Project is small size (diseconomies of scale) 2. CEC permit required
Lodi | MacDonald, Dyer | TBD | Mainzer | TBD - May be able to support up to 500MW | No | TBD | 1. Gas accessible 2. Transmission is nearby 3. Wastewater discharge may be an issue 4. Muni may add value | 1. Determine value proposition 2. Await results of the transmission study 3. Investigate wastewater discharge 4. Assess Lodi's commitment to follow through with the project | 1. NP-15 2. Hourly, daily, monthly volatility 3. Value added from muni
Mountain View (Thermo Ecoteck) | Gilbert | TBD | TBD | 4x7FA | Yes (from Ecoteck) | CC | 1. Gilbert awaits invitation to partner from Thermo Ecoteck 2. CEC permit applied for early 2000 | None | 1. SP-15 2. RMR? | 1. Will have 50% partner
Roseville | MacDonald, Dyer | TBD | Mainzer | TBD - May be able to support up to 500MW | No | SC | 1. Muni has some value added to offer. | 1. Determine value proposition 2. Decide whether or not the site is too problematic 3. Assess Roseville's commitment to follow through with the project | 1. NP-15 2. Hourly, daily, monthly volatility 3. Value added from muni
Santa Clara | MacDonald, Dyer | TBD | Mainzer | TBD - May be able to support 250MW to 500MW | No | SC | 1. Muni has some value added to offer. 2. Very positive site visit and customer | 1. Determine whether an F or G turbine will fit on the site 2. Proactively develop a JV arrangement with the City (meeting with city on 05/03/00 went well.) Aiming for deal by mid may 3. Obtain rights over site (including, if possible, the 3.3 acre neighboring land) | 1. NP-15 2. Hourly, daily, monthly volatility 3. Value added from muni | 1. Project may be small size (diseconomies of scale)
III. YEAR 2002 TARGET COMPLETION OF DEVELOPMENT
Martinez | Cheng | Cheng | TBD | 1 x 7FA (250MW) | No | SC | 1. Adjacent to Shell refinery | 1. Determine value proposition 2. Investigate water sources and transmission issues 3. Decide whether Enron is willing to pay $800K - $1.6M for the site (up front). Bid due by end of June 2000. |  | 1. Project is small (diseconomies of scale)
Pastoria 2002 | Parquet | Wehn | Cheng, Browner, Hackett, Russell | 1x7FA (250MW) | Yes | CC | 1. Expansion of pastoria 2000 and 1000MW transmission line; 2. Significant permitting issues; 3. Pastoria 2000 permitting must be completed prior to Pastoria 2002 commencement | 1. Create ERCs | 1. SP-15; 2. Border price gas; 3. Possible RMR contract for all Pastoria 1000MW | 1. Power transmission line (cost of approximately $40 million); 2. Offsets
Sacramento | Cheng | Cheng | TBD | 2x7FA (500MW) | No | CC | 1. High capacity transmission and gas lines nearby 2. Access to SMUD, NP-15 and WAPA transmission lines | 1. Determine value proposition 2. Site visited on 04/26/00 - three major issues: water, emissions and transmission. | 1. NP-15, SMUD and WAPA; 2. Possible RMR contract