## Projects
Dates
Project Description |  |  | Responsible person | No. of units | Unit cost | Est. cost | Labor cost | Total cost/unit | Station cost | Other costs | Delivery | Submitted | Approved | Ordered | Received | Begin Installation | Completion
1 | Hydraulic valve lifters |  | Randy | 16 | 640 | 10240 | [9 empty] | 2000-10-18
| CECO |  | Hank, Matt
2 | Hydraulic valve lifter tester |  | Kent Beebe | 1 |  | 0
Borrow from Bushton or Beatrice
3 | Fuel balancing valves | Sta 2 | Randy Johnson | 0 | 550 | 0 |  |  | 0 |  | 2000-11-01 | [6 empty] | 16hrs for installation per unit
|  | Sta 1 |  | 33 | 550 | 18150 |  |  | 18150 |  | 2000-11-01 | [6 empty] | 16hrs for installation per unit
4 | Recip Trap 9240 |  | Ken Young | 1 | 50000 | 50000 |  |  |  | 50000
Matt Francis
5 | Cam modifications |  | Kent Beebe | No cam modifications for high altitude
Cam selection for high altitude, D-R revisions
6 | Platimum spark plugs |  | Ken Young
7 | Air vs Fuel flow program change |  | Ken Young
Kent Bebee
8 | Install magnetic pickups |  | Matt Francis
9 | Plug reach verification |  | Hank Hull
Matt Francis
10 | Press & temp meas schematics |  | Randy Johnson
11 | Oil consumption rate verification |  | Randy
Matt
12 | Piston revisions |  | Kent Beebe
13 | Piston ring use & design |  | Hank
Ken Young
14 | Pipeline control valves/effect |  | Gary Choquette
15 | Mhealth data |  | Ken Young
Mech Spc't
16 | Engine perf/cntl data comparison |  | Kent Beebe
Ken Young
17 | Compressor testing |  | Ken Young
| GC scheduling |  | Analyst
18 | Unit 201 turbo speed drop |  | Ken Young
19 | Compressor valves (CECO poppets) |  | Randy, Hank | [12 empty] | 2000-10-18
20 | Review Cooling System (46degF) |  | Kent Beebe Ken Young | [12 empty] | 2000-10-18
203
21 | Indicating Valves (compr/eng) |  | Ken Young
22

## Projects cost
|  | Responsible person | No. of units | Unit cost | Est. cost
Fuel balancing valves | Sta 2 | Randy Johnson | 0 | 550 | 0
| Sta 1 |  | 33 | 550 | 18150 | capital?
Rocker arm shafts |  | Woody | 8 | 2040 | 16320 | O&M or standby capital ?
Rocker arm bushings |  | Woody | 24 |  |  | O&M or standby capital ?
CECO hydraulic lifters |  | Randy | 14 | 535 | 7490 | capital?
High voltage megger |  | Ken Young | 1 | 3000 | 3000 | Large tool
Pressure gage, portable |  | Ken Young | 1 | -------------- | -------------- | No cost, have in DMS team
Tony Smith
|  |  | Total cost = |  | 44960

## Team member sched
[58 empty] | S1 | S1 | S1 | S1 | S1
|  | Analyst Schedule | [48 empty] | S1 | S1 | S1 | S1 | S1 |  |  | S2 | S2 | S2 | S2 | S2
|  | S# indicates station number | [28 empty] | S2 | S2 | S2 | S2 | [6 empty] | S4 |  |  |  | S4 | S4 | S3 | S3 |  |  | S2 | S2 | S2 | S2 | S2 |  |  |  |  | S4 | S4 | S4 |  |  | S4 | S4 | S4 | S3 | S3
|  | Outages indicated in Red | [43 empty] | Sta |  | Sta |  |  |  | Sta |  | Sta |  |  |  |  | Sta |  | Sta |  |  |  |  | Sta |  | Sta
[10 empty] | May | [17 empty] | May | [12 empty] | June |  |  |  |  | 4 |  | 3 |  |  |  | 2 |  | 2 |  |  |  |  | 1 |  | 1 |  |  |  |  | 4 |  | 3 |  |  | July
|  |  | S | S | M | T | W | T | F | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | out | T | out | S | S | M | out | W | out | F | S | S | M | out | W | out | F | S | S | M | out | W | out | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
| Team Member Schedule |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Ken Young |  |  |  | V | V | V | V | V | May M 21: Alb; May T 22: S2; May W 23: S2; May T 24: S2; May F 25: S2; May W 30: c; June T 5: S4; 4 out 6: S4; 4 T 7: S3; 3 out 8: S3; 3 M 11: S1; 2 out 12: S1; 2 W 13: S1; 2 out 14: S1; 2 F 15: S1; 2 M 18: S1; 1 out 19: S1; 1 W 20: S1; 1 out 21: S1; 1 F 22: S1
` | Randy Johnson | [8 empty] | May M 21: S2; May T 22: S2; May W 23: S2; May T 24: S2; May F 25: S2; May W 30: c; June T 5: S4; 4 out 6: S4; 4 T 7: S3; 3 out 8: S3; 3 M 11: c; 2 out 12: c; 2 W 13: c; 2 out 14: S1; 2 F 15: S1; 2 M 18: S1; 1 out 19: S1; 1 W 20: S1; 1 out 21: S1; 1 F 22: S1
Kent Beebe | bar: 3 M 11 to 2 F 15; 2 M 18 to 1 F 22
| Matt Francis | [8 empty] | May M 21: S2; May T 22: S2; May W 23: V; May T 24: V; May F 25: V; May T 29: V; May W 30: c; June F 1: S4; June T 5: S4; 4 out 6: S4; 4 T 7: S3; 3 out 8: S3; 3 M 11: S1; 2 out 12: S1; 2 W 13: S1; 2 out 14: S1; 2 F 15: S1; 2 M 18: S1; 1 out 19: S1; 1 W 20: S1; 1 out 21: S1; 1 F 22: S1; 1 M 25: S4; 4 out 26: S4; 4 W 27: S4; 3 out 28: S3; 3 F 29: S3
Hank Hull
Bo Ragan
| Jonny Hendricks | [8 empty] | May M 21: Alb; May T 22: c; May W 23: c; May T 24: c; May F 25: c; May W 30: c; June T 5: S4; 4 out 6: S4; 4 T 7: S3; 3 out 8: S3; 3 M 11: S2; 2 out 12: S2; 2 W 13: S2; 2 out 14: S2; 2 F 15: S2; 2 M 18: S2; 1 out 19: S2; 1 W 20: S2; 1 out 21: S2; 1 F 22: S2
| Todd Ingalls | [8 empty] | May M 21: Alb; May T 22: S2; May W 23: S2; May T 24: S2; May F 25: S2; June M 4: V; June T 5: V; 4 out 6: V; 4 T 7: V; 3 out 8: V; 3 M 11: S2; 2 out 12: c; 2 W 13: c; 2 out 14: c; 2 F 15: S2; 2 M 18: S1; 1 out 19: S1; 1 W 20: S1; 1 out 21: S1; 1 F 22: S1
Glen Hawthorn | bar: 3 M 11
Scott Hill
Station 2
Gary Maestas
Gary Choquette
Ron Matthews
Other Participants
Ralph Mireles, Analyst | bar: May W 30; 3 M 11 to 2 W 13; 1 W 20 to 1 F 22
David Carbajal, Analyst | bar: May W 30; 1 W 20 to 1 F 22
Larry Cambell, Emissions Spc
Butch Russell, Emissions Spc
Steve San Miguel | bar: May W 30; 3 M 11 to 2 W 13
Stoney Buchanan | bar: May W 30; 3 M 11 to 2 F 15; 2 M 18 to 1 F 22
Conf call
Conf call
Conf call
Conf call
Conf call

## Contacts
Contacts
Phone Numbers
Team Members | Office | Cell | Pager | Fax | Conference Ph#
Ken Young | 806-342-2043 | 806-886-8105 | 888-859-5919 | 806-342-2043
Randy Johnson | 520-774-2980 | 520-699-9136 | 888-827-1820
Kent Beebe | 316-562-4342 | 316-562-7774
Matt Francis, Analyst | 520 774 2980 ext 111 | c.520 699 8990 v.520 699 0489 | 800 587 7912
Hank Hull (Sta 2 )
Bo Ragan ( Sta 1 ) | 520-757-3620 | 520-716-1219 | 888-621-4103 | 520-757-4558
JB Callado ( Sta 3 ) | 520-714-9184
Chris Hulls ( Sta 3 ) | 520-714-9184
Howard Begay ( Sta 4 ) | 520-871-4266
Robert Sterns ( Sta 4 ) | 520-871-4266
Other Contacts
Gary Maestas | 713-345-5191
Rich Jolly
David "Tiny" Roensch, Advisor | 520-774-2980 x112 | 520-853-3253 | 800-375-4409 | 520-774-1669
Rick Smith - Gallup Team Advisor
Gary Choquette, Planning
Ron Matthews, Planning | 713-853-5830 | ----------------------------------------------------- |  |  | 800-713-8600 | 9473
Jerry Graves, GC | 713-345-8923 | 713-857-0057 | 888-530-1670
Ralph Mireles, Analyst
Mark McDonald, Analyst
Larry Campbell, Enviro Spec | 505-625-8022 | 505-626-6211
John Digiacomo, D-R Serv. Mgr. | 607-937-2679
Dave Boxall, D-R Mech Supr | 607-937-2107
Mike Jordan, D-R Mech | 607-937-2094
Jeff Horton - KAMs Inc | 800- 228- 5267
Erin Horton,Mfg Mgr - KAMs Inc | 405- 232- 2636
Carl Milam, CECO ---- | 915-367-7821 | [5 empty] | www.ceconet.com
Frank Tobert - Dynalco Service | 954-739-4300
800-368-6666
Scott Jenkins - Cook Manley | 281-261-5700
John Metcalf - Cook Manley | 281-261-5700 | [5 empty] | Engineer
Bob Parrb - T.F.Hudgins | 713-682-3651 | [5 empty] | Sales..