## Sheet1
Enron Transportation Services
System Outage Request/Notification
|  |  |  | Submittal Date |  | 2002-01-29
|  |  | Planned | X | Late: |  | Unplanned:
Region/Location: |  | Albuquerque
Reported By: |  | Team San Juan , Chris Gaston |  |  |  |  | New: |  | Revised
Telephone No: |  |  |  |  | If a Revision Enter outage ID#
or the Original Est. Start Date
FAX No:
Starting Date: |  | 2002-04-12 | Time: | 00:00 | Completion Date: |  | 2002-04-12 | Time: | 24:00
Descripition of Work: |  |  | Turn aroud at Bisti station,
Unit Down 24 hrs ,Unit maintenance,Sub station & PCR Building maintenance,
Valve Maintenance,
Facilities Affected
Compressor Station: |  | Bisti |  |  |  |  | Estimated Volume:
| Units: | # 1 |  |  |  |  | Horse Power:
Services Affected
Mainline: | [6 empty] | Aprox. Mile Post:
Branchline/Transmission: | [5 empty] | Reduced Operation Pressure:
| TBS: | [5 empty] | Farmtap:
Comments:
All Outages Fax Or E:mail To (Jerry Graves) |  |  |  | fax# (713)-345-3478 Houston
Facility Planning (Outage Coordinator) |  |  |  |  | fax# (402)-3987041 Omaha
For Unplanned Outages Add these Burst FAX Numbers ( Project Link):
( For unplanned outages in the Holcomb, Liberal, Mullinville & Amarillo Regions Only)
Oneok - Tulsa |  | Delaine Kruth |  |  | (918) 732-1355 |  | ET&S Gas Control (Houston): |  |  | 7138539155
Oneok - Bushton |  | Alan Siemer |  |  | (316) 562-4373 |  | ET&S Gary Spraggins: |  |  | 7136468000
Exxon-Mobil-Liberal |  | Ulysses |  |  | (316) 356-7580
[7 empty] | Anadarko: |  |  | 3166294505
OXY-Liberal |  | Jay Muse |  |  | (316) 624-7014
ETS - Liberal Operatons |  |  |  |  | (316) 626-2251