## 022802Bu
PLANNED AND UNPLANNED OUTAGES AFFECTING THE BUSHTON UNIVERSE.
2002-02-28
The information provided is tentative and may be changed without further notice. Northern Natural Gas Transwestern and Florida Gas Transmission are not responsible for any reliance on this information.
# | Region | Location | Units | Title | EstStart | EstComp | Dur (Days) | Est Flow Affected | Est Thru Affected | DescOfWork | ActStart | ActComp | Act Flow Affected | Planned Unplanned
18461 | AMA | BEAVER 12 | 1 | SUCTION SCRUBBER | 2001-12-29 12:00 | 2002-03-22 16:00 | 83.2 | 0 | 0 | Have suction scrubber rebuilt. | 2001-12-29 12:00 |  | 0 | U
18362 | AMA | BEAVER 12 | 3 | UNIT OVERHAUL | 2002-03-26 13:00 | 2002-04-26 16:00 | 31.1 | 0 | 0 | Overhaul Engine & Compressors. |  |  | 0 | P
18376 | AMA | BEAVER 2 | 5 | OVERHAUL | 2002-07-08 08:00 | 2002-08-09 16:00 | 32.3 | 0 | 0 | Major engine (Mike White OH). |  |  | 0 | P
18528 | AMA | BEAVER 2 | ALL | ESD | 2002-04-29 08:00 | 2002-04-29 12:00 | 0.2 | 10 | 1.7 | Annual ESD. |  |  | 0 | P
18380 | AMA | BEAVER 6 | 1 | OVERHAUL | 2002-09-01 08:00 | 2002-09-30 16:00 | 29.3 | 0 | 0 | Major Engine & compressor. |  |  | 0 | P
18460 | AMA | BEAVER 6 | ALL | ANNUAL ESD | 2002-05-08 10:00 | 2002-05-08 12:00 | 0.1 | 10.5 | 0.9 | Annual ESD. Will blind flange and not blow the station down. |  |  | 0 | P
18374 | AMA | BEAVER 7 | 1 | OVERHAUL | 2002-06-15 08:00 | 2002-06-30 16:00 | 15.3 | 0 | 0 | Major overhaul. |  |  | 0 | P
18384 | AMA | BEAVER 7 | 4 | OVERHAUL | 2002-10-15 08:00 | 2002-10-30 16:00 | 15.3 | 0 | 0 | Major Engine. |  |  | 0 | P
18386 | AMA | BEAVER 7 | 4 | OVERHAUL | 2002-11-01 08:00 | 2002-11-30 16:00 | 29.3 | 0 | 0 | Major Compressor. |  |  | 0 | P
18365 | AMA | BEAVER PLANT | 9 | OVERHAUL | 2002-03-01 08:00 | 2002-03-30 16:00 | 29.3 | 0 | 0 | Major engine & compressors. |  |  | 0 | P
18367 | AMA | BEAVER PLANT | 12 | OVERHAUL | 2002-04-01 08:00 | 2002-04-30 16:00 | 29.3 | 0 | 0 | Major enigne & compressors. |  |  | 0 | P
18369 | AMA | BEAVER PLANT | 14 | OVERHAUL | 2002-05-01 08:00 | 2002-06-01 16:00 | 31.3 | 0 | 0 | Major engine and compressors. |  |  | 0 | P
18412 | AMA | BEAVER PLANT | 18 | WATER PUMP | 2002-02-06 15:00 | 2002-03-07 16:00 | 29 | 0 | 0 | Water pump gears. | 2002-02-06 15:00 |  | 0 | U
18522 | AMA | BEAVER PLANT | ESD | ESD | 2002-04-29 08:00 | 2002-04-29 12:00 | 0.2 | 600 | 100 | Annual ESD. |  |  | 0 | P
18385 | AMA | ELLIS 1 | 1 | OVERHAUL | 2002-10-15 08:00 | 2002-11-15 16:00 | 31.3 | 0 | 0 | Major Engine. |  |  | 0 | P
18459 | AMA | ELLIS 1 | ALL | ANNUAL ESD | 2002-05-07 09:00 | 2002-05-07 11:00 | 0.1 | 21 | 1.8 | Annual ESD. Will blind flange and not blow the station down. |  |  | 0 | P
18513 | AMA | ELLIS 2 | ALL | ESD | 2002-05-15 09:00 | 2002-05-15 11:00 | 0.1 | 0 | 0 | Annual ESD. |  |  | 0 | P
18505 | AMA | NORTHRUP | 1 2 | RELIEF VALVE TEST | 2002-03-19 08:00 | 2002-03-19 16:00 | 0.3 | 15 | 5 | Testing the the relief valves. |  |  | 0 | P
18529 | AMA | NORTHRUP | ALL | SAMPLE DEHY DESICCATE | 2002-02-28 08:00 | 2002-02-28 12:00 | 0.2 | 15 | 2.5 | Need to pull a sample of the dehy desiccate. |  |  | 0 | U
18524 | AMA | NORTHRUP | ALL | ESD | 2002-04-29 08:00 | 2002-04-29 16:00 | 0.3 | 10 | 3.3 | Annual ESD. |  |  | 0 | P
18504 | AMA | PERRYTON BARLOW | 1 2 3 | TEST RELIEF VALVES | 2002-03-18 08:00 | 2002-03-18 16:00 | 0.3 | 7 | 2.3 | Relief valve testing. |  |  | 0 | P
18525 | AMA | PERRYTON BARLOW | ALL | ESD | 2002-04-29 08:00 | 2002-04-29 16:00 | 0.3 | 7 | 2.3 | Annual ESD. |  |  | 0 | P
18523 | AMA | SPEARMAN | ESD & A LINE | ESD & A LINE LEAKS | 2002-04-29 08:00 | 2002-04-30 16:00 | 1.3 | 48 | 64 | Annual ESD. Need to repair several A Line leaks. ESD and back on with 25 mmcf in 4 hours. |  |  | 0 | P
18378 | AMA | WOODWARD 1 | 3 | OVERHAUL | 2002-08-01 08:00 | 2002-08-30 16:00 | 29.3 | 0 | 0 | Major Engine. |  |  | 0 | P
18514 | AMA | WOODWARD 1 | ALL | ESD | 2002-06-12 09:00 | 2002-06-12 11:00 | 0.1 | 0 | 0 | Annual ESD. |  |  | 0 | P
18381 | AMA | WOODWARD 2 | 4 | OVERHAUL | 2002-09-01 08:00 | 2002-09-30 16:00 | 29.3 | 0 | 0 | Major Engine. |  |  | 0 | P
18515 | AMA | WOODWARD 2 | ALL | ESD | 2002-07-17 09:00 | 2002-07-17 11:00 | 0.1 | 0 | 0 | Annual ESD. |  |  | 0 | P
18382 | AMA | WOODWARD 3 | 4 | OVERHAUL | 2002-09-15 08:00 | 2002-09-30 16:00 | 15.3 | 0 | 0 | Major Compressor. |  |  | 0 | P
18516 | AMA | WOODWARD 3 | ALL | ESD | 2002-06-19 09:00 | 2002-06-19 11:00 | 0.1 | 0 | 0 | Annual ESD. |  |  | 0 | P
17151 | BEA | BUSHTON | 26 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  | 0 | P
17152 | BEA | BUSHTON | 27 | OVERHAUL | 2002-06-03 08:00 | 2002-07-03 16:00 | 30.3 | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  | 0 | P
18506 | BEA | BUSHTON | 31 | EXHAUST HEADER | 2002-03-05 07:00 | 2002-03-07 15:30 | 2.3 | 0 | 0 | Replace section of exhaust header. |  |  | 0 | P
18527 | BEA | BUSHTON | ALL | ESD | 2002-05-07 07:30 | 2002-05-07 20:00 | 0.5 | 400 | 216.7 | Annual ESD. We should be able to bypass some volumes through the station using Clifton H.P. |  |  | 0 | P
17154 | BEA | CUNNINGHAM | 5 | OVERHAUL & CRACKED MANIFOLD | 2002-03-04 07:00 | 2002-03-25 15:30 | 21.3 | 50 | 1066.7 | Major overhaul MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. Repair Manifold. (Flow affect is about 50 mmcfd depending on the needs on the pipeline). |  |  | 0 | P
18466 | LIB | BEAVER 1 | 3 | BORESCOPE | 2002-03-12 08:00 | 2002-03-13 16:00 | 1.3 | 0 | 0 | Borescope power cylinder. |  |  | 0 | P
18465 | LIB | BEAVER 1 | ALL | ESD | 2002-04-29 08:00 | 2002-04-29 12:00 | 0.2 | 14 | 2.3 | Annual ESD. |  |  | 0 | P
18401 | LIB | BURDETT | 1 | BORESCOPE & MINOR MAINTENANCE | 2002-04-29 07:30 | 2002-05-10 16:00 | 11.4 | 0 | 0 | Borescope and minor maintenance. |  |  | 0 | P
18402 | LIB | BURDETT | 2 | BORESCOPE & MAINTENANCE | 2002-05-20 07:30 | 2002-05-31 16:00 | 11.4 | 0 | 0 | Borescope and minor maintenance. |  |  | 0 | P
18403 | LIB | BURDETT | 3 | BORESCOPE & MAINTENANCE | 2002-06-10 07:30 | 2002-06-21 16:00 | 11.4 | 0 | 0 | Borescope and minor maintenance. |  |  | 0 | P
18404 | LIB | BURDETT | 4 | BORESCOPE & MAINTENANCE | 2002-07-01 07:30 | 2002-07-12 16:00 | 11.4 | 0 | 0 | Borescope and minor maintenance. |  |  | 0 | P
18405 | LIB | BURDETT | 5 | BORESCOPE & MAINTENANCE | 2002-07-22 07:30 | 2002-08-02 16:00 | 11.4 | 0 | 0 | Borescope and minor maintenance. |  |  | 0 | P
18406 | LIB | BURDETT | 6 | BORESCOPE & MAINTENANCE | 2002-08-12 07:30 | 2002-08-30 16:00 | 18.4 | 0 | 0 | Possible overhaul- ECS other wise Borescope & minor maintenance. |  |  | 0 | P
18408 | LIB | BURDETT | ALL | ANNUAL ESD | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 | 0 | 0 | Annual ESD will shut down during the same time as Holcomb's ESD. |  |  | 0 | P
18407 | LIB | BURDETT | ALL | RELIEF VALVE TESTING | 2002-06-17 07:30 | 2002-06-21 16:00 | 4.4 | 0 | 0 | Will take one unit down at a time to do the testing. |  |  | 0 | P
18409 | LIB | BURDETT | ALL | JACKET WATER PROJECT | 2002-07-01 08:00 | 2002-07-01 16:00 | 0.3 | 0 | 0 | There is no firm date for this outage yet if at all. |  |  | 0 | P
18468 | LIB | CLARK 1 | 1 | BORESCOPE | 2002-03-05 08:00 | 2002-03-06 16:00 | 1.3 | 2 | 2.7 | Borescope the power cylinder. |  |  | 0 | P
18467 | LIB | CLARK 1 | ALL | ESD | 2002-04-29 08:00 | 2002-04-29 20:00 | 0.5 | 6.5 | 3.3 | Annual ESD. |  |  | 0 | P
18469 | LIB | CLARK 2 | ALL | ESD | 2002-04-29 08:00 | 2002-04-29 20:00 | 0.5 | 6 | 3 | Annual ESD. |  |  | 0 | P
18511 | LIB | FINNEY 1 2 3 4 | ALL | ANNUAL ESD | 2002-05-02 07:30 | 2002-05-02 16:00 | 0.4 | 0 | 0 | Annual ESD's for the Finney Co. Stations. 1 2 3 and 4. |  |  | 0 | P
18012 | LIB | FINNEY 2 | 1 | MAINTENANCE | 2002-03-05 08:00 | 2002-03-07 16:00 | 2.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18368 | LIB | FINNEY 2 | 1 | OVERHAUL | 2002-04-15 08:00 | 2002-04-30 16:00 | 15.3 | 0 | 0 | Inframe engine & compressor OH. |  |  | 0 | P
18013 | LIB | FINNEY 2 | 2 | MAINTENANCE | 2002-03-07 08:00 | 2002-03-08 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18014 | LIB | FINNEY 2 | 3 | MAINTENANCE | 2002-03-12 08:00 | 2002-03-13 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18016 | LIB | FINNEY 2 | 5 | MAINTENANCE | 2002-03-18 08:00 | 2002-03-18 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18017 | LIB | FINNEY 2 | 6 | MAINTENANCE | 2002-03-19 08:00 | 2002-03-20 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18018 | LIB | FINNEY 2 | 7 | MAINTENANCE | 2002-03-21 08:00 | 2002-03-22 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18019 | LIB | FINNEY 2 | 8 | MAINTENANCE | 2002-03-26 08:00 | 2002-03-27 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18020 | LIB | FINNEY 2 | 9 | MAINTENANCE | 2002-03-28 08:00 | 2002-03-29 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18364 | LIB | FINNEY 3 | 1 | ENGINE EXCHANGE | 2002-04-01 08:00 | 2002-04-15 16:00 | 14.3 | 0 | 0 | Engine exchange. |  |  | 0 | P
18047 | LIB | FINNEY 3 | 1 | MAINTENANCE | 2002-12-06 08:00 | 2002-12-06 16:00 | 0.3 | 0 | 0 | Scheduled maintenance - work orders & DET list. |  |  | 0 | P
18015 | LIB | FINNEY 3 | 3 | MAINTENANCE | 2002-03-14 09:00 | 2002-03-14 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18400 | LIB | FINNEY 4 | 3 | OVERHAUL | 2002-03-11 08:00 | 2002-04-05 16:30 | 25.3 | 3 | 76 | The unit will pulled out and overhauled. (Unit #2 will be down also due to no demand form unit #3). |  |  | 0 | P
18363 | LIB | FINNEY 4 | 4 | OVERHAUL | 2002-04-15 08:00 | 2002-05-10 16:30 | 25.3 | 3 | 76 | Unit will be pulled out and overhauled. (Unit Exchange if possible). |  |  | 0 | P
18456 | LIB | HOLCOMB | 1 | CAM BOX | 2002-03-11 08:00 | 2002-03-12 16:00 | 1.3 | 0 | 0 | Working on the Cam Box. |  |  | 0 | P
17836 | LIB | HOLCOMB | 10 | REPLACE PISTONS & RINGS | 2002-05-01 08:00 | 2002-05-31 16:00 | 30.3 | 0 | 0 | Replace pistons and rings overhaul 2 & 3 compressors. |  |  | 0 | P
17839 | LIB | HOLCOMB | ESD | ANNUAL ESD | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 | 135 | 22.5 | Annual ESD and maintenance. |  |  | 0 | P
17840 | LIB | HOLCOMB | HOLCOMB SOUTH | ESD | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 | 8 | 1.3 | Outage coordinated with Holcomb's Annual ESD. |  |  | 0 | P
18458 | LIB | HUGOTON | 16 | WARRENTY WORK | 2002-02-26 08:00 | 2002-02-26 16:00 | 0.3 | 0 | 0 | Cooper is doing warrenty work on the blower. |  |  | 0 | P
18314 | LIB | HUGOTON | 16 | SERVICE & MAINTENANCE | 2002-10-08 08:00 | 2002-10-08 16:00 | 0.3 | 0 | 0 | Service and maintenance. |  |  | 0 | P
18102 | LIB | HUGOTON | 17 | SERVICE | 2002-10-15 08:00 | 2002-10-15 14:00 | 0.3 | 0 | 0 | Service and maintenance. 1800 HP |  |  | 0 | P
18089 | LIB | HUGOTON | ALL | ESD | 2002-05-07 07:30 | 2002-05-09 16:00 | 2.4 | 80 | 190 | Planned ESD. (Actual completion time depends on contractors). |  |  | 0 | P
17634 | LIB | MORTON 1 | 3 | MP2 | 2002-07-08 07:30 | 2002-07-26 16:00 | 18.4 | 0 | 0 | MP2 8 000 hour inspection. |  |  | 0 | P
17644 | LIB | MORTON 1 | 3 | CONTROLS PM | 2002-12-02 07:30 | 2002-12-06 16:00 | 4.4 | 0 | 0 | Controls PM |  |  | 0 | P
17622 | LIB | MORTON 1 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-07 13:00 | 0.3 | 18 | 4.5 | Annual ESD. |  |  | 0 | P
17626 | LIB | MORTON 6 | 1 | MP 2 | 2002-05-13 07:30 | 2002-05-15 16:00 | 2.4 | 4 | 9.5 | MP2 8 000 hour inspect. |  |  | 0 | P
17628 | LIB | MORTON 6 | 2 | MP2 | 2002-05-28 07:30 | 2002-05-30 16:00 | 2.4 | 4 | 9.5 | MP2 8 000 hr inspection |  |  | 0 | P
17643 | LIB | MORTON 6 | 2 | CONTROLS PM | 2002-10-14 07:30 | 2002-10-16 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17623 | LIB | MORTON 6 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-07 13:00 | 0.3 | 8 | 2 | Annual ESD. |  |  | 0 | P
18370 | LIB | MULLINVILLE | 8 AUX. | OVERHAUL | 2002-05-01 08:00 | 2002-05-03 16:00 | 2.3 | 0 | 0 | TEO |  |  | 0 | P
18494 | LIB | MULLINVILLE | ALL | ESD | 2002-04-29 08:00 | 2002-04-29 20:00 | 0.5 | 400 | 200 | Annual ESD. |  |  | 0 | P
18375 | LIB | STEVENS 1 | 4 | OVERHAUL | 2002-06-15 08:00 | 2002-06-30 16:00 | 15.3 | 0 | 0 | Major compressor and all five cylinders. |  |  | 0 | P
18073 | LIB | STEVENS 1 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-07 10:30 | 0.1 | 30 | 3.8 | Annual ESD. |  |  | 0 | P
17773 | LIB | STEVENS 2 | 3 | SERVICE | 2002-12-04 08:00 | 2002-12-04 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM. 1324 HP |  |  | 0 | P
17774 | LIB | STEVENS 2 | 6 | SERVICE | 2002-03-06 08:00 | 2002-03-06 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM 1234 HP |  |  | 0 | P
17817 | LIB | STEVENS 2 | 6 | MP2 | 2002-10-09 08:00 | 2002-10-09 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17780 | LIB | STEVENS 2 | 7 | SERVICE | 2002-07-23 08:00 | 2002-07-23 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM. 1234 HP |  |  | 0 | P
18379 | LIB | STEVENS 2 | 8 | OVERHAUL | 2002-08-10 08:00 | 2002-08-30 16:00 | 20.3 | 0 | 0 | Compressor overhaul. |  |  | 0 | P
17788 | LIB | STEVENS 2 | 8 | SERVICE | 2002-12-05 08:00 | 2002-12-05 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM. 764 HP |  |  | 0 | P
17842 | LIB | STEVENS 2 | ALL | ANNUAL ESD | 2002-05-07 08:00 | 2002-05-07 10:30 | 0.1 | 19 | 1.6 | Annual ESD |  |  | 0 | P
17846 | LIB | STEVENS 3 | 3 | SERVICE | 2002-03-19 08:00 | 2002-03-20 16:00 | 1.3 | 0 | 0 | Service unit plus panel S/D & PM MP2 Tasks. 1100 HP |  |  | 0 | P
18493 | LIB | STEVENS 3 | ALL | ESD | 2002-05-07 07:30 | 2002-05-07 10:30 | 0.1 | 6 | 0.8 | Annual ESD. |  |  | 0 | P
18436 | LIB | STEVENS 4 | 1 | MP2 | 2002-03-20 08:00 | 2002-03-20 20:00 | 0.5 | 3.5 | 1.8 | MP2 tasks. |  |  | 0 | P
18437 | LIB | STEVENS 4 | 1 | MP2 | 2002-04-17 08:00 | 2002-04-17 20:00 | 0.5 | 3.5 | 1.8 | MP2 tasks. |  |  | 0 | P
18438 | LIB | STEVENS 4 | 1 | SERVICE | 2002-05-09 08:00 | 2002-05-10 20:00 | 1.5 | 3.5 | 5.3 | Service and MP2 tasks. |  |  | 0 | P
18439 | LIB | STEVENS 4 | 1 | MP2 | 2002-06-19 08:00 | 2002-06-19 20:00 | 0.5 | 3.5 | 1.8 | MP2 tasks. |  |  | 0 | P
18440 | LIB | STEVENS 4 | 1 | MP2 | 2002-07-17 08:00 | 2002-07-17 20:00 | 0.5 | 3.5 | 1.8 | MP2 tasks. |  |  | 0 | P
18441 | LIB | STEVENS 4 | 1 | MP2 | 2002-08-14 08:00 | 2002-08-14 20:00 | 0.5 | 3.5 | 1.8 | MP2 tasks. |  |  | 0 | P
18442 | LIB | STEVENS 4 | 1 | SERVICE | 2002-09-11 08:00 | 2002-09-12 16:00 | 1.3 | 3.5 | 4.7 | Service and MP2 tasks. |  |  | 0 | P
18443 | LIB | STEVENS 4 | 1 | MP2 | 2002-10-16 08:00 | 2002-10-16 20:00 | 0.5 | 3.5 | 1.8 | MP2 tasks. |  |  | 0 | P
17882 | LIB | STEVENS 4 | 1 | SERVICE | 2002-11-05 08:00 | 2002-11-06 16:00 | 1.3 | 0 | 0 | Panel S/D & PM MP 2. |  |  | 0 | P
18444 | LIB | STEVENS 4 | 1 | MP2 | 2002-12-11 08:00 | 2002-12-11 20:00 | 0.5 | 3.5 | 1.8 | MP2 tasks. |  |  | 0 | P
18446 | LIB | STEVENS 4 | 2 | SERVICE | 2002-03-13 08:00 | 2002-03-14 16:00 | 1.3 | 3.5 | 4.7 | Service and MP2 tasks. |  |  | 0 | P
18447 | LIB | STEVENS 4 | 2 | MP2 | 2002-04-18 08:00 | 2002-04-18 20:00 | 0.5 | 3.5 | 1.8 | MP2 tasks. |  |  | 0 | P
18448 | LIB | STEVENS 4 | 2 | MP2 | 2002-05-23 08:00 | 2002-05-23 20:00 | 0.5 | 3.5 | 1.8 | MP2 tasks. |  |  | 0 | P
18430 | LIB | STEVENS 4 | 2 | MP2 | 2002-06-20 08:00 | 2002-06-20 20:00 | 0.5 | 3 | 1.5 | MP2 tasks. |  |  | 0 | P
18431 | LIB | STEVENS 4 | 2 | SERVICE | 2002-07-10 08:00 | 2002-07-11 16:00 | 1.3 | 3 | 4 | Service & MP2. |  |  | 0 | P
18432 | LIB | STEVENS 4 | 2 | MP2 | 2002-08-15 08:00 | 2002-08-15 20:00 | 0.5 | 3 | 1.5 | MP2 tasks. |  |  | 0 | P
18433 | LIB | STEVENS 4 | 2 | MP2 | 2002-09-26 08:00 | 2002-09-26 20:00 | 0.5 | 3 | 1.5 | MP2 tasks. |  |  | 0 | P
18434 | LIB | STEVENS 4 | 2 | MP2 | 2002-10-17 08:00 | 2002-10-17 20:00 | 0.5 | 3 | 1.5 | MP2 tasks. |  |  | 0 | P
17885 | LIB | STEVENS 4 | 2 | SERVICE | 2002-11-13 08:00 | 2002-11-14 16:00 | 1.3 | 0 | 0 | Service unit panel S/D & MP 2. |  |  | 0 | P
18435 | LIB | STEVENS 4 | 2 | MP2 | 2002-12-12 08:00 | 2002-12-12 20:00 | 0.5 | 3 | 1.5 | MP2 tasks. |  |  | 0 | P
17889 | LIB | STEVENS 4 | 3 | SERVICE | 2002-11-06 08:00 | 2002-11-06 20:00 | 0.5 | 0 | 0 | Panel S/D & MP 2. |  |  | 0 | P
17892 | LIB | STEVENS 4 | 4 | OVERHAUL | 2002-06-01 08:00 | 2002-07-01 16:00 | 30.3 | 0 | 0 | Comp. & engine overhaul. |  |  | 0 | P
17895 | LIB | STEVENS 4 | ALL | ANNUAL ESD | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 | 18 | 42 | Annual ESD. (Station will be back up when Hugoton comes back on). |  |  | 0 | P
18471 | LIB | STEVENS 6 | ALL | ESD | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 | 18 | 42 | Annual ESD. (The station will be back on line when the Hugoton plant comes back on). |  |  | 0 | P
18062 | LIB | STEVENS 7 | 1 | MP2 | 2002-03-05 09:00 | 2002-03-07 16:00 | 2.3 | 4 | 9.2 | MP2 Tasks. |  |  | 0 | P
18472 | LIB | STEVENS 7 | ALL | ESD | 2002-05-07 08:00 | 2002-05-07 10:30 | 0.1 | 30 | 2.5 | Annual ESD. |  |  | 0 | P
17986 | LIB | SUBLETTE | 13 | MP2 | 2002-02-27 08:00 | 2002-02-28 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17987 | LIB | SUBLETTE | 13 | MP2 | 2002-03-13 08:00 | 2002-03-14 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17988 | LIB | SUBLETTE | 13 | MP2 | 2002-03-27 08:00 | 2002-03-28 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17939 | LIB | SUBLETTE | 14 | MP2 | 2002-03-07 08:00 | 2002-03-08 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17940 | LIB | SUBLETTE | 14 | MP2 | 2002-03-20 08:00 | 2002-03-21 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17945 | LIB | SUBLETTE | 19 | MP2 | 2002-03-04 08:00 | 2002-03-05 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17946 | LIB | SUBLETTE | 19 | MP2 | 2002-03-25 08:00 | 2002-03-26 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17951 | LIB | SUBLETTE | 20 | MP2 | 2002-03-15 08:00 | 2002-03-16 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17952 | LIB | SUBLETTE | 20 | MP2 | 2002-03-29 08:00 | 2002-03-30 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17957 | LIB | SUBLETTE | 21 | MP2 | 2002-03-11 08:00 | 2002-03-12 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17958 | LIB | SUBLETTE | 21 | MP2 | 2002-03-28 08:00 | 2002-03-29 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17963 | LIB | SUBLETTE | 22 | MP2 | 2002-03-01 08:00 | 2002-03-02 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17964 | LIB | SUBLETTE | 22 | MP2 | 2002-03-22 08:00 | 2002-03-23 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17969 | LIB | SUBLETTE | 23 | MP2 | 2002-03-05 08:00 | 2002-03-06 08:00 | 1 | 9 | 9 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17970 | LIB | SUBLETTE | 23 | MP2 | 2002-03-26 08:00 | 2002-03-27 08:00 | 1 | 9 | 9 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17975 | LIB | SUBLETTE | 24 | MP2 | 2002-03-08 08:00 | 2002-03-09 08:00 | 1 | 9 | 9 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17976 | LIB | SUBLETTE | 24 | MP2 | 2002-03-21 08:00 | 2002-03-22 08:00 | 1 | 9 | 9 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17981 | LIB | SUBLETTE | 26 | MP2 | 2002-03-04 08:00 | 2002-03-05 08:00 | 1 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17982 | LIB | SUBLETTE | 26 | MP2 | 2002-03-25 08:00 | 2002-03-26 08:00 | 1 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17933 | LIB | SUBLETTE | 27 | MP2 | 2002-03-15 08:00 | 2002-03-16 08:00 | 1 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17934 | LIB | SUBLETTE | 27 | MP2 | 2002-03-29 08:00 | 2002-03-30 08:00 | 1 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
18473 | LIB | SUBLETTE | ALL | ESD | 2002-05-07 08:00 | 2002-05-07 14:00 | 0.3 | 0 | 0 | Annual ESD. (Flow affects are in Hugoton's outage). |  |  | 0 | P
17754 | LIB | TATE | 10 | INSPECTION | 2002-12-02 08:00 | 2002-12-13 16:00 | 11.3 | 0 | 0 | Unit inspection. |  |  | 0 | P
17755 | LIB | TATE | 11 | INSPECTION | 2002-12-16 08:00 | 2002-12-20 16:00 | 4.3 | 0 | 0 | Unit inspection. |  |  | 0 | P
17757 | LIB | TATE | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 | 14 | 2.3 | Annual ESD test. |  |  | 0 | P
17620 | LIB | TEXAS 1 | 2 | CONTROLS PM | 2002-04-08 07:30 | 2002-04-08 16:00 | 0.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17669 | LIB | TEXAS 1 | 2 | ENGINE SERVICE | 2002-08-27 08:00 | 2002-08-27 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17670 | LIB | TEXAS 1 | 2 | INSPEC TION | 2002-10-21 08:00 | 2002-10-25 16:00 | 4.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
17627 | LIB | TEXAS 1 | 3 | CONTROLS PM | 2002-05-14 07:30 | 2002-05-16 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17672 | LIB | TEXAS 1 | 3 | ENGINE SERVICE | 2002-06-05 08:00 | 2002-06-05 16:00 | 0.3 | 0 | 0 | Engine service |  |  | 0 | P
17621 | LIB | TEXAS 1 | 6 | CONTROLS PM | 2002-04-15 07:30 | 2002-04-17 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17624 | LIB | TEXAS 1 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-08 14:00 | 1.3 | 10 | 12.9 | Annual ESD. |  |  | 0 | P
17629 | LIB | TEXAS 2 | 1 | CONTROLS PM | 2002-06-10 07:30 | 2002-06-10 16:00 | 0.4 | 0 | 0 | Controls PM |  |  | 0 | P
17631 | LIB | TEXAS 2 | 2 | CONTROLS PM | 2002-06-18 07:30 | 2002-06-18 16:00 | 0.4 | 0 | 0 | Controls PM |  |  | 0 | P
17633 | LIB | TEXAS 2 | 3 | CONTROLS PM | 2002-07-08 07:30 | 2002-07-08 16:00 | 0.4 | 0 | 0 | Controls PM |  |  | 0 | P
17635 | LIB | TEXAS 2 | 4 | CONTROLS PM | 2002-07-15 07:30 | 2002-07-15 16:00 | 0.4 | 0 | 0 | Controls PM |  |  | 0 | P
17636 | LIB | TEXAS 2 | 5 | CONTROLS PM | 2002-08-05 07:30 | 2002-08-05 16:00 | 0.4 | 0 | 0 | Controls PM |  |  | 0 | P
17618 | LIB | TEXAS 2 | 6 | CONTROLS PM | 2002-03-04 07:30 | 2002-03-04 16:00 | 0.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17676 | LIB | TEXAS 2 | 6 | ENGINE SERVICE | 2002-04-18 08:00 | 2002-04-18 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17677 | LIB | TEXAS 2 | 6 | INSPECTION | 2002-07-22 08:00 | 2002-07-22 16:00 | 0.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
17678 | LIB | TEXAS 2 | 6 | ENGINE SERVICE | 2002-09-18 08:00 | 2002-09-18 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17619 | LIB | TEXAS 2 | 7 | CONTROLS PM | 2002-03-11 07:30 | 2002-03-11 16:00 | 0.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17674 | LIB | TEXAS 2 | 7 | INSPECTION | 2002-06-24 08:00 | 2002-06-24 16:00 | 0.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
17675 | LIB | TEXAS 2 | 7 | ENGINE SERVICE | 2002-07-30 08:00 | 2002-07-30 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17625 | LIB | TEXAS 2 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-08 14:00 | 1.3 | 15 | 19.4 | Annual ESD. |  |  | 0 | P