## Palo Verde 03
Owner Name | Arizona Public Service Co.
Station Name | Palo Verde Nuclear Power Station
Unit Name | Palo Verde 03
NERC Region | WSCC
State | AZ
Fuel Type | Nuclear
Capacity | 1,403 MW
Start Date | 2001-09-28
End Date | 2001-11-06
Prv. Start Date | 2001-09-28
Prv. End Date | 2001-11-05
Comments | Refuel. Connected to the grid this morning, still doing testing. Hoping to reach 100% in a couple of days, it all depends on how testing goes.
SIC | 4911
Plant ID | 1015283
Unit ID | 1007878
Outage ID | 7842

## Palo Verde 02
Owner Name | Arizona Public Service Co.
Station Name | Palo Verde Nuclear Power Station
Unit Name | Palo Verde 02
NERC Region | WSCC
State | AZ
Fuel Type | Nuclear
Capacity | 1,403 MW
Start Date | 2001-09-28
End Date | 2001-11-09
Prv. Start Date | 2001-10-11
Prv. End Date | 2001-11-05
Comments | CEA changeout. Expect to be back on line by Friday. Full power a couple of days later.
SIC | 4911
Plant ID | 1015283
Unit ID | 1007874
Outage ID | 18635

## Electrifarm CT 03
Owner Name | MidAmerican Energy Company
Station Name | Electrifarm Peaking Generation
Unit Name | CT 03
NERC Region | MAPP
State | IA
Fuel Type | Natural Gas / Fuel Oil
Capacity | 104 MW
Start Date | 2001-09-28
End Date | 2001-11-08
Prv. Start Date | 2001-10-28
Prv. End Date | 2001-10-31
Comments | Boroscope
SIC | 4911
Plant ID | 1049331
Unit ID | 1015245
Outage ID | 17059

## Comanche 01-2 CT
Owner Name | AEP - Public Service Company of Oklahoma
Station Name | Comanche Power Station
Unit Name | Unit 01-2 CT/HRSG
NERC Region | SPP
State | OK
Fuel Type | Natural Gas / Fuel Oil
Capacity | 85 MW
Start Date | 2001-09-28
End Date | 2001-11-08
Prv. Start Date | 2001-11-07
Prv. End Date | 2001-11-10
Comments | Inspection
SIC | 4911
Plant ID | 1009084
Unit ID | 1007259
Outage ID | 18676

## E S Joslin 01
Owner Name | AEP-Central Power & Light Co.
Station Name | E S Joslin Power Station
Unit Name | E S Joslin 01
NERC Region | ERCOT
State | TX
Fuel Type | Nat. gas/ Fuel Oil
Capacity | 261 MW
Start Date | 2001-09-28
End Date | 2001-11-20
Prv. Start Date | 2001-10-19
Prv. End Date | 2001-11-01
Comments | Retubing, heat exchanger work.
SIC | 4911
Plant ID | 1014722
Unit ID | 1008093
Outage ID | 17810

## Moss Landing 07
Owner Name | Duke Energy Moss Landing LLC
Station Name | Moss Landing Power Station
Unit Name | Unit 07
NERC Region | WSCC
State | CA
Fuel Type | Natural Gas
Capacity | 812 MW
Start Date | 2001-09-28
End Date | 2002-04-28
Prv. Start Date | 2001-12-07
Prv. End Date | 2002-01-17
Comments | Turb/Boiler/SCR
SIC | 4931
Plant ID | 1011212
Unit ID | 1005367
Outage ID | 8919

## Hugo 01
Owner Name | Western Farmers Electric Cooperative
Station Name | Hugo Power Station
Unit Name | Hugo 01
NERC Region | SPP
State | OK
Fuel Type | Coal
Capacity | 400 MW
Start Date | 2001-11-02
End Date | 2001-11-11
Prv. Start Date | 2001-10-15
Prv. End Date | 2001-11-04
Comments | Winter Prep
SIC | 4931
Plant ID | 1013859
Unit ID | 1007842
Outage ID | 16167