## Intermountain 01
Owner Name | Intermountain Power Service Corporation
Station Name | Intermountain Power Station
Unit Name | Intermountain 01
NERC Region | WSCC
State | UT
Fuel Type | Coal
Capacity | 820 MW
Start Date | 2002-01-11
End Date | 2002-02-07
Prv. Start Date | 2002-01-12
Prv. End Date | 2002-02-08
Comments | Scrubber Work
SIC | 4911
Plant ID | 1015331
Unit ID | 1007133
Outage ID | 18624

## Morgantown 02
Owner Name | Mirant Mid-Atlantic, LLC
Station Name | Morgantown Power Station
Unit Name | Morgantown 02
NERC Region | MAAC
State | MD
Fuel Type | Coal
Capacity | 626 MW
Start Date | 2002-01-10
End Date | 2002-02-20
Prv. Start Date | 2002-01-12
Prv. End Date | 2002-02-22
Comments | Boiler / Turbine / Generator Work
SIC | 4931
Plant ID | 1012656
Unit ID | 1006200
Outage ID | 16981

## Coronado 01
Owner Name | Salt River Project Agricultural Improvement
Station Name | Coronado Generating Station
Unit Name | Coronado 01
NERC Region | WSCC
State | AZ
Fuel Type | Coal
Capacity | 411 MW
Start Date | 2001-11-29
End Date | 2002-01-07
Prv. Start Date | 2001-11-29
Prv. End Date | 2002-01-09
Comments | Turb O/H
SIC | 4911
Plant ID | 1016260
Unit ID | 1007076
Outage ID | 9521

## Hatch 02
Owner Name | Georgia Power Company.
Station Name | Edwin I Hatch Nuclear Power Station
Unit Name | Hatch 02
NERC Region | SERC
State | GA
Fuel Type | Nuclear
Capacity | 865 MW
Start Date | 2001-12-25
End Date | 2002-01-09
Prv. Start Date | 2001-12-25
Prv. End Date | 2002-01-08
Comments | Steam bypass valve problem.
SIC | 4911
Plant ID | 1012040
Unit ID | 1004272
Outage ID | 19297