## Risk
ENRON NORTH AMERICA
TECHNICAL RISK REPORT
Business Unit | Project Name | Responsible Party | Project Type | $$ Exposure | Assessment of Risk | Updated | Update/Comments
West QF | Elvis (LVCLP) | J. Blackburn | O&M |  | The trips and alarms caused by the Mark V LM Control System remain a concern. The erroneous trips and alarms have stopped since GE replaced the control engine in May. The trips result is lost revenues associated with the PPA and merchant sales. | 2000-07-20 | GE continues to perform a root cause analysis to determine the cause. LVCLP officially filed a warranty claim that covers any issues involved with the workmanship, material, design and software of the control system.
| Priscilla (LVCII) | Bill Williams/ Mark Mullen/ Don Hammond | Development/ Construction |  | 1) Bid player options limited. Two bidders involved. Med risk. 2) Site boundary noise level - Low risk 3) HRSG long lead items - Med risk | 2000-07-20 | 1) High level of involvement in bid scope preparation and bidder response preparation. 2) Modeling for mitigation. 3) Working optionality early in the process with HRSG suppliers.
| Columbia | Bill Williams/ Mark Mullen/ Don Hammond | Development/ Construction | Development Budget Amount | 1) Verify the quantity of water the Port can provide under its current water right. 2) Interconnection - Need to get ahead of Avista-Steag 3) Determine if the project can go through the Washington Energy Facility Siting Council's (EFSEC) expedited process. 4) Determine if a full year of ambient air data collection is required. | 2000-07-20 | 1) Pursue options with the City of Longview if quantity is not available at the Port. 2) Issued request for interconnection to BPA 7/19/00. 3) Meeting scheduled with EFSEC to discuss expedited process. 4) Consultant hired to determine if data is required by 7/31/00.
| Black Mtn Power (Cactus) | Chuck Ward | Operational Review |  | No current Risk | 2000-08-03 | The facility is currently over 95% available and ENA's ownership is 15%. The plant availability has to fall below 90% for capacity payments to decrease substantially.
| Bighorn (Colstrip) | Chuck Ward | Operational Review |  | No current Risk | 2000-08-03 | Big Horn's historic availability exceeds 92%.
Canada | Invasion Energy | Kitigawa | Operational Review |  |  | 2000-08-03
Canada/ Industrials | Papier Masson | Wayne Mays | Construction | $3-$5mm | 1) Construction completion - Delays in achieving mechanical completion. Weekly conference calls with EPC contractor to monitor. 2) Production ramp-up not meeting plan. | 2000-07-20 | 1) Construction completion delayed 4 weeks due to problems with piping contractor. 2) Production ramp-up curve has been delayed one week from plan. Close to summer "non-construction" period which could impact project completion. Some contractors are seeking additional payments for delays and changes in scope - $3-$5mm on a $70 mm project.
Industrials | Garden State |  | Asset Monetization |  |  | 2000-08-03
| Dioshawa |  | Asset Monetization |  |  | 2000-08-03
| Pomona |  | Asset Monetization |  |  | 2000-08-03
Principal Investing | Catalytica | Lydecker / Mays | Xonon |  |  | 2000-08-03
| Linder Petroleum | Lydecker | Operational Review |  |  | 2000-08-03
| Venoco | Lydecker | Operational Review |  |  | 2000-08-03
Special Assets | Heartland Steel | Wayne Mays | Construction |  | 1) Production ramp-up, output quantity and quality not matching ramp-up production. Brought in industry technical expert (David Armstrong from Metal Projects Engineering and Management in Chicago) to assist in plant evaluation and study. He has been on site with Enron financial people for 4 weeks. | 2000-07-20 | Working through problems with automated production and billing system. Technical problems with cold mill startup have been discovered. Alignment check scheduled for next week.
| Kafus | Wayne Mays | Construction |  | 1) Construction risk at Lackawanna MDF plant. Stone and Webster Engineers and Constructors did not pay subcontractors for 60 days so subs left on May 5. Have met with CanFibre and closely monitoring their construction progress. 2) Riverside MDF plant - Production ramp-up outputquantity and quality not matching projections. Brought in industry expert (jim Wilson from Oregon State University Forest products) to assist in evaluation. 3) Kanaf - production ramp-up. Evaluated new plant manager. 4) Kafus Biocomposites - production ramp-up, review and monitoring. | 2000-07-20 | 1) Lackawanna - Stone and Webstre is now off the property and CanFibre is managing the project directly. 2) Riverside - sales is not keeping up with production so the plant may be shut down for two weeks in August. 3) Kanaf - production quality has improved markedly and now seems to be acceptable and stable. 4) Kafus Biocomposites - rejected material has been removed from building and they are now producing acceptable product.
| City Forest | Wayne Mays | Construction |  | 1) Production ramp up not matching projection for outputquantity and quality. Brought in industry experts (Floyd Gustafson and Associates) to assist in evaluation process. Poor internal coordination between two divisions of the paper machine manufacturer (voith Sulzer) let to problems with Yankee dryer and headbox. Weekly conference calls to review progress. | 2000-07-20 | Have a sheet wrinkle problem since last September which is still not completely understood. It was learned in May that the Yankee had an incorrect face profile, which was reground in June. Production is now up to over 60 tons per day but needs to come up another 20 tons per day. Ramp-up is still 6 months behind where it should be.
| EcoGas | Maffet/Mays | Operational Review |  |  | 2000-08-03
| NG Resources | Wayne Mays |  |  |  | 2000-07-20
East | Austin | Virgo
East QF | Linden 6 | Mike Coleman | Construction |  | 1) Construction risk - quarantees and liquidated damages with EPC contractor (NEPCO) 2) Machine - GE guarantees East Coast Power has a capable project manager following this project. | 2000-07-20 | Orders have been placed for major equipment.
| East Coast Power |  |  |  |  | 2000-08-03
| MCN | Mike Mazowita 248-442-4823 | O&M |  |  | 2000-07-20
| ADA Cogen | Mike Mazowita 248-442-4823 | O&M |  |  | 2000-07-20
| Tenaska | Mike Mazowita 248-442-4823 | O&M |  |  | 2000-07-20
Mexico | Vitro | Virgo | Development/ Construction |  | 1) Engineering and design of project - will assign an engineering manager to work with contract engineer during critical early stages of project. 2) Construction risk - will assign a construction manager from ENA to monitor project through completion. | 2000-07-20 | Hiring ENA engineering manager and will utilize ENA construction management team. Core team will be complemented by EE&CC or other resources on specific issues.
HPL/LRC | Project Neptune |  | Development/ Construction |  |  | 2000-08-03
Coal | American Coal Company | Helfrich | Operational Review |  |  | 2000-08-03
| Black Mtn Resources | Helfrich | Operational Review |  |  | 2000-08-03
| DPR Holding Co | Wayne Mays | Reserves & Operational |  |  | 2000-08-03
| Jupiter Holdings | Helfrich | Operational Review |  |  | 2000-08-03
Energy Capital Resources | Aspect Resources | Pruett | Operational Review |  |  | 2000-07-20
| Bonne Terre Exploration | Pruett | Operational Review |  |  | 2000-08-03
| Brighman Exploration | Neyman | Operational Review |  |  | 2000-08-03
| CGAS | Pruett | Operational Review |  |  | 2000-08-03
| Cypress Energy | Pruett | Operational Review |  |  | 2000-08-03
| Juniper Energy | Pruett | Operational Review |  |  | 2000-08-03
| Mariner Energy | Melendrez | Operational Review |  |  | 2000-08-03
| Sapphire Bay | Pruett | Operational Review |  |  | 2000-08-03
| Sacramento Basin (Amerada Hess) | Neyman | Operational Review |  |  | 2000-08-03
| Sierra Well Service | Neyman | Operational Review |  |  | 2000-08-03
| Texland Ltd | Pruett | Operational Review |  |  | 2000-08-03
| Vastar Onshore | Pruett | Operational Review |  |  | 2000-08-03
| WB Oil & Gas | Neyman | Operational Review |  |  | 2000-08-03
Other | Syntroleum | Vetters | Operational Review |  | Austrialian Synfuels project | 2000-08-03
| Masada | Lydecker | Operational Review |  | Solid Waste Conversion | 2000-08-03

## No Risk
ENRON NORTH AMERICA
TECHNICAL RISK REPORT
Industry Group | Project Name | Responsible Party | Project Type | $$ Exposure | Assessment of Risk | Updated | Update/Comments
Power | Active Power | Kuykendall |  |  | Private Minority Interest, no technical risk | 2000-08-01
| Encorp | Vetters |  |  | Private Minority Interest, no technical risk | 2000-08-01
| Mobile Energy | Helfrich |  |  | No technical risk | 2000-08-01
Coal | Destec | Helfrich |  |  | 15 year monetized coal contract/No technical risk | 2000-08-01
Exploration / Exploitation | Ameritex Ventures | Pruett |  |  | No technical risk | 2000-08-01
| Carrizzo | Pruett |  |  | Written off | 2000-08-01
| Costilla | Pruett |  |  | Written off | 2000-08-01
| EEX E&P | Pruett |  |  | Syndicated | 2000-08-01
| Esenjay | Pruett / Lydecker |  |  | U.S. Public, no technical risk | 2000-08-01
| Eugene Offshore | Pruett |  |  | Sold | 2000-08-01
| Hughes Rawls | Pruett |  |  | Sale in progress | 2000-08-01
| Lyco Energy | Pruett |  |  | No technical risk | 2000-08-01
| Place Resources | Pruett |  |  | Canadian Public no technical risk | 2000-08-01
| Quicksilver | Pruett |  |  | U.S. Public, no technical risk | 2000-08-01
| Ridgelake Energy | Pruett |  |  | Overriding interest, no technical risk | 2000-08-01
| Startech Energy | Pruett |  |  | Canadian Public no technical risk | 2000-08-01
| Zargon | Pruett |  |  | Public Minority Interest, no technical risk | 2000-08-01
Acquisition & Development | Beau Canada | Kitigawa |  |  | Canadian Public no technical risk | 2000-08-01
| Belco Oil & Gas | Lydecker |  |  | Minority Warrants, no technical risk | 2000-08-01
| Chesapeake Energy | Lydecker |  |  | No technical risk | 2000-08-01
| Hogan Exploration | -- |  |  | Written off no technical risk | 2000-08-01
| Inland Resources | Lydecker |  |  | Preferred minority interest, no technical risk | 2000-08-01
| Lewis Energy Group | -- |  |  | Sold | 2000-08-01
| Queen Sand Resources | Neyman |  |  | Minority Public, no technical risk | 2000-08-01
| Swift Energy | Neyman |  |  | VPP ending, no technical risk | 2000-08-01
| Titan Exploration | Pruett |  |  | Minority Public, no technical risk | 2000-08-01
Oil Field Service/Other | Alpine | Calger |  |  | Small preferred position, minimal risk | 2000-08-01
| Black Bay | Lydecker |  |  | Seismic Sales, no technical risk | 2000-08-01
| Bonus Resources | Neyman |  |  | No technical risk | 2000-08-01
| EB/GB | Neyman |  |  | No technical risk | 2000-08-01
| EnSerCo | Vass / Lydecker |  |  | Sale in progress | 2000-08-01
| Gasco Distribution | Enerson |  |  | Loan Payoff in 5/00, no technical risk | 2000-08-01
| Hanover Compressor | Byargeon |  |  | Minority Public, no technical risk | 2000-08-01
| HV Marine | Lydecker |  |  | Minority Warrants, no technical risk | 2000-08-01
| ICE Drilling Systems | -- |  |  | Sold | 2000-08-01
| Industrial Holdings | Enerson |  |  | Debt written down, no technical risk | 2000-08-01
| Keathley Canyon | Lydecker |  |  | Seismic Sales, no technical risk | 2000-08-01
| LSI Electric Speciality | Lydecker |  |  | Cable sales, no technical risk | 2000-08-01
| Paradigm Geophysical | Neyman |  |  | Warrants, no technical risk | 2000-08-01
| Tetonka Drilling | Lydecker |  |  | Minority Interest, no technical risk | 2000-08-01
| TransCoastal Marine | Lydecker |  |  | Bankruptcy, no technical risk | 2000-08-01
| Tri-Point | Lydecker |  |  | Written off, no technical risk | 2000-08-01
| Quanta Services | -- |  |  | Sold | 2000-08-01
| Utiliquest | Kuykendall |  |  | Locates pipe & wires subsurface, no technical risk | 2000-08-01
Pulp & Paper | PCDI Oconto Falls | Helfrich |  |  | Converting to Debt, no technical risk | 2000-08-01
| Repap | -- |  |  | Sold | 2000-08-01
Steel | NSM | -- |  |  | Written off, no technical risk | 2000-08-01
| Qualitech | -- |  |  | Bankruptcy, no debt survived, no technical risk | 2000-08-01
Other | Chuckwalla | Kerrigan |  |  | ENA FASB 125 transaction | 2000-08-01
| Cook Inlet | -- |  |  | Sold | 2000-08-01
| Crown Energy | -- |  |  | Sold? | 2000-08-01
| ENA CLO Trust | -- |  |  | Sold? | 2000-08-01
| Hancock Mezzanine Partners | Lydecker |  |  | Investment vehicle, no technical risk | 2000-08-01
| Terradyne Group | -- |  |  | Sold? | 2000-08-01