## Sheet2 (hidden)
TVA Peaking Plant
Issues/Savings
Issue
EECC increased current estimate
Fuel cost during start up not included
Tax Handling Fee to LLC for arms length transaction .25% not included in plan
Savings Recognized
| New Albany | Caledonia | Brownsville | Total
Decrease Environmental permitting | -310000 | -300000 | -233000 | -843000
Decrease Legal expense | -550000 | -550000 | -350000 | -1450000
Decrease Development | -200000 | -200000 | -200000 | -600000
Total Savings | -1060000 | -1050000 | -783000 | -2893000

## NA Mquip (hidden)
New Albany
Major Equipment Detail
Refurbishment with DLN Units 1-6
(includes commission) |  | 26785396
| Spare Parts | 5214604
32000000
Dow Unit
| Purchase & spares | 1347000
| Dissassembly | 500000
| Commission 10% | 134700
1981700
4 Kepco Units (original)
| Purchase | 27502700
| Commission IBC(10%) | 2700000
| Commission Natole | 900000
| Less Steam Turbine | -700000 | Allocate to 2000
| Disassemble & move to Kunsan Port | 1307660
| Less Steam Turbine | -200500 | Allocate to 2000
| Freight Reimbursement to IBC | 1274025
| Less Steam Turbine | -100000 | Allocate to 2000
| Commission (7%) | 89181.75
32773066.75
1 Kepco Unit (new set)
| 1 of 4 Purchase price | 6875000
| Disassembly & shipping | 500000
| Commission | 0
7375000
Unidentified |  | 0 | Spare parts to be reconciled per Miller
Total IBC items |  | 74129766.75
Transformers etc |  | 10870000
Grand Total Major Equipment |  | 84999766.75

## EECC (hidden)
EECC RECONCILIATION
| Control | Current
| Budget | Estimate |  | Net Increase
Brownsville | 395276 | 587051 |  | 191775
0
Caledonia | 395276 | 620100 |  | 224824
New Albany | 395276 | 641831 |  | 246555
Fulton | 395276 | 225000 | a | -170276
Total | 1581104 | 2073982 |  | 492878
a) Sunk Cost

## Summary
ENRON CAPITAL & TRADE RESOURCES
Energy Services | [5 empty] | Report Date: |  |  |  | 2001-01-03 10:29
DOYLE I, LLC
COST SUMMARY ($ thousands) | [5 empty] | Expenditures to date: |  |  |  | as of 12/28/00
Control Budget
2000-11-30
Actuals
|  | Control Budet | Current Estimate | Actuals to Date | Estimate to Complete |  | Total to Complete |  | Variance | %
Project | MW | as of 04/23/99 | as of 12/28/00 | as of 12/28/00 | as of 12/28/00 |  | as of 12/28/00 |  | from CB | Complete
Doyle I, LLC | 342 | 112383.9879 | 116563.0041 | 122175.5774 | -5579.1373 |  | 116596.4401 |  | -4212.4521 | 104.8%
[11 empty] | 789237 | 284327 | -781296
[11 empty] | 1575586 | 36409 | 1375824 | 1193997
TOTAL PROGRAM | 342 | 112383.9879 | 116563.0041 | 122175.5774 | -5579.1373 |  | 116596.4401 |  | -4212.4521 | 104.8% |  | 84124 | -124750 | 0
Target $$/MW |  | 328.6082 | 340.8275
Control Budget vs Actual plus Est. to Complete Variance Explanations (000s)
|  |  | Variance of Current Period* |  | Variance in Last Report |  | Variance Change
Major Equipment |  |  | -5512.8671 |  | -5400.7466 |  | -112.1205 | a
EECC |  |  | -956.7096 |  | -956.7096 |  | 0
NEPCO |  |  | -3661.6382 |  | -3661.6382 |  | 0
Transformer & Switchyard |  |  | 1178.5135 |  | 1178.5135 |  | 0
Spare Parts |  |  | 1694.67 |  | 1694.67 |  | 0
Land Acquisition |  |  | -15.602 |  | -47.602 |  | 32 | b
Environmental Permitting |  |  | 287.5505 |  | 287.5505 |  | 0
Gas Interconnection |  |  | 22.01 |  | 22.01 |  | 0
Sale Tax on Equipment |  |  | -7 |  | -7 |  | 0
Insurance during Construction |  |  | -77.787 |  | -77.787 |  | 0
Start-up Fuel |  |  | 400 |  | 400 |  | 0
Interest During Construction |  |  | 636.8817 |  | 636.8817 |  | 0
Development & Legal Expenses |  |  | 74.5261 |  | 67.8939 |  | 6.6322
ENA Production Bonus |  |  | 1725 |  | 1725 |  | 0 | [5 empty] | 15283 | 0
Total Variance |  |  | -4212.4521 |  | -4138.9638 |  | -73.4883
*The variance is the difference between the Control Budget and the Actual plus Est. to Complete | [12 empty] | 4599 | 0
[13 empty] | 77915 | 0
Explanation of Variance Change Relative to Last Report
a) Additional Power Support Invoices and OEC invoice for Jaw Clutch and Converter
b) Land options reclassed to Athens - 01 Site
[13 empty] | 227 | 0
[13 empty] | 2378 | 0
0
[13 empty] | 1793 | 0
[13 empty] | 6232 | 0
[13 empty] | 6253 | 0
[13 empty] | 537 | 0
[13 empty] | -124 | 0
[13 empty] | -593 | 0
[13 empty] | -3714 | 0
[13 empty] | -3835 | 0
[13 empty] | 13581 | 0
[13 empty] | 474 | 0
[13 empty] | 154456 | 0
[13 empty] | 237 | 0
[13 empty] | 30621 | 0
[13 empty] | 13 | 0
[13 empty] | 33700 | 0
[13 empty] | 16775 | 0
[13 empty] | 1575 | 0
[13 empty] | 12102 | 0
279713
[13 empty] | 406956 | 0
0
[13 empty] | -218197 | 0
0
0
[13 empty] | -125 | -125
[13 empty] | 21644 | 24619
0
0
0

## ENA
Enron North America
Doyle I, LLC
|  |  | 342 |  | MW
[11 empty] | Actuals |  | Actuals |  | as of 12/08/00 |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  |  |  | Anticipated |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals
|  |  | ENA |  | ENA |  | Increase / |  | Actuals to Date |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | Actuals to Date |  | Increase / |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | Actuals to Date |  | Estimate |  | Actuals Plus |  | (Over)/Under
|  |  | Control Budget |  | Current Estimate |  | (Decrease) |  | 12/31/98 |  | 01/31/99 |  | 02/28/99 |  | 03/31/99 |  | 04/30/99 |  | 05/31/99 |  | 06/30/99 |  | 07/31/99 |  | 08/31/99 |  | 09/30/99 |  | 10/31/99 |  | 11/30/99 |  | 12/31/99 |  | Total Project |  | (Savings) |  | 2000-01-31 |  | 2000-02-29 |  | 2000-03-31 |  | 2000-04-30 |  | 2000-05-31 |  | 2000-06-30 |  | 2000-07-31 | 2000-08-31 | 2000-09-30 | 2000-10-31 | 2000-11-30 | 2000-12-31 | Total Project |  | To Complete |  | Est. to Complete |  | Budget |  | Comments
|  |  | as of 07/12/99 |  | as of 12/28/00 | [25 empty] | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/31/99 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 | as of 12/28/00 | as of 12/28/00 | as of 12/28/00 | as of 12/28/00 | as of 12/28/00 | as of 12/28/00
MAJOR EQUIPMENT
| TURBINE UNITS, Purchase - GE 7B's (3) | Kepco | 23437881 |  | 23437881 |  | 0 |  | 21150000 |  | 2196801.3 |  | 0 |  | -1200000 |  |  |  | 1291080 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23437881.3 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 23437881.3 |  | 0 |  | 23437881.3 |  | -0.3
| TURBINE UNITS, Disassemble | IBC | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| TURBINE UNITS, Freight | IBC | 2340538.83 |  | 2340538.83 |  | 0 |  | 0 |  | 2067105.18 |  | 0 |  | 0 |  | 0 |  | 0 |  | 273433.65 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2340538.83 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2340538.83 |  | 0 |  | 2340538.83 |  | 0
| TURBINE REFURBISHMENT | PS | 16047731 |  | 19979482 |  | 3931751 | [11 empty] | 966786.41 |  | 256779.49 |  | -432926.73 |  | 1119216.99 |  | 1564738.16 |  | 3742746.99 |  | 1639068 |  | 2397592.29 |  | 11254001.6 |  |  |  | 2139491 |  | 1346842.89 |  | 1992348.5 |  | 67904.56 |  | 1233270.87 |  | 73206.14 |  | 1533103.96 | 789237 | 284327 | -781296 | 47044 | 42529 | 20022010.52 |  | 0 |  | 20022010.52 |  | -3974279.52
| UNIT 1 REPAIR |  | 0 |  | 6488243.8 |  | 6488243.8 | [27 empty] | 0 | [15 empty] | 2204629.8 | 1575586 | 120533 | 1375824 | 1199262 | 12409 | 6488243.8 |  | 0 |  | 6488243.8 |  | -6488243.8
| INSURANCE COVERAGE FOR REPAIR |  | 0 |  | -5000000 |  | -5000000 | [27 empty] | 0 | [17 empty] | 0 | -124750 | 0 | 0 | -124750 |  | -4875250 |  | -5000000 |  | 5000000
| LEC Burners | PS | 4408479 |  | 4408479 |  | 0 |  | 0 |  | 0 |  | 3055146.4 |  | 0 |  | 2444117 |  | 0 |  | 0 |  | -1531631.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 611029 |  | 4578660.5 |  | 0 |  | 0 |  | -170181 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4408479.5 |  | 0 |  | 4408479.5 |  | -0.5
| TURBINE UNITS, Purchase - GE 7EA's (2) | GE | 32172000 |  | 32516180 |  | 344180 |  | 0 |  | 0 |  | 0 |  | 2850000 |  | 370000 |  | 2132000 |  | 2132000 |  | 2132000 |  | 2132000 |  | 2132000 |  | 2132000 |  | 3764000 |  | 532622 |  | 20308622 |  | 0 |  | 1632000 |  | 1632000 |  | 6800000 |  | 1360000 |  | 400000 |  | 0 |  | 0 | 444275 | 0 | 0 | 0 | -3534 | 32573363 |  | 0 |  | 32573363 |  | -401363
| TURBINE UNITS, Scope Change - Evap Cooling | GE | 896000 |  | 896000 |  | 0 | [9 empty] | 0 | [17 empty] | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 896000 | 0 | 0 | 0 | 0 | 896000 |  | 0 |  | 896000 |  | 0
| TURBINE UNITS, Scope Change - Exhause Stack | GE | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| ENA TURBINE COST Adder |  | 345000 |  | 0 |  | -345000 | [35 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 345000
| Refurb & 7EA Contract Management |  | 500000 |  | 506020 |  | 6020 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 10132 |  | 52750 |  | 34278 |  | 21750.25 |  | 118910.25 |  | 0 |  | 20421.09 |  | 22912.59 |  | 41788.38 |  | 55874.52 |  | 41048.95 |  | 83153.61 |  | 0 | 77829 | 0 | 26056 |  |  | 487994.39 |  | 18025.61 |  | 506020 |  | -6020
0
| Subtotal Major Equip |  | 80147629.83 |  | 85572824.63 |  | 5425194.8 |  | 21150000 |  | 4263906.48 |  | 3055146.4 |  | 1650000 |  | 2814117 |  | 4389866.41 |  | 2662213.14 |  | 167441.37 |  | 3251216.99 |  | 3706870.16 |  | 5927496.99 |  | 5437346 |  | 3562993.54 |  | 62038614.48 |  | 0 |  | 3791912.09 |  | 2831574.48 |  | 8834136.88 |  | 1483779.08 |  | 1674319.82 |  | 156359.75 |  | 3737733.76 | 3782927 | 404860 | 495834 | 1246306 | 51404 | 90529761.34 |  | -4857224.39 |  | 85672536.95 |  | -5524907.12
| AUX TRANSFORMERS |  | 173702 |  | 165430 |  | -8272 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 165430 |  | 0 |  | 165430 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 165430 |  | 0 |  | 165430 |  | 8272
| LOAD CENTER TRANSFORMERS |  | 79124 |  | 75356 |  | -3768 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 75356 |  | 0 |  | 75356 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 75356 |  | 0 |  | 75356 |  | 3768
| CIRCUIT BREAKERS |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [7 empty] | 0 |  | 0 | [19 empty] | 0 |  | 0 |  | 0 |  | 0
| TD OF I-ABB |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| FREIGHT - TRANSFORMERS |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| TRANSFORMER INSTALLATION |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| OFF LOAD CIRCUIT BREAKERS |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| MISC TVA REQUIREMENTS |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| REIMBURSEMENT to OPC for Substation |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
0
| Subtotal |  | 252826 |  | 240786 |  | -12040 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 240786 |  | 0 |  | 240786 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 240786 |  | 0 |  | 240786 |  | 12040
| TOTAL MAJOR EQUIPMENT |  | 80400455.83 |  | 85813610.63 |  | 5413154.8 |  | 21150000 |  | 4263906.48 |  | 3055146.4 |  | 1650000 |  | 2814117 |  | 4389866.41 |  | 2662213.14 |  | 167441.37 |  | 3251216.99 |  | 3706870.16 |  | 5927496.99 |  | 5678132 |  | 3562993.54 |  | 62279400.48 |  | 0 |  | 3791912.09 |  | 2831574.48 |  | 8834136.88 |  | 1483779.08 |  | 1674319.82 |  | 156359.75 |  | 3737733.76 | 3782927 | 404860 | 495834 | 1246306 | 51404 | 90770547.34 |  | -4857224.39 |  | 85913322.95 |  | -5512867.12
-3950.7612
EECC PROGRAM MGT
| CONSTRUCTION PROJECT MANAGEMENT |  | 896000 |  | 881255 |  | -14745 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 232222.14 |  | 232222.14 |  | 0 |  | 0 |  | 148832.78 |  | 99049.01 |  | 183623.47 |  | 99012.9 |  | 118514.96 |  |  | 0 | 0 | 0 | 0 | 0 | 881255.26 |  | 0 |  | 881255.26 |  | 14744.74
| REFURB PROJECT MANAGEMENT |  | 596600 |  | 766932 |  | 170332 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 122468.05 |  | 122468.05 |  | 0 |  | 0 |  | 179805.53 |  | -25877.58 |  | -13990.39 |  | 60553.39 |  | 21614.99 |  | 135174 | 109257 | 88371 | 89556 | 0 | 0 | 766931.99 |  | 0.01 |  | 766932 |  | -170332
| PRE NTP ENGINEERING |  | 89556 |  | 136622 |  | 47066 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 136622.33 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 136622.33 |  | 0 |  | 136622.33 |  | -47066.33
| FEES |  | 0 |  | 754056 |  | 754056 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 678650 | 0 | 75406 | 0 | 0 | 0 | 754056 |  | 0 |  | 754056 |  | -754056
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [19 empty] | 0 |  | 0 |  | 0 |  | 0
| TOTAL EECC PROGRAM MGT |  | 1582156 |  | 2538865 |  | 956709 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 354690.19 |  | 354690.19 |  | 0 |  | 0 |  | 465260.64 |  | 73171.43 |  | 169633.08 |  | 159566.29 |  | 140129.95 |  | 813824 | 109257 | 163777 | 89556 | 0 | 0 | 2538865.58 |  | 0.01 |  | 2538865.59 |  | -956709.59
Project Management |  |  | 1253748 |  | 1195767 |  | -57981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 90134 |  | 87718 |  | 177852 |  |  |  | 221627 |  | 242149 |  | -12854.87 |  | 149885.87 |  | 228576.91 |  | 116177.68 |  | 0 | 0 | 88541 | 15283 | -35871 | 0 | 1191366.59 |  | 4400.41 |  | 1195767 |  | 57981
Project Indirects
| Equipment Rental |  | 1321189 |  | 854518 |  | -466671 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 1975 |  | 5425 |  | 7400 |  |  |  | 113798 |  | 70030 |  | 121040.7 |  | 47460.94 |  | 141964.7 |  | 103377.05 |  | 0 | 0 | 218508 | 4599 | 26340 | 0 | 854518.39 |  | 0 |  | 854518.39 |  | 466670.61
| General Provisions |  | 4671455 |  | 2835497 |  | -1835958 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 160671 |  | 274023 |  | 434694 |  |  |  | 812195.2 |  | 257395 |  | 108531.67 |  | 137461.29 |  | 251786.94 |  | 216129.25 |  | 0 | 0 | 454908 | 77915 | 62728 | 0 | 2813744.35 |  | 21752.65 |  | 2835497 |  | 1835958
| Subtotal Project Indirects |  | 5992644 |  | 3690015 |  | -2302629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 162646 | 0 | 279448 |  | 442094 | 0 | 0 | 0 | 925993.2 |  | 327425 |  | 229572.37 |  | 184922.23 |  | 393751.64 |  | 319506.3 |  | 0 | 0 | 673416 | 82514 | 89068 | 0 | 3668262.74 |  | 21752.65 | 0 | 3690015.39 | 0 | 2302628.61
a) Duplicate entry corrected in November
| Engineering Management |  | 120323 |  | 242008 |  | 121685 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 4681 |  | 71981 |  | 76662 |  |  |  | 22504 |  | 12392 |  | 11655.04 |  | 5163.49 |  | 14402.08 |  | 6004.72 |  | 0 | 0 | 80773 | 227 | 3259 | 0 | 233042.33 |  | 8965.67 |  | 242008 |  | -121685
| Civil / Sitework Engineering |  | 7367 |  | 5061 |  | -2306 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0 |  |  |  | 1652 |  | 0 |  | 641.53 |  | 353.46 |  | 0 |  | 0.04 |  | 0 | 0 | 0 | 2378 | 0 | 0 | 5025.03 |  | 35.97 |  | 5061 |  | 2306
| Fundation / Piling |  | 26973 |  | 24636 |  | -2337 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 14689 |  | 2205 |  | 7194.77 |  | 522 |  | 0 |  | 7.56 |  | 0 | 0 | 0 | 0 | 0 | 0 | 24618.33 |  | 17.67 |  | 24636 |  | 2337
| Structural Steel Engineering |  | 0 |  | 1294 |  | 1294 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 842 |  | 0 |  | 397.45 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 1 | 0 | 0 | 0 | 1240.45 |  | 53.55 |  | 1294 |  | -1294
| Architectural Engineering |  | 8302 |  | 96.96 |  | -8205.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 97 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 97 |  | 0 |  | 97 |  | 8205
| A/G Piping Engineering |  | 60328 |  | 181581 |  | 121253 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 64017 |  | 17072 |  | 91172.15 |  | 690.48 |  | 8590.65 |  | 25.54 |  | 0 | 0 | 0 | 0 | 0 | 0 | 181567.82 |  | 13.18 |  | 181581 |  | -121253
| A/G Electrical Engineering |  | 123231.3 |  | 366044 |  | 242812.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 141342 |  | 46330 |  | 84577.12 |  | 39045.43 |  | 46947.13 |  | 1849.63 |  | 0 | 0 | 4079 | 1793 | 0 | 0 | 365963.31 |  | 80.69 |  | 366044 |  | -242812.7
| Instrumentation & CO |  | 65501.3 |  | 131207 |  | 65705.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 50196 |  | 14534 |  | 8581.87 |  | 12604.8 |  | 18583.02 |  | 11253.32 |  | 0 | 0 | 9181 | 6232 | 0 | 0 | 131166.01 |  | 40.99 |  | 131207 |  | -65705.7
| Major Equipment |  | 69399 |  | 100709 |  | 31310 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 44338 |  | 19597 |  | 11547.92 |  | 5182.1 |  | 8998.09 |  | 1474.15 |  | 0 | 0 | 3151 | 6253 | 62 | 0 | 100603.26 |  | 105.74 |  | 100709 |  | -31310
| Reserves |  | 93993 |  | 0 |  | -93993 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 93993
| Subtotal Engineering / General Provisions/ Start -up |  | 575417.6 |  | 1052636.96 |  | 477219.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4681 | 4681 | 71981 |  | 76662 | 0 | 0 | 0 | 339677 |  | 112130 |  | 215767.85 |  | 63561.76 |  | 97520.97 |  | 20614.96 |  | 0 | 0 | 97185 | 16883 | 3321 | 0 | 1043323.54 |  | 9313.46 | 0 | 1052637 | 0 | -477219.4 | 0
Procurement
| Transportation & Freight |  | 55000 |  | 162107 |  | 107107 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 16782 |  | 2740 |  | 4507.89 |  | 2951.83 |  | 74023.15 |  | 22753.06 |  | 0 | 0 | 24670 | 537 | 12462 | 0 | 161426.93 |  | 680.07 |  | 162107 |  | -107107
| Site Improvement |  | 1125 |  | 0 |  | -1125 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 1125
| U/G Eletrical |  | 385611 |  | 135998 |  | -249613 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 83801 |  | 6346 |  | 19137.88 |  | 668.25 |  | 13362.87 |  | 4987.71 |  | 0 | 0 | 4437 | -124 | 0 | 0 | 132616.71 |  | 3381.29 |  | 135998 |  | 249613
| U/G Piping |  | 221748 |  | 59508 |  | -162240 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 21780 |  | 208 |  | 0 |  | 32078.24 |  | 0 |  | 4510 |  | 0 | 0 | 136 | 0 | 796 | 0 | 59508.24 |  | 0 |  | 59508.24 |  | 162239.76
| Concrete |  | 520255 |  | 582784 |  | 62529 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 284484 |  | 118121 |  | 42915.77 |  | 52186.79 |  | 40600.91 |  | 25430.8 |  | 0 | 0 | 12971 | -593 | 5438 | 0 | 581555.27 |  | 1228.73 |  | 582784 |  | -62529
| Grout |  | 28687 |  | 15419 |  | -13268 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 1980 |  | 0 |  | 2480.4 |  | 0 |  | 6837.82 |  | 0 |  | 0 | 0 | 4121 | 0 | 0 | 0 | 15419.22 |  | 0 |  | 15419.22 |  | 13267.78
| Structural Steel |  | 25200 |  | 201462 |  | 176262 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 1298 |  | 2892.77 |  | 103900.94 |  | 9031 |  | 77231.02 |  | 0 | 0 | 6938 | 0 | 170 | 0 | 201461.73 |  | 0.27 |  | 201462 |  | -176262
| A/G Piping |  | 235231 |  | 578334 |  | 343103 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 75709 |  | 12553 |  | 126314.12 |  | 70639.99 |  | 106016.22 |  | 104218.86 |  | 0 | 0 | 71558 | -3714 | 2583 | 0 | 565878.19 |  | 12455.81 |  | 578334 |  | -343103
| A/G Electrical |  | 1465168 |  | 1856975 |  | 391807 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 78626 |  | 70598 |  | 177809.74 |  | 148549.42 |  | 1009485.16 |  | 90830.91 |  | 0 | 0 | 153771 | -3835 | 32256 | 0 | 1758091.23 |  | 98883.77 |  | 1856975 |  | -391807
| Instrumentation & CO |  | 821468 |  | 816313 |  | -5155 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 44694 |  | 155409.5 |  | 5203.54 |  | 137380.14 |  | 329795.96 |  | 13027 |  | 0 | 0 | 66831 | 13581 | 47221 | 0 | 813143.14 |  | 3169.86 |  | 816313 |  | 5155
| Major Equipment |  | 482077 |  | 646393 |  | 164316 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 1940 |  | 153374.43 |  | 152360.11 |  | 166887.51 |  | 155187.96 |  | 0 | 0 | 6495 | 0 | 1178 | 0 | 637423.01 |  | 8969.99 |  | 646393 |  | -164316
| Reserves |  | 7851 |  | 0 |  | -7851 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 7851
| Subtotal Procurement |  | 4249421 |  | 5055293 |  | 805872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 607856 |  | 369213.5 |  | 534636.54 |  | 700715.71 |  | 1756040.6 |  | 498177.32 |  | 0 | 0 | 351928 | 5852 | 102104 | 0 | 4926523.67 |  | 128769.79 | 0 | 5055293.46 | 0 | -805872.46 | 0
Site Preparation/Improvement
| Site Preparation |  | 581938 |  | 340664 |  | -241274 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 52531 |  | 52531 |  |  |  | 239463 |  | 0 |  | 7759.51 |  | 11613.35 |  | 3416.43 |  | 19260.73 |  | 0 | 0 | 6126 | 474 | 0 | 0 | 340644.02 |  | 19.98 |  | 340664 |  | 241274
| Site Improvement |  | 478046 |  | 404051 |  | -73995 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 141564.34 |  | 0 |  | 0 |  | 17332.69 |  | 6089.37 |  | 1947.15 |  | 0 | 0 | 65695 | 154456 | 16956 | 0 | 404040.55 |  | 10.45 |  | 404051 |  | 73995
| Subtotal Site Preparation/Improvement |  | 1059984 | 0 | 744715 |  | -241274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52531 | 0 | 52531 | 0 | 0 | 0 | 381027.34 | 0 | 0 | 0 | 7759.51 | 0 | 28946.04 |  | 9505.8 |  | 21207.88 |  | 0 | 0 | 71821 | 154930 | 16956 | 0 | 744684.57 | 0 | 30.43 | 0 | 744715 | 0 | 315269 | 0
Underground Electrical
| Electrical |  | 207977 | 198001 | 331302 |  | 123325 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 12469 |  | 12469 |  |  |  | 132074 |  | 79635 |  | 41045.29 |  | 33832.75 |  | 17809.13 |  | 13577.51 |  | 0 | 0 | 620 | 237 | 0 | 0 | 331299.68 |  | 2.32 |  | 331302 |  | -123325
| Subtotal Underground Electrical |  | 207977 |  | 331302 |  | 123325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 12469 |  | 12469 | 0 | 0 | 0 | 132074 |  | 79635 |  | 41045.29 |  | 33832.75 |  | 17809.13 |  | 13577.51 |  | 0 | 0 | 620 | 237 | 0 | 0 | 331299.68 |  | 2.32 | 0 | 331302 | 0 | -123325 | 0
Underground Piping
| Piping |  | 226450 | 226404 | 330499 |  | 104049 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 6680 |  | 6680 |  |  |  | 99113 |  | 149364 |  | 35633.75 |  | 30375.31 |  | 5402.52 |  | 973.65 |  | 0 | 0 | 2944 | 0 | 0 | 0 | 330486.23 |  | 12.77 |  | 330499 |  | -104049
| Subtotal Underground Piping |  | 226450 |  | 330499 |  | 104049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 6680 |  | 6680 | 0 | 0 | 0 | 99113 |  | 149364 |  | 35633.75 |  | 30375.31 |  | 5402.52 |  | 973.65 |  | 0 | 0 | 2944 | 0 | 0 | 0 | 330486.23 |  | 12.77 | 0 | 330499 | 0 | -104049 | 0
Concrete
| Concrete |  | 616280 | 616436 | 730459 |  | 114179 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 34133 |  | 34133 |  |  |  | 317556 |  | 161276 |  | 51574.93 |  | 46795.37 |  | 71523.73 |  | 35698.67 |  | 0 | 0 | 11872 | 0 | 0 | 0 | 730429.7 |  | 29.3 |  | 730459 |  | -114179
| Subtotal Concrete |  | 616280 |  | 730459 |  | 114179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 34133 |  | 34133 | 0 | 0 | 0 | 317556 |  | 161276 |  | 51574.93 |  | 46795.37 |  | 71523.73 |  | 35698.67 |  | 0 | 0 | 11872 | 0 | 0 | 0 | 730429.7 |  | 29.3 | 0 | 730459 | 0 | -114179 | 0
Grout
| Special Concrete |  | 39760 | 39766 | 49628 |  | 9868 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 2142 |  | 6816 |  | 13772.69 |  | 6899.68 |  | 16373.81 |  | 3613.61 |  | 0 | 0 | 0 | 0 | 0 | 0 | 49617.79 |  | 10.21 |  | 49628 |  | -9868
| Subcontract |  | 39760 |  | 49628 |  | 9868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2142 |  | 6816 |  | 13772.69 |  | 6899.68 |  | 16373.81 |  | 3613.61 |  | 0 | 0 | 0 | 0 | 0 | 0 | 49617.79 |  | 10.21 | 0 | 49628 | 0 | -9868
Structural Steel
| Stuctural Steel |  | 7087 | 7089 | 3533 |  | -3554 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 2885.01 |  | 0 |  | 647.64 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3532.65 |  | 0.35 |  | 3533 |  | 3554
| Subtotal Structural Steel |  | 7087 |  | 3533 |  | -3554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 2885.01 |  | 0 |  | 647.64 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3532.65 |  | 0.35 | 0 | 3533 | 0 | 3554 | 0
Architectural |  |  | 0 |  | 20624 |  | 20624 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 9140 |  | 6976.6 |  | 1015.5 |  | 3384 |  | 107.9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20624 |  | 0 |  | 20624 |  | -20624
Buildings |  |  | 296640 | 296640 | 393895 |  | 97255 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 88703 |  | 67823 |  | 142280 |  | 7535.9 |  | 80643.6 |  | 13712.5 |  | 0 | 0 | -6803 | 0 | 0 | 0 | 393895 |  | 0 |  | 393895 |  | -97255
Aboveground Piping
| Labor |  | 184017 |  | 516967 |  | 332950 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 129 |  | 47927 |  | 162508.25 |  | 107087.6 |  | 70825.01 |  | 19994.25 |  | 0 | 0 | 77868 | 30621 | 0 | 0 | 516960.11 |  | 6.89 |  | 516967 |  | -332950
| Subcontract |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Subtotal Aboveground Piping |  | 184017 |  | 516967 |  | 332950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 129 |  | 47927 |  | 162508.25 |  | 107087.6 |  | 70825.01 |  | 19994.25 |  | 0 | 0 | 77868 | 30621 | 0 | 0 | 516960.11 |  | 6.89 | 0 | 516967 | 0 | -332950 | 0
Aboveground Electrical
| Labor |  | 550994 |  | 1379111 |  | 828117 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 3446 |  | 161193 |  | 308705.95 |  | 314283.99 |  | 359812.81 |  | 166901.61 |  | 0 | 0 | 61134 | 13 | 3494 | 0 | 1378984.36 |  | 126.64 |  | 1379111 |  | -828117
| Subcontract | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Subtotal Aboveground Electrical |  | 550994 |  | 1379111 |  | 828117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 3446 |  | 161193 |  | 308705.95 |  | 314283.99 |  | 359812.81 |  | 166901.61 |  | 0 | 0 | 61134 | 13 | 3494 | 0 | 1378984.36 |  | 126.64 | 0 | 1379111 | 0 | -828117
Instrumentation |  |  | 320617 | 295512 | 318325 |  | -2292 | -295512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 1017 |  | 6363.37 |  | 17726.01 |  | 110496.56 |  | 57260.27 |  | 0 | 0 | 16930 | 33700 | 50792 | 0 | 294285.21 |  | 24039.79 |  | 318325 |  | 2292
Insulation & Paint | [58 empty] | 0 |  | 0 |  | 0
| Insulation |  | 292985.4 | 0 | 92401 |  | -200584.4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 29087.19 |  | 0 |  | 0 | 0 | 35464 | 0 | 27850 | 0 | 92401.19 |  | 0 |  | 92401.19 |  | 200584.21
| Paint |  | 106500 | 399485 | 269715 |  | 163215 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 13630.45 |  | 23468.33 |  | 25550 |  | 0 | 0 | 140542 | 0 | 50515 | 0 | 253705.78 |  | 16009.22 |  | 269715 |  | -163215
| Subtotal Insulation & Paint |  | 399485.4 |  | 362116 |  | -37369.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 13630.45 |  | 52555.52 |  | 25550 |  | 0 | 0 | 176006 | 0 | 78365 | 0 | 346106.97 |  | 16009.22 | 0 | 362116.19 | 0 | 37369.21 | 0
Mechanical Equipment
| Labor |  | 1847148.4 |  | 2254517 |  | 407368.6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 35957 |  | 416568 |  | 232835.01 |  | 391854.14 |  | 590778.52 |  | 312054.61 |  | 0 | 0 | 274455 |  | 0 | 0 | 2254502.28 |  | 14.72 |  | 2254517 |  | -407368.6
| Subcontract |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Subtotal Mechanical Equipment |  | 1847148.4 |  | 2254517 |  | 407368.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 35957 |  | 416568 |  | 232835.01 |  | 391854.14 |  | 590778.52 |  | 312054.61 |  | 0 | 0 | 274455 | 0 | 0 | 0 | 2254502.28 |  | 14.72 | 0 | 2254517 | 0 | -407368.6 | 0
Substation/Switchyard |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
Plant Startup
| Field - Plant Start |  | 610650.4 | 448332 | 2305920 |  | 1695269.6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 28048 |  | 150321 |  | 190491.73 |  | 118524.41 |  | 762670.33 |  | 435866.9 |  | 0 | 0 | 452296 | 16775 | 51157 | 0 | 2206150.37 |  | 99769.63 |  | 2305920 |  | -1695269.6
| Startup Reserves |  | 210000 | 155150 | 0 |  | -210000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 210000
| Subtotal Plant Startup |  | 820650.4 |  | 2305920 |  | 1485269.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 28048 |  | 150321 |  | 190491.73 |  | 118524.41 |  | 762670.33 |  | 435866.9 |  | 0 | 0 | 452296 | 16775 | 51157 | 0 | 2206150.37 |  | 99769.63 | 0 | 2305920 | 0 | -1485269.6 | 0
Construction Reserve |  |  | 155000 | 295512 | 0 |  | -155000 | -295512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 155000
Rework |  |  | 0 | 295512 | 23713 |  | 23713 | -295512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 588 |  | 5454.33 |  | 9549.78 |  | 1111.09 |  | 5433.75 |  | 0 | 0 | 0 | 1575 | -8 | 0 | 23703.95 |  | 9.05 |  | 23713 |  | -23713
Backcharges |  |  | 0 | 295512 | 1770005 |  | 1770005 | -295512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 108874 |  | 70185.8 |  | 106144.05 |  | 145110.23 |  | 246618.84 |  | 0 | 0 | 962412 | 12102 | 95435 | 0 | 1746881.92 |  | 23123.08 |  | 1770005 |  | -1770005
| Total Project |  | 18803320.8 | 592152 | 22529040.96 | 0 | 3799715.16 | -295512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257461 | 4681 | 544960 | 0 | 802421 | 0 | 0 | 0 | 3183348.54 | 0 | 2411459.5 | 0 | 2245594.11 | 0 | 2333286.55 | 0 | 4774540.42 |  | 2313048.21 | 0 | 0 | 0 | 3312625 | 370485 | 454813 | 0 | 22201621.33 | 0 | 327420.71 | 0 | 22529042.04 | 0 | -3725721.24 | 0
Overhead Lump Sum |  |  | 2048928 |  | 2049926 |  | 998 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 302030 |  | 328718 |  | 630748 |  |  |  | 157687 |  | 0 |  | 157687 |  | 157687 |  | 0 |  | 473061 |  | 0 | 0 | 473056 | 0 | 0 | 0 | 2049926 |  | 0 |  | 2049926 |  | -998
Fee |  |  | 1251833 |  | 1207802 |  | -44031 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 1207802 | 0 | 0 | 0 | 1207802 |  | 0 |  | 1207802 |  | 44031
Contingency |  |  | 149000 | 777891 | 0 |  | -149000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 149000
Change Orders |  |  | 0 |  | 279713 |  | 279713 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [7 empty] | 6359 |  | 6359 |  |  |  | 25613 |  | 5200 |  | 27607 |  | 49564.46 |  | 78831.16 |  | 34130.55 |  | 0 | 0 | 9070 |  | 0 | 0 | 236375.17 |  | 43337.83 |  | 279713 |  | -279713
Adjustment (See Note 1) |  |  | -137360 |  | 0 | [51 empty] | 0 |  | 0 |  | 0 |  | -137360
Productivity Savings |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [9 empty] | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
Difference between NEPCO Billing and Actual Cost |  |  | 0 |  | 0 | [25 empty] | 27263 |  | 1621960 |  | 1649223 |  |  |  | 1942376.46 |  | -2416659.5 |  | -2430888.4 |  | 1386737.99 |  | -2971206.58 |  | 1353159.24 |  | 0 | 0 | 1006932 | 406956 | -454813 | 0 | -528182.79 |  | 528182.79 |  | 0 |  | 0
TOTAL NEPCO |  |  | 22115721.8 | #REF! | 26066481.96 | #REF! | 3887395.16 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 586754 | #REF! | 2501997 | #REF! | 3088751 | #REF! | 0 | #REF! | 5309025 | #REF! | 0 | #REF! | -0.29 | #REF! | 3927276 |  | 1882165 |  | 4173399 |  | 0 | 0 | 6009485 | 777441 | 0 | 0 | 25167541.71 | #REF! | 898941.33 | #REF! | 26066483.04 | #REF! | -3950761.24 | #REF!
| TOTAL EECC & NEPCO SCOPE |  | 104098333.63 | #REF! | 114418957.59 | #REF! | 10257258.96 | #REF! | 21150000 | #REF! | 4263906.48 | #REF! | 3055146.4 | #REF! | 1650000 | #REF! | 2814117 | #REF! | 4389866.41 | #REF! | 2662213.14 | #REF! | 167441.37 | #REF! | 3251216.99 | #REF! | 3706870.16 | #REF! | 5927496.99 |  | 6264886 | #REF! | 6419680.73 |  | 65722841.67 | #REF! | 0 | #REF! | 9100937.09 |  | 3296835.12 |  | 8907308.02 |  | 5580688.16 |  | 3716051.11 |  | 4469888.7 |  | 4551557.76 | 3892184 | 6578122 | 1362831 | 1246306 | 51404 | 118476954.63 |  | -3958283.05 | #REF! | 114518671.58 | #REF! | -10420337.95 | #REF!
NEPCO REIMBURSEMENT FROM GENCO |  |  | 0 |  | -230000 |  | -230000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | -230000 | 0 | 0 | -230000 |  | 0 |  | -230000 |  | 230000
REIMBURSEMENT FROM OPC/GTC |  |  | 0 |  | -6148211.06 |  | -6148211.06 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -5479320 |  | 0 |  | 0 |  | 0 | -470694 | 0 | -198197 | 0 | 0 | -6148211 |  | -0.06 |  | -6148211.06 |  | 6148211.06
TRANSFORMER / SWITCHYARD
| Transformer/Switchyard Equipments |  | 0 |  | 4969697.54 | [17 empty] | 1157656.2 |  |  |  | -657656.2 |  | 57410.7 |  | 1073726 |  | 333333.34 |  | 1964470.04 |  |  |  | 0 |  | 1787991.9 |  | -53400 |  | 703803.9 |  | 72000 |  | 494831.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4969697.54 |  | 0 |  | 4969697.54 |  | -4969697.54
Transformers / Switchyard Expenses |  |  | 0 |  | 4969697.54 |  | 4969697.54 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1157656.2 |  | 0 |  | -657656.2 |  | 57410.7 |  | 1073726 |  | 333333.34 |  | 1964470.04 |  | 0 |  | 0 |  | 1787991.9 |  | -53400 |  | 703803.9 |  | 72000 |  | 494831.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4969697.54 |  | 0 |  | 4969697.54 |  | -4969697.54
SEWER LINE |  |  | 0 |  | 371000 |  | 371000 | [27 empty] | 0 |  |  |  | 160750 | [5 empty] | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 160750 |  | 0 |  | 160750 |  | -160750
REIMBURSEMENT FROM DOYLE FOR SEWER LINE |  |  | 0 |  | -430123 |  | -430123 | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -160750 |  | 0 |  | -59123 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -219873 |  | 0 |  | -219873 |  | 219873
SPARE PARTS |  |  | 1694670 |  | 1545 |  | -1693125 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1545.19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1545.19 |  | -0.19 |  | 1545 |  | 1693125
SPARE PARTS REIMBURSEMENT FROM OPC |  |  | 0 |  | -1545 |  | -1545 | [27 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | -1545 | 0 | 0 | -1545 |  | 0 |  | -1545 |  | 1545
LAND ACQUISITION
| Land acquisition/option |  | 351920.32 |  | 409522 |  | 57601.68 |  | 45000 |  | 0 |  | 0 |  | 0 |  | 16000 |  | 0 |  | 0 |  | 322565.77 |  | -156519.93 |  | 0 |  | 16000 | [5 empty] | 243045.84 |  | 0 |  | 156476.52 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | -32000 | 367522.36 |  | 0 |  | 367522.36 |  | -15602.04
| Other |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Other |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Subtotal Land Acquisition |  | 351920.32 |  | 409522 |  | 57601.68 |  | 45000 |  | 0 |  | 0 |  | 0 |  | 16000 |  | 0 |  | 0 |  | 322565.77 |  | -156519.93 |  | 0 |  | 16000 |  | 0 |  | 0 |  | 243045.84 |  | 0 |  | 156476.52 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | -32000 | 367522.36 |  | 0 |  | 367522.36 |  | -15602.04
ENVIRONMENTAL PERMITTING
| Permitting |  | 400000 |  | 59014.38 |  | -340985.62 |  | 0 |  | 0 |  |  |  | 7006.62 |  | 0 |  | 33128.17 |  | 0 |  | 0 |  | 969.25 |  | 0 |  | 1848.15 |  | 6327.25 |  | 2158 |  | 51437.44 |  | 0 |  | 26.24 |  | 0 |  | 1050.7 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 6500 | 59014.38 |  | 0 |  | 59014.38 |  | 340985.62
| Environmental Consulting Technologies |  | 0 |  | 53435.16 |  | 53435.16 |  | 0 |  | 0 |  | 3168.79 |  | 9937.5 |  | 0 |  | 10765.92 |  | 10111.38 |  | 0 |  | 12516.78 |  | 3179.36 |  | 0 |  | 0 |  | 1506.69 |  | 51186.42 |  | 0 |  | 0 |  | 2248.74 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 53435.16 |  | 0 |  | 53435.16 |  | -53435.16
| Other |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
0
| Subtotal Environmental Permitting |  | 400000 |  | 112449.54 |  | -287550.46 |  | 0 |  | 0 |  | 3168.79 |  | 16944.12 |  | 0 |  | 43894.09 |  | 10111.38 |  | 0 |  | 13486.03 |  | 3179.36 |  | 1848.15 |  | 6327.25 |  | 3664.69 |  | 102623.86 |  | 0 |  | 26.24 |  | 2248.74 |  | 1050.7 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 6500 | 112449.54 |  | 0 |  | 112449.54 |  | 287550.46
MOBILIZATION OF O&M
| Mobilization Fee | Mobilization Fee | 1128564 |  | 1182703 |  | 54139 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 162232.94 |  | 258779.11 |  | 307609.97 |  | 192998 |  | 213192.12 | 0 | 0 | 47891 | 0 | 0 | 1182703.14 |  | 0 |  | 1182703.14 |  | -54139.14
| EI Hourly Billing | EI Hourly billing | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Other | Other | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL MOBILIZATION OF O&M |  | 1128564 | 0 | 1182703 | 0 | 54139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 162232.94 |  | 258779.11 |  | 307609.97 |  | 192998 |  | 213192.12 | 0 | 0 | 47891 | 0 | 0 | 1182703.14 |  | 0 | 0 | 1182703.14 | 0 | -54139.14
Subtotal Mobilization of O&M
REIMBURSEMENT OF MOBILIZATION OF O&M |  |  | -1128564 |  | -1182703 |  | -54139 | [35 empty] | -227769.94 |  | -258779.11 |  | -307610 |  | -192998 |  | -213192 | 0 | 0 | 0 | 0 | 0 | -1200349.05 |  | 0 |  | -1200349.05 |  | 71785.05
GAS INTERCONNECTION |  |  | 1000000 |  | 977990 |  | -22010 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 977990 |  | 0 |  | 0 |  | 977990 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 977990 |  | 0 |  | 977990 |  | 22010
ELECTRICAL INTERCONNECTION | [6 empty] | 0 | [27 empty] | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| W.O. Cost |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
| O.H Cost (21.6%) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Facilities Study |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
| Other |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Subtotal Electrical Interconnection |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
SALES TAX ON EQUIPMENT |  |  | 250000 |  | 257000 |  | 7000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 152853.97 |  | 0 | 0 | 0 | 0 | 0 | 0 | 152853.97 |  | 104146.03 |  | 257000 |  | -7000
INSURANCE DURING CONSTR |  |  | 400000 |  | 477787 |  | 77787 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 407787 |  | 70000 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 477787 |  | 0 |  | 477787 |  | -77787
START UP FUEL |  |  | 400000 |  | 0 |  | -400000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 400000
CAPITALIZED SALARIES |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
INTEREST DURING CONSTRUCTION |  |  | 2964064 |  | 2327182.27 |  | -636881.73 |  | 176250 |  | 141763 |  | 159611 |  | 184622 |  | 187002 |  | 112135 |  | 226003 |  | 218114 |  | 230971 |  | 250137 |  | 268825 |  | 316229.18 |  | 360766 |  | 2832428.18 |  | 0 |  | 106625.85 |  | -419033.64 |  | -155521.1 |  | -59780.1 |  | 97886 |  | -45626.92 |  | -29796 | 0 | 0 | 0 | 0 | 0 | 2327182.27 |  | 0 |  | 2327182.27 |  | 636881.73
| Subtotal - CapX |  | 111558987.95 | #REF! | 117513251.88 | #REF! | 5890898.93 | #REF! | 21371250 | #REF! | 4405669.48 | #REF! | 3217926.19 | #REF! | 1851566.12 | #REF! | 3017119 | #REF! | 4545895.5 | #REF! | 2898327.52 | #REF! | 1865777.34 | #REF! | 3339154.09 | #REF! | 3302530.32 | #REF! | 7249570.84 | 0 | 7661168.43 | #REF! | 7117444.76 | 0 | 71843399.59 | #REF! | 0 | #REF! | 9524815.7 | 0 | 4915079.12 | 0 | 8703900.62 | 0 | 686268.96 | 0 | 3885937.08 | 0 | 5073492.64 | 0 | 4521761.88 | 3421490 | 6578122 | 980980 | 1246306 | 25904 | 121407457.59 | 0 | -3854137.27 | #REF! | 117553320.32 | #REF! | -5994332.37 | #REF!
FINANCING FEE
| Bank fees |  | 0 |  | 0 |  | 0 | [27 empty] | 0 | [21 empty] | 0 |  | 0 |  | 0 |  | 0
| Escrow |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Legal Fees |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Insurance |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Other |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Subtotal Financing Fee |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
RESALE HANDLING FEES (.25%) |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
DEVELOPMENT EXPENSES
| Salaries |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Travel Expenses |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Deloitte & Touche |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Utility Consulting Services |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| HARC Development Service- Tom Young |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Engineering Assessment |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| ICF - Studies |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Maps |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Other - GLC |  | 375000 |  | 378323.93 |  | 3323.93 |  | 1805.25 |  | 0 |  | 1397.02 |  | 4883.08 |  | 8855.27 |  | 15614.51 |  | 12657.16 |  | 20604.31 |  | 1219.95 |  | 3244.27 |  | 1324.73 |  | 4156.31 |  | 231655.07 |  | 307416.93 |  | 0 |  | 2548.75 |  | 11863.81 |  | 4209.87 |  | -6394.29 |  | 1949.99 |  | 3605.21 |  | 1672.66 | 5557 | 17144 | 20082 | 8668 | 0 | 378323.93 |  | 0 |  | 378323.93 |  | -3323.93
| TOTAL DEVELOPMENT EXPENSE |  | 375000 |  | 378323.93 |  | 3323.93 |  | 1805.25 |  | 0 |  | 1397.02 |  | 4883.08 |  | 8855.27 |  | 15614.51 |  | 12657.16 |  | 20604.31 |  | 1219.95 |  | 3244.27 |  | 1324.73 |  | 4156.31 |  | 231655.07 |  | 307416.93 |  | 0 |  | 2548.75 |  | 11863.81 |  | 4209.87 |  | -6394.29 |  | 1949.99 |  | 3605.21 |  | 1672.66 | 5557 | 17144 | 20082 | 8668 | 0 | 378323.93 |  | 0 |  | 378323.93 |  | -3323.93
LEGAL EXPENSES | [34 empty] | 0
| King, Spalding |  | 300000 |  | 304747.25 |  | 4747.25 |  | 21898.53 |  | 6134.01 |  | 9917.44 |  | 0 |  | 0 |  | 43465.95 |  | 0 |  | 0 |  | 0 |  | 28510.25 |  | 0 |  | 104668 |  | 65033.33 |  | 279627.51 |  | 0 |  | 2036.4 |  | 0 |  | 15743.99 |  | 0 |  | 0 |  | 7252.35 |  | 0 | 0 | 0 | 87 | 0 | 0 | 304747.25 |  | 0 |  | 304747.25 |  | -4747.25 |  | Included fees expensed on WO# E07A59
| Kilpatrick, Stockton |  | 150000 |  | 104427 |  | -45573 |  | 31211.02 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2585.04 |  | 0 |  | 9442.62 |  | 2771.63 |  | 0 |  | 13549 |  | 59559.31 |  | 0 |  | 3255.75 |  | 0 |  | 0 |  | 28641.6 |  | -31.37 |  | 13001.75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 104427.04 |  | 0 |  | 104427.04 |  | 45572.96 |  | Included fees expensed on WO# E07A59
| Other |  | 0 |  | 0 |  | 0 |  | 2705 |  |  |  | 934 | [5 empty] | 0 |  | -10271.2 | [7 empty] | 0 |  | 0 |  | 0 |  | -6632.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -6632.2 |  | 0 |  | -6632.2 |  | 6632.2
| Bracewell & Patterson |  | 40000 |  | 29698 |  | -10302 | [27 empty] | 0 | [7 empty] | 23988.75 |  |  |  | 4231.25 |  | 947.5 |  | 530 |  |  |  | 0 | 0 | 29697.5 |  | 0 |  | 29697.5 |  | 10302.5
| Reimbursement from OPC |  | -40000 |  | -42444 |  | -2444 | [27 empty] | 0 | [11 empty] | -23988.75 |  | 0 |  | 0 | 0 | 0 | -18455 | 0 | 0 | -42443.75 |  | 0 |  | -42443.75 |  | 2443.75
| TOTAL LEGAL EXPENSE |  | 450000 |  | 396428.25 |  | -53571.75 |  | 55814.55 |  | 6134.01 |  | 10851.44 |  | 0 |  | 0 |  | 43465.95 |  | -10271.2 |  | 2585.04 |  | 0 |  | 37952.87 |  | 2771.63 |  | 104668 |  | 78582.33 |  | 332554.62 |  | 0 |  | 5292.15 |  | 0 |  | 39732.74 |  | 28641.6 |  | -19788.87 |  | 21201.6 |  | 530 | 0 | 0 | -18368 | 0 | 0 | 389795.84 |  | 0 |  | 389795.84 |  | 60204.16
DEBT RESERVE |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
CONTINGENCY |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
WORKING CAPITAL |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Subtotal - Expense |  | 825000 |  | 774752.18 |  | -50247.82 |  | 57619.8 |  | 6134.01 |  | 12248.46 |  | 4883.08 |  | 8855.27 |  | 59080.46 |  | 2385.96 |  | 23189.35 |  | 1219.95 |  | 41197.14 |  | 4096.36 |  | 108824.31 |  | 310237.4 |  | 639971.55 |  | 0 |  | 7840.9 |  | 11863.81 |  | 43942.61 |  | 22247.31 |  | -17838.88 |  | 24806.81 |  | 2202.66 | 5557 | 17144 | 1714 | 8668 | 0 | 768119.77 |  | 0 |  | 768119.77 |  | 56880.23
TOTAL DOYLE EXPENSE --- ENA |  |  | 112383987.95 |  | 118288004.06 |  | 5840651.11 |  | 21428869.8 |  | 4411803.49 |  | 3230174.65 |  | 1856449.2 |  | 3025974.27 |  | 4604975.96 |  | 2900713.48 |  | 1888966.69 |  | 3340374.04 |  | 3343727.46 |  | 7253667.2 |  | 7769992.74 |  | 7427682.16 |  | 72483371.14 |  | 0 |  | 9532656.6 |  | 4926942.93 |  | 8747843.23 |  | 708516.27 |  | 3868098.2 |  | 5098299.45 |  | 4523964.54 | 3427047 | 6595266 | 982694 | 1254974 | 25904 | 122175577.36 |  | -3854137.27 |  | 118321440.09 |  | -5937452.14
| ENA Output Bonus |  | 0 |  | -1725000 | [29 empty] | 0 | [21 empty] | 0 |  | -1725000 |  | -1725000 |  | 1725000
TOTAL DOYLE -- ENA |  |  | 112383987.95 |  | 116563004.06 |  | 5840651.11 |  | 21428869.8 |  | 4411803.49 |  | 3230174.65 |  | 1856449.2 |  | 3025974.27 |  | 4604975.96 |  | 2900713.48 |  | 1888966.69 |  | 3340374.04 |  | 3343727.46 |  | 7253667.2 |  | 7769992.74 |  | 7427682.16 |  | 72483371.14 |  | 0 |  | 9532656.6 |  | 4926942.93 |  | 8747843.23 |  | 708516.27 |  | 3868098.2 |  | 5098299.45 |  | 4523964.54 | 3427047 | 6595266 | 982694 | 1254974 | 25904 | 122175577.36 |  | -5579137.27 |  | 116596440.09 |  | -4212452.14
TARGET $$/MW |  |  | 328608.1519 |  | 340827.4973 | [55 empty] | 340925.2634
Doyle Payment | [34 empty] | 0 |  |  |  | -23500000 |  | -67845224.04 |  | -10539776 |  | -6144590 |  | 0 |  | -2403255 |  | -735341 | -1143360 | 0 | 0 | 0 | 0 | -112311546.04
OPC Deposit on Power Purchase Agreement | [20 empty] | -5000000 | [13 empty] | -5000000 | [5 empty] | 5000000 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL DOYLE -- ENA ( Net of Payment Received ) |  |  | 112383987.95 | 0 | 116563004.06 | 0 | 5840651.11 | 0 | 21428869.8 | 0 | 4411803.49 | 0 | 3230174.65 | 0 | 1856449.2 | 0 | 3025974.27 | 0 | 4604975.96 | 0 | -2099286.52 | 0 | 1888966.69 | 0 | 3340374.04 | 0 | 3343727.46 | 0 | 7253667.2 | 0 | 7769992.74 | 0 | 7427682.16 | 0 | 67483371.14 | 0 | 0 | 0 | -13967343.4 | 0 | -57918281.11 | 0 | -1791932.77 | 0 | -5436073.73 |  | 3868098.2 |  | 2695044.45 |  | 3788623.54 | 2283687 | 6595266 | 982694 | 1254974 | 25904 | 9864031.32 | 0 | -5579137.27 | 0 | 116596440.09 | 0 | -4212452.14
| ENA PDA -- Contract Amount |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Write off of Loss in September 00 | [62 empty] | 4500000
Net Income (Loss) | [62 empty] | 287547.86
Note on Y12: Lindsay Long: IBC Turbo invoices Warehouse 56,200, security - 10,121, other is reclass of amounts not belonging to Doyle.
Note on Y15: Lindsay Long: Doyle originally charged for all LEC burners. This amount to reclass excess over 3 LEC burners.
Note on Q16: Lindsay Long: Net of $2,850,000 and (1,200,000)= 1,650,000. $2.8MM was refunded 4/99.
Note on BK16: tvos: $60K refund from GE and $57K adjustment to tie to G/L
Note on B158: Adjustment made for part of Change order works which are included in line 46 to 137, running against the orginal budget.
Note on B174: awu3: Include Substation/Switchyard from Nepco Billing
Note on AS204: Enron: O&M Reimbursement 1 March $65537 2 April 421012.05
Note on K253: Lindsay Long: Includes $21,899 expensed on E07A59.
Note on M253: Lindsay Long: Expensed on WO# E07A59.
Note on O253: Lindsay Long: Expensed on WO# E07A59.
Note on U253: Lindsay Long: Expensed on WO# E07A59.
Note on K254: Lindsay Long: Includes $2,485 expensed on E07A59.
Note on W255: Lindsay Long: Reverse Ogden, Newell legal costs not belonging to Doyle.

## Doyle
Enron North America
Doyle I, LLC
|  |  | 342 |  | MW
[10 empty] | Actuals |  | Actuals |  | as of 09/11/00 |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  |  |  | Anticipated |  | Actuals |  | Actuals |  | Actuals | Actuals | Actuals | Actuals |  | Actuals | Actuals
|  |  | ENA |  | ENA |  | Increase / | Actuals to Date |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | Actuals to Date |  | Increase / |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) |  | (Mo-to-date) | (Mo-to-date) | Actuals to Date |  | Estimate |  | Actuals Plus |  | (Over)/Under
|  |  | Control Budget |  | Current Estimate |  | (Decrease) | 12/31/98 |  | 01/31/99 |  | 02/28/99 |  | 03/31/99 |  | 04/30/99 |  | 05/31/99 |  | 06/30/99 |  | 07/31/99 |  | 08/31/99 |  | 09/30/99 |  | 10/31/99 |  | 11/30/99 |  | 12/31/99 |  | Total Project |  | (Savings) |  | 2000-01-31 |  | 2000-02-29 |  | 2000-03-31 | 2000-04-30 | 2000-05-31 | 2000-06-30 |  | 2000-07-31 | 2000-08-31 | Total Project |  | To Complete |  | Est. to Complete |  | Budget |  | Comments
|  |  | as of 07/12/99 |  | as of 12/28/00 |  | as of 12/28/00 | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/31/99 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 | as of 12/28/00 | as of 12/28/00 | as of 12/28/00 |  | as of 12/28/00 | as of 12/28/00 | as of 12/28/00 |  | 0 |  | 0 |  | 0
ENA PDA -- Contract Amount |  |  | 112383987.95 | 0 | 112383987.95 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23500000 | 0 | 67845224.04 | 0 | 10539776 | 5723578 | 0 | 2403255 |  | 1221890 | 1143360 | 112377083.04 |  | 6904.91 | 0 | 112383987.95 | 0 | 0
MOBILIZATION OF O&M
| Mobilization Fee | Mobilization Fee | 1128564 |  | 1128564 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1425 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 421012.05 | 307609.97 | 192998 |  | 213192 | 0 | 1134812.02 |  | 0 |  | 1134812.02 |  | -6248.02
| EI Hourly Billing | EI Hourly billing | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Other | Other | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| TOTAL MOBILIZATION OF O&M |  | 1128564 | 0 | 1128564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 421012.05 | 307609.97 | 192998 |  | 213192 | 0 | 1134812.02 |  | -60717 | 0 | 1134812.02 | 0 | -6248.02
OPC REIMBURSEMENT FOR MOBILIZATION |  |  | -1128564 | 0 | -1128564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | -728622 |  |  | -406190 | -1134812 |  | 6248 |  | -1128564 |  | 0
Subtotal Mobilization of O&M
INTEREST DURING CONSTRUCTION |  |  | 3921610 | 0 | 3921610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 1756082.36 | 0 | 419034 |  | 2159779 | 0 | 4334895.36 |  | 0 |  | 4334895.36 |  | -413285.36
SEWER LINE |  |  | 430123 |  | 430123 |  | 0 | 0 | [25 empty] | 0 |  |  |  | 0 |  | 160750 |  | 0 | 59123 | 0 | 0 |  | 0 | 0 | 219873 |  | 210250 |  | 430123 |  | 0
ENA CONSTRUCTION COMPLETION BONUS |  |  | 1725000 |  | 1725000 |  | 0 | [41 empty] | 0 |  | 1725000 |  | 1725000 |  | 0
PURCHASE OF NEIGHBOR LAND |  |  | 200000 |  | 200000 |  | 0 | 0 | [25 empty] | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 200000 |  | 200000 |  | 0
OPC - SUBSTATION REIMBURSEMENT |  |  | 2000000 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2000000 |  | 2000000 |  | 0
REIMBURSEMENT FROM OPC/GTC |  |  | -5800000 |  | -5800000 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -5479320 |  | 0 |  | 0 | [6 empty] | -5479320 |  | -320680 |  | -5800000 |  | 0
TRANSFORMER / SWITCHYARD |  |  | 5800000 |  | 5800000 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 5479320 |  | 0 |  | 0 | [6 empty] | 5479320 |  | 320680 |  | 5800000 |  | 0
TOTAL DOYLE |  |  | 120660720.95 | 0 | 120660720.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23500000 | 0 | 68005974.04 | 0 | 10539776 | 7959795.41 | 307609.97 | 3015287 | 0 | 3594861 | 1143360 | 116931851.42 | 0 | 4087685.91 | 0 | 121080254.33 | 0 | -419533.38 | 0
Note on B32: awu3: Include Substation/Switchyard from Nepco Billing
Note on B36: awu3: Include Substation/Switchyard from Nepco Billing

## Turbine Detail
Enron Capital & Trade Resources
Doyle I, LLC | [34 empty] | 2001-01-03 10:29
Detail of Major Equipment | [34 empty] | O:\Fin_Ops\Engysvc\PowerPlants\Walton EMC\00 Weekly Reports\[Doyle Wkly 122800-Doyle.xls]ENA
[6 empty] | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals | Actuals | Actuals | Actuals | Actuals |  | Actuals | Actuals |  |  | Actuals | Actuals |  | Actuals | Actuals | Actuals | Actuals
| Contract | Contract | Budget | Actuals to Date |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) |  | (Mo-to-date) | (Mo-to-date) |  |  | (Mo-to-date) | (Mo-to-date) |  | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | Project
| Date | Price | as of 07/12/99 | 1998-12-31 |  | 1999-01-31 |  | 1999-02-28 |  | 1999-03-31 |  | 1999-04-30 |  | 1999-05-31 |  | 1999-06-30 |  | 1999-07-31 | 1999-08-31 | 1999-09-30 | 1999-10-31 | 1999-11-30 |  | 1999-12-31 | 2000-01-31 |  |  | 2000-02-29 | 2000-03-31 |  | 2000-04-30 | 2000-05-31 | 2000-06-30 | 2000-07-31 | to date
(3) GE 7B Turbine Units from Youngwol
KEPCO through IBC for units fromYoungwol | 1998-12-01 | 21150000 | 25778420 | 21150000 |  | 1200000 |  |  |  | -1200000 | [24 empty] | 21150000
IBC - Removal of 1 KEPCO Youngwol turbine |  | 332267.1 |  |  |  | 332267.1 | [28 empty] | 332267.1
IBC - Removal of 2 KEPCO Youngwol turbine |  | 664534.2 |  |  |  | 664534.2 | [28 empty] | 664534.2
0
TURBINE UNITS, Disassemble |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [16 empty] | 0
0
IBC - Freight for 2 KEPCO Youngwol turbine | N/A | 1378070.12 |  |  |  | 1378070.12 | [28 empty] | 1378070.12
IBC - Freight for 1 KEPCO Youngwol turbine | N/A | 689035.06 |  |  |  | 689035.06 | [9 empty] | 268110.4 | [18 empty] | 957145.46
IBC - Freight for Dow parts | [15 empty] | 5323 | [18 empty] | 5323
IBC - DOW Refurb work per NA refurb contract | 1998-11-25 | 1291080 | [11 empty] | 1291080 | [20 empty] | 1291080
Total Cost 3 GE 7B Turbines before Refurbishment |  | 25504986.48 | 25778420 | 21150000 |  | 4263906.48 |  | 0 |  | -1200000 |  | 0 |  | 1291080 |  | 273433.4 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 25778419.88
TURBINE REFURBISHMENT
Refurbishment Costs |  | 13906531 | 13906531 | [10 empty] | 318442.41 |  | 78641.11 |  | -397083.52 | 743136.99 | 614097.41 | 2140753.46 | 821804 |  | 1830588.45 | 1983024.4 |  |  | 859544.09 | 1976684.41 |  | 67904.56 | 1121091.27 | 73206 | 1527614.65 | 13759449.69
IBC - for Inlet (Air Intake per NA refurb contract) | 1998-11-25 | 396000 | 396000 | [10 empty] | 396000 | [9 empty] | 96762 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 492762
IBC - Compressor stack/unstack; blade 1 manuf (Rotor) |  | 245000 | 245000 | [10 empty] | 252344 | [9 empty] | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 252344
IBC - Warehouse lease |  | 400000 | 400000 | [12 empty] | 53311.19 |  | 56199.77 | 97500 |  | 50944.98 | 15834 |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 273789.94
IBC - WH Security | [15 empty] | 4671.74 |  | 10120.87 | [5 empty] | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 14792.61
Mississippi Major Impact Authority - lease Tri-State Com Park | [19 empty] | 12500 |  |  |  | 12500 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 25000
Mike Nelson Contractors, Inc. - site preparation | [19 empty] | 39924.05 |  |  |  | 0 | 0 |  |  | 2500 | 0 |  | 0 | 0 | 0 | 0 | 42424.05
AJ Mechanical - Refurb work | [15 empty] | 22604.87 |  | -22604.87 |  |  | 52405 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 52405
AJ Mechanical - Refurb work | [15 empty] | 28671.86 |  | -28671.86 | [5 empty] | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
AJ Mechanical - Refurb work | [15 empty] | 26120.07 |  | -26120.07 | [5 empty] | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
AJ Mechanical - Refurb work | [15 empty] | 24767.55 |  | -24767.55 | [5 empty] | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
IBC - WH Security - 7% fee | [15 empty] | 327.02 | [7 empty] | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 327.02
IBC - Compressor stack/unstack; blade 1 manuf - 7% fee | [15 empty] | 17664.08 | [7 empty] | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 17664.08
Benchmark Transportation - move turbines | [18 empty] | 278580 | 111465 | 369853 | 186919 |  | 33581.34 | 30650 |  |  | 336366 | 7135 |  | 0 | 0 | 0 | 0 | 1354549.34
H&M Industrial Services - transport turbines to Iuka/site prep | [19 empty] | 93525.5 | 864783.5 | 364511 |  | 159160.5 | 125816.6 |  |  | 148432.99 | 8529.09 |  | 0 | 112179.6 | 0 | 0 | 1876938.78
2 GE 7EA TURBINE UNITS - Exhaust stack - $500,000 ea |  | 1000000 | 1192000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 463226.2 | [14 empty] | 463226.2
Power Systems - Reburbishment Management |  | 500000 | 500000 | [16 empty] | 230000 | 264007.08 | 250000 |  | 265000 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 5489.31 | 1014496.39
Total Turbine Refurbishment 3 GE 7B |  | 16447531 | 16639531 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 966786.41 |  | 256779.49 |  | -432927.23 | 1119216.99 | 1564738.16 | 3742747.02 | 1639068 |  | 2397592.29 | 2139491 |  |  | 1346843.08 | 1992348.5 |  | 67904.56 | 1233270.87 | 73206 | 1533103.96 | 19640169.1
Other - LEC Burners
3 sets LEC @ $1,280,000 ea | 1999-04-26 | 3840000 | 3840000 |  |  |  |  | 2560000 |  |  |  | 2048000 | [5 empty] | -1152000 | [5 empty] | 611029 | 0 |  |  | -170181 | 0 |  | 0 | 0 | 0 | 0 | 3896848
3 sets IGV's @$116,160 ea |  | 348480 | 348480 |  |  |  |  | 348480 |  |  |  | 278784 | [5 empty] | -313632 | [5 empty] | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 313632
3 sets Fuel Manifolds/Combustion Cases w/ |  | 219999 | 219999 |  |  |  |  | 146666 |  |  |  | 117332.8 | [5 empty] | -65999.7 | [5 empty] | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 197999.1
hardware @ $73,333 ea | [23 empty] | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Total LEC Burners |  | 4408479 | 4408479 | 0 |  | 0 |  | 3055146 |  | 0 |  | 2444116.8 |  | 0 |  | 0 |  | -1531631.7 | 0 | 0 | 0 | 0 |  | 611029 | 0 |  |  | -170181 | 0 |  | 0 | 0 | 0 | 0 | 4408479.1
Evap Cooling Sys - 3 Refurb 7EAs @$366,667 ea (Power Systems) |  | 1100000 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Total GE 7B - 3 from Youngwol |  | 47460996.48 | 46826430 | 21150000 |  | 4263906.48 |  | 3055146 |  | -1200000 |  | 2444116.8 |  | 2257866.41 |  | 530212.89 |  | -1964558.93 | 1119216.99 | 1564738.16 | 3742747.02 | 1639068 |  | 3008621.29 | 2139491 |  |  | 1176662.08 | 1992348.5 |  | 67904.56 | 1233270.87 | 73206 | 1533103.96 | 49827068.08
(2) GE 7EA Turbine Units
Air Liquide mo payment | 1999-04-01 | 4000000 | 4000000 | [8 empty] | 500000 |  | 500000 |  | 500000 |  | 500000 | 500000 | 500000 | 500000 | 500000 |  | 532622 | 0 |  |  | 0 | 0 | 4532622 | 0 | 400000 | 0 | 0 | 4932622
EPS Consultants - Option refund | [34 empty] | 0
M&M leasing - Option refund | [34 empty] | 0
GE payment | 1999-04-01 | 14000000 | 14086000 | [6 empty] | 2850000 |  | -65000 |  | 816000 |  | 816000 |  | 816000 | 816000 | 816000 | 816000 | 1632000 |  | 0 | 816000 |  |  | 816000 | 3400000 |  | 680000 | 0 | 0 | 0 | 15025000
GE payment | 1999-04-01 | 14000000 | 14086000 | [6 empty] | 0 |  | -65000 |  | 816000 |  | 816000 |  | 816000 | 816000 | 816000 | 816000 | 1632000 |  | 0 | 816000 |  |  | 816000 | 3400000 |  | 680000 | 0 | 0 | 0 | 12175000
Total Cost 2 GE 7EA Turbines |  | 32000000 | 32172000 | 0 |  | 0 |  | 0 |  | 2850000 |  | 370000 |  | 2132000 |  | 2132000 |  | 2132000 | 2132000 | 2132000 | 2132000 | 3764000 |  | 532622 | 1632000 |  |  | 1632000 | 6800000 |  | 1360000 | 400000 | 0 | 0 | 32132622
2 GE 7EA TURBINE UNITS - Evaporative cooling - $408,000 ea |  | 816000 | 896000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [16 empty] | 0
Total GE 7EA - 2 |  | 33816000 | 34260000 | 0 | 0 | 0 | 0 | 0 | 0 | 2850000 | 0 | 370000 | 0 | 2132000 | 0 | 2132000 | 0 | 2132000 | 2132000 | 2132000 | 2132000 | 3764000 | 0 | 532622 | 1632000 | 0 | 0 | 1632000 | 6800000 | 0 | 1360000 | 400000 | 0 | 0 | 32132622
Refurb & 7 EA Contract Management | [19 empty] | 10132 | 52750 | 34278 |  | 21750.25 | 20421 |  |  | 22912.59 | 41788.38 |  | 55874.52 | 41048.95 | 51911 | 0 | 352866.69
Total Turbines |  | 81276996.48 | 81086430 | 21150000 |  | 4263906.48 |  | 3055146 |  | 1650000 |  | 2814116.8 |  | 4389866.41 |  | 2662212.89 |  | 167441.07 | 3251216.99 | 3706870.16 | 5927497.02 | 5437346 | 0 | 3562993.54 | 3791912 |  |  | 2831574.67 | 8834136.88 |  | 1483779.08 | 1674319.82 | 125117 | 1533103.96 | 82312557.77
Note on K42: Lindsay Long: Payment equal to 50% of purchase price.
Note on O42: Lindsay Long: Payment for 40% of contract price, remaining 10% upon delivery.
Note on K43: Lindsay Long: Payment equal to 50% of purchase price.
Note on O43: Lindsay Long: Payment equal to 50% of purchase price.
Note on K44: Lindsay Long: Payment equal to 50% of purchase price.
Note on O44: Lindsay Long: Payment equal to 50% of purchase price.
Note on I66: Allan Wu: Deposit of &1200000 on turbines refunded in April
Note on M66: Allan Wu: Deposit of $1200000 paid in January refunded and $2850000 paid this month refunded in April
Note on O66: Allan Wu: Deposit of $2850000 refunded this month.

## IDC
ECT - NORTH AMERICA
4Q98 & 1999 PLAN
DETAILS OF CAPITAL EXPENDITURES
Generation Services - RC 1231 | [29 empty] | 2001-01-03 10:29
O:\Fin_Ops\Engysvc\PowerPlants\Walton EMC\00 Weekly Reports\[Doyle Wkly 122800-Doyle.xls]ENA
est.
| FY | [6 empty] | 1998 | Actual | Actual | Actual | Actual | [8 empty] | 1999 | [7 empty] | 2000 + | GRAND | FY
| 1998 | July | Aug | Sept | Oct | Nov | Dec | Total | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Jan | Feb | Mar | Apr | May | Jun | Jul | Total | TOTAL | 2001
Project Doyle (Walton) | [6 empty] | 21150000 | 21252620 | 4270040.49 | 3070563.65 | 1671827.2 | 2838972.27 | 4492840.96 | -2325289.52 | 1670852.69 | 3109403.04 | 3093590.46 | 6984842.2 | 7453763.56 | 7066916.16 | 43398323.16 | -14073969.25 | -57499247.47 | -1636411.67 | -5376293.63 | 3770212.2 | 2740671.37 | 3818419.54 | -72075038.45 | -7424095.29
Project Doyle (Walton) - Cum Total | [8 empty] | 25522660.49 | 28593224.14 | 30265051.34 | 33104023.61 | 37596864.57 | 35271575.05 | 36942427.74 | 40051830.78 | 43145421.24 | 50130263.44 | 57584027 | 64650943.16 | 64650943.16 | 50576973.91 | -6922273.56 | -8558685.23 | -13934978.86 | -10164766.66 | -7424095.29 | -3605675.75
| FY | [6 empty] | 1998 | [12 empty] | 1999 | [7 empty] | 2000 + | GRAND | FY
| 1998 | July | Aug | Sept | Oct | Nov | Dec | Total | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Jan | Feb | Mar | Apr | May | Jun | July | Total | TOTAL | 2001
Project Doyle (Walton) | [6 empty] | 176250 | 176250 | 126683.0513 | 146563.8542 | 159407.8294 | 171624.578 | 191481.5722 | 197352.024 | 195579.5909 | 208526.1168 | 225325.8909 | 252621.646 | 291726.2033 | 331053.0442 | 2497945.4011 | 312075.6087 | -419033.64 | -41927.5967 | -60920.3402 | -65270.1441 | -47636.5011 | -29872.2966 | -322712.6135 | 2351482.7877
Project Doyle (Walton) - Cum IDC | [8 empty] | 302933.0513 | 449496.9055 | 608904.735 | 780529.3129 | 972010.8851 | 1169362.9091 | 1364942.5 | 1573468.6168 | 1798794.5077 | 2051416.1537 | 2343142.357 | 2674195.4011 | 2674195.4011 | 2986271.0099 | 2567237.3699 | 2525309.7732 | 2464389.4329 | 2399119.2888 | 2351482.7877 | 2321610.4911
O:\Fin_Ops\Engysvc\PowerPlants\Walton EMC\00 Weekly Reports\[Doyle Wkly 122800-Doyle.xls]ENA
Note on T11: Lindsay Long: Estimate thru 10/15

## Invoice Detail
Doyle, LLC
Invoice Detail
| 08/31/99 | Description
Payroll | 793.07
Power Systems | 20000 | Milestone payment - Wood Group
Power Systems | 100000 | August project management fee
Kilpatrick & Stockton | -156519.93 | Defer 1/2 Bush land payment until 2000
Power Spares, Inc. | 510000 | LEC transition piece
General Electric | 1632000 | Gas turbine payment for August
Environmental Consultants | 3916.79 | May permitting costs
Neel-Schaffer, Inc. | 969.25 | Permitting survey
Air Liquide | 500000 | Steam turbine payment for August
Bryan Garrett | 426.88 | Travel
Power Spares, Inc. | 10000 | Monthly consignment fee
Power Spares, Inc. | 13833.93 | May reimbursement - warehouse costs
Power Spares, Inc. | 9303.06 | June reimbursement - warehouse costs
Power Systems | 80000 | Milestone payment 2
Benchmark Transportation | 278580 | move turbines to Mississippi
IBC Turbo, Inc. | 97500 | Pensacola lease
Environmental Consultants | 8599.99 | May/June invoice
| 230971 | Interest During Construction
3340374.04
09/30/99
Kilpatrick & Stockton | 2387.16 | June - sales tax
King & Spalding | 23476.13 | June - loan agreement
Kilpatrick & Stockton | 7055.46 | May - site issues
General Electric | 1632000 | September turbine payment
Air Liquide | 500000 | September payment
Environmental Consulting | 2197.53 | July invoice
H & M Industrial Services | 45905 | transport turbine
H & M Industrial Services | 47620.5 | transport turbine
Power Systems | 150000 | Initial project payment
Power Systems | 80000 | Project management - September
Turbine Technology | 545437.8 | Refurb
Mississippi Major | 12500 | Lease payment
Mike Nelson, Contractor | 17510.9 | Facility preparation
Bryan Garrett | 2098.81 | Travel expenses
Robert Virgo | 1145.46 | Travel expenses
GLC Consulting Services | 10132 | Consulting services
King & Spalding | 5034.12 | Legal
Benchmark Transportation | 104297 | transport turbine
Benchmark Transportation | 7168 | transport turbine
Power Systems | 463226.2 | 1st,2nd,3rd stage buckets, nozzle
Power Spares | 5000 | Consignment Fee
| 250137 | Interest During Construction
Environmental Consulting | 981.83 | August invoice
Mike Nelson, Contractor | 22413.15 | Facility preparation
Power Systems | 63659.61 | Refurb
| -907656.2 | Reclass of Transformer
| 250000 | Reclass of Transformer
3343727.46
10/31/99
IBC Turbo | 15834 | Pensacola lease
Neel Schaffer, Inc. | 1848.15 | July survey/permitting invoice
Air Liquide | 500000 | October turbine payment
Power Systems | 63668.61 | Turbine refurb
Power Systems | 630000 | Nozzle
H & M Industrial Services | 54196.5 | Iuka building prep
GE | 1632000 | October turbine payment
Power Spares, Inc. | 5000 | Consignment fee
IBC Turbo | 15834 | Refurbish
Power Spares, Inc. | 11145.5 | GE Rotor-Test/Inspect
GLC Consulting SE | 52750 | Consultant
Williams Gas Pipeline | 977990 | Interconnect
Mike Nelson Contractor | 11000 | IUKA Site Preparation
Mike Nelson Contractor | 3000 | IUKA Site Preparation
Garrett Bryan | 126.84 | Golf Outing
Garrett Bryan | 1131.4 | Mex-Customer Outing
Garrett Bryan | 66.49 | Meals
Kilpatrick Stockton Land Option | 8000 | Land Acquisition
Kilpatrick Stockton Land Option | 8000 | Land Acquisition
Power Systems | 100000 | Project Management fee for Turbine Refurbishment
Power Systems | 125000 | Project Management time and expense for Turbine Refurbishment
Power Systems | 39007.08 | Reimburse Pensacola Payroll and Facility Charges
Power Systems | 755700 | Pass-Through Payment Wood Group Item #2
Power Spares, Inc. | 9030.98 | Expense reimbursement billing for Sep 1999 pursuant to the
Consignment agreement dated Feburary 17, 1999
Kilpatrick Stockon | 2771.63 | Legal fee for closing documents
Turbine Technology | 272718.9 | Rewire
Turbine Technology | 136359.45 | Rewire
Power Systems | 9000 | Transportation
Power Spares | 203476.5 | 2nd, 3 rd stage Shroud Block
AJ Michanical Inc | 52404.53 | Refurbish Turbine at Warehouse #8, Pensacola
Applied Engineering | 5179.43 | Refurbish
The Salvage Association | 22526 | INS Moving Refurbishment
Power Spares | 10245.82 | Expense reimbursement billing for August 1999 pursuant to the
the consignment agreement dated Feburary 17, 1999
Banchmark Transpotation | 129539 | Moving Turbines
Banchmark Transpotation | 10985 | Moving Turbines
Banchmark Transpotation | 119361.69 | Moving Turbines
Banchmark Transpotation | 5289 | Moving Turbines
Banchmark Transpotation | 20808 | Moving Turbines
Banchmark Transpotation | 49370 | Moving Turbines
Banchmark Transpotation | 34500 | Moving Turbines
ABB Power T&D Company | 57410.7 | First 10% total payment of 2 type HGC-3 Generator Circuit Breakers
Power Spares, INC | 5000 | Monthly consignment fee dated Feburary 17th, 1999
Power Systems SPC I | 127328.22 | Pass through payment to H&M milestone payment #2
Hoist & Crane Service GroupVI (HCSG) | 6980 | Start up of 250 Ton Crane/Repairs
Power Systems SPC I | 683258.64 | Pass through payment to H&M milestone payment #2
6984842.06
11/30/99
Neel Schaffer Inc | 3359.69 | Consulting
H&M Industrial Service, INC | 33146.06 | Labor of Iuka building preparation
H&M Industrial Service, INC | 8777.07 | Iuka material for installation
H&M Industrial Service, INC | 5422.76 | Iuka material for installation
H&M Industrial Service, INC | 2644.2 | Iuka Travel Expense
Power Spares, Inc. | 10000 | Parts
Power Spares, Inc. | 5000 | Consign Fee - Sell Spare Parts
Powre System, LLC | 82044.9 | Refurbishment
GE | 1632000 | Nov Turbine Payment
Air Liquide America Corporation | 500000 | Letter Agreement Payment
IBC Turbo, Inc | 15834 | Refurbishment- Pensacola Lease
King & Spalding | 14179.86 | Legal Expense
King & Spalding | 79879.31 | Legal Expense
King & Spalding | 10609.34 | Legal Expense
Environmental Committee | 666.62 | Permitting Fee
Coffer, Walter | 9.17 | Meals
Coffer, Walter | 484.41 | Travel
Garrett Bryan | 2152.82 | Travel
G.L.C Consulting Services | 34278 | Turbine Consultant
GE | 1632000 | Dec Turbine Payment
Spears R. Clay | 1383.69 | Travel
Spears R. Clay | 126.22 | Travel
Environmental Con | 2300.25 | Permitting Fee
Power Systems SPC | 150000 | Project Management Time and Expenses- November 1999
Power Systems SPC | 82875 | Pass-through payment to H&M- For total Intel work without installation
Power Systems SPC | 100000 | Project Management fee- November 1999
Power Systems SPC | 159160.5 | Pass-through payment to H&M- Milestone Payment #1
Power Systems SPC | 2742.2 | Reimbursement of additional Pensacola facility charges
Power Spares, Inc | 7017.42 | Expense Reimbrusement billing for October 1999
Power Spares, Inc | 15000 | Monthly Consignment Fee Pursuant to consignment agreement dated Feb 17, 1999
H & M Industrial Services, Inc | 9000 | Install metal siding on turbine building
H & M Industrial Services, Inc | 63485.07 | Clean-up & Electrical of turbine building IUKA facility
National Energy Production Corp (NEPCO) | 201869 | Reimbursable portion of the work completed for August
National Energy Production Corp (NEPCO) | 82855 | Reimbursable portion of the work completed for September
National Energy Production Corp (NEPCO) | 151015 | Fixed Lump sum portion of the work completed for August
National Energy Production Corp (NEPCO) | 151015 | Fixed Lump sum portion of the work completed for September
Journal Entry | 316229.18 | IDC to ENA for November
Journal Entry | 186919 | Reclass Benchmark Invoice from Project 2000 to Doyle
Journal Entry | 700000 | Transfer Power Spares Inventory to Doyle
Journal Entry | 1314512
7769992.74
12/31/99
Power System | 60398.33 | Dow unit Refurbishment
Power System | 34252.67 | VW turbine Refurbishment
Power System | 96762 | Inlets & Exhausts
Power System | 356900 | Turbine-TAW Generator Refurbishment
Environmental Committee | 2158.32 | Permitting Fee
GLC Consulting | 21750.25 | GLC consulting
Enron Engineering & Construction | 4589.45 | Support to develop engineering in June, 1998
Enron Engineering & Construction | 16484.03 | Support to develop engineering in July and August, 1998
Enron Engineering & Construction | 9568.95 | Support to develop engineering in Sep through November, 1998
Enron Engineering & Construction | 2059.32 | Support to develop engineering in December, 1998
Enron Engineering & Construction | 9301.58 | Support to develop engineering in February, 1999
Enron Engineering & Construction | 27961.73 | Support to develop engineering in March, 1999
Enron Engineering & Construction | 19918.9 | Support to develop engineering in April, 1999
Enron Engineering & Construction | 27650.83 | Support to develop engineering in May, 1999
Enron Engineering & Construction | 41293.92 | Support to develop engineering in June and July, 1999
Enron Engineering & Construction | 19502.89 | Support to develop engineering in August, 1999
Enron Engineering & Construction
Enron Engineering & Construction
Enron Engineering & Construction
Mississippi Major Impact Authority | 12500 | Lease Payment
Coffer Walter | 316.65 | Travel
Sewell Robert D | 746.73 | Travel
Sewell Robert D | 18.72 | Travel
Byran Garrett | 1640.13 | Travel
Byran Garrett | 828.67 | Travel
Power System | 59980.39 | Doyle Refurbish- Repair Bearing s on YW 90 and YW 91
Power System | 450000 | Doyle Refurbish- LEC Installation - Doyle Project (75% of $600,000)
Power System | 611029 | Doyle Refurbish- 10% of second LEC order as quoted on February 8th, 1999
Power System | 139019.7 | Doyle Refurbish- Evap coolers- Pass through payment to Caldwell Energy Milestone1
Benchmark Transportion Services | 3446 | Transport turbine from IUKA to Sanford
Benchmark Transportion Services | 2561.2 | Transport parts to Tampa Armature
Benchmark Transportion Services | 1832 | Tarped Flated load from Power Systems to Tampa Armature
Benchmark Transportion Services | 7160 | 2 Trucks EX Turbine Technology to Nepco Carrying 1 exciter Cabinet and 1 control module
Benchmark Transportion Services | 7160 | 3 Trucks EX Turbine Technology to Nepco Carrying 1 exciter Cabinet and 1 control module
Turbine Technology Service | 272718.9 | Doyle Refurbish- TTS Contract December Payment
Turbine Technology Service | 303021 | Doyle Refurbish- TTS Contract November payment
National Energy Production Corp | 328718 | Doyle Construction - October and November fixed overhead charges
National Energy Production Corp | 2173279 | Doyle Construction - Cost Reimbursement for November
Enron Engineering & Construction | 73114.29 | EECC Fixed Overhead for Turbine Refurbishment
Enron Engineering & Construction | 192000 | EECC Construction Overhead
Enron Engineering & Construction | 22838.53 | EECC Development Cost
Enron Engineering & Construction | 40222.14 | EECC Doyle Substation Cost-- Engineering support in August through October
Enron International Asset Management | 22069.5 | Doyle Development Expense
ABB Power T&D Company | 166666.67 | Doyle - OPC substation
Kilpatrick Stockton | 4050.27 | Doyle - Legal
King & Spalding | 5515.93 | Doyle- Legal
Coffer Walter | 580.92 | Travel
ABB Power T&D Company INC | 166666.67 | 115KV Step-up Transformer
Power System SPC | 1370.36 | Refurbishment Transportion
Power System SPC | 558 | Refurbishment Transportion
Power System SPC | 90000 | Project Management Fee - December 1999
Power System SPC | 175000 | Project Management Time and Expense - November 1999
Power System SPC | 159160.5 | Pass Through to H&M Milestone Payment #4
Power System SPC | 152369.1 | Pass Through Payment to Tampa Armature Works- Scope 1, Milestone Payment #2 & #3.
Benchmark | 1627.5 | Refurbishment Transportion
Benchmark | 1250 | Refurbishment Transportion
Benchmark | 2280 | Refurbishment Transportion
Benchmark | 1624.25 | Refurbishment Transportion
Benchmark | 3446 | Refurbishment Transportion
Benchmark | 269.39 | Refurbishment Transportion
Riviera Finance | 925 | Refurbishment Transportion
Air Liquide America Corporation | 532622 | Payment for December 1, 1999 under Agreement for Two Electirc 7EA Model Turb.
Enron Engineering | 49353.76 | Refurbishment Engineering- EECC Refurbishment Oversight
Environmental Consulting & Technology | 1506.69 | Permitting Fee
Clay Spears | 200.12 | Meals
Clay Spears | 2231.25 | Trvl/Houston-Doyle Project
Kilpatrick Stockton LLP | 9498.73
King & Spalding | 59517.4 | Legal Expenses
Zisman Stuwart & Tweed Sheila | 1852.25 | Travel Expenses
ENA | 360766 | December Interest during Construcion
7427682.48
01/31/00
H&M Industrial Services, Inc | 32319.35 | Facility Work
H&M Industrial Services, Inc | 47656.79 | Inventory Control Personnel Total Cost of Work to Date
H&M Industrial Services, Inc | 45840.46 | Inventory Control Personnel Total Cost of Work to Date
National Energy Production Corp | 5151338 | Nepco Nov and Dec Expense
National Energy Production Corp | 157687 | Nepco Fixed Lump Sum portion of work
Power System MFG | 158159 | Doyle Refurbishment - HGP Parts Refurbish
Power System MFG | 3190 | Doyle Refurbishment - Bleed Value Engineering
Power System SPC | 109470.47 | IUKA Facility
Power System SPC | 226375.68 | TTS Technical Direction
Power System SPC | 107307.5 | IUKA Facility
Power System SPC | 45988.93 | Equipment Inventory
Power System SPC | 59973.51 | IUKA Inventory Labor
Power System SPC | 316800 | Boyle Generator Rewind
Power System SPC | 13506.95 | Doyle Refurbishment - Transportaion
Power System SPC | 165580.24 | H&M Turbine Refurbishment
Power System SPC | 29582.71 | Turbine Refurbishment
Power System SPC | 33612 | Doyle Refurbishment- TAW Accessory Refurbishment
Power System SPC | 28581 | Doyle Refurbishment- TAW Accessory Refurbishment
Power System SPC | 89336.27 | Doyle Refurbishment- TAW Accessory Refurbishment
Power System SPC | 29084.32 | Doyle Refurbishment- Wood Group make-up payment
Power System SPC | 125000 | Doyle Refurbishment- Project Management
Power System SPC | 139743.6 | Doyle Refurbishment- TAW Generator Refurbishment
Turbine Technology | 272718.9 | Refurbishment--TTS Contract
Power Spares | 15000 | IUKA Equipment Inventory--Consignment Fee
Power Spares | 10231.82 | IUKA Equipment Inventory--Consignment Fee
GE | 1632000 | Two 7 EA Gas Turbine Generators Process Payment #9 of 10
Benchmark Transportation Service | 30050 | Doyle Refurbishment - Transportaion
Benchmark Transportation Service | 300 | Doyle Refurbishment - Transportaion
Benchmark Transportation Service | 300 | Doyle Refurbishment - Transportaion
Environmental Consulting & Technology | 26.24 | Permitting
Brimhall Delivery Service | 1069.5 | Refurbishment--Transportation
Brimhall Delivery Service | 2712 | Refurbishment--Transportation
Kilpatrick Stockton LLP | 156476.52 | Land Purchase
GLC Consulting | 20421.09 | Construction Management Fee
Enron North America | -199260.36 | IDC True-up
King & Spalding | 2036.4 | Legal Expeneses
Kilpatrick Stockton | 3255.75 | Legal Expeneses
Monroe Water & Light | 160750 | Sewer line Construction
Clay Spears | 1960.12 | Travel Expenses
Clay Spears | 588.63 | Travel Expenses
Walton EMC Monroe | -9000000 | Reimbursement from Oglethorpe
Walton EMC Monroe | -14500000 | Reimbursement from Oglethorpe
ENA | 305886.21 | IDC
-13967343.4
2/29/2000
G.L.C Consulting | 22912.59 | Refurbishment Contract Management
EECC | 26674.37 | Doyle Refurbish Oversight
EECC | 104388.35 | EECC Refurbishment Cost Reimbursement
EECC | 64000 | Doyle Construction Fixed Overhead Dec
EECC | 24371.43 | Doyle Refurbishment fixed Overhead DEC
EECC | 136622.33 | Pre- NTP engineering Support
EECC | 64000 | Doyle Construction Fixed Overhead Jan
EECC | 24371.43 | Doyle Refurbishment fixed Overhead Jan
EECC | 8383.51 | Engineering Support - Substation Cost- Jan
EECC | 12449.27 | Engineering Support - Substation Cost-Dec
ABB Power T&D Company INC | 172232.1 | Doyle 230kV Breakers
ABB Power T&D Company INC | 53400 | Spare Parts
ABB Power T&D Company INC | 156450 | ABB Rewind Transport from Pensacola to St. Louis
ABB Power T&D Company INC | 76106.1 | 230KV transformer
ABB Power T&D Company INC | 228318.3 | 230KV transformer
ABB Power T&D Company INC | 456636.6 | 230KV transformer
ABB Power T&D Company INC | 456636.6 | 230KV transformer
ABB Power T&D Company INC | 152212.2 | 230KV transformer
ABB Power T&D Company INC | 36000 | Labor for installment
Power System Mfg, LLC | 64112 | O&M Mobilization expense by OEC
Power System Spc | 105000 | Doyle Refurbish : PSSPC scheduel Bonus
Power System Spc | 27013.53 | Doyle Refurbish : PSSPC Work
Power System Spc | 139615.51 | H&M Enclosure Work
Power System Spc | 5374.81 | Doyle Refurbish: Freight Expense
Power System Spc | 76991.62 | Doyle Refurbish: H&M Turbine Refurb
Power System Spc | 323039.5 | Doyle Refurbish: PSSPC Parts
Power System Spc | 21839.9 | Doyle Refurbish: IUKA Facility Expenses
Power System Spc | 50000 | Doyle Refurbish: PSSPC Contract
Power System Spc | 45737.22 | Doyle Refurbish: Parts
Mike Nelson | 2500 | IUKA facility Preparation
Jacoby, Ben F | 421.55 | Travel
Jacoby, Ben F | 3436.57 | Travel
John L. Wortham | 407787 | Doyle Construction Invoices
H & M Industrial Service | 20139.65 | Doyle - Refurb Inlets
H & M Industrial Service | 3526.51 | Doyle Refurb - Transportation
H & M Industrial Service | 6000 | IUKA Facility-Spare Parts Inventory
H & M Industrial Service | 22018.36 | IUKA Facility
H & M Industrial Service | 32599.83 | IUKA Facility
H & M Industrial Service | 7781.75 | Doyle: Refurbish - Inlet
H & M Industrial Service | 27313.69 | Doyle Inlet Duct
H & M Industrial Service | 26390.01 | Doyle : Dow Inlet Duct
H & M Industrial Service | 2663.19 | Doyle exhaust stacks
Benchmark Transportation | 900 | Doyle Refurb - Transportation
Benchmark Transportation | 750 | Doyle Refurb - Transportation
Benchmark Transportation | 324436 | Doyle Refurb - Transportation
Benchmark Transportation | 1415 | Doyle Refurb - Transportation
Tishomingo Railroad | 1600 | transportation
Environmental Consulting Technology | 2248.74 | Doyle Permitting
GE | 1632000 | Turbine Payment
Jacoby, Ben | 3454.11 | Travel
Jacoby, Ben | 169.3 | Travel
Spears, Clay | 886.67 | Travel
Spears, Clay | 25.32 | Travel
Benchmark Transportation | 750 | Doyle Refurb - Transportation
Benchmark Transportation | 750 | Doyle Refurb - Transportation
Benchmark Transportation | 3685 | Doyle Refurb - Transportation
Turbine Technology | 3680 | Replacement of the battery compartment to the Dow Sarnia Control Cabinet
Neel-Schaffer INC | 2462.22 | Doyle Development Cost-- Walton County Power Plant Permitting and Survey
Bryan Garrett | 149.62 | Travel
Bryan Garrett | 858.45 | Travel
Walton EMC | -9577967.64 | Reimbursement from Walton
Power System SPC | -780 | Doyle Refurbish- Refund for Overpaid
Walton EMC | -58847040.04 | Reimbursement from Walton
Journal Entry | 5000000 | Reclass OPC Deposit to Doyle LLC's book (39W)
Journal Entry | -170181 | Move LEC Burners' extra parts to Power Spares Inventory
-57918280.87
3/31/2000
G.L.C. Consulting SE | 41788.38 | Doyle Development Cost
Benchmarks Transportation | 750 | Pickup at IUKA of 27 pieces and deliver to Nepco
Benchmarks Transportation | 3685 | Pickup at turbine tech and and deliver to Nepco Monroe- 2 control Cabinets and oversized freight
Benchmarks Transportation | 2700 | Pickup at Power Systems. IUKA, and deliver to Nepco- Tunnel Exhaust, Dampers, Vent Stacks
Power System SPC | 29554.93 | Doyle Refurbishment - PSSPC
Power System SPC | 227108.35 | Doyle Refurbishment - PSSPC
Power System SPC | 139019.7 | Doyle Refurbishment - Pass through Payment to Caldwell Energy Milestone Payment 2
Power System SPC | 182928.4 | Doyle Refurbishment -PSSPC Parts
Power System SPC | 100000 | Doyle Refurbishment - PSSPC Management Expenses -December
Power System SPC | 90000 | Doyle Refurbishment - PSSPC Management Expenses - Final Bill
Power System SPC | 925 | Iuka Freight - Kreider Transport
Power System Mfg, LLC | 2603 | Doyle Refurbishment - PSSPC
H & M Industrial Services, INC | 8529.09 | Doyle Refurbishment - H&M Inlets-Transporting Rain Hoods for YW-90 and YW-91 from Jackson
Walton EMC | -4391241.41 | Reimbursement from Walton
Walton EMC | -135811.59 | Reimbursement from Walton
Spears, Clay | 1078.7 | Travel
John L. Wortham & Son | 70000 | Insurance for IUKA Turbine Transport
Power System SPC | 81517.1 | Doyle Refurbishment - Pass Through Payment to Tampa Armature Work Scope -2
Power System MFG | 98995.6 | Doyle Refurbishment- PSSPC Parts- Remanufacture 2 sets of Buss Duct
Neel-Schaffer INC | 931.7 | Doyle Permitting Fee
King & Spalding | 15743.99 | Doyle Legal Expenses
Power System MFG, LLC | 135000 | Doyle Refurbishment - LEC Installation
John L. Wortham & Son LLP | 19206.15 | Insurance for Doyle Refurbishment - Turbine
GE | 3400000 | Turbine Payment
Power System SPC, INC | 25000 | Doyle Refurbishment - PSSPC Parts
Power System SPC, INC | 16218 | Doyle Refurbishment - H&M Technical Direction
Power System SPC, INC | 35488.88 | Doyle Refurbishment - PSSPC Rotors
Power System SPC, INC | 15561.65 | Doyle Refurbishment - HGP Parts
Power System SPC, INC | 208451.79 | Doyle Refurbishment - H&M Exhaust / Inlet
Turbine Technology | 545437.8 | #6 Payment for TTS Refurbishment Contract
Joacoby Ben F | 1919.12 | Travle
Joacoby Ben F | 465.81 | Travle
Joacoby Ben F | 221.24 | Travle
Power System SPC. INC | 95528.39 | Doyle Line #7 Expenses and Power Support
Power System Mfg. LLC | 42682.61 | Doyle Refurbishment - Flow through purchase orders to Enron from Monrose Site
- PSSPC turbine Refurbishment
Power System Mfg. LLC | 3337.77 | Doyle Refurbishment - Flow through purchase orders to Enron from Monrose Site
- PSSPC turbine Refurbishment
Power System Mfg. LLC | 22927 | Doyle Refurbishment - Flow through purchase orders to Enron from Monrose Site
Doyle Start - up expenses
Cumpton & Associates, LLP | 525 | Doyle - Development Expenses
Environmental Consulting & Technology | 119 | Doyle Permitting Fee
EECC | 88371.43 | EECC Construction Oversight -1/14 of the total Fixed Overhead
EECC | -25877.58 | EECC Refurbishment Oversight - Engineering Support for the refurbishment
EECC | 10677.58 | OPC Switchyard
GE | 3400000 | Turbine Payment
Bracewell & Patter | 18563.75 | OPC Reimbursable expenses - FERC filing
Bracewell & Patter | 5425 | OPC Reimbursable expenses - FERC filing
Journal Entry | -155521.1 | March IDC
Journal Entry | -6078260 | Cash Received from Walton
Journal Entry | -53400 | Cash Received from parts sold back to ABB
Journal Entry | -140807.71 | Reclass parts from power spares to 34k inventory
-1791932.48
04/30/2000.
Power System SPC | 30855.72 | Turbine Refurb -- Inlet System pass through to Caldwell Energy
Power System MFG | 3204 | Turbine refurb-- manual panic switches added to fire extinguishing system - 3 units
Power System MFG | 1389 | Turbine Refurb -- Repair Accessory CAB door damaged on shipment - Dow
Power System MFG | 8874.49 | Turbine Refurb -- cooling fans on generator blowers
Power System MFG | 8517.35 | Turbine Refurb -- CB 20 vavles for compressor air
Power System MFG | 15064 | Turbine Refurb -- PSSPC management expense
EECC | 88371.43 | Construction Management- March
EECC | 88371.43 | Construction management - April
EECC | -13990.39 | Refurb Management
EECC | 6880.61 | Switchyard Engineering Support
NEPCO | 157687 | Fix Lump Sum Portion
NEPCO | 3769589 | Reimbursable protion of the work
ABB | 18000 | Field Installation on Transformer
ABB | 3829.4 | 115kv Breaker --Substation
ABB | 11488.2 | 115 KV Breaker -- Substation
ABB | 22976.4 | 115 KV Breaker -- Substation
ABB | 22976.4 | 115 KV Breaker -- Substation
ABB | 7658.8 | 115 KV Breaker -- Substation
ABB | 28705.33 | 230 KV Breaker -- Switchyard
ABB | 28705.28 | 230 KV Breaker -- Switchyard
ABB | 172231.95 | 230 KV Breaker -- Switchyard
ABB | 57410.65 | 230 KV Breaker -- Switchyard
ABB | 112540 | 230 KV Breaker -- Switchyard
ABB | 152212.2 | 230 KV Breaker -- Switchyard
ABB | 7658.8 | 115 KV Breaker -- Switchyard
ABB | 57410.49 | 230 KV Breaker -- Switchyard
GE | 680000 | Two (2) 7EA Gas Turbine Generators
GE | 680000 | Two (2) 7EA Gas Turbine Generators
Kilpatrick Stockton | 10253.1 | Legal
Kilpatrick Stockton | 880.28 | Legal
Kilpatrick Stockton | 1508.22 | Legal
GLC Consulting Services | 55874.52 | Oversight of construction & refurb
Kilpatrick Stockton LLP | 16000 | Land Option Extention Expense
Robert Virgo | 70 | Meals
Oglethorpe Corp | -5479320 | Reimbursement for the Transformer and Substation
Walton | -5723578 | Reimbursement for the project
Walton | -421012.05 | Reimbursement for the mobilization of O&M Expense for March and April
Walton | -59123 | Reimbursement for Sewerline Construction Cost
Ben Jacoby | -3858.12 | reclass wrong coding
Ben Jacoby | -2606.17 | reclass wrong coding
-5376293.68
05/31/2000.
Power Systems Spc | 67119.2 | Refurb - H & M Generator Work
Power Systems Spc | 248327 | Refurb- TAW
Power Systems Spc | 521129.48 | Refurb - H & M Exhaust Milestone
GLC consulting | 41048.95 | Oversight of construction & Refurb
EECC | 50693.68 | EECC Refurbish Oversight
EECC | 4851.98 | OPC Switchyard Engineering
Walton Tribune | 20 | Doyle Permitting
ABB power T&D co | 72000 | OPC Transformer Assemble
Robert Virgo | 199.9 | Travel
Robert Virgo | 1730.09 | Travel
EECC | 88371.43 | EECC Fixed Overhead
EECC | 9859.71 | EECC Refurbishment Project Management
EECC | 5789.49 | EECC Switchyard / Transformer work
NEPCO | 1724478 | Nepco Reimbursable expense
NEPCO | 157687 | Nepco Fixed Overhead Expense
Power System Mfg | 9587.59 | PSSPC TD of I for Refurb work
Power System Mfg | 269792 | PSSPC on Site additional Work
Power System SPC | 5136 | Doyle PSSPC Refurb Work
H&M Industrial Services. INC | 112179.6 | H&M Exhaust System Transportation
Bracewell & Patterson | 4231.25 | FERC Application / Approval Expense
Journal Entry | -15000 | Reclass IUKA warehouse cost to Inventory
Air Lique America | 400000 | Air Liquide Equity Purchase Payment
Kilpatrick Stockton | -31.37
Journal Entry | -59780.1 | IDC
Journal Entry | 97886 | IDC
Oglethrope Power Company | -23988.75 | Reimbursement for legal cost - Bracewell Patterson
3793318.13
06/30/2000
Power Systems MFG | 30074 | PSSPC on site work
Power Systems MFG | 1545.19 | O & M Spare Parts
Power Systems MFG | 1180.37 | Refurb unit 3 repair
Power Systems MFG | 1701.62 | ENA Contract Management
Elliott On-Site Service | 11048.44 | Refurb unit 3 repair
NEPCO | 157687 | May Lump Sum Portion
NEPCO | 157687 | Jun Lump Sum Portion
NEPCO | 157687 | March Lump Sum Portion
NEPCO | 353456 | Jun Payment
NEPCO | 3346882 | March Payment
EECC | 21614.99
EECC | 88371.43 | EECC Construction Management
EECC | 4265.95
ABB | 166666.67 | ABB Transformer
GLC | 51910.59 | Refurb Management
Secretary of State | 481019.03 | Sale Tax on Transformer
In Place Machining | 11661.52 | Refurb unit 3 repair
RTA Engineering | 17540.19 | Refurb unit 3 bearing work
King & Spalding | 6519.85 | Legal
King & Spalding | 132.5 | Legal
King & Spalding | 600 | Legal
Bracewell & Patterson | 947.5 | Legal
Walton EMC | -2403255 | Walton EMC
IDC to ENA | -45626.92 | IDC for June
GLC | 31243.02 | Refurb Management
EECC | 25877.58 | Short Payment for fix overhead
Allan Wu | 655.21 | Travel
Journal Entry | 2950 | Development Expenses
Kilpatrick & Stockton | 13001.75 | Legal
2695044.48
07/31/2000
Power Systems SPC | 690000 | Doyle Extras provided by Tampa Armature Works as agreed to in the settlement agreement
dated June 20, 2000
Power Systems SPC | 440065 | H & M Exhaust system
Power Systems SPC | 134402.02 | H & M Turbine compartment work
Power Systems SPC | 57637.64 | Refurbish Waterwash system
Power Systems MFG | 28510.18 | Refurbish Turbine Construction
Power Systems MFG | 7645.99 | Refurbish Turbine Parts
Power Systems MFG | 9355 | Refurb TD of I : PSSPC
Power Systems MFG | 5489.31 | ENA Construction Oversight
Power Systems MFG | 92518.79 | Unit 1 Repairs
Power Systems MFG | 7958 | Refurbishment Turbine Work
Power Systems MFG | 19096.68 | ENA Project Oversight
Power Systems MFG | 144960.28 | Unit 1 Repairs
Power Spares | 625000 | Unit 1 repair parts
Turbine Technology | 3855.35 | Remaining Payment for Milestone 7
Turbine Technology | 129088.79 | Doyle: TTS : TD of I
Theresa Vos | 21 | Travel
Robert Virgo | 794 | Travel
Robert Virgo | 73.25 | Travel
Theresa Vos | 784.41 | Travel
Bracewell & Patterson | 530 | Legal
GE | 429388 | Unit 1 Repairs
GE | 912762.73 | Unit 1 Repairs
3739936.42

## WO_Recon
Doyle Plant
Work Order Reconciliation to Cost Summary
|  |  |  | 1998 | January, 1999 | Feburary, 1999 | March, 1999 | April, 1999 | May, 1999 | June, 1999 | July, 1999 | August, 1999 | September, 1999 | October, 1999 | November,1999 | December, 1999 | January, 2000 | Feburary, 2000 | March, 2000 | April, 2000 | May, 2000 | June, 2000 | July, 2000 | August, 2000 | 2000-09-01 | 2000-10-01 | 2000-11-01 | 2000-12-01
|  |  | Project to Date | Year to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date | Month to Date
Work Order # |  | E1231F | 242537.65 | 0 | 50885.83 | 89235.65 | 24496.32 | 23145.27 | 50885.83 | 2011.79 | 1794.59 | 33136.99 | 5000 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296592.27
Work Order # |  | S70015 | 0 | 0 | 11083 | 0 | 0 | 5284.62 | 11083 | 9113.87 | 5936.81 | 793.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -43294 | 43294.37
Work Order # |  | S80015 | -5393556.26 | 78236.31 | 1200000 | 27666109 | 1836952.77 | 3002544.18 | 4504541.42 | -2110412.18 | 1881235.19 | 3075472.98 | 3569698.46 | 7824421 | 7183239 | 11215325 | -17754986 | -53991005 | -5719208 | -5344083 | 3793318.13 | 2695044.48 | 0 | 0 | 0 | 0 | 0 | 0 | -5393556.26
|  | C.008015 | 8227169.15 | [19 empty] | 3848215 | 2599222 | 1779732.15 | 923102 | 1254974 | -31282 | 10373963.15
| Total Work Order |  | 3076150.54 | 78236.31 | 1261968.83 | 27755344.65 | 1861449.09 | 3030974.07 | 4566510.25 | -2099286.52 | 1888966.59 | 3109403.04 | 3574698.46 | 7840421 | 7183239 | 11215325 | -17754986 | -53991005 | -5719208 | -5344083 | 3793318.13 | 2695044.48 | 3848215 | 2599222 | 1779732.15 | 923102 | 1254974 | -74576 | 5276999.53
Items on Cost Summary not on
Work Order
| Legal fees expensed on E07A59 |  | 83900.89 | 43465.95 | 0 | 0 | 0 | 0 | 43465.95 | 0 | 0 | 0 | 0 | [15 empty] | 86931.9
| Loss Expensed | [23 empty] | 4500000 |  |  |  | 4500000
| Duplicate Payments not reversed |  | 0 | [20 empty] | -315534 | 315534 | 0 | 0 | 0 | 0
| Sewer Line |  | 0 | [8 empty] | 230971 | -230970 |  |  |  |  | 0 | 0 | 60920.3402 | -59780 |  | 0 |  |  |  |  | -1141 | 0.34024
| Accrued Inventory Transfer |  | -421012 | [7 empty] | 0 | [6 empty] | 0 | 0 | -0.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.05
| OPC Substation Cost in Doyle Budget | [27 empty] | 0
| Power Transformer/OPC | [27 empty] | 0
| Total per Cost Summary |  | 9864031.32 | 21428869.8 | 4411803.49 | 3230174.65 | 1856449.2 | 3025974.27 | 4604975.96 | -2099286.52 | 1888966.69 | 3340374.04 | 3343727.46 | 7253667.2 | 7769992.74 | 7427682.16 | -13967343.4 | -57918281.11 | -1791932.77 | -5436073.73 | 3868098.2 | 2695044.45 | 3788623.54 | 2283687 | 6595266 | 982694 | 1254974 | 25904 | 9864031.32
|  | Difference | -6282967.89 | -21307167.54 | -3149834.66 | 24525170 | 4999.89 | 4999.8 | 5000.24 | 4.6566e-10 | -0.1 | 0 | 1 | 586753.8 | -586753.74 | 3787642.84 | -3787642.6 | 3927276.11 | -3927275.23 | 31070.4398 | -15000.07 | 0.03 | 59591.46 | 1 | 0.15 | -59592 | 0 | -99339 | -98.1802
Note on F26: tvos: IDC Booked backwards in July - to be corrected in August.
Note on P26: awu3: Mobolization
Note on AH26: awu3: timing diff - sewerline
Note on AJ26: awu3: Mobolization Cost
Note on AN26: capital salaries
Note on AP26: awu3: Mobolization Reimbursement 59123 Sewer Line
Note on AT26: tvos: IDC booked backwards. To be corrected in Aug.

## Refurb Cost by Vendors
AJ Mechanical, INC. | 183010.45 | Zero out in July
AJ Mechanical, INC. | 135431.96 | Zero out in July
AJ Mechanical, INC. | 22604.87 | Zero out in July
AJ Mechanical, INC. | 26120.07 | Zero out in July
AJ Mechanical, INC. | 24767.55 | Zero out in July
AJ Mechanical, INC. | 28671.86 | Zero out in July
AJ Mechanical, INC. | 78641.11 | Zero Out in July
AJ Mechanical, INC. | 52404.53 | Refurbish Turbine at Warehouse #8, Pensacola
AJ Mechanical, INC. Total | 551652.4
Applied Engineering | 5179.43 | Refurbish
Applied Engineering Total | 5179.43
Banchmark Transpotation | 129539 | Moving Turbines
Banchmark Transpotation | 10985 | Moving Turbines
Banchmark Transpotation | 119361.69 | Moving Turbines
Banchmark Transpotation | 5289 | Moving Turbines
Banchmark Transpotation | 20808 | Moving Turbines
Banchmark Transpotation | 49370 | Moving Turbines
Banchmark Transpotation | 34500 | Moving Turbines
Banchmark Transpotation | 1627.5 | Refurbishment Transportion
Banchmark Transpotation | 1250 | Refurbishment Transportion
Banchmark Transpotation | 2280 | Refurbishment Transportion
Banchmark Transpotation | 1624.25 | Refurbishment Transportion
Banchmark Transpotation | 3446 | Refurbishment Transportion
Banchmark Transpotation | 269.39 | Refurbishment Transportion
Banchmark Transpotation | 278580 | move turbines to Mississippi
Banchmark Transpotation | 104297 | transport turbine
Banchmark Transpotation | 7168 | transport turbine
Banchmark Transpotation | 750 | Doyle Refurb - Transportation
Banchmark Transpotation | 750 | Doyle Refurb - Transportation
Banchmark Transpotation | 3685 | Doyle Refurb - Transportation
Banchmark Transpotation | 30050 | Doyle Refurbishment - Transportaion
Banchmark Transpotation | 300 | Doyle Refurbishment - Transportaion
Banchmark Transpotation | 300 | Doyle Refurbishment - Transportaion
Banchmark Transpotation | 900 | Doyle Refurb - Transportation
Banchmark Transpotation | 750 | Doyle Refurb - Transportation
Banchmark Transpotation | 324436 | Doyle Refurb - Transportation
Banchmark Transpotation | 1415 | Doyle Refurb - Transportation
Banchmark Transpotation | 3446 | Transport turbine from IUKA to Sanford
Banchmark Transpotation | 2561.2 | Transport parts to Tampa Armature
Banchmark Transpotation | 1832 | Tarped Flated load from Power Systems to Tampa Armature
Banchmark Transpotation | 7160 | 2 Trucks EX Turbine Technology to Nepco Carrying 1 exciter Cabinet and 1 control module
Banchmark Transpotation | 7160 | 3 Trucks EX Turbine Technology to Nepco Carrying 1 exciter Cabinet and 1 control module
Banchmark Transpotation | 750 | Pickup at IUKA of 27 pieces and deliver to Nepco
Banchmark Transpotation | 3685 | Pickup at turbine tech and and deliver to Nepco Monroe- 2 control Cabinets and oversized freight
Banchmark Transpotation | 2700 | Pickup at Power Systems. IUKA, and deliver to Nepco- Tunnel Exhaust, Dampers, Vent Stacks
Banchmark Transpotation Total | 1163025.03
Brimhall Delivery Service | 1069.5 | Refurbishment--Transportation
Brimhall Delivery Service | 2712 | Refurbishment--Transportation
Brimhall Delivery Service Total | 3781.5
Elliott On-Site Service | 11048.44 | Refurb unit 3 repair
Elliott On-Site Service Total | 11048.44
H & M Industrial Service | 20139.65 | Doyle - Refurb Inlets
H & M Industrial Service | 3526.51 | Doyle Refurb - Transportation
H & M Industrial Service | 6000 | IUKA Facility-Spare Parts Inventory
H & M Industrial Service | 22018.36 | IUKA Facility
H & M Industrial Service | 32599.83 | IUKA Facility
H & M Industrial Service | 7781.75 | Doyle: Refurbish - Inlet
H & M Industrial Service | 27313.69 | Doyle Inlet Duct
H & M Industrial Service | 26390.01 | Doyle : Dow Inlet Duct
H & M Industrial Service | 2663.19 | Doyle exhaust stacks
H & M Industrial Service | 45905 | transport turbine
H & M Industrial Service | 47620.5 | transport turbine
H & M Industrial Service | 54196.5 | Iuka building prep
H & M Industrial Service | 9000 | Install metal siding on turbine building
H & M Industrial Service | 63485.07 | Clean-up & Electrical of turbine building IUKA facility
H & M Industrial Service | 8529.09 | Doyle Refurbishment - H&M Inlets-Transporting Rain Hoods for YW-90 and YW-91 from Jackson
H & M Industrial Service | 33146.06 | Labor of Iuka building preparation
H & M Industrial Service | 8777.07 | Iuka material for installation
H & M Industrial Service | 5422.76 | Iuka material for installation
H & M Industrial Service | 2644.2 | Iuka Travel Expense
H & M Industrial Service | 32319.35 | Facility Work
H & M Industrial Service | 47656.79 | Inventory Control Personnel Total Cost of Work to Date
H & M Industrial Service | 45840.46 | Inventory Control Personnel Total Cost of Work to Date
H & M Industrial Service | 112179.6 | H&M Exhaust System Transportation
H & M Industrial Service Total | 665155.44
Hoist & Crane Service GroupVI (HCSG) | 6980 | Start up of 250 Ton Crane/Repairs
Hoist & Crane Service GroupVI (HCSG) Total | 6980
IBC Turbo INC | 15834 | Pensacola lease
IBC Turbo INC | 15834 | Refurbish
IBC Turbo INC | 252344 | Compressor for Doyle
IBC Turbo INC | 4671.74 | Warehouse Security
IBC Turbo INC | 53311.19 | Warehouse Lease Rent
IBC Turbo INC | 327.02 | 7% IBC Turbo Miscellaneous Expenses Fee
IBC Turbo INC | 17664.08 | 7% IBC Turbo Fee for the Compressor work in May
IBC Turbo INC | 15834 | Refurbishment- Pensacola Lease
IBC Turbo INC | 97500 | Pensacola lease
IBC Turbo INC | 62060.03 | For Work done by AJ Mechanical
IBC Turbo INC | 6680.84 | Warehouse Security
IBC Turbo INC | 56199.97 | Reimburse IBC for warehouse activities
IBC Turbo INC | 3440.53 | Warehouse Security
IBC Turbo INC Total | 601701.4
In Place Machining | 11661.52 | Refurb unit 3 repair
In Place Machining Total | 11661.52
John L. Wortham & Son LLP | 19206.15 | Insurance for Doyle Refurbishment - Turbine
John L. Wortham & Son LLP Total | 19206.15
Journal Entry | 396000 | Turbine Air Intake Syetem Cost Reclassed from New Albany to Doyle
Journal Entry | -22604.87 | Zero out with June
Journal Entry | -26120.07 | Zero out with June
Journal Entry | -24767.55 | Zero out with June
Journal Entry | -28671.86 | Zero out with June
Journal Entry | -62060.03 | Zero out
Journal Entry | -183010.45 | Rcls Turbine
Journal Entry | -135431.96 | Rcls Turbine
Journal Entry | -78641.11 | Rcls Turbine
Journal Entry | 186919 | Reclass Benchmark Invoice from Project 2000 to Doyle
Journal Entry | 700000 | Transfer Power Spares Inventory to Doyle
Journal Entry | -140807.71 | Reclass parts from power spares to 34k inventory
Journal Entry Total | 580803.39
Mike Nelson | 2500 | IUKA facility Preparation
Mike Nelson | 11000 | IUKA Site Preparation
Mike Nelson | 3000 | IUKA Site Preparation
Mike Nelson | 17510.9 | Facility preparation
Mike Nelson | 22413.15 | Facility preparation
Mike Nelson Total | 56424.05
Mississippi Major Impact Authority | 12500 | Lease payment
Mississippi Major Impact Authority | 12500 | Lease Payment
Mississippi Major Impact Authority Total | 25000
Power Spares | 5000 | Consignment Fee
Power Spares | 203476.5 | 2nd, 3 rd stage Shroud Block
Power Spares | 10245.82 | Expense reimbursement billing for August 1999 pursuant to the
Power Spares | 15000 | IUKA Equipment Inventory --Consignment Fee
Power Spares | 10231.82 | IUKA Equipment Inventory --Consignment Fee
Power Spares | 5000 | Monthly consignment fee dated Feburary 17th, 1999
Power Spares | 7017.42 | Expense Reimbrusement billing for October 1999
Power Spares | 15000 | Monthly Consignment Fee Pursuant to consignment agreement dated Feb 17, 1999
Power Spares | 13833.93 | May reimbursement - warehouse costs
Power Spares | 9303.06 | June reimbursement - warehouse costs
Power Spares | 10000 | Monthly consignment fee
Power Spares | 510000 | LEC transition piece
Power Spares | 5000 | Consignment fee
Power Spares | 11145.5 | GE Rotor-Test/Inspect
Power Spares | 9030.98 | Expense reimbursement billing for Sep 1999 pursuant to the
Power Spares | 10000 | Parts
Power Spares | 5000 | Consign Fee - Sell Spare Parts
Power Spares Total | 854285.03
Power System | 60398.33 | Dow unit Refurbishment
Power System | 34252.67 | VW turbine Refurbishment
Power System | 96762 | Inlets & Exhausts
Power System | 356900 | Turbine-TAW Generator Refurbishment
Power System | 59980.39 | Doyle Refurbish- Repair Bearing s on YW 90 and YW 91
Power System | 450000 | Doyle Refurbish- LEC Installation - Doyle Project (75% of $600,000)
Power System | 139019.7 | Doyle Refurbish- Evap coolers- Pass through payment to Caldwell Energy Milestone1
Power System | 158159 | Doyle Refurbishment - HGP Parts Refurbish
Power System | 3190 | Doyle Refurbishment - Bleed Value Engineering
Power System | 98995.6 | Doyle Refurbishment- PSSPC Parts- Remanufacture 2 sets of Buss Duct
Power System | 3204 | Turbine refurb-- manual panic switches added to fire extinguishing system - 3 units
Power System | 1389 | Turbine Refurb -- Repair Accessory CAB door damaged on shipment - Dow
Power System | 8874.49 | Turbine Refurb -- cooling fans on generator blowers
Power System | 8517.35 | Turbine Refurb -- CB 20 vavles for compressor air
Power System | 15064 | Turbine Refurb -- PSSPC management expense
Power System
Power System
Power System
Power System | 9587.59 | PSSPC TD of I for Refurb work
Power System | 269792 | PSSPC on Site additional Work
Power System | 64112 | Doyle Refurbish
Power System | 2603 | Doyle Refurbishment - PSSPC
Power System | 135000 | Doyle Refurbishment - LEC Installation
Power System | 42682.61 | Doyle Refurbishment - Flow through purchase orders to Enron from Monrose Site
Power System | 3337.77 | Doyle Refurbishment - Flow through purchase orders to Enron from Monrose Site
Power System | 22927 | Doyle Refurbishment - Flow through purchase orders to Enron from Monrose Site
Power System | 109470.47 | IUKA Facility
Power System | 226375.68 | TTS Technical Direction
Power System | 107307.5 | IUKA Facility
Power System | 45988.93 | Equipment Inventory
Power System | 59973.51 | IUKA Inventory Labor
Power System | 316800 | Boyle Generator Rewind
Power System | 13506.95 | Doyle Refurbishment - Transportaion
Power System | 165580.24 | H&M Turbine Refurbishment
Power System | 29582.71 | Turbine Refurbishment
Power System | 33612 | Doyle Refurbishment- TAW Accessory Refurbishment
Power System | 28581 | Doyle Refurbishment- TAW Accessory Refurbishment
Power System | 89336.27 | Doyle Refurbishment- TAW Accessory Refurbishment
Power System | 29084.32 | Doyle Refurbishment- Wood Group make-up payment
Power System | 125000 | Doyle Refurbishment- Project Management
Power System | 139743.6 | Doyle Refurbishment- TAW Generator Refurbishment
Power System | 105000 | Doyle Refurbish : PSSPC scheduel Bonus
Power System | 27013.53 | Doyle Refurbish : PSSPC Work
Power System | 139615.51 | H&M Enclosure Work
Power System | 5374.81 | Doyle Refurbish: Freight Expense
Power System | 76991.62 | Doyle Refurbish: H&M Turbine Refurb
Power System | 323039.5 | Doyle Refurbish: PSSPC Parts
Power System | 21839.9 | Doyle Refurbish: IUKA Facility Expenses
Power System | 50000 | Doyle Refurbish: PSSPC Contract
Power System | 45737.22 | Doyle Refurbish: Parts
Power System | -780 | Doyle Refurbish: Refund for overpaid
Power System | 29554.93 | Doyle Refurbishment - PSSPC
Power System | 227108.35 | Doyle Refurbishment - PSSPC
Power System | 139019.7 | Doyle Refurbishment - Pass through Payment to Caldwell Energy Milestone Payment 2
Power System | 182928.4 | Doyle Refurbishment -PSSPC Parts
Power System | 925 | Iuka Freight - Kreider Transport
Power System | 81517.1 | Doyle Refurbishment - Pass Through Payment to Tampa Armature Work Scope -2
Power System | 100000 | Doyle Refurbishment - PSSPC Management Expenses -December
Power System | 90000 | Doyle Refurbishment - PSSPC Management Expenses - Final Bill
Power System | 30855.72 | Turbine Refurb -- Inlet System pass through to Caldwell Energy
Power System | 5136 | Doyle PSSPC Refurb Work
Power System | 1370.36 | Refurbishment Transportion
Power System | 558 | Refurbishment Transportion
Power System | 90000 | Project Management Fee - December 1999
Power System | 175000 | Project Management Time and Expense - November 1999
Power System | 159160.5 | Pass Through to H&M Milestone Payment #4
Power System | 152369.1 | Pass Through Payment to Tampa Armature Works- Scope 1, Milestone Payment #2 & #3.
Power System | 25000 | Doyle Refurbishment - PSSPC Parts
Power System | 16218 | Doyle Refurbishment - H&M Technical Direction
Power System | 35488.88 | Doyle Refurbishment - PSSPC Rotors
Power System | 15561.65 | Doyle Refurbishment - HGP Parts
Power System | 208451.79 | Doyle Refurbishment - H&M Exhaust / Inlet
Power System | 95528.39 | Doyle Line #7 Expenses and Power Support
Power System | 20000 | Milestone payment - Wood Group
Power System | 100000 | August project management fee
Power System | 80000 | Milestone payment 2
Power System | 150000 | Initial project payment
Power System | 80000 | Project management - September
Power System | 463226.2 | 1st,2nd,3rd stage buckets, nozzle
Power System | 63659.61 | Refurb
Power System | 63668.61 | Turbine refurb
Power System | 630000 | Nozzle
Power System | 100000 | Project Management fee for Turbine Refurbishment
Power System | 125000 | Project Management time and expense for Turbine Refurbishment
Power System | 39007.08 | Reimburse Pensacola Payroll and Facility Charges
Power System | 755700 | Pass-Through Payment Wood Group Item #2
Power System | 9000 | Transportation
Power System | 440065 | H & M Exhaust system
Power System | 134402.02 | H & M Turbine compartment work
Power System | 57637.64 | Refurbish Waterwash system
Power System | 30074 | PSSPC on site work
Power System | 1180.37 | Refurb unit 3 repair
Power System | 1701.62 | ENA Contract Management
Power System | 28510.18 | Refurbish Turbine Construction
Power System | 7645.99 | Refurbish Turbine Parts
Power System | 9355 | Refurb TD of I : PSSPC
Power System | 5489.31 | ENA Construction Oversight
Power System | 7958 | Refurbishment Turbine Work
Power System | 19096.68 | ENA Project Oversight
Power System | 150000 | Project Management Time and Expenses- November 1999
Power System | 82875 | Pass-through payment to H&M- For total Intel work without installation
Power System | 100000 | Project Management fee- November 1999
Power System | 159160.5 | Pass-through payment to H&M- Milestone Payment #1
Power System | 2742.2 | Reimbursement of additional Pensacola facility charges
Power System | 67119.2
Power System | 248327
Power System | 521129.48
Power System | 690000 | Doyle Extras provided by Tampa Armature Works as agreed to in the settlement agreement
Power System | 127328.22 | Pass through payment to H&M milestone payment #2
Power System | 683258.64 | Pass through payment to H&M milestone payment #2
Power System | 82044.9 | Refurbishment
Power System Total | 12556638.09
Riviera Finance | 925 | Refurbishment Transportion
Riviera Finance Total | 925
RTA Engineering | 17540.19 | Refurb unit 3 bearing work
RTA Engineering Total | 17540.19
The Salvage Association | 22526 | INS Moving Refurbishment
The Salvage Association Total | 22526
Tishomingo Railroad | 1600 | transportation
Tishomingo Railroad Total | 1600
Turbine Technology Service | 545437.8 | Refurb
Turbine Technology Service | 272718.9 | Rewire
Turbine Technology Service | 136359.45 | Rewire
Turbine Technology Service | 272718.9 | Refurbishment--TTS Contract
Turbine Technology Service | 3680 | Replacement of the battery compartment to the Dow Sarnia Control Cabinet
Turbine Technology Service | 545437.8 | # 6 Payment for TTS Refurbishment contract
Turbine Technology Service | 3855.35 | Remaining Payment for Milestone 7
Turbine Technology Service | 129088.79 | Doyle: TTS : TD of I
Turbine Technology Service | 272718.9 | Doyle Refurbish- TTS Contract December Payment
Turbine Technology Service | 303021 | Doyle Refurbish- TTS Contract November payment
Turbine Technology Service Total | 2485036.89
Total Refurbishment Cost | 19640169.95
Grand Total | 42134018.74

## Refurb Cost by Month
Doyle, LLC
Turbine Refurbishment Invoice Detail by Month
Description
05/31/99
AJ Mechanical, INC. | 183010.45 | Zero out in July
AJ Mechanical, INC. | 135431.96 | Zero out in July
Journal Entry | 396000 | Turbine Air Intake Syetem Cost Reclassed from New Albany to Doyle
IBC Turbo INC | 252344 | Compressor for Doyle
966786.41
06/30/99
AJ Mechanical, INC. | 22604.87 | Zero out in July
AJ Mechanical, INC. | 26120.07 | Zero out in July
AJ Mechanical, INC. | 24767.55 | Zero out in July
AJ Mechanical, INC. | 28671.86 | Zero out in July
IBC Turbo INC | 4671.74 | Warehouse Security
IBC Turbo INC | 53311.19 | Warehouse Lease Rent
IBC Turbo INC | 327.02 | 7% IBC Turbo Miscellaneous Expenses Fee
IBC Turbo INC | 17664.08 | 7% IBC Turbo Fee for the Compressor work in May
AJ Mechanical, INC. | 78641.11 | Zero Out in July
256779.49
07/31/99
Journal Entry | -22604.87 | Zero out with June
Journal Entry | -26120.07 | Zero out with June
Journal Entry | -24767.55 | Zero out with June
Journal Entry | -28671.86 | Zero out with June
IBC Turbo. INC | 62060.03 | For Work done by AJ Mechanical
Journal Entry | -62060.03 | Zero out
Journal Entry | -183010.45 | Rcls Turbine
IBC Turbo. INC | 6680.84 | Warehouse Security
IBC Turbo. INC | 56199.97 | Reimburse IBC for warehouse activities
IBC Turbo. INC | 3440.53 | Warehouse Security
Journal Entry | -135431.96 | Rcls Turbine
Journal Entry | -78641.11 | Rcls Turbine
-432926.53
08/31/99
Power Spares, Inc. | 13833.93 | May reimbursement - warehouse costs
Power Spares, Inc. | 9303.06 | June reimbursement - warehouse costs
Power Spares, Inc. | 10000 | Monthly consignment fee
Power Systems | 20000 | Milestone payment - Wood Group
Power Systems | 100000 | August project management fee
Power Spares, Inc. | 510000 | LEC transition piece
Power Systems | 80000 | Milestone payment 2
Benchmark Transportation | 278580 | move turbines to Mississippi
IBC Turbo, Inc. | 97500 | Pensacola lease
1119216.99
09/30/99
Power Spares | 5000 | Consignment Fee
H & M Industrial Services | 45905 | transport turbine
H & M Industrial Services | 47620.5 | transport turbine
Power Systems | 150000 | Initial project payment
Power Systems | 80000 | Project management - September
Turbine Technology | 545437.8 | Refurb
Mississippi Major | 12500 | Lease payment
Mike Nelson, Contractor | 17510.9 | Facility preparation
Benchmark Transportation | 104297 | transport turbine
Benchmark Transportation | 7168 | transport turbine
Power Systems | 463226.2 | 1st,2nd,3rd stage buckets, nozzle
Mike Nelson, Contractor | 22413.15 | Facility preparation
Power Systems | 63659.61 | Refurb
1564738.16
10/31/99
IBC Turbo | 15834 | Pensacola lease
Power Systems | 63668.61 | Turbine refurb
Power Systems | 630000 | Nozzle
H & M Industrial Services | 54196.5 | Iuka building prep
Power Spares, Inc. | 5000 | Consignment fee
IBC Turbo | 15834 | Refurbish
Power Spares, Inc. | 11145.5 | GE Rotor-Test/Inspect
Mike Nelson Contractor | 11000 | IUKA Site Preparation
Mike Nelson Contractor | 3000 | IUKA Site Preparation
Power Systems | 100000 | Project Management fee for Turbine Refurbishment
Power Systems | 125000 | Project Management time and expense for Turbine Refurbishment
Power Systems | 39007.08 | Reimburse Pensacola Payroll and Facility Charges
Power Systems | 755700 | Pass-Through Payment Wood Group Item #2
Power Spares, Inc. | 9030.98 | Expense reimbursement billing for Sep 1999 pursuant to the
Consignment agreement dated Feburary 17, 1999
Turbine Technology | 272718.9 | Rewire
Turbine Technology | 136359.45 | Rewire
Power Systems | 9000 | Transportation
Power Spares | 203476.5 | 2nd, 3 rd stage Shroud Block
AJ Michanical Inc | 52404.53 | Refurbish Turbine at Warehouse #8, Pensacola
Applied Engineering | 5179.43 | Refurbish
The Salvage Association | 22526 | INS Moving Refurbishment
Power Spares | 10245.82 | Expense reimbursement billing for August 1999 pursuant to the
the consignment agreement dated Feburary 17, 1999
Banchmark Transpotation | 129539 | Moving Turbines
Banchmark Transpotation | 10985 | Moving Turbines
Banchmark Transpotation | 119361.69 | Moving Turbines
Banchmark Transpotation | 5289 | Moving Turbines
Banchmark Transpotation | 20808 | Moving Turbines
Banchmark Transpotation | 49370 | Moving Turbines
Banchmark Transpotation | 34500 | Moving Turbines
Power Spares, INC | 5000 | Monthly consignment fee dated Feburary 17th, 1999
Power Systems SPC I | 127328.22 | Pass through payment to H&M milestone payment #2
Hoist & Crane Service GroupVI (HCSG) | 6980 | Start up of 250 Ton Crane/Repairs
Power Systems SPC I | 683258.64 | Pass through payment to H&M milestone payment #2
3742746.85
11/30/99
H&M Industrial Service, INC | 33146.06 | Labor of Iuka building preparation
H&M Industrial Service, INC | 8777.07 | Iuka material for installation
H&M Industrial Service, INC | 5422.76 | Iuka material for installation
H&M Industrial Service, INC | 2644.2 | Iuka Travel Expense
Power Spares, Inc. | 10000 | Parts
Power Spares, Inc. | 5000 | Consign Fee - Sell Spare Parts
Powre System, LLC | 82044.9 | Refurbishment
IBC Turbo, Inc | 15834 | Refurbishment- Pensacola Lease
Power Systems SPC | 150000 | Project Management Time and Expenses- November 1999
Power Systems SPC | 82875 | Pass-through payment to H&M- For total Intel work without installation
Power Systems SPC | 100000 | Project Management fee- November 1999
Power Systems SPC | 159160.5 | Pass-through payment to H&M- Milestone Payment #1
Power Systems SPC | 2742.2 | Reimbursement of additional Pensacola facility charges
Power Spares, Inc | 7017.42 | Expense Reimbrusement billing for October 1999
Power Spares, Inc | 15000 | Monthly Consignment Fee Pursuant to consignment agreement dated Feb 17, 1999
H & M Industrial Services, Inc | 9000 | Install metal siding on turbine building
H & M Industrial Services, Inc | 63485.07 | Clean-up & Electrical of turbine building IUKA facility
Journal Entry | 186919 | Reclass Benchmark Invoice from Project 2000 to Doyle
Journal Entry | 700000 | Transfer Power Spares Inventory to Doyle
1639068.18
12/31/99
Power System | 60398.33 | Dow unit Refurbishment
Power System | 34252.67 | VW turbine Refurbishment
Power System | 96762 | Inlets & Exhausts
Power System | 356900 | Turbine-TAW Generator Refurbishment
Enron Engineering & Construction
Enron Engineering & Construction
Enron Engineering & Construction
Mississippi Major Impact Authority | 12500 | Lease Payment
Power System | 59980.39 | Doyle Refurbish- Repair Bearing s on YW 90 and YW 91
Power System | 450000 | Doyle Refurbish- LEC Installation - Doyle Project (75% of $600,000)
Power System | 139019.7 | Doyle Refurbish- Evap coolers- Pass through payment to Caldwell Energy Milestone1
Benchmark Transportion Services | 3446 | Transport turbine from IUKA to Sanford
Benchmark Transportion Services | 2561.2 | Transport parts to Tampa Armature
Benchmark Transportion Services | 1832 | Tarped Flated load from Power Systems to Tampa Armature
Benchmark Transportion Services | 7160 | 2 Trucks EX Turbine Technology to Nepco Carrying 1 exciter Cabinet and 1 control module
Benchmark Transportion Services | 7160 | 3 Trucks EX Turbine Technology to Nepco Carrying 1 exciter Cabinet and 1 control module
Turbine Technology Service | 272718.9 | Doyle Refurbish- TTS Contract December Payment
Turbine Technology Service | 303021 | Doyle Refurbish- TTS Contract November payment
Power System SPC | 1370.36 | Refurbishment Transportion
Power System SPC | 558 | Refurbishment Transportion
Power System SPC | 90000 | Project Management Fee - December 1999
Power System SPC | 175000 | Project Management Time and Expense - November 1999
Power System SPC | 159160.5 | Pass Through to H&M Milestone Payment #4
Power System SPC | 152369.1 | Pass Through Payment to Tampa Armature Works- Scope 1, Milestone Payment #2 & #3.
Benchmark | 1627.5 | Refurbishment Transportion
Benchmark | 1250 | Refurbishment Transportion
Benchmark | 2280 | Refurbishment Transportion
Benchmark | 1624.25 | Refurbishment Transportion
Benchmark | 3446 | Refurbishment Transportion
Benchmark | 269.39 | Refurbishment Transportion
Riviera Finance | 925 | Refurbishment Transportion
2397592.29
01/31/00
H&M Industrial Services, Inc | 32319.35 | Facility Work
H&M Industrial Services, Inc | 47656.79 | Inventory Control Personnel Total Cost of Work to Date
H&M Industrial Services, Inc | 45840.46 | Inventory Control Personnel Total Cost of Work to Date
Power System MFG | 158159 | Doyle Refurbishment - HGP Parts Refurbish
Power System MFG | 3190 | Doyle Refurbishment - Bleed Value Engineering
Power System SPC | 109470.47 | IUKA Facility
Power System SPC | 226375.68 | TTS Technical Direction
Power System SPC | 107307.5 | IUKA Facility
Power System SPC | 45988.93 | Equipment Inventory
Power System SPC | 59973.51 | IUKA Inventory Labor
Power System SPC | 316800 | Boyle Generator Rewind
Power System SPC | 13506.95 | Doyle Refurbishment - Transportaion
Power System SPC | 165580.24 | H&M Turbine Refurbishment
Power System SPC | 29582.71 | Turbine Refurbishment
Power System SPC | 33612 | Doyle Refurbishment- TAW Accessory Refurbishment
Power System SPC | 28581 | Doyle Refurbishment- TAW Accessory Refurbishment
Power System SPC | 89336.27 | Doyle Refurbishment- TAW Accessory Refurbishment
Power System SPC | 29084.32 | Doyle Refurbishment- Wood Group make-up payment
Power System SPC | 125000 | Doyle Refurbishment- Project Management
Power System SPC | 139743.6 | Doyle Refurbishment- TAW Generator Refurbishment
Power Spares | 15000 | IUKA Equipment Inventory --Consignment Fee
Power Spares | 10231.82 | IUKA Equipment Inventory --Consignment Fee
Turbine Technology | 272718.9 | Refurbishment--TTS Contract
Benchmark Transportation Service | 30050 | Doyle Refurbishment - Transportaion
Benchmark Transportation Service | 300 | Doyle Refurbishment - Transportaion
Benchmark Transportation Service | 300 | Doyle Refurbishment - Transportaion
Brimhall Delivery Service | 1069.5 | Refurbishment--Transportation
Brimhall Delivery Service | 2712 | Refurbishment--Transportation
2139491
2/29/2000
Power System Mfg, LLC | 64112 | Doyle Refurbish
Power System Spc | 105000 | Doyle Refurbish : PSSPC scheduel Bonus
Power System Spc | 27013.53 | Doyle Refurbish : PSSPC Work
Power System Spc | 139615.51 | H&M Enclosure Work
Power System Spc | 5374.81 | Doyle Refurbish: Freight Expense
Power System Spc | 76991.62 | Doyle Refurbish: H&M Turbine Refurb
Power System Spc | 323039.5 | Doyle Refurbish: PSSPC Parts
Power System Spc | 21839.9 | Doyle Refurbish: IUKA Facility Expenses
Power System Spc | 50000 | Doyle Refurbish: PSSPC Contract
Power System Spc | 45737.22 | Doyle Refurbish: Parts
Power System Spc | -780 | Doyle Refurbish: Refund for overpaid
Mike Nelson | 2500 | IUKA facility Preparation
H & M Industrial Service | 20139.65 | Doyle - Refurb Inlets
H & M Industrial Service | 3526.51 | Doyle Refurb - Transportation
H & M Industrial Service | 6000 | IUKA Facility-Spare Parts Inventory
H & M Industrial Service | 22018.36 | IUKA Facility
H & M Industrial Service | 32599.83 | IUKA Facility
H & M Industrial Service | 7781.75 | Doyle: Refurbish - Inlet
H & M Industrial Service | 27313.69 | Doyle Inlet Duct
H & M Industrial Service | 26390.01 | Doyle : Dow Inlet Duct
H & M Industrial Service | 2663.19 | Doyle exhaust stacks
Benchmark Transportion | 900 | Doyle Refurb - Transportation
Benchmark Transportion | 750 | Doyle Refurb - Transportation
Benchmark Transportion | 324436 | Doyle Refurb - Transportation
Benchmark Transportion | 1415 | Doyle Refurb - Transportation
Tishomingo Railroad | 1600 | transportation
Benchmark Transportation | 750 | Doyle Refurb - Transportation
Benchmark Transportation | 750 | Doyle Refurb - Transportation
Benchmark Transportation | 3685 | Doyle Refurb - Transportation
Turbine Technology | 3680 | Replacement of the battery compartment to the Dow Sarnia Control Cabinet
1346843.08
3/31/00
Benchmarks Transportation | 750 | Pickup at IUKA of 27 pieces and deliver to Nepco
Benchmarks Transportation | 3685 | Pickup at turbine tech and and deliver to Nepco Monroe- 2 control Cabinets and oversized freight
Benchmarks Transportation | 2700 | Pickup at Power Systems. IUKA, and deliver to Nepco- Tunnel Exhaust, Dampers, Vent Stacks
Power System SPC | 29554.93 | Doyle Refurbishment - PSSPC
Power System SPC | 227108.35 | Doyle Refurbishment - PSSPC
Power System SPC | 139019.7 | Doyle Refurbishment - Pass through Payment to Caldwell Energy Milestone Payment 2
Power System SPC | 182928.4 | Doyle Refurbishment -PSSPC Parts
Power System SPC | 925 | Iuka Freight - Kreider Transport
Power System Mfg, LLC | 2603 | Doyle Refurbishment - PSSPC
Power System SPC | 81517.1 | Doyle Refurbishment - Pass Through Payment to Tampa Armature Work Scope -2
Power System MFG | 98995.6 | Doyle Refurbishment- PSSPC Parts- Remanufacture 2 sets of Buss Duct
H & M Industrial Services, INC | 8529.09 | Doyle Refurbishment - H&M Inlets-Transporting Rain Hoods for YW-90 and YW-91 from Jackson
Power System MFG, LLC | 135000 | Doyle Refurbishment - LEC Installation
John L. Wortham & Son LLP | 19206.15 | Insurance for Doyle Refurbishment - Turbine
Power System SPC, INC | 25000 | Doyle Refurbishment - PSSPC Parts
Power System SPC, INC | 16218 | Doyle Refurbishment - H&M Technical Direction
Power System SPC, INC | 35488.88 | Doyle Refurbishment - PSSPC Rotors
Power System SPC, INC | 15561.65 | Doyle Refurbishment - HGP Parts
Power System SPC, INC | 208451.79 | Doyle Refurbishment - H&M Exhaust / Inlet
Turbine Technology | 545437.8 | # 6 Payment for TTS Refurbishment contract
Power System SPC. INC | 95528.39 | Doyle Line #7 Expenses and Power Support
Power System Mfg. LLC | 42682.61 | Doyle Refurbishment - Flow through purchase orders to Enron from Monrose Site
- PSSPC turbine Refurbishment
Power System Mfg. LLC | 3337.77 | Doyle Refurbishment - Flow through purchase orders to Enron from Monrose Site
- PSSPC turbine Refurbishment
Power System Mfg. LLC | 22927 | Doyle Refurbishment - Flow through purchase orders to Enron from Monrose Site
Power System SPC | 100000 | Doyle Refurbishment - PSSPC Management Expenses -December
Power System SPC | 90000 | Doyle Refurbishment - PSSPC Management Expenses - Final Bill
Journal Entry | -140807.71 | Reclass parts from power spares to 34k inventory
1992348.5
04/30/2000.
Power System SPC | 30855.72 | Turbine Refurb -- Inlet System pass through to Caldwell Energy
Power System MFG | 3204 | Turbine refurb-- manual panic switches added to fire extinguishing system - 3 units
Power System MFG | 1389 | Turbine Refurb -- Repair Accessory CAB door damaged on shipment - Dow
Power System MFG | 8874.49 | Turbine Refurb -- cooling fans on generator blowers
Power System MFG | 8517.35 | Turbine Refurb -- CB 20 vavles for compressor air
Power System MFG | 15064 | Turbine Refurb -- PSSPC management expense
67904.56
05/31/2000.
Power Systems Spc | 67119.2
Power Systems Spc | 248327
Power Systems Spc | 521129.48
Power System Mfg | 9587.59 | PSSPC TD of I for Refurb work
Power System Mfg | 269792 | PSSPC on Site additional Work
Power System SPC | 5136 | Doyle PSSPC Refurb Work
H&M Industrial Services. INC | 112179.6 | H&M Exhaust System Transportation
1233270.87
06/30/2000
Power Systems MFG | 30074 | PSSPC on site work
Power Systems MFG | 1180.37 | Refurb unit 3 repair
Power Systems MFG | 1701.62 | ENA Contract Management
Elliott On-Site Service | 11048.44 | Refurb unit 3 repair
In Place Machining | 11661.52 | Refurb unit 3 repair
RTA Engineering | 17540.19 | Refurb unit 3 bearing work
73206.14
07/31/2000
Power Systems SPC | 690000 | Doyle Extras provided by Tampa Armature Works as agreed to in the settlement agreement
Power Systems SPC | 440065 | H & M Exhaust system
Power Systems SPC | 134402.02 | H & M Turbine compartment work
Power Systems SPC | 57637.64 | Refurbish Waterwash system
Power Systems MFG | 28510.18 | Refurbish Turbine Construction
Power Systems MFG | 7645.99 | Refurbish Turbine Parts
Power Systems MFG | 9355 | Refurb TD of I : PSSPC
Power Systems MFG | 5489.31 | ENA Construction Oversight
Power Systems MFG | 7958 | Refurbishment Turbine Work
Power Systems MFG | 19096.68 | ENA Project Oversight
Turbine Technology | 3855.35 | Remaining Payment for Milestone 7
Turbine Technology | 129088.79 | Doyle: TTS : TD of I
1533103.96
Total Project to Date Refurb Cost | 19640169.95

## LEC Burners
Enron Capital & Trade Resources
Doyle I, LLC
LEC Burner Contract Allocation
| Contract | Total Contract Price |  | Allocation
| Date | Per Unit | Total | 3 units | Remaining | Total
|  |  |  | (Doyle) | (???)
LEC Burners
4 sets LEC @ $1,280,000 ea = $5,120,000 | 1999-04-26 | 1280000 | 5120000 | 3840000 | 1280000 | 5120000
6 sets IGV's @$116,160 ea = $696,960 |  | 116160 | 696960 | 348480 | 348480 | 696960
4 sets Fuel Manifolds/Combustion Cases w/ |  | 73333 | 293332 | 219999 | 73333 | 293332
hardware @ $73,333 ea = $293,333
Total LEC Burners |  | 1469493 | 6110292 | 4408479 | 1701813 | 6110292
Paid 90% |  |  |  | 3967631.1 | 1531631.7 | 5499262.8
Unpaid 10% |  |  |  | 440847.9 | 170181.3 | 611029.2

## InvDetail_InceptiontoDate
COMPANY 34K
S80015 - WALTON (PROJECT DOYLE ) - GA
|  |  |  | Work | Project |  | Invoice |  | Property | Cost | GL Effective
Text90 | Text91 | txtShade | txtAuthAmt | Order | Name | VendorName | Number | Description | Unit | Category | Date | Invoice Amount
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | W R BUSH, EVELYN L BUSH, | BLANKFORD | PROJECT DOYLE | 90000 | LAND | 9/30/1998 | 29000
[12 empty] | Text93: | 29000
[12 empty] | Text98: | 29000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KILPATRICK STOCKTON LLP | DALTON1 | LAND OPTION | 90000 | LAND | 11/30/1998 | 8000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KILPATRICK STOCKTON LLP | DALTON2 | LAND OPTION | 90000 | LAND | 11/30/1998 | 8000
[12 empty] | Text93: | 16000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | HOLLAND & KNIGHT | 781506 | LEGAL FEES | 99000 | LEGL | 11/30/1998 | 2705
[12 empty] | Text93: | 2705
[12 empty] | Text98: | 18705
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KEENAN,JEFFREY M | EXP122898 | TRVL-TX-KC | 99000 | TRVL | 12/30/1998 | 474.67
[12 empty] | Text93: | 474.67
[12 empty] | Text98: | 474.67
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | OGDEN NEWELL & WELCH | 65836 | LEGAL FEES | 99000 | LEGL | 12/31/1998 | 10271.2
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KILPATRICK STOCKTON LLP | 102184343102830 | SITE SELECTION | 99000 | LEGL | 12/31/1998 | 345.13
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KILPATRICK STOCKTON LLP | 102184343102830 | SITE SELECTION | 99000 | LEGL | 12/31/1998 | 14346.82
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KILPATRICK STOCKTON LLP | 102184343102830 | SITE SELECTION | 99000 | LEGL | 12/31/1998 | 3762.91
[12 empty] | Text93: | 28726.06
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | PROVENZANO,MARK | EXP112498 | TRVL-GA-TX | 99000 | TRVL | 12/31/1998 | 825.25
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | SPEARS,R CLAY | EXP122298 | ATHENS, GA | 99000 | TRVL | 12/31/1998 | 505.33
[12 empty] | Text93: | 1330.58
[12 empty] | Text98: | 30056.64
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | EPS CONSULTANTS INC | 99123 | GENERATORS-PROJECT | 90000 | MJEQ | 1/31/1999 | 1200000
[12 empty] | Text93: | 1200000
[12 empty] | Text98: | 1200000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA039905E | RCLS DEVL EXP/E1231F | 99000 | AFCD | 2/28/1999 | -80567.19
[12 empty] | Text93: | -80567.19
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA029906{ | RCLS FRGT/IBC | 90000 | FRGT | 2/28/1999 | 689035.06
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA029906{ | RCLS FREIGHT/IBC | 90000 | FRGT | 2/28/1999 | 1378070.12
[12 empty] | Text93: | 2067105.18
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA029906{ | RCLS IDCS/JAN | 99000 | IDCS | 2/28/1999 | 9574.71
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA029906A | INT DUR CONSTR/DEC | 99000 | IDCS | 2/28/1999 | 176250
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA019906D | CAPITALIZED INT/FEB | 99000 | IDCS | 2/28/1999 | 159611
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA029906A | INT DUR CONSTR/JAN | 99000 | IDCS | 2/28/1999 | 132188
[12 empty] | Text93: | 477623.71
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA039906D | EXP LEGAL | 99000 | LEGL | 2/28/1999 | -933.86
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | HOLLAND & KNIGHT | 799836 | LEGAL FEES | 99000 | LEGL | 2/28/1999 | 933.86
[12 empty] | Text93: | 0
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | L-1005-99 | LEC BURNERS | 90000 | PRTS | 2/28/1999 | 3055146.4
[12 empty] | Text93: | 3055146.4
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA029906{ | FR 7 GAS TBN GENERAT | 90000 | TMAT | 2/28/1999 | 332267.1
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA029906{ | FR 7 GAS TBN GENERAT | 90000 | TMAT | 2/28/1999 | 664534.2
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA029906A | 7B GAS TURBINES (3) | 10101 | TMAT | 2/28/1999 | 21150000
[12 empty] | Text93: | 22146801.3
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | SPEARS,R CLAY | EXP012999 | TRVL-HOUSTON/NASHVIL | 99000 | TRVL | 2/28/1999 | 605.32
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | SPEARS,R CLAY | EXP012999 | TRVL-HOUSTON/NASHVIL | 99000 | TRVL | 2/28/1999 | 461.4
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | SPEARS,R CLAY | EXP012999 | MEALS | 99000 | TRVL | 2/28/1999 | 330.3
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA039906D | EXPENSE TRAVEL | 99000 | TRVL | 2/28/1999 | -1397.02
[12 empty] | Text93: | 0
[12 empty] | Text98: | 27666109.4
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA059909F | MAR CAPITAL INTEREST | 99000 | IDCS | 3/31/1999 | 179551
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | NCR019908D | NORWEST INVESTMENT | 99000 | IDCS | 3/31/1999 | -6178.4
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA059909F | MAR ADJUSTMENT | 99000 | IDCS | 3/31/1999 | 11249.29
[12 empty] | Text93: | 184621.89
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA019907A | REV LEGAL EXP | 99000 | LEGL | 3/31/1999 | 933.86
[12 empty] | Text93: | 933.86
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | NCR019908D | NORWEST INVESTMENT | 90000 | TMAT | 3/31/1999 | -1200000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | M & M LEASING AND ENRON ESCROW | WT031799 | TURBINES | 90000 | TMAT | 3/31/1999 | 2850000
[12 empty] | Text93: | 1650000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA019907A | REV TRAVEL EXP | 99000 | TRVL | 3/31/1999 | 1397.02
[12 empty] | Text93: | 1397.02
[12 empty] | Text98: | 1836952.77
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON INT'L ASSET MANAGEMENT | K51770199 | EXPENSES DOYLE | 99000 | CSUP | 4/30/1999 | 1425
[12 empty] | Text93: | 1425
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA059912D | CAPITAL INTEREST/APR | 99000 | IDCS | 4/30/1999 | 196081
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | JAR029912C | NORWEST | 99000 | IDCS | 4/30/1999 | -5006.93
[12 empty] | Text93: | 191074.07
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GENERAL ELECTRIC COMPANY | N01G4464 | GAS TURBINE | 10100 | MJEQ | 4/30/1999 | 2720000
[12 empty] | Text93: | 2720000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1009-99 | LEC BURNERS WALTON | 90000 | PRTS | 4/30/1999 | 2444117
[12 empty] | Text93: | 2444117
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | AIR LIQUIDE AMERICA CORP | 990406 | TURBINES WALTON | 90000 | TMAT | 4/30/1999 | 500000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | JAR029912C | NORWEST | 90000 | TMAT | 4/30/1999 | -2854071.89
[12 empty] | Text93: | -2354071.89
[12 empty] | Text98: | 3002544.18
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KEENAN,JEFFREY M | EXP020899 | TRVL-GA | 99000 | TRVL | 5/30/1999 | 500.82
[12 empty] | Text93: | 500.82
[12 empty] | Text98: | 500.82
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | AJ MECHANICAL, INC. | 99129 | TURBINE | 99000 | CSUP | 5/31/1999 | 183010.45
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | AJ MECHANICAL, INC. | 99128 | TURBINE | 99000 | CSUP | 5/31/1999 | 135431.96
[12 empty] | Text93: | 318442.41
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA029915D | CAPITAL INTEREST/MAY | 99000 | IDCS | 5/31/1999 | 194517
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | JAR059915D | NORWEST | 99000 | IDCS | 5/31/1999 | -2940.76
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA029915D | TRUE-UP IDC THRU APR | 99000 | IDCS | 5/31/1999 | -79441
[12 empty] | Text93: | 112135.24
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AP159914H | RECL REFURB FR NA | 90000 | MJEQ | 5/31/1999 | 1291080
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GENERAL ELECTRIC COMPANY | N01G4598 | GENERATOR | 10100 | MJEQ | 5/31/1999 | 1632000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AP159914H | RECLASS REFURB COSTS | 90000 | MJEQ | 5/31/1999 | 396000
[12 empty] | Text93: | 3319080
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | AIR LIQUIDE AMERICA CORP | 990501 | TURBINES | 10200 | TMAT | 5/31/1999 | 500000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | IBC TURBO INC | DOYLE90001 | COMPRESSOR DOYLE | 90000 | TMAT | 5/31/1999 | 252344
[12 empty] | Text93: | 752344
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | VIRGO,ROBERT | EXP051299 | TRVL/TAMPA/HOU/MOINT | 99000 | TRVL | 5/31/1999 | 839.59
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | VIRGO,ROBERT | EXP043099 | FL-PROJECT DOYLE | 99000 | TRVL | 5/31/1999 | 1199.36
[12 empty] | Text93: | 2038.95
[12 empty] | Text98: | 4504040.6
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | JAR039918{ | OLGE THROPE | 99000 | AFCD | 6/30/1999 | -5000000
[12 empty] | Text93: | -5000000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | AJ MECHANICAL, INC. | 99133 | TURBINE | 99000 | CSUP | 6/30/1999 | 24767.55
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | AJ MECHANICAL, INC. | 99134 | TURBINE | 99000 | CSUP | 6/30/1999 | 26120.07
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | AJ MECHANICAL, INC. | 99131 | TURBINE | 99000 | CSUP | 6/30/1999 | 22604.87
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | AJ MECHANICAL, INC. | 99132 | TURBINE | 99000 | CSUP | 6/30/1999 | 28671.86
[12 empty] | Text93: | 102164.35
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | LL019918G | FRGHT ON DOYLE TURBI | 90000 | FRGT | 6/30/1999 | 268110.4
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | IBC TURBO INC | SFS-2-98-0012 | FULTON POWER | 90000 | FRGT | 6/30/1999 | 5323.25
[12 empty] | Text93: | 273433.65
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | LL049918G | JUNE IDC | 99000 | IDCS | 6/30/1999 | 226003
[12 empty] | Text93: | 226003
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | LL029918G | RCLS LEGL NOT DOYLE | 99000 | LEGL | 6/30/1999 | -10271.2
[12 empty] | Text93: | -10271.2
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GENERAL ELECTRIC CO #05 | N01G4599 | 7EA GAS TURBINE | 10100 | MJEQ | 6/30/1999 | 1632000
[12 empty] | Text93: | 1632000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | IBC TURBO INC | TL9990008 | WAREHOUSE SECURITY | 99000 | OTHR | 6/30/1999 | 4671.74
[12 empty] | Text93: | 4671.74
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENVIRONMENTAL CONSULTING & | 991137 | PERMITTING | 99000 | PERM | 6/30/1999 | 7636.15
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENVIRONMENTAL CONSULTING & | 991233 | PERMITTING | 99000 | PERM | 6/30/1999 | 2475.23
[12 empty] | Text93: | 10111.38
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | IBC TURBO INC | TL5990027 | WAREHOUSE LEASE | 99000 | RENT | 6/30/1999 | 53311.19
[12 empty] | Text93: | 53311.19
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | AIR LIQUIDE AMERICA CORP | 990601 | TURBINES WALTON | 10200 | TMAT | 6/30/1999 | 500000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | IBC TURBO INC | WT063099 | 7% ADM FEE | 90000 | TMAT | 6/30/1999 | 17664.08
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | AJ MECHANICAL, INC. | 99130 | REFURBISH TURBINE DO | 90000 | TMAT | 6/30/1999 | 78641.11
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | IBC TURBO INC | WT063099 | 7% ADM FEE | 90000 | TMAT | 6/30/1999 | 327.02
[12 empty] | Text93: | 596632.21
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | COFFER,WALTER | EXP051499 | TRVL/IAH/DC/TRANSMIS | 99000 | TRVL | 6/30/1999 | 321.96
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | MILLER,MICHAEL J | EXP060999 | TRVL-HOU-CINCINNATI | 99000 | TRVL | 6/30/1999 | 1209.54
[12 empty] | Text93: | 1531.5
[12 empty] | Text98: | -2110412.18
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | MILLER,MICHAEL J | EXP061899 | TRVL-PENSACOLA | 99000 | TRVL | 7/30/1999 | 953.02
[12 empty] | Text93: | 953.02
[12 empty] | Text98: | 953.02
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T&D COMPANY INC | A23020-39 | TRANSFORMERS | 99000 | CSUP | 7/31/1999 | 115801
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T&D COMPANY INC | AD138 | TRANSFORMERS | 99000 | CSUP | 7/31/1999 | 7535.6
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T&D COMPANY INC | A23020-51 | TRANSFORMERS | 99000 | CSUP | 7/31/1999 | 107223.2
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T&D COMPANY INC | A23020-45 | TRANSFORMERS | 99000 | CSUP | 7/31/1999 | 329902.3
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AMC019920A | ABB MFG DEPOSIT | 99000 | CSUP | 7/31/1999 | 250000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T&D COMPANY INC | AD138 | TRANSFORMERS | 99000 | CSUP | 7/31/1999 | 16543
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T&D COMPANY INC | A23020-39 | TRANSFORMERS | 99000 | CSUP | 7/31/1999 | 52749.2
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T&D COMPANY INC | A23020-44 | TRANSFORMERS | 99000 | CSUP | 7/31/1999 | 188515.6
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T&D COMPANY INC | AD138 | TRANSFORMERS | 99000 | CSUP | 7/31/1999 | 15326.6
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | IBC TURBO INC | SFS-2-98-0027 | DOYLE | 99000 | CSUP | 7/31/1999 | 62060.03
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | TAB029921D | RCLS TURBINE | 99000 | CSUP | 7/31/1999 | -26120.07
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | TAB029921D | RCLS TURBINE | 99000 | CSUP | 7/31/1999 | -24767.55
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | TAB029921D | RCLS TURBINE | 99000 | CSUP | 7/31/1999 | -28671.86
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | TAB029921D | RCLS TURBINE | 99000 | CSUP | 7/31/1999 | -22604.87
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | TAB029921D | RCLS TURBINE | 99000 | CSUP | 7/31/1999 | -183010.45
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | TAB029921D | RCLS TURBINE | 99000 | CSUP | 7/31/1999 | -62060.03
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T&D COMPANY INC | AD138 | TRANSFORMERS | 99000 | CSUP | 7/31/1999 | 74059.7
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | TAB029921D | RCLS TURBINE | 99000 | CSUP | 7/31/1999 | -135431.96
[12 empty] | Text93: | 737049.44
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | LL019921H |  | 99000 | IDCS | 7/31/1999 | 218114
[12 empty] | Text93: | 218114
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KILPATRICK STOCKTON LLP | WT072699 | BUSH WALTON SITE | 90000 | LAND | 7/31/1999 | 315565.77
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KILPATRICK STOCKTON LLP | WT072999 | BUSH WALTON | 90000 | LAND | 7/31/1999 | 7000
[12 empty] | Text93: | 322565.77
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KILPATRICK STOCKTON LLP | 10319831 | LEGAL FEES | 99000 | LEGL | 7/31/1999 | 2585.04
[12 empty] | Text93: | 2585.04
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GENERAL ELECTRIC COMPANY | NO1G4632 | GE TURBINE | 10100 | MJEQ | 7/31/1999 | 1632000
[12 empty] | Text93: | 1632000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | IBC TURBO INC | TL5990028 | DOYLE | 99000 | OTHR | 7/31/1999 | 56199.77
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | IBC TURBO INC | TL9990010 | DOYLE SECURITY | 99000 | OTHR | 7/31/1999 | 3440.53
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KIWANIS CLUB OF MONROE, GA | INV0699 | CONTRIBUTION | 99000 | OTHR | 7/31/1999 | 100
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | IBC TURBO INC | TL9990009 | DOYLE SECURITY SVCS | 99000 | OTHR | 7/31/1999 | 6680.84
[12 empty] | Text93: | 66421.14
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | LL029921H | TRSF LECS TO INV | 90000 | PRTS | 7/31/1999 | -1531632
[12 empty] | Text93: | -1531632
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | TAB029921D | RCLS TURBINE | 90000 | TMAT | 7/31/1999 | -78641.11
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | AIR LIQUIDE AMERICA CORP | 990701 | JULY TURBINE | 10200 | TMAT | 7/31/1999 | 500000
[12 empty] | Text93: | 421358.89
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | SPEARS,R CLAY | EXP072099 | TRVL/SEATTLE-DOYLEPO | 99000 | TRVL | 7/31/1999 | 2182.8
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | SPEARS,R CLAY | EXP061699 | TRVL/TN-IAH/BROWNSVI | 99000 | TRVL | 7/31/1999 | 978.73
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | VIRGO,ROBERT | EXP062499 | TRVL/IAH-TAMPADOYLE | 99000 | TRVL | 7/31/1999 | 1117.25
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | COFFER,WALTER | EXP071999 | TRAVEL-PENSACOLA | 99000 | TRVL | 7/31/1999 | 1157.17
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GARRETT,BRYAN | EXP061099 | TRAVEL-ATLANTA | 99000 | TRVL | 7/31/1999 | 5551.71
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GARRETT,BRYAN | EXP061099 | SUPPLIES | 99000 | TRVL | 7/31/1999 | 34.19
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | SPEARS,R CLAY | EXP072099 | MEALS | 99000 | TRVL | 7/31/1999 | 37.62
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | COFFER,WALTER | EXP071999 | MEALS | 99000 | TRVL | 7/31/1999 | 27.79
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | SPEARS,R CLAY | EXP061699 | MEALS | 99000 | TRVL | 7/31/1999 | 259.17
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GARRETT,BRYAN | EXP061099 | MEALS | 99000 | TRVL | 7/31/1999 | 170.25
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | COFFER,WALTER | EXP072699 | TRAVEL-ATLANTA | 99000 | TRVL | 7/31/1999 | 303.21
[12 empty] | Text93: | 11819.89
[12 empty] | Text98: | 1880282.17
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | PMF-899 | INV. PMF-899 | 99000 | CSUP | 8/31/1999 | 20000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | PMF-899 | INV.#PMF-899 | 99000 | CSUP | 8/31/1999 | 100000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | HOU-99-253 | TRANSPORT TURBINES | 99000 | CSUP | 8/31/1999 | 278580
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | PMF-899A | MILESTONE PYMT 2 | 99000 | CSUP | 8/31/1999 | 80000
[12 empty] | Text93: | 478580
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | JAR 059922I | DEFER1/2BUSH LAN PMT | 90000 | LAND | 8/31/1999 | -149519.93
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | JAR 079924E | DEF.LAND PAY | 90000 | LAND | 8/31/1999 | -7000
[12 empty] | Text93: | -156519.93
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GENERAL ELECTRIC COMPANY | N01G4736 | GAS TURBINE | 10100 | MJEQ | 8/31/1999 | 1632000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SPARES, INC. | I-1010-99 | LEC TRANSITION PIECE | 10100 | MJEQ | 8/31/1999 | 510000
[12 empty] | Text93: | 2142000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | IBC TURBO INC | SA990001 | PENSACOLA LEASE | 99000 | OTHR | 8/31/1999 | 97500
[12 empty] | Text93: | 97500
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | NEEL-SCHAFFER INC | 906809 | PERMITTING SURVEY | 99000 | PERM | 8/31/1999 | 969.25
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENVIRONMENTAL CONSULTING & | 991865 | MAY/JULY INV | 99000 | PERM | 8/31/1999 | 8599.99
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENVIRONMENTAL CONSULTING & | 991581 | MAY PERMITTING/COSTS | 99000 | PERM | 8/31/1999 | 3916.79
[12 empty] | Text93: | 13486.03
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | AIR LIQUIDE AMERICA CORP | 990801 | TURBINE PAYMENT | 10200 | TMAT | 8/31/1999 | 500000
[12 empty] | Text93: | 500000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GARRETT,BRYAN | EXP081099 | MEALS | 99000 | TRVL | 8/31/1999 | 7.58
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GARRETT,BRYAN | EXP081099 | GA-DOYLE PROJECT | 99000 | TRVL | 8/31/1999 | 419.3
[12 empty] | Text93: | 426.88
[12 empty] | Text98: | 3075472.98
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | PMF-899 | INITIAL PAY PROJ | 99000 | COSU | 9/30/1999 | 150000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | PMF-899 | SEPT PROJ MGMT | 99000 | COSU | 9/30/1999 | 80000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | G.L.C. CONSULTING SERVICE | 10 | CONSULTING | 99000 | COSU | 9/30/1999 | 10132
[12 empty] | Text93: | 240132
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | TAB029927H | RECLASS TRANSFORMERS | 99000 | CSUP | 9/30/1999 | -907656.2
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | TURBINE TECHNOLOGY SERVICES | 2792 | REFURB | 99000 | CSUP | 9/30/1999 | 545437.8
[12 empty] | Text93: | -362218.4
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AW019928{ |  | 99000 | IDCS | 9/30/1999 | 250137
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AW019928{ |  | 99000 | IDCS | 9/30/1999 | 230971
[12 empty] | Text93: | 481108
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KING & SPALDING | 124115 | JUNE LOAN AGREEMENT | 99000 | LEGL | 9/30/1999 | 23476.13
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KILPATRICK STOCKTON LLP | 10327884 | JUNE SALES TAX ISSUE | 99000 | LEGL | 9/30/1999 | 2387.16
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KILPATRICK STOCKTON LLP | 10319830 | MAY INV SITE ISSUES | 99000 | LEGL | 9/30/1999 | 7055.46
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KING & SPALDING | LEGAL083099 | DOYLE I PROJECT | 99000 | LEGL | 9/30/1999 | 5034.12
[12 empty] | Text93: | 37952.87
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GENERAL ELECTRIC COMPANY | N01G4849 | SEPT TURBINE | 10100 | MJEQ | 9/30/1999 | 1632000
[12 empty] | Text93: | 1632000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | WT090899 | 2922 | 99000 | OTHR | 9/30/1999 | 47620.5
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | MISSISSIPPI MAJOR IMPACT AUTH | MILLER MISSISSIP | LEASE PMT | 99000 | OTHR | 9/30/1999 | 12500
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | WT090899 | INC. 002921 | 99000 | OTHR | 9/30/1999 | 45905
[12 empty] | Text93: | 106025.5
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENVIRONMENTAL CONSULTING & | 992147 | JULY INVOICE | 99000 | PERM | 9/30/1999 | 2197.53
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENVIRONMENTAL CONSULTING & | 992444 | AUG. INVOICE | 99000 | PERM | 9/30/1999 | 981.83
[12 empty] | Text93: | 3179.36
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | HOU-99-272 | HOU99272 | 90000 | TMAT | 9/30/1999 | 7168
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | HOU-99-253A | HOU99253A | 90000 | TMAT | 9/30/1999 | 104297
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | MIKE NELSON CONTRACTORS, INC | INV090299 | FACILITY PREPARATION | 90000 | TMAT | 9/30/1999 | 17510.9
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | AIR LIQUIDE AMERICA CORP | 990901 | TURBINE | 10200 | TMAT | 9/30/1999 | 500000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | TAB029927H | RECLASS TRANSFORMERS | 90000 | TMAT | 9/30/1999 | 250000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | 2953 | TURBINE REFURB | 90000 | TMAT | 9/30/1999 | 63659.61
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | MIKE NELSON CONTRACTORS, INC | INV091399 |  | 90000 | TMAT | 9/30/1999 | 22413.15
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | 2954 | 5 EXHAUST SYS | 90000 | TMAT | 9/30/1999 | 463226.2
[12 empty] | Text93: | 1428274.86
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | VIRGO,ROBERT | EXP091399 | MEALS-TRVL-FL | 99000 | TRVL | 9/30/1999 | 1145.46
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GARRETT,BRYAN | EXP090199 | GA-DOYLE PROJECT | 99000 | TRVL | 9/30/1999 | 2025.33
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GARRETT,BRYAN | EXP090199 | MEALS | 99000 | TRVL | 9/30/1999 | 73.48
[12 empty] | Text93: | 3244.27
[12 empty] | Text98: | 3569698.46
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | PMF-899A | VARIOUS | 99000 | COSU | 10/31/1999 | 39007.08
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | G.L.C. CONSULTING SERVICE | 11 | CONSULTANT | 99000 | COSU | 10/31/1999 | 52750
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SPARES, INC. | I-1024-99 | TURBINE REFURB | 99000 | COSU | 10/31/1999 | 9030.98
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | PMF-899 | PROJ MGT TURBINE | 99000 | COSU | 10/31/1999 | 100000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | PMF-899 | PROJ MGMT TURBINE | 99000 | COSU | 10/31/1999 | 125000
[12 empty] | Text93: | 325788.06
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | PMF-899 | TURBIN REFURB | 99000 | CSUP | 10/31/1999 | 755700
[12 empty] | Text93: | 755700
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AW029930E |  | 99000 | IDCS | 10/31/1999 | 268825
[12 empty] | Text93: | 268825
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KILPATRICK STOCKTON LLP | 10337504 | CLOSING DOCUMENTS | 99000 | LEGL | 10/31/1999 | 2771.63
[12 empty] | Text93: | 2771.63
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T&D COMPANY INC | 390402 | GENERATOR CIRCUIT | 90000 | MJEQ | 10/31/1999 | 57410.7
[12 empty] | Text93: | 57410.7
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SPARES, INC. | I-1020-99 | CONSIGNMENT FEE | 99000 | OTHR | 10/31/1999 | 5000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | IBC TURBO INC | SA990003 | REFURB | 99000 | OTHR | 10/31/1999 | 15834
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | IBC TURBO INC | SA9900002 | REFURB PENSACOLA | 99000 | OTHR | 10/31/1999 | 15834
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SPARES, INC. | 1-1021-99 | SELL SPARE PARTS | 99000 | OTHR | 10/31/1999 | 5000
[12 empty] | Text93: | 41668
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | NEEL-SCHAFFER INC | 3-3410-07 | JULY SURVEY/PERM | 99000 | PERM | 10/31/1999 | 1848.15
[12 empty] | Text93: | 1848.15
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GENERAL ELECTRIC COMPANY | N01G4942 | OCT TURBINE | 90000 | TMAT | 10/31/1999 | 1632000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | PMF-900 | TURBINE REFUR | 90000 | TMAT | 10/31/1999 | 127328.22
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | WT102299 | REFURB | 90000 | TMAT | 10/31/1999 | 9000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SPARES, INC. | I-1025-99 | 2ND,3RD STAGE SHROUD | 90000 | TMAT | 10/31/1999 | 203476.5
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | HOU-99-273 | REFURB | 90000 | TMAT | 10/31/1999 | 10985
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | HOU-99-274 | REFURB | 90000 | TMAT | 10/31/1999 | 5289
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SPARES, INC. | I-1013-99 | GE ROTOR-TEST/INSPCT | 90000 | TMAT | 10/31/1999 | 11145.5
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | 1-1018-99 | NOZZLE | 90000 | TMAT | 10/31/1999 | 630000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | TAB059930H | ACCRUE 9/99 NEPCO | 90000 | TMAT | 10/31/1999 | 586754
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | TURBINE TECHNOLOGY SERVICES | 2822 | REWIRE | 90000 | TMAT | 10/31/1999 | 272718.9
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | TURBINE TECHNOLOGY SERVICES | 2821 | REWIRE | 90000 | TMAT | 10/31/1999 | 136359.45
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | AIR LIQUIDE AMERICA CORP | 991001 | LETTER AGREEMENT | 90000 | TMAT | 10/31/1999 | 500000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | HOU-99-289 | REFURB | 90000 | TMAT | 10/31/1999 | 129539
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | HOU-99-296 | REFURB | 90000 | TMAT | 10/31/1999 | 34500
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | HOIST & CRANE SERVICE GROUP | 3420329 | TURBINE REFURBISHM'T | 90000 | TMAT | 10/31/1999 | 6980
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | HOU-99-297 | REFURB | 90000 | TMAT | 10/31/1999 | 49370
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | 7997 | LUKA BLDG PREP | 90000 | TMAT | 10/31/1999 | 54196.5
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | THE SALVAGE ASSOC. LIMITED | 745620 | INS MOVING REFURB | 90000 | TMAT | 10/31/1999 | 22526
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | HOU-99-295 | REFURB | 90000 | TMAT | 10/31/1999 | 119361.69
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | APPLIED ENGINEERING CORP. | WT102299 | REFURB | 90000 | TMAT | 10/31/1999 | 5179.43
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | HOU-99-275 | REFURB | 90000 | TMAT | 10/31/1999 | 20808
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | 3004 | TURBINE REFURB | 90000 | TMAT | 10/31/1999 | 63668.61
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | MIKE NELSON CONTRACTORS, INC | SPEARS MIKENELSO | IUKA SITE PREP | 90000 | TMAT | 10/31/1999 | 3000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | MIKE NELSON CONTRACTORS, INC | SPEARS MIKE | IUKA SITE PREP | 90000 | TMAT | 10/31/1999 | 11000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | WILLIAMS GAS PIPELINE-TRANSCO | WT101299 | INTERCONNECT | 90000 | TMAT | 10/31/1999 | 977990
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SPARES, INC. | I-1019-99 | REFURB | 90000 | TMAT | 10/31/1999 | 10245.82
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | AJ MECHANICAL, INC. | 99137 | REFURB | 90000 | TMAT | 10/31/1999 | 52404.53
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | PMF-899A | 2ND MILESTONE PMT | 90000 | TMAT | 10/31/1999 | 683258.64
[12 empty] | Text93: | 6369084.79
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GARRETT,BRYAN | EXP100899 | MEALS | 99000 | TRVL | 10/31/1999 | 66.49
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GARRETT,BRYAN | EXP100899 | GOLF OUTING | 99000 | TRVL | 10/31/1999 | 126.84
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GARRETT,BRYAN | EXP100899 | MEX-CUSTOMER OUTING | 99000 | TRVL | 10/31/1999 | 1131.4
[12 empty] | Text93: | 1324.73
[12 empty] | Text98: | 7824421.06
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | NEEL-SCHAFFER INC | 909605 | CONSULTING | 99000 | COSU | 11/1/1999 | 3359.69
[12 empty] | Text93: | 3359.69
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | W.O.7997 | LABOR | 99000 | INST | 11/1/1999 | 33146.06
[12 empty] | Text93: | 33146.06
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KING & SPALDING | WT110599 | OUTSIDE LEGAL | 99000 | LEGL | 11/1/1999 | 10609.34
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KING & SPALDING | WT110599 | OUTSIDE LEGAL | 99000 | LEGL | 11/1/1999 | 14179.86
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KING & SPALDING | WT110599 | OUTSIDE LEGAL | 99000 | LEGL | 11/1/1999 | 79879.31
[12 empty] | Text93: | 104668.51
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GENERAL ELECTRIC COMPANY | N01G5204 | TURBINE | 90000 | MJEQ | 11/1/1999 | 1632000
[12 empty] | Text93: | 1632000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SPARES, INC. | I-1028-99 | CONSIGNMENT FEE | 99000 | OTHR | 11/1/1999 | 15000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | IBC TURBO INC | SA990004 | REFURB LEASE | 99000 | OTHR | 11/1/1999 | 15834
[12 empty] | Text93: | 30834
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | W.O.7997 | MATERIALS | 99000 | OVHD | 11/1/1999 | 8777.07
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | W.O.7997 | MATERIALS | 99000 | OVHD | 11/1/1999 | 5422.76
[12 empty] | Text93: | 14199.83
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | AIR LIQUIDE AMERICA CORP | 991101 | 991101 | 10200 | TMAT | 11/1/1999 | 500000
[12 empty] | Text93: | 500000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | W.O.7997 | TRAVEL EXP | 99000 | TRVL | 11/1/1999 | 2644.2
[12 empty] | Text93: | 2644.2
[12 empty] | Text98: | 2320852.29
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENVIRONMENTAL CONSULTING & | 992727 | PERMITTING FEE | 99000 | COSU | 11/30/1999 | 666.62
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENVIRONMENTAL CONSULTING & | 992825 | PERMITTING FEE | 99000 | COSU | 11/30/1999 | 2300.25
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | G.L.C. CONSULTING SERVICE | 12 | TURBINECONSULTANT | 99000 | COSU | 11/30/1999 | 34278
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | WT113099 | PMF 902 11/03 | 99000 | COSU | 11/30/1999 | 150000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | WT113099 | PMF 903 11/15 | 99000 | COSU | 11/30/1999 | 100000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | NATIONAL ENERGY PRODUCTION | WT113099 | 99001R 09/20 | 99000 | COSU | 11/30/1999 | 201869
[12 empty] | Text93: | 489113.87
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | NATIONAL ENERGY PRODUCTION | WT113099 | 99002R 10/15 | 99000 | CSUP | 11/30/1999 | 82855
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | NATIONAL ENERGY PRODUCTION | WT113099 | 990011 9/20 | 99000 | CSUP | 11/30/1999 | 151015
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | NATIONAL ENERGY PRODUCTION | WT113099 | 99002L- 10/15 | 99000 | CSUP | 11/30/1999 | 151015
[12 empty] | Text93: | 384885
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AWU29934A |  | 99000 | IDCS | 11/30/1999 | 316229.18
[12 empty] | Text93: | 316229.18
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | WT113099 | PMF905 11/03 | 99000 | INST | 11/30/1999 | 82875
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | WT113099 | INV. 003132 | 99000 | INST | 11/30/1999 | 9000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | WT113099 | PMF 904 11/3 | 99000 | INST | 11/30/1999 | 159160.5
[12 empty] | Text93: | 251035.5
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SPARES, INC. | WT113099 | 102899 11/30/99 | 99000 | OTHR | 11/30/1999 | 15000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SPARES, INC. | WT113099 | 102999 10/31/99 | 99000 | OTHR | 11/30/1999 | 7017.42
[12 empty] | Text93: | 22017.42
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | WT113099 | 102199 11/8 | 99000 | OVHD | 11/30/1999 | 2742.2
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | WT113099 | 3135 | 99000 | OVHD | 11/30/1999 | 63485.07
[12 empty] | Text93: | 66227.27
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | TAB129934{ | RCLSS SPARE PARTS-NA | 90000 | PRTS | 11/30/1999 | 186919
[12 empty] | Text93: | 186919
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AW019934{ |  | 90000 | TMAT | 11/30/1999 | 1314512
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | 100453A | REFUR | 90000 | TMAT | 11/30/1999 | 82044.9
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | 110422000289933D | ACCRUE 9/99 NEPCO | 90000 | TMAT | 11/30/1999 | -586754
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GENERAL ELECTRIC COMPANY | N01G5098 | NOV TURBINE | 90000 | TMAT | 11/30/1999 | 1632000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AWU29934{ |  | 90000 | TMAT | 11/30/1999 | 700000
[12 empty] | Text93: | 3141802.9
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GARRETT,BRYAN | EXP110899 | GA-DOYLE PROJECT | 99000 | TRVL | 11/30/1999 | 2152.82
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | COFFER,WALTER | EXP110399 | GA-DOYLE PROJECT | 99000 | TRVL | 11/30/1999 | 484.41
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | COFFER,WALTER | EXP110399 | MEALS | 99000 | TRVL | 11/30/1999 | 9.17
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | SPEARS,R CLAY | EXP110999 | YTRVL/HOU-EASTORGINA | 99000 | TRVL | 11/30/1999 | 1383.69
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | SPEARS,R CLAY | EXP110999 | MEALS | 99000 | TRVL | 11/30/1999 | 126.22
[12 empty] | Text93: | 4156.31
[12 empty] | Text98: | 4862386.45
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | 1024-99 | TURBINES | 99000 | CSUP | 12/1/1999 | 59980.39
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1023-99 | TURBINE | 99000 | CSUP | 12/1/1999 | 356900
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | NATIONAL ENERGY PRODUCTION | 99003L | DOYLE PROJECT | 99000 | CSUP | 12/1/1999 | 2173279
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | NATIONAL ENERGY PRODUCTION | 99003L | DOYLE PROJECT | 99000 | CSUP | 12/1/1999 | 328718
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1023-99 | TURBINE | 99000 | CSUP | 12/1/1999 | 34252.67
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1023-99 | TURBINE | 99000 | CSUP | 12/1/1999 | 60398.33
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | WT121499 | DOYLE PROJECT | 99000 | CSUP | 12/1/1999 | 450000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1023-99 | TURBINE | 99000 | CSUP | 12/1/1999 | 96762
[12 empty] | Text93: | 3560290.39
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | S9P732-1 | DOYLE PROJECT | 99000 | ENGR | 12/1/1999 | 40222.14
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | S9P733-01 | REFURB | 99000 | ENGR | 12/1/1999 | 49353.76
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | TURBINE TECHNOLOGY SERVICES | 2914 | REFURB | 99000 | ENGR | 12/1/1999 | 272718.9
[12 empty] | Text93: | 362294.8
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ99-0004-MS | TURBINE | 90000 | FRGT | 12/1/1999 | 3446
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ99-0004-MS | TURBINE | 90000 | FRGT | 12/1/1999 | 7160
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ99-0004-MS | TURBINE | 90000 | FRGT | 12/1/1999 | 7160
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ99-0004-MS | TURBINE | 90000 | FRGT | 12/1/1999 | 1832
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ99-0004-MS | TURBINE | 90000 | FRGT | 12/1/1999 | 2561.2
[12 empty] | Text93: | 22159.2
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KILPATRICK STOCKTON LLP | 10337506 | LEGAL DOYLE | 99000 | LEGL | 12/1/1999 | 4050.27
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KING & SPALDING | 131259 | LEGAL | 99000 | LEGL | 12/1/1999 | 5515.93
[12 empty] | Text93: | 9566.2
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T&D COMPANY INC | MP99278 | OPC SUBSTATION | 90000 | MJEQ | 12/1/1999 | 166666.67
[12 empty] | Text93: | 166666.67
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | S9P732-1 | DOYLE PROJECT | 99000 | OVHD | 12/1/1999 | 265114.29
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | S9P732-1 | DOYLE PROJECT | 99000 | OVHD | 12/1/1999 | 22838.53
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON INT'L ASSET MANAGEMENT | K051771099 | DOYLE PRE MOBILIZATI | 99000 | OVHD | 12/1/1999 | 22069.5
[12 empty] | Text93: | 310022.32
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | 1024-99 | TURBINES | 90000 | PRTS | 12/1/1999 | 611029
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | TURBINE TECHNOLOGY SERVICES | 2894 | DOYLE REFURB | 90000 | PRTS | 12/1/1999 | 303021
[12 empty] | Text93: | 914050
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | AIR LIQUIDE AMERICA CORP | 991223 | LETTER AGREEMENT | 10200 | TMAT | 12/1/1999 | 532622
[12 empty] | Text93: | 532622
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | 1024-99 | TURBINES | 90000 | WATR | 12/1/1999 | 139019.7
[12 empty] | Text93: | 139019.7
[12 empty] | Text98: | 6016691.28
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | RIVIERA FINANCE | ENA |  | 90000 | FRGT | 12/30/1999 | 925
[12 empty] | Text93: | 925
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GARRETT,BRYAN | EXP120699 | MEALS-TIPS-TRVL-GA | 99000 | TRVL | 12/30/1999 | 828.67
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GARRETT,BRYAN | EXP112399 | TRVL-HOU-GA | 99000 | TRVL | 12/30/1999 | 1640.13
[12 empty] | Text93: | 2468.8
[12 empty] | Text98: | 3393.8
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | G.L.C. CONSULTING SERVICE | 13 | GLC CONSULTING | 99000 | COSU | 12/31/1999 | 21750.25
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENVIRONMENTAL CONSULTING & | 993052 | PERMITTING FEE | 99000 | COSU | 12/31/1999 | 2158.32
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENVIRONMENTAL CONSULTING & | 993387 | PERMITTING | 99000 | COSU | 12/31/1999 | 1506.69
[12 empty] | Text93: | 25415.26
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | WT120899 | J8T651-0899-09/21/99 | 99000 | CSUP | 12/31/1999 | 19502.89
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | WT120899 | J8T651-0399-05/07/99 | 99000 | CSUP | 12/31/1999 | 27961.73
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | GARCIA 1299 | 1-1026-99 12/09/99 | 99000 | CSUP | 12/31/1999 | 152369.1
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | GARCIA 1299 | 1-1031-99 12/10/99 | 99000 | CSUP | 12/31/1999 | 159160.5
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | GARCIA 1299 | PMF-907 12/10/99 | 99000 | CSUP | 12/31/1999 | 175000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | WT120899 | J8T651-0699-06/15/99 | 99000 | CSUP | 12/31/1999 | 41293.92
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | WT120899 | J8T651-0599-06/15/99 | 99000 | CSUP | 12/31/1999 | 27650.83
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | WT120899 | J8T651-0499-06/02/99 | 99000 | CSUP | 12/31/1999 | 19918.9
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | WT120899 | J8T651-1298-01/25/99 | 99000 | CSUP | 12/31/1999 | 2059.32
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | WT120899 | J8T651-0299-04/01/99 | 99000 | CSUP | 12/31/1999 | 9301.58
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | WT120899 | J8T651-898A-11/16/98 | 99000 | CSUP | 12/31/1999 | 16484.03
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | WT120899 | J87651-1198-12/10/98 | 99000 | CSUP | 12/31/1999 | 9568.95
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | WT120899 | 8JT651-698-8/3/98 | 99000 | CSUP | 12/31/1999 | 4589.45
[12 empty] | Text93: | 664861.2
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | TAB070000F | ACCRUE 12/99 NEPCO | 99000 | ENGR | 12/31/1999 | 3787643
[12 empty] | Text93: | 3787643
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | 3230 | REFURBISHMENT TRANSP | 90000 | FRGT | 12/31/1999 | 1370.36
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | GARCIA 122399 | INV#965301-10/21/99 | 90000 | FRGT | 12/31/1999 | 1250
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | GARCIA 122399 | INV#965341-10/28/99 | 90000 | FRGT | 12/31/1999 | 1624.25
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | EPPERSON TRUCKING INC | 51886 | REFURBISHM'T/TRANSP | 90000 | FRGT | 12/31/1999 | 558
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-99-0015 | REFURBISHMENT TRANSP | 90000 | FRGT | 12/31/1999 | 269.39
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | GARCIA 122399 | INV#PRJ-99-0004-MS | 90000 | FRGT | 12/31/1999 | 3446
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | GARCIA 122399 | INV#965282-10/14/99 | 90000 | FRGT | 12/31/1999 | 1627.5
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | GARCIA 122399 | INV#965334-10/27/99 | 90000 | FRGT | 12/31/1999 | 2280
[12 empty] | Text93: | 12425.5
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AWU10000H |  | 99000 | IDCS | 12/31/1999 | 360766
[12 empty] | Text93: | 360766
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA020000F | LEGAL EXPS/DOYLE | 99000 | LEGL | 12/31/1999 | 69016.13
[12 empty] | Text93: | 69016.13
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | MISSISSIPPI MAJOR IMPACT AUTH | MILLER | LEASE PYMT | 99000 | OTHR | 12/31/1999 | 12500
[12 empty] | Text93: | 12500
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | GARCIA 1299 | PMF-906 12/15/99 | 99000 | OVHD | 12/31/1999 | 90000
[12 empty] | Text93: | 90000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T&D COMPANY INC | MP99298 | ABB TRANSFORMER SETU | 90000 | TMAT | 12/31/1999 | 166666.67
[12 empty] | Text93: | 166666.67
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | KA020000F | TRAVEL EXPS/DOYLE | 99000 | TRVL | 12/31/1999 | 1852.25
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | SEWELL,ROBERT D | EXP112499 | MEALS | 99000 | TRVL | 12/31/1999 | 18.72
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | SPEARS,R CLAY | EXP121099 | TRVL/HOU-DOYLEPROJ | 99000 | TRVL | 12/31/1999 | 2231.25
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | SPEARS,R CLAY | EXP121099 | MEALS | 99000 | TRVL | 12/31/1999 | 200.12
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | COFFER,WALTER | EXP121699 | GA-PROJECT DOYLE | 99000 | TRVL | 12/31/1999 | 580.92
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | SEWELL,ROBERT D | EXP112499 | TRVL/TN-GLEASONGROUN | 99000 | TRVL | 12/31/1999 | 746.73
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | COFFER,WALTER | EXP120199 | GA-DOYLE PROJECT | 99000 | TRVL | 12/31/1999 | 316.65
[12 empty] | Text93: | 5946.64
[12 empty] | Text98: | 5195240.4
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | 3307 | 3136 | 99000 | CSUP | 1/1/2000 | 45840.46
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | 3307 | 3308 | 99000 | CSUP | 1/1/2000 | 47656.79
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | 1029-99 | 1034-99 | 99000 | CSUP | 1/1/2000 | 89336.27
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | 3307 | 3307 | 99000 | CSUP | 1/1/2000 | 32319.35
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | NATIONAL ENERGY PRODUCTION | 99005L | 99005L | 99000 | CSUP | 1/1/2000 | 157687
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1028-99 | 1-1028-99 | 99000 | CSUP | 1/1/2000 | 109470.47
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1028-99 | 1-1038-99 | 99000 | CSUP | 1/1/2000 | 226375.68
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1028-99 | 1-1040-99 | 99000 | CSUP | 1/1/2000 | 59973.51
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | WT012800 | 1-1044-00 | 99000 | CSUP | 1/1/2000 | 139743.6
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | WT012800 | ADDTL PMT | 99000 | CSUP | 1/1/2000 | 29084.32
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | 1029-99 | 1032-99 | 99000 | CSUP | 1/1/2000 | 33612
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | NATIONAL ENERGY PRODUCTION | 99005L | 99005R | 99000 | CSUP | 1/1/2000 | 5151338
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | WT011200 | DOYLE REFURB | 99000 | CSUP | 1/1/2000 | 3190
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | 1029-99 | 1029-99 | 99000 | CSUP | 1/1/2000 | 165580.24
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | WT012800 | INV 1-1048-00 | 99000 | CSUP | 1/1/2000 | 125000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | 1029-99 | 1033-99 | 99000 | CSUP | 1/1/2000 | 28581
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | TURBINE TECHNOLOGY SERVICES | 2918 | REFURBISHMENT | 99000 | CSUP | 1/1/2000 | 272718.9
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | 1029-99 | 1030-99 | 99000 | CSUP | 1/1/2000 | 29582.71
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1028-99 | 1-1041-00 | 99000 | CSUP | 1/1/2000 | 316800
[12 empty] | Text93: | 7063890.3
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0037-MS | PRJ-00-0043-MS | 90000 | FRGT | 1/1/2000 | 1000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0037-MS | PRJ-00-0044-MS | 90000 | FRGT | 1/1/2000 | 1000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0037-MS | PRJ-00-0042-MS | 90000 | FRGT | 1/1/2000 | 1000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0037-MS | PRJ-00-0038-MS | 90000 | FRGT | 1/1/2000 | 1000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0037-MS | PRJ-00-41-MS | 90000 | FRGT | 1/1/2000 | 1000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0037-MS | PRJ-00-0048-MS | 90000 | FRGT | 1/1/2000 | 1000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1028-99 | 1-1042-00 | 90000 | FRGT | 1/1/2000 | 13506.95
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | WT010500 | DOYLE REFURB | 90000 | FRGT | 1/1/2000 | 158159
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0037-MS | PRJ-00-0045-MS | 90000 | FRGT | 1/1/2000 | 1000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-0027-MS | PRJ-0027-MS | 90000 | FRGT | 1/1/2000 | 300
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0037-MS | PRJ-00-0047 | 90000 | FRGT | 1/1/2000 | 1000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-0027-MS | PRJ-0026-MS | 90000 | FRGT | 1/1/2000 | 300
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0037-MS | PRJ-00-40-MS | 90000 | FRGT | 1/1/2000 | 2450
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0037-MS | PRJ-00-045-MS | 90000 | FRGT | 1/1/2000 | 1750
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0037-MS | PRJ-00-0037-MS | 90000 | FRGT | 1/1/2000 | 16000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0037-MS | PRJ-00-0037-MS | 90000 | FRGT | 1/1/2000 | 1850
[12 empty] | Text93: | 202315.95
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GENERAL ELECTRIC COMPANY | N01G5325 | TURBINE | 90000 | MJEQ | 1/1/2000 | 1632000
[12 empty] | Text93: | 1632000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1028-99 | 1-1039-99 | 99000 | OVHD | 1/1/2000 | 107307.5
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SPARES, INC. | I-1034-99 | I-1034-99 | 99000 | OVHD | 1/1/2000 | 15000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SPARES, INC. | I-1034-99 | I-1035-99 | 99000 | OVHD | 1/1/2000 | 10231.82
[12 empty] | Text93: | 132539.32
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1028-99 | 1-1039-99 | 90000 | PRTS | 1/1/2000 | 45988.93
[12 empty] | Text93: | 45988.93
[12 empty] | Text98: | 9076734.5
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENVIRONMENTAL CONSULTING & | 993126 | PERMITTING | 99000 | COSU | 1/31/2000 | 26.24
[12 empty] | Text93: | 26.24
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | TURBINE TECHNOLOGY SERVICES | 2918 | REFURBISHMENT TTS | 99000 | CSUP | 1/31/2000 | 272718.9
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AWU020002H |  | 99000 | CSUP | 1/31/2000 | -272718.9
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | G.L.C. CONSULTING SERVICE | 14 | GLC CONSULTING | 99000 | CSUP | 1/31/2000 | 20421.09
[12 empty] | Text93: | 20421.09
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | TAB010002E | REV NEPCO ACCUAL | 99000 | ENGR | 1/31/2000 | -3787643
[12 empty] | Text93: | -3787643
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BRIMHALL DELIVERY SERVICE | 75119 | REFURBISHM'T/TRANSPT | 90000 | FRGT | 1/31/2000 | 1356
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BRIMHALL DELIVERY SERVICE | 75117 | REFURBISHM'T/TRANSPT | 90000 | FRGT | 1/31/2000 | 1356
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BRIMHALL DELIVERY SERVICE | 73396 | REFURBISHM'T/TRANSPT | 90000 | FRGT | 1/31/2000 | 1069.5
[12 empty] | Text93: | 3781.5
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AWU10003H |  | 99000 | IDCS | 1/31/2000 | 305886.21
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AW010002G |  | 99000 | IDCS | 1/31/2000 | -199260.36
[12 empty] | Text93: | 106625.85
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KILPATRICK STOCKTON LLP | WT010700 | LAND PURCHASE | 90000 | LAND | 1/31/2000 | 156476.52
[12 empty] | Text93: | 156476.52
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KILPATRICK STOCKTON LLP | 10348727 | DOYLE LEGAL EXPENSE | 99000 | LEGL | 1/31/2000 | 3255.75
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KING & SPALDING | 133624 | DOYLE LEGAL EXPENSE | 99000 | LEGL | 1/31/2000 | 2036.4
[12 empty] | Text93: | 5292.15
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | JAR 030003B | WALTON EMC MONORE | 99000 | OTHR | 1/31/2000 | -14500000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | JAR 030003B | WALTON EMC MONROE | 99000 | OTHR | 1/31/2000 | -9000000
[12 empty] | Text93: | -23500000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | MONROE WATER,LIGHT,& GAS COMM. | ENA |  | 99000 | OVHD | 1/31/2000 | 160750
[12 empty] | Text93: | 160750
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | SPEARS,R CLAY | EXP012700 | MEALS | 99000 | TRVL | 1/31/2000 | 588.63
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | SPEARS,R CLAY | EXP012700 | TRLV/ATL-DOYLEPORJE | 99000 | TRVL | 1/31/2000 | 1960.12
[12 empty] | Text93: | 2548.75
[12 empty] | Text98: | -26831720.9
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | G.L.C. CONSULTING SERVICE | 16 | REF CONTRACT MGMT | 99000 | COSU | 2/1/2000 | 22912.59
[12 empty] | Text93: | 22912.59
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | JOHN L. WORTHAM & SON, LLP | 402485 | DOYLE CONST | 99000 | CRED | 2/1/2000 | 407787
[12 empty] | Text93: | 407787
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | WT021700 | 3643 | 99000 | CSUP | 2/1/2000 | 27313.69
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | WT020400 | I-1043-00 | 99000 | CSUP | 2/1/2000 | 27013.53
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | WT020400 | I-1055-00 | 99000 | CSUP | 2/1/2000 | 139615.51
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | WT020400 | I-1037-99 | 99000 | CSUP | 2/1/2000 | 76991.62
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | WT020400 | I-1049-00 | 99000 | CSUP | 2/1/2000 | 21839.9
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | WT020400 | I-1047-00 | 99000 | CSUP | 2/1/2000 | 50000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | TURBINE TECHNOLOGY SERVICES | 2991 | REFURBISH | 99000 | CSUP | 2/1/2000 | 3680
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | WT021700 | 3639 | 99000 | CSUP | 2/1/2000 | 6000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | S9P732-2 | R0000002801-3 | 99000 | CSUP | 2/1/2000 | 88371.43
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | WT021700 | 3642 | 99000 | CSUP | 2/1/2000 | 26390.01
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | WT021700 | 3645 | 99000 | CSUP | 2/1/2000 | 3526.51
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | WT021700 | 3644 | 99000 | CSUP | 2/1/2000 | 20139.65
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | WT021700 | 3646 | 99000 | CSUP | 2/1/2000 | 7781.75
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | WT020400 | INV I-1036-99 | 99000 | CSUP | 2/1/2000 | 105000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | WT021700 | 3648 | 99000 | CSUP | 2/1/2000 | 22018.36
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0063-MS | PRJ-00-0063-MS | 99000 | CSUP | 2/1/2000 | 900
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0063-MS | PRJ-00-0056-MS | 99000 | CSUP | 2/1/2000 | 324436
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0063-MS | PRJ-00-0057-MS | 99000 | CSUP | 2/1/2000 | 1415
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0063-MS | PRJ-00-0058-MS | 99000 | CSUP | 2/1/2000 | 750
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | WT021700 | 3640 | 99000 | CSUP | 2/1/2000 | 2663.19
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | S9P732-2 | S9P33-02 | 99000 | CSUP | 2/1/2000 | 104388.35
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | S9P732-2 | P9P553-0699 | 99000 | CSUP | 2/1/2000 | 136622.33
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | S9P732-2 | R00002802-3 | 99000 | CSUP | 2/1/2000 | 26674.37
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | TS99232 | TS99209 | 99000 | CSUP | 2/1/2000 | 156450
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | S9P732-2 | R00002803-3 | 99000 | CSUP | 2/1/2000 | 8383.51
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | S9P732-2 | S9P732-2 | 99000 | CSUP | 2/1/2000 | 88371.43
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0065MS | TRANSP | 99000 | CSUP | 2/1/2000 | 750
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0061-MS | TRANSP | 99000 | CSUP | 2/1/2000 | 3685
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0064-MS | TRANSP | 99000 | CSUP | 2/1/2000 | 750
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | S9P732-2 | S9P34-2 | 99000 | CSUP | 2/1/2000 | 12449.27
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | WT021700 | 3647 | 99000 | CSUP | 2/1/2000 | 32599.83
[12 empty] | Text93: | 1526970.24
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | WT020400 | I-1055-00 | 90000 | FRGT | 2/1/2000 | 5374.81
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | WT020400 | O&M MOBILIZATION | 90000 | FRGT | 2/1/2000 | 64112
[12 empty] | Text93: | 69486.81
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | TS99298 | LABOR TO INSTALL | 99000 | INST | 2/1/2000 | 36000
[12 empty] | Text93: | 36000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | TS99232 | AD567 | 90000 | MJEQ | 2/1/2000 | 228318.3
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T&D COMPANY INC | 390603 | 230KV BREAKERS | 90000 | MJEQ | 2/1/2000 | 172232.1
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GENERAL ELECTRIC COMPANY | N01G5474 | GE TURBINES | 90000 | MJEQ | 2/1/2000 | 1632000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | TS99232 | AD626 | 90000 | MJEQ | 2/1/2000 | 152212.2
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | TS99232 | AD568 | 90000 | MJEQ | 2/1/2000 | 456636.6
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | TS99232 | AD566 | 90000 | MJEQ | 2/1/2000 | 76106.1
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | TS99232 | AD569 | 90000 | MJEQ | 2/1/2000 | 456636.6
[12 empty] | Text93: | 3174141.9
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | TS99232 | TS99232 | 90000 | PRTS | 2/1/2000 | 53400
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1052-00 | DOYLE REFURB PARTS | 90000 | PRTS | 2/1/2000 | 45737.22
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | WT020400 | I-1051-00 | 90000 | PRTS | 2/1/2000 | 323039.5
[12 empty] | Text93: | 422176.72
[12 empty] | Text98: | 5659475.26
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | JACOBY,BEN F. | EXP021100 | TRVL-CA-HOU-TN | 99000 | TRVL | 2/28/2000 | 3454.11
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | JACOBY,BEN F. | EXP021100 |  | 99000 | TRVL | 2/28/2000 | 169.3
[12 empty] | Text93: | 3623.41
[12 empty] | Text98: | 3623.41
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENVIRONMENTAL CONSULTING & | 145 | DOYLE PERMITTING | 99000 | COSU | 2/29/2000 | 2248.74
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | NEEL-SCHAFFER INC | 912322 | DOYLE DEVEL. EXP. | 99000 | COSU | 2/29/2000 | 2462.22
[12 empty] | Text93: | 4710.96
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | MIKE NELSON CONTRACTORS, INC | SPEARS NELSON | IUKA SITE PREP | 99000 | CSUP | 2/29/2000 | 2500
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | 00000JR80-10006{ | Doyle Refund | 99000 | CSUP | 2/29/2000 | -780
[12 empty] | Text93: | 1720
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | TAB050006G | ACCRUE 2/00 NEPCO | 99000 | ENGR | 2/29/2000 | 3927276
[12 empty] | Text93: | 3927276
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | TISHOMINGO RAILROAD CO., INC. | 99-349 | DOYLE REFURB-TURBINE | 90000 | FRGT | 2/29/2000 | 1600
[12 empty] | Text93: | 1600
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | 00000JR61-10006{ | Walton EMC Monroe | 99000 | OTHR | 2/29/2000 | -9577967.64
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | 00000JR79-10006{ | Walton-A.Wu | 99000 | OTHR | 2/29/2000 | -58847040.04
[12 empty] | Text93: | -68425007.68
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AWU010005I |  | 90000 | TMAT | 2/29/2000 | 5000000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AWU040006F | LEC BURNER-POWER SPA | 90000 | TMAT | 2/29/2000 | -170181
[12 empty] | Text93: | 4829819
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GARRETT,BRYAN | EXP022200 | GA-DOYLE PROJECT | 99000 | TRVL | 2/29/2000 | 858.45
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | SPEARS,R CLAY | EXP020300 | TRVL/TRVL/GA-DOYLEPR | 99000 | TRVL | 2/29/2000 | 886.67
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | SPEARS,R CLAY | EXP020300 | MEALS | 99000 | TRVL | 2/29/2000 | 25.32
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | JACOBY,BEN F. | EXP012800 | MEALS | 99000 | TRVL | 2/29/2000 | 421.55
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | JACOBY,BEN F. | EXP012800 | TRVL-CA-HOU-MA | 99000 | TRVL | 2/29/2000 | 3436.57
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GARRETT,BRYAN | EXP022200 | MEALS | 99000 | TRVL | 2/29/2000 | 149.62
[12 empty] | Text93: | 5778.18
[12 empty] | Text98: | -59654103.54
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | G.L.C. CONSULTING SERVICE | 17 | DEVELOPMENT | 99000 | COSU | 3/1/2000 | 41788.38
[12 empty] | Text93: | 41788.38
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | JOHN L. WORTHAM & SON, LLP | 404007 | LUKA TRANSP | 99000 | CRED | 3/1/2000 | 70000
[12 empty] | Text93: | 70000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1052-00A | BAL DUE FROM PREVBAL | 99000 | CSUP | 3/1/2000 | 25000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0060-MS | DOYLE REFURB TRANSP | 99000 | CSUP | 3/1/2000 | 3685
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0053-MS | DOYLE REFURB TRANSP | 99000 | CSUP | 3/1/2000 | 750
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1054-00 | DOYLE REFURB | 99000 | CSUP | 3/1/2000 | 227108.35
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | 3641 | DOYLE REFURB | 99000 | CSUP | 3/1/2000 | 8529.09
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1062-00 | DOYLE REFURB | 99000 | CSUP | 3/1/2000 | 81517.1
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1058-00 | PROJECT EXPENSES | 99000 | CSUP | 3/1/2000 | 182928.4
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1066-00 | DOYLE REFURB | 99000 | CSUP | 3/1/2000 | 35488.88
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1067-00 | DOYLE REFURB | 99000 | CSUP | 3/1/2000 | 15561.65
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1061-00 | DOYLE REFURB | 99000 | CSUP | 3/1/2000 | 100000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1068-00 | DOYLE REFURB | 99000 | CSUP | 3/1/2000 | 208451.79
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1060-00 | DOYLE REFURB | 99000 | CSUP | 3/1/2000 | 925
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | RTA02072000 | DOYLE REFURB | 99000 | CSUP | 3/1/2000 | 98995.6
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1057-00 | DOYLE REFURB | 99000 | CSUP | 3/1/2000 | 139019.7
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1063-00 | DOYLE REFURB | 99000 | CSUP | 3/1/2000 | 90000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | TURBINE TECHNOLOGY SERVICES | 2920 | DOYLE TTS | 99000 | CSUP | 3/1/2000 | 545437.8
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1064-00 | DOYLE REFURB | 99000 | CSUP | 3/1/2000 | 16218
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | 32 | DOYLE REFURB | 99000 | CSUP | 3/1/2000 | 135000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | 31 | DOYLE REFURB | 99000 | CSUP | 3/1/2000 | 45811.72
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1070-00 | DOYLE PSSPC | 99000 | CSUP | 3/1/2000 | 95528.39
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | 36 | DOYLE REFURB | 99000 | CSUP | 3/1/2000 | 42682.61
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | 13100 | NEW ALBANY | 99000 | CSUP | 3/1/2000 | 2603
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | JOHN L. WORTHAM & SON, LLP | 399487399491 | 399487 | 99000 | CSUP | 3/1/2000 | 19206.15
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | R00002801-3- | R000028013 | 99000 | CSUP | 3/1/2000 | 88371.43
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | 41 | INV 41 | 99000 | CSUP | 3/1/2000 | 3337.77
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | R00002801-3- | R00002802-04 | 99000 | CSUP | 3/1/2000 | -25877.58
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BENCHMARK TRANSPORTATION | PRJ-00-0059-MS | DOYLE REFURB | 99000 | CSUP | 3/1/2000 | 2700
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | R00002801-3- | R00002802-04 | 99000 | CSUP | 3/1/2000 | 10677.58
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1056-00 | DOYLE REFURB | 99000 | CSUP | 3/1/2000 | 29554.93
[12 empty] | Text93: | 2229212.36
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GENERAL ELECTRIC CO #05 | N01G5726 | TURBINE GENERATORS | 90000 | MJEQ | 3/1/2000 | 3400000
[12 empty] | Text93: | 3400000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | 42 | DOYLE REFURB | 90000 | OPER | 3/1/2000 | 22927
[12 empty] | Text93: | 22927
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GENERAL ELECTRIC COMPANY | N01G5668 | GE TURBINES | 90000 | TMAT | 3/1/2000 | 3400000
[12 empty] | Text93: | 3400000
[12 empty] | Text98: | 9163927.74
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | NEEL-SCHAFFER INC | 913880 | DOYLE PERMITTING | 99000 | CSUP | 3/31/2000 | 931.7
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | JR 1670009H | POWER SYSTEM MFG. | 99000 | CSUP | 3/31/2000 | -45811.72
[12 empty] | Text93: | -44880.02
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | 030723000250009A | ACCRUE 2/00 NEPCO | 99000 | ENGR | 3/31/2000 | -3927276
[12 empty] | Text93: | -3927276
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BRACEWELL & PATTERSON, L.L.P. | 21047482 | OPC EXPENSE | 99000 | ENVR | 3/31/2000 | 18563.75
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BRACEWELL & PATTERSON, L.L.P. | 2326.003 | OPC EXPENSE | 99000 | ENVR | 3/31/2000 | 5425
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENVIRONMENTAL CONSULTING & | 506 | DOYLE PERMITTING FEE | 99000 | ENVR | 3/31/2000 | 119
[12 empty] | Text93: | 24107.75
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AWU010009E |  | 99000 | IDCS | 3/31/2000 | -155521.1
[12 empty] | Text93: | -155521.1
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KING & SPALDING | 135705 | DOYLE LEGAL EXPENSE | 99000 | LEGL | 3/31/2000 | 15743.99
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | COMPTON & ASSOCIATES,LLP | 526 | DOYLE DEVELOPMENT EX | 99000 | LEGL | 3/31/2000 | 525
[12 empty] | Text93: | 16268.99
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | JR 1670009H | WALTON EMC MONROE | 99000 | OTHR | 3/31/2000 | -6078260
[12 empty] | Text93: | -6078260
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AWU10010A |  | 90000 | TMAT | 3/31/2000 | -140807.71
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | 0000JR150-10009A | Walton EMC | 90000 | TMAT | 3/31/2000 | -4527053
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AWU20010A |  | 90000 | TMAT | 3/31/2000 | -53400
[12 empty] | Text93: | -4721260.71
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | JACOBY,BEN F. | EXP031000 | MEALS | 99000 | TRVL | 3/31/2000 | 465.81
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | JACOBY,BEN F. | EXP031000 | CAB FARE | 99000 | TRVL | 3/31/2000 | 1919.12
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | JACOBY,BEN F. | EXP031000 | CHANGE FEE | 99000 | TRVL | 3/31/2000 | 221.24
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | SPEARS,R CLAY | EXP022500 | MEALS-TRVL-GA-HOU | 99000 | TRVL | 3/31/2000 | 1078.7
[12 empty] | Text93: | 3684.87
[12 empty] | Text98: | -14883136.22
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | 51 | DOYLE REFURB | 99000 | CSUP | 4/1/2000 | 3204
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | R00002803-5 | SWITCHUPGRADE | 99000 | CSUP | 4/1/2000 | 6880.61
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | R00002802-5 | EECC REFUB MGMT | 99000 | CSUP | 4/1/2000 | -13990.39
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | R00002801-5 | DOYLE EECC FIX O/H | 99000 | CSUP | 4/1/2000 | 88371.43
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1071-00 | DOYLE REFURB | 99000 | CSUP | 4/1/2000 | 30855.72
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | NATIONAL ENERGY PRODUCTION | 99006R | NEPCO REIMB COST | 99000 | CSUP | 4/1/2000 | 3769589
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | NATIONAL ENERGY PRODUCTION | 99006L | NEPCO FIXED OVERHEAD | 99000 | CSUP | 4/1/2000 | 157687
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | R00002801-6 | CONST MGMT | 99000 | CSUP | 4/1/2000 | 88371.43
[12 empty] | Text93: | 4130968.8
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KILPATRICK STOCKTON LLP | 10348738 | DOYLE | 99000 | LEGL | 4/1/2000 | 1508.22
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KILPATRICK STOCKTON LLP | 10343143 | DOYLE | 99000 | LEGL | 4/1/2000 | 880.28
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KILPATRICK STOCKTON LLP | 10329737 | DOYLE LEGAL EXP | 99000 | LEGL | 4/1/2000 | 10253.1
[12 empty] | Text93: | 12641.6
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GENERAL ELECTRIC COMPANY | N01G5727 | GENERATOR PMT | 90000 | MJEQ | 4/1/2000 | 680000
[12 empty] | Text93: | 680000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | 0002-05494 | DOYLE | 90000 | TMAT | 4/1/2000 | 7658.8
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | AD660 | DOYLE | 90000 | TMAT | 4/1/2000 | 3829.4
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | AD664 | DOYLE | 90000 | TMAT | 4/1/2000 | 7658.8
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | AD662 | DOYLE | 90000 | TMAT | 4/1/2000 | 22976.4
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | AD663 | DOYLE | 90000 | TMAT | 4/1/2000 | 22976.4
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | AD661 | DOYLE | 90000 | TMAT | 4/1/2000 | 11488.2
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | 0003-05671 | DOYLE | 90000 | TMAT | 4/1/2000 | 57410.49
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | 0001-04897 | DOYLE | 90000 | TMAT | 4/1/2000 | 152212.2
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | 0001-04896 | DOYLE | 90000 | TMAT | 4/1/2000 | 112540
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | GENERAL ELECTRIC COMPANY | N01G5669 | GE TURBINES | 90000 | TMAT | 4/1/2000 | 680000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | TS00019 | INV TS00019 | 90000 | TMAT | 4/1/2000 | 18000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | AD742 | DOYLE | 90000 | TMAT | 4/1/2000 | 57410.65
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | AD717 | DOYLE | 90000 | TMAT | 4/1/2000 | 172231.95
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | AD716 | DOYLE | 90000 | TMAT | 4/1/2000 | 28705.28
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | AD715 | DOYLE | 90000 | TMAT | 4/1/2000 | 28705.33
[12 empty] | Text93: | 1383803.9
[12 empty] | Text98: | 6207414.3
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | G.L.C. CONSULTING SERVICE | 18 | DEVELOPMENT | 99000 | COSU | 4/30/2000 | 55874.52
[12 empty] | Text93: | 55874.52
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | WT041000 | INV48 | 99000 | CSUP | 4/30/2000 | 1389
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | WT041000 | INV53 | 99000 | CSUP | 4/30/2000 | 15064
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | WT041000 | INV49 | 99000 | CSUP | 4/30/2000 | 8874.49
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | WT041000 | INV50 | 99000 | CSUP | 4/30/2000 | 8517.35
[12 empty] | Text93: | 33844.84
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | TAB180012F | OGLETHORPE CORR | 10300 | MECH | 4/30/2000 | -5479320
[12 empty] | Text93: | -5479320
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | VIRGO,ROBERT | EXP042500 | MEALS | 99000 | OTHR | 4/30/2000 | 70
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | KILPATRICK STOCKTON LLP | WT042500 | LAND OPTION EXT | 99000 | OTHR | 4/30/2000 | 16000
[12 empty] | Text93: | 16070
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AWU10012A |  | 99000 | PMAN | 4/30/2000 | 32211.37
[12 empty] | Text93: | 32211.37
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | JR 2100012E | WALTON CASH | 90000 | TMAT | 4/30/2000 | -6203713.05
[12 empty] | Text93: | -6203713.05
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | TAB050012C | RCLSS TRVL 2/00 | 99000 | TRVL | 4/30/2000 | -3858.12
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | TAB050012C | RCLSS TRVL 3/00 | 99000 | TRVL | 4/30/2000 | -2606.17
[12 empty] | Text93: | -6464.29
[12 empty] | Text98: | -11551496.61
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | R0002801-7 | R00002803-7 | 99000 | CSUP | 5/1/2000 | 5789.49
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | NATIONAL ENERGY PRODUCTION | 99008R,99008L | 99008L | 99000 | CSUP | 5/1/2000 | 157687
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | NATIONAL ENERGY PRODUCTION | 99008R,99008L | 99008R | 99000 | CSUP | 5/1/2000 | 1724478
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1045-00 | DOYLE | 99000 | CSUP | 5/1/2000 | 5136
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | H & M INDUSTRIAL SERVICES, INC | 1 | DOYLE REFURB | 99000 | CSUP | 5/1/2000 | 112179.6
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | 5557 | 55 | 99000 | CSUP | 5/1/2000 | 9587.59
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS MFG., LLC | 5557 | 57 | 99000 | CSUP | 5/1/2000 | 269792
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | R0002801-7 | R0002802-7 | 99000 | CSUP | 5/1/2000 | 9859.71
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1074-00 | SVCS | 99000 | CSUP | 5/1/2000 | 248327
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1075-00 | SVCS | 99000 | CSUP | 5/1/2000 | 67119.2
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | POWER SYSTEMS SPC, INC. | I-1076-00 | SVCS | 99000 | CSUP | 5/1/2000 | 521129.48
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | R0002801-7 | R0002801-7 | 99000 | CSUP | 5/1/2000 | 88371.43
[12 empty] | Text93: | 3219456.5
[12 empty] | Text98: | 3219456.5
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | G.L.C. CONSULTING SERVICE | 19 | DEVELOPMENT | 99000 | COSU | 5/31/2000 | 41048.95
[12 empty] | Text93: | 41048.95
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | WT051900 | INVR00002803-6 | 99000 | CSUP | 5/31/2000 | 4851.98
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ENRON ENGINEERING & | WT051900 | INV R00002802-6 | 99000 | CSUP | 5/31/2000 | 50693.68
[12 empty] | Text93: | 55545.66
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | THE WALTON TRIBUNE | 922737 | DOYLE ENVIRONMENTAL | 99000 | ENVR | 5/31/2000 | 20
[12 empty] | Text93: | 20
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | BRACEWELL & PATTERSON, L.L.P. | 21050311 | FERC APPLICATION | 99000 | LEGE | 5/31/2000 | 4231.25
[12 empty] | Text93: | 4231.25
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA |  | AW010014F |  | 90000 | MATL | 5/31/2000 | -15000
[12 empty] | Text93: | -15000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | ABB POWER T & D COMPANY | TS00022 | DOYLE-OPC | 90000 | MJEQ | 5/31/2000 | 72000
[12 empty] | Text93: | 72000
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | VIRGO,ROBERT | EXP050400 | MEALS | 99000 | TRVL | 5/31/2000 | 199.9
|  |  |  | S80015 | WALTON (PROJECT DOYLE ) - GA | VIRGO,ROBERT | EXP050400 | TRVL/TAMPA-DOYLESITE | 99000 | TRVL | 5/31/2000 | 1730.09
[12 empty] | Text93: | 1929.99
[12 empty] | Text98: | 159775.85

## Draw Sche
Enron Capital & Trade Services
Business Analysis & Reporting
Power Plants - Doyle |  |  | 342
[11 empty] | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  |  |  | Anticipated |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Estimate |  | Estimate |  | Estimate
|  |  | ENA |  | ENA |  | Increase / |  | Actuals to Date |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | Actuals to Date |  | Increase / |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  |  |  | Estimate |  | Actuals Plus |  | (Over)/Under
|  |  | Control Budget |  | Current Estimate |  | (Decrease) |  | 12/31/98 |  | 01/31/99 |  | 02/28/99 |  | 03/31/99 |  | 04/30/99 |  | 05/31/99 |  | 06/30/99 |  | 07/31/99 |  | 08/31/99 |  | 09/30/99 |  | 10/31/99 |  | 11/30/99 |  | 12/31/99 |  | Total Project |  | (Savings) |  | 2000-01-31 |  | 2000-02-29 |  | 2000-03-31 |  | 2000-04-30 |  | 2000-05-31 |  | 2000-06-30 |  | 2000-07-31 |  | 2000-08-31 |  | Total Project |  | To Complete |  | Est. to Complete |  | Budget |  | Comments
|  |  | as of 07/12/99 |  | as of 12/28/00 | [25 empty] | as of 02/11/00 |  | as of 02/11/00 |  | as of 12/31/99 |  | as of 02/11/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 12/28/00 |  | as of 08/31/00
MAJOR EQUIPMENT
| TURBINE UNITS, Purchase - GE 7B's (3) | Kepco | 23437881 |  | 23437881 |  | 0 |  | 21150000 |  | 2196801.3 |  | 0 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23437881.3 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 23437881.3 |  | 0 |  | 23437881.3 |  | -0.3
| TURBINE UNITS, Disassemble | IBC | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| TURBINE UNITS, Freight | IBC | 2340538.83 |  | 2340538.83 |  | 0 |  | 0 |  | 2067105.18 |  | 0 |  | 0 |  | 0 |  | 0 |  | 273433.65 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2340538.83 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 2340538.83 |  | 0 |  | 2340538.83 |  | 0
| TURBINE REFURBISHMENT | PS | 16047731 |  | 19979482 |  | 3931751 | [11 empty] | 2257866.41 |  | 256779.49 |  | -432926.73 |  | 1119216.99 |  | 907081.96 |  | 3742746.99 |  | 1639068 |  | 3008621.29 |  | 11254001.6 |  |  |  | 2139491 |  | 1346842.89 |  | 1992348.5 |  | 67904.56 |  | 1233270.87 |  | 1286793 |  | 325000 |  | 0 | 0 | 19645652.42 |  | 0 |  | 19645652.42 |  | -3597921.42
| UNIT 1 REPAIR |  | 0 |  | 6488243.8 |  | 6488243.8 | [27 empty] | 0 | [7 empty] | 0 |  | 0 |  | 0 |  | 3500000 | [5 empty] | 3500000
| INSURANCE |  | 0 |  | -5000000 |  | -5000000 | [27 empty] | 0 | [7 empty] | 0 |  | 0 |  | 0 |  | -3248000 | [5 empty] | -3248000
| LEC Burners | PS | 4408479 |  | 4408479 |  | 0 |  | 0 |  | 0 |  | 3055146.4 |  | 0 |  | 2444117 |  | 0 |  | 0 |  | -1531631.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4578660.5 |  | 0 |  | 0 |  | -170181 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4408479.5 |  | 0 |  | 4408479.5 |  | -0.5
| TURBINE UNITS, Purchase - GE 7EA's (2) | GE | 32172000 |  | 32516180 |  | 344180 |  | 0 |  | 0 |  | 0 |  | 1650000 |  | 370000 |  | 2132000 |  | 2132000 |  | 2132000 |  | 2132000 |  | 2132000 |  | 2132000 |  | 3764000 |  | 532622 |  | 20308622 |  | 0 |  | 1632000 |  | 1632000 |  | 6800000 |  | 1360000 |  | 400000 |  | 439378 |  | 0 |  | 0 | 0 | 32572000 |  | 0 |  | 32572000 |  | -400000
| TURBINE UNITS, Scope Change - Evap Cooling | GE | 896000 |  | 896000 |  | 0 | [9 empty] | 0 | [17 empty] | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 298666.6667 |  | 298666.6667 |  | 298666.6667 | 0 | 896000 |  | 0 |  | 896000 |  | 0
| TURBINE UNITS, Scope Change - Exhause Stack | GE | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| ENA TURBINE COST Adder |  | 345000 |  | 0 |  | -345000 | [27 empty] | 0 | [7 empty] | 0 |  | 0 |  | 0 | [13 empty] | 345000
| Refurb & 7EA Contract Management |  | 500000 |  | 506020 |  | 6020 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 10132 |  | 52750 |  | 34278 |  | 21750.25 |  | 118910.25 |  | 0 |  | 20421.09 |  | 22912.59 |  | 41788.38 |  | 55874.52 |  | 41048.95 |  | 205064 |  | 0 |  | 0 |  | 506019.78 |  | 0.22 |  | 506020 |  | -6020
0
| Subtotal Major Equip |  | 80147629.83 |  | 85572824.63 |  | 5425194.8 |  | 21150000 |  | 4263906.48 |  | 3055146.4 |  | 1650000 |  | 2814117 |  | 4389866.41 |  | 2662213.14 |  | 167441.37 |  | 3251216.99 |  | 3049213.96 |  | 5927496.99 |  | 5437346 |  | 3562993.54 |  | 62038614.48 |  | 0 |  | 3791912.09 |  | 2831574.48 |  | 8834136.88 |  | 1483779.08 |  | 1674319.82 |  | 2481901.6667 |  | 623666.6667 |  | 298666.6667 | 0 | 84058571.83 |  | 0.22 |  | 83806572.05 |  | -3658942.22
| AUX TRANSFORMERS |  | 173702 |  | 173702 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 165430 |  | 0 |  | 165430 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 8272 |  | 0 |  | 0 |  | 0 | 0 | 173702 |  | 0 |  | 173702 |  | 0
| LOAD CENTER TRANSFORMERS |  | 79124 |  | 79124 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 75356 |  | 0 |  | 75356 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3768 |  | 0 |  | 0 |  | 0 | 0 | 79124 |  | 0 |  | 79124 |  | 0
| CIRCUIT BREAKERS |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [7 empty] | 0 |  | 0 | [17 empty] | 0 |  | 0 |  | 0 |  | 0
| TD OF I-ABB |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| FREIGHT - TRANSFORMERS |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| TRANSFORMER INSTALLATION |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| OFF LOAD CIRCUIT BREAKERS |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| MISC TVA REQUIREMENTS |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| REIMBURSEMENT to OPC for Substation |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
0
| Subtotal |  | 252826 |  | 252826 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 240786 |  | 0 |  | 240786 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 12040 |  | 0 |  | 0 |  | 0 | 0 | 252826 |  | 0 |  | 252826 |  | 0
| MAJOR EQUIPMENT |  | 80400455.83 |  | 85825650.63 |  | 5425194.8 |  | 21150000 |  | 4263906.48 |  | 3055146.4 |  | 1650000 |  | 2814117 |  | 4389866.41 |  | 2662213.14 |  | 167441.37 |  | 3251216.99 |  | 3049213.96 |  | 5927496.99 |  | 5678132 |  | 3562993.54 |  | 62279400.48 |  | 0 |  | 3791912.09 |  | 2831574.48 |  | 8834136.88 |  | 1483779.08 |  | 1686359.82 |  | 2481901.6667 |  | 623666.6667 |  | 298666.6667 | 0 | 84311397.83 |  | 0.22 |  | 84059398.05 |  | -3658942.22
EECC PROGRAM MGT
| CONSTRUCITON PROJECT MANAGEMENT |  | 896000 |  | 896000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 192000 |  | 192000 |  | 0 |  | 0 |  | 128000 |  | 115200 |  | 115180 |  | 115202 |  | 115203 |  | 115204 |  | 115204 |  | 895989 |  | 11 |  | 896000 |  | 0
| REFURB PROJECT MANAGEMENT |  | 596600 |  | 596600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 122468.05 |  | 122468.05 |  | 0 |  | 0 |  | 75417.18 |  | 79743 |  | 79743 |  | 79743 |  | 79743 |  | 79743 |  | 79743 |  | 596600.23 |  | 0 |  | 596600.23 |  | -0.23
| PRE NTP ENGINEERING |  | 136622 |  | 136622 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 136622.33 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 136622.33 |  | 0 |  | 136622.33 |  | -0.33
| FEES |  | 0 |  | 664550 |  | 664550 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 132910 |  | 132901 |  | 132912 |  | 132913 |  | 132914 |  | 132914 |  | 664550 |  | 0 |  | 664550 |  | 0
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [17 empty] | 0 |  | 0 |  | 0 |  | 0
| EECC PROGRAM MGT |  | 1582156 |  | 2538865 |  | 664550 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 314468.05 |  | 354690 |  | 0 |  | 0 |  | 360872 |  | 73171 |  | 169633 |  | 159566 |  | 671254 |  | 327871 |  | 176715 | 0 | 2293772 |  | 11 |  | 2293772.56 |  | -0.56
Engineering / General Provisions / Start-Up
| Equipment & Small Tools |  | 1321202 | 1296974 | 1321202 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 1975 |  | 5425 |  | 7400 |  |  |  | 113798 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 121198 |  | 1200004 |  | 1321202 |  | 0
| Field Staff |  | 1144865 | 1043067 | 1144865 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 52268 |  | 64981 |  | 117249 |  |  |  | 190587 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 307836 |  | 837029 |  | 1144865 |  | 0
| Temp Facilities & Indirect Support |  | 614691 | 603264 | 614691 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 3551 |  | 22528 |  | 26079 |  |  |  | 144496 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 170575 |  | 444116 |  | 614691 |  | 0
| Indirect Supplies |  | 388912 | 384400 | 388912 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 8394 |  | 8588 |  | 16982 |  |  |  | 91156 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 108138 |  | 280774 |  | 388912 |  | 0
| Payroll Burdens |  | 2989004 | 2876774 | 2989004 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 61847 |  | 179051 |  | 240898 |  |  |  | 472898 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 713796 |  | 2275208 |  | 2989004 |  | 0
| HO Project Management Support |  | 109057 | 109057 | 109057 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 37866 |  | 22737 |  | 60603 |  |  |  | 31040 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 91643 |  | 17414 |  | 109057 |  | 0
| Business Expenses |  | 611825 | 611825 | 611825 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 68325 |  | 51552 |  | 119877 |  |  |  | 72378 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 192255 |  | 419570 |  | 611825 |  | 0
| Field Non-Productive Labor |  | 74199 | 74199 | 74199 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 18554 |  | 12304 |  | 30858 |  |  |  | 31268 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 62126 |  | 12073 |  | 74199 |  | 0
| Indirect Engineering Labor |  | 120318 | 120318 | 120318 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 4681 |  | 71981 |  | 76662 |  |  |  | 22504 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 99166 |  | 21152 |  | 120318 |  | 0
| Direct Project Engineering |  | 361113 | 420103 | 361113 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 29018 |  | 37404 |  | 66422 |  |  |  | 145574 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 211996 |  | 149117 |  | 361113 |  | 0
| Freight & Taxes |  | 101715 | 101715 | 101715 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 5143 |  | 5143 |  |  |  | 25078 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 30221 |  | 71494 |  | 101715 |  | 0
| Vendor Reps |  | 49000 | 49000 | 49000 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 49000 |  | 49000 |  | 0
| Contingency |  | 7917 | 7917 | 7917 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | -12494 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | -12494 |  | 20411 |  | 7917 |  | 0
| Reserve |  | 458990 | 0 | 458990 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 458990 |  | 458990 |  | 0
| Subtotal Engineering / General Provisions/ Start -up |  | 8352808 |  | 8352808 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 286479 | 286479 | 481694 |  | 768173 | 0 | 0 | 0 | 1328283 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 2096456 |  | 6256352 | 0 | 8352808 | 0 | 0 | 0
[57 empty] | 0 |  | 0 |  | 0
Procurement | [56 empty] | 0 |  | 0 |  | 0
| Pipe, Valves, Specialties & Hangers |  | 235231 | 235231 | 235231 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 50961 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 50961 |  | 184270 |  | 235231 |  | 0
| Conduit, Tray & Wire ** |  | 418046 | 418046 | 418046 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 2923 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 2923 |  | 415123 |  | 418046 |  | 0
| Bus Duct |  | 320844 | 320844 | 320844 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 320844 |  | 320844 |  | 0
| Dry Transformers & Panels (net 30) |  | 16500 | 16500 | 16500 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 16500 |  | 16500 |  | 0
| Oil Filled Transformers (10%-90%) |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Motor Control Center |  | 136474 | 136474 | 136474 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 31518 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 31518 |  | 104956 |  | 136474 |  | 0
| Switchgear 5KV,480V |  | 234498 | 234498 | 234498 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 234498 |  | 234498 |  | 0
| Control Panels & Termination Box |  | 17558 | 17558 | 17558 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 17558 |  | 17558 |  | 0
| Electrical Devices |  | 3424 | 3424 | 3424 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 3424 |  | 3424 |  | 0
| Light Pole & Light Fixtures |  | 112525 | 112525 | 112525 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 43412 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 43412 |  | 69113 |  | 112525 |  | 0
| Electric Heat Trace & Test |  | 16483 | 16483 | 16483 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 16483 |  | 16483 |  | 0
| Special Systems |  | 159816 | 159816 | 159816 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 159816 |  | 159816 |  | 0
| Field Mounted Instruments |  | 84730 | 84730 | 84730 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 84730 |  | 84730 |  | 0
| Stack Monitoring (10% RD, 80% RE, 10%) |  | 420000 | 420000 | 420000 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 420000 |  | 420000 |  | 0
| Control Valves & Miscellaneous Equipment |  | 77100 | 77100 | 77100 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 77100 |  | 77100 |  | 0
| Tubing, Tray & Mounts |  | 13998 | 13998 | 13998 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 13998 |  | 13998 |  | 0
| DCS |  | 209400 | 209400 | 209400 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 44694 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 44694 |  | 164706 |  | 209400 |  | 0
| Pumps |  | 99002 | 99002 | 99002 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 99002 |  | 99002 |  | 0
| Aux. Equipment (90% 10%) 940120 |  | 68000 | 68000 | 68000 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 68000 |  | 68000 |  | 0
| Fuel Gas Filter NET 30 |  | 75000 | 75000 | 75000 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 75000 |  | 75000 |  | 0
| Pressure Reduce Station(AD10%, HT40%,S 40%, 10%) |  | 155000 | 155000 | 155000 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 155000 |  | 155000 |  | 0
| Minor Skid Mounted Systems |  | 32000 | 32000 | 32000 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 32000 |  | 32000 |  | 0
| Tanks-Non Pressurized |  | 51600 | 51600 | 51600 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 51600 |  | 51600 |  | 0
| Subtotal Procurement |  | 2957229 |  | 2957229 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 173508 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 173508 |  | 2783721 | 0 | 2957229 | 0 | 0 | 0
Site Preparation/Improvement
| Site Preparation/Improvement |  | 1061109 | 1061109 | 1061109 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 52531 |  | 52531 |  |  |  | 369238 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | 421769 |  | 639340 |  | 1061109 |  | 0
| Subtotal Site Preparation/Improvement |  | 1061109 |  | 1061109 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 52531 |  | 52531 | 0 | 0 | 0 | 369238 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | 421769 |  | 639340 | 0 | 1061109 | 0 | 0 | 0
Underground Electrical
| Labor |  | 198001 | 198001 | 198001 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 12469 |  | 12469 |  |  |  | 132074 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 144543 |  | 53458 |  | 198001 |  | 0
| Material |  | 385611 | 385611 | 385611 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 72441 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 72441 |  | 313170 |  | 385611 |  | 0
| Subcontract |  | 10000 | 10000 | 10000 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 10000 |  | 10000 |  | 0
| Subtotal Underground Electrical |  | 593612 |  | 593612 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 12469 |  | 12469 | 0 | 0 | 0 | 204515 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 216984 |  | 376628 | 0 | 593612 | 0 | 0 | 0
Underground Piping
| Labor |  | 226404 | 226404 | 226404 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 6680 |  | 6680 |  |  |  | 99113 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 105793 |  | 120611 |  | 226404 |  | 0
| Material |  | 221748 | 221748 | 221748 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 21779 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 21779 |  | 199969 |  | 221748 |  | 0
| Subcontract |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Subtotal Underground Piping |  | 448152 |  | 448152 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 6680 |  | 6680 | 0 | 0 | 0 | 120892 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 127572 |  | 320580 | 0 | 448152 | 0 | 0 | 0
Concrete
| Labor |  | 616436 | 616436 | 616436 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 34133 |  | 34133 |  |  |  | 317556 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 351689 |  | 264747 |  | 616436 |  | 0
| Material |  | 520255 | 520255 | 520255 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 284422 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 284422 |  | 235833 |  | 520255 |  | 0
| Subcontract |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Subtotal Concrete |  | 1136691 |  | 1136691 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 34133 |  | 34133 | 0 | 0 | 0 | 601978 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 636111 |  | 500580 | 0 | 1136691 | 0 | 0 | 0
Special Concrete
| Labor |  | 39766 | 39766 | 39766 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 2142 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 2142 |  | 37624 |  | 39766 |  | 0
| Material |  | 28687 | 28687 | 28687 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 1980 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 1980 |  | 26707 |  | 28687 |  | 0
| Subcontract |  | 68453 |  | 68453 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 4122 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 4122 |  | 64331 | 0 | 68453 | 0 | 0
Structural Steel
| Labor |  | 7089 | 7089 | 7089 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 7089 |  | 7089 |  | 0
| Material |  | 25200 | 25200 | 25200 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 25200 |  | 25200 |  | 0
| Subtotal Structure Steel |  | 32289 |  | 32289 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 32289 | 0 | 32289 | 0 | 0 | 0
Architectural |  |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
Buildings |  |  | 296640 | 296640 | 296640 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 88703 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 88703 |  | 207937 |  | 296640 |  | 0
Aboveground Piping
| Labor |  | 183985 | 171091 | 183985 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 129 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 129 |  | 183856 |  | 183985 |  | 0
| Subcontract |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Subtotal Aboveground Piping |  | 183985 |  | 183985 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 129 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 129 |  | 183856 | 0 | 183985 | 0 | 0 | 0
Aboveground Electrical
| Labor |  | 470919 | 437240 | 470919 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 3446 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 3446 |  | 467473 |  | 470919 |  | 0
| Subcontract |  | 80000 | 80000 | 80000 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 80000 |  | 80000 |  | 0
| Subtotal Aboveground Electrical |  | 550919 |  | 550919 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 3446 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 3446 |  | 547473 | 0 | 550919 | 0 | 0
Instrumentation |  |  | 295512 | 295512 | 295512 |  | 0 | -295512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 295512 |  | 295512 |  | 0
Insulation & Paint | [56 empty] | 0 |  | 0 |  | 0
| Labor |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Subcomtract |  | 399485 | 399485 | 399485 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 399485 |  | 399485 |  | 0
| Subtotal Insulation & Paint |  | 399485 |  | 399485 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 399485 | 0 | 399485 | 0 | 0 | 0
Mechanical Equipment
| Labor |  | 881025 | 858573 | 881025 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 31324 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 31324 |  | 849701 |  | 881025 |  | 0
| Subcontract |  | 941930 | 941930 | 941930 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 4633 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 4633 |  | 937297 |  | 941930 |  | 0
| Subtotal Mechanical Equipment |  | 1822955 |  | 1822955 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 35957 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 35957 |  | 1786998 | 0 | 1822955 | 0 | 0 | 0
Substation/Switchyard |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
Plant Startup
| Labor |  | 448332 | 448332 | 448332 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 26998 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 26998 |  | 421334 |  | 448332 |  | 0
| Material |  | 155150 | 155150 | 155150 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 1050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 1050 |  | 154100 |  | 155150 |  | 0
| Subcontract |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Subtotal Plant Startup |  | 603482 |  | 603482 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 28048 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 28048 |  | 575434 | 0 | 603482 | 0 | 0 | 0
| Total Project |  | 18803321 | 592152 | 18803321 | 0 | 0 | -295512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286479 | 286479 | 587507 | 0 | 873986 | 0 | 0 | 0 | 2958819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 11 | 3832805 | 0 | 14970516 | 0 | 18803321 | 0 | 0
Overhead Lump Sum |  |  | 2048928 |  | 2048928 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 302030 |  | 328718 |  | 630748 |  |  |  | 157687 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 788435 |  | 1260493 |  | 2048928 |  | 0
Fee |  |  | 1297298 |  | 1297298 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 1297298 |  | 1297298 |  | 0
Reimbursement from Genco |  |  | -230000 |  | -230000 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | -230000 |  | -230000 |  | 0
Contingency |  |  | 149109 | 777891 | 0 |  | -149109 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
Difference between NEPCO Billing and Actual Cost |  |  | 0 |  | 0 | [25 empty] | -1755 |  | 1579413 |  | 1577658 |  |  |  | 2166906 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 3744564 |  | -3744564 |  | 0 |  | 0
NEPCO |  |  | 22115722 | 1370043 | 26066481.96 | 0 | -149109 | -295512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586754 | 286479 | 2495638 | 0 | 3088751 | 0 | 0 | 0 | 5309025 | 0 | 0 | 0 | 0 |  | 3927276 | 0 | 1882165 | 0 | 4402242 | 0 | 467274 |  | 375703 | 11 | 22821307 | 0 |  | 0 | 22159961 | 0 |  | 0
| EECC & NEPCO SCOPE |  | 104098333.83 | 1370043 | 114430997.59 | 0 | 5940635.8 | -295512 | 21150000 | 0 | 4263906.48 | 0 | 3055146.4 | 0 | 1650000 | 0 | 2814117 | 0 | 4389866.41 | 0 | 2662213.14 | 0 | 167441.37 | 0 | 3251216.99 | 0 | 3049213.96 | 0 | 5927496.99 |  | 6264886 | 286479 | 6373099.59 |  | 65722841.48 | 0 | 0 | 0 | 9100937.09 |  | 3192446.48 |  | 8907307.88 |  | 5580688.08 |  | 3728090.82 |  | 7555397.6667 |  | 1418811.6667 |  | 851084.6667 | 11 | 109426476.83 |  | 11.22 | 0 | 108513131.61 | 0 | -3658942.78 | 0
| Reimbursement from Genco |  |  |  | -230000 | [43 empty] | -230000 | [5 empty] | -230000
| Saving from Transformer |  |  |  | -1205656 | [29 empty] | 1964470 | [5 empty] | 1787992 |  | -53400 |  | -4775516 |  | -129202 | [7 empty] | -1183424
SPARE PARTS |  |  | 1694670 | 0 | 0 |  | -1694670 |  | 0 |  | 0 |  | 0 |  | 5000 |  | 5000 |  | 5000 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 |  | 0 |  | 0
LAND ACQUISITION
| Land acquisition/option |  | 351920.32 |  | 351920.32 |  | 0 |  | 45000 |  | 0 |  | 0 |  | 0 |  | 16000 |  | 0 |  | 0 |  | 322565.77 |  | -156519.93 |  | 0 |  | 16000 | [5 empty] | 243045.84 |  | 0 |  | 156476.52 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 399522.36 |  | 0 |  | 399522.36 |  | -47602.04
| Other |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Other |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  | 0
0
| LAND ACQUISITION |  | 351920.32 |  | 409522 |  | 0 |  | 45000 |  | 0 |  | 0 |  | 0 |  | 16000 |  | 0 |  | 0 |  | 322565.77 |  | -156519.93 |  | 0 |  | 16000 |  | 0 |  | 0 |  | 243045.84 |  | 0 |  | 156476.52 |  | 0 |  | 0 |  | 0 |  |  |  | 10000 |  | 0 |  | 0 | 0 | 409522.36 |  | 0 |  | 399522.36 |  | -47602.04
ENVIRONMENTAL PERMITTING
| Permitting |  | 400000 |  | 76464 |  | -323536 |  | 0 |  | 0 |  |  |  | 7006.62 |  | 0 |  | 33128.17 |  | 0 |  | 0 |  | 969.25 |  | 0 |  | 1848.15 |  | 6327.25 |  | 2158 |  | 51437.44 |  | 0 |  | 26.24 |  | 0 |  | 25039 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 76502.68 |  | 0 |  | 76502.68 |  | -38.68
| Environmental Consulting Technologies |  | 0 |  | 51186 |  | 51186 |  | 0 |  | 0 |  | 3168.79 |  | 9937.5 |  | 0 |  | 10765.92 |  | 10111.38 |  | 0 |  | 12516.78 |  | 3179.36 |  | 0 |  | 0 |  | 1506.69 |  | 51186.42 |  | 0 |  | 0 |  | 2249 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 53435.42 |  | 0 |  | 53435.42 |  | -2249.42
| Other |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| ENVIRONMENTAL PERMITTING |  | 400000 |  | 105950 |  | -272350 |  | 0 |  | 0 |  | 3168.79 |  | 16944.12 |  | 0 |  | 43894.09 |  | 10111.38 |  | 0 |  | 13486.03 |  | 3179.36 |  | 1848.15 |  | 6327.25 |  | 3664.69 |  | 102623.86 |  | 0 |  | 26.24 |  | 2249 |  | 1051 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 105950.1 |  | 0 |  | 129938.1 |  | -2288.1
| Mobilization ( Net of Reimbursement ) | [33 empty] | 1425 | [5 empty] | 64112 |  | 0 |  | 0 |  | 0 | [7 empty] | 0
GAS INTERCONNECTION |  |  | 1000000 |  | 977990 |  | -22010 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 977990 |  | 0 |  | 0 |  | 977990 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 977990 |  | 0 |  | 977990 |  | 0
ELECTRICAL INTERCONNECTION | [6 empty] | 0 | [27 empty] | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| W.O. Cost |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
| O.H Cost (21.6%) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Facilities Study |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
| Other |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Subtotal Electrical Interconnection |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
SEWER LINE |  |  | 0 |  | -59123 |  | -59123 | [27 empty] | 0 |  |  |  | 160750 |  | -160750 |  | 0 |  | -59123 | [7 empty] | 0 | 0 | -59123 |  | 0 |  | -59123 |  | 0
SALES TAX ON EQUIPMENT |  |  | 250000 |  | 250000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 250000 |  | 0 | 0 | 250000 |  | 0 |  | 250000 |  | 0
INSURANCE DURING CONSTR |  |  | 400000 |  | 477787 |  | 77787 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 407787 |  | 70000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 477787 |  | 0 |  | 477787 |  | 0
START UP FUEL |  |  | 400000 |  | 0 |  | -400000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
CAPITALIZED SALARIES |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
INTEREST DURING CONSTRUCTION |  |  | 2964064 |  | 2327182.27 |  | -636881.73 |  | 176250 |  | 141763 |  | 159611 |  | 184622 |  | 187002 |  | 112135 |  | 226003 |  | 218114 |  | 230971 |  | 250137 |  | 268825 |  | 316229.18 |  | 360766 |  | 2832428.18 |  | 0 |  | 106625.85 |  | -419034 |  | -155521 |  | -59780 |  | 97886 |  | 0 |  | 0 |  | 0 | 0 | 2402605.03 |  | 0 |  | 2402605.03 |  | -75422.76
| Subtotal - CapX |  | 111558988.15 | 1370043 | 117484649.86 | 0 | 2933388.07 | -295512 | 21371250 | 0 | 4405669.48 | 0 | 3217926.19 | 0 | 1856566.12 | 0 | 3022119 | 0 | 4550895.5 | 0 | 2898327.52 | 0 | 708121.14 | 0 | 3339154.09 | 0 | 3302530.32 | 0 | 7192160.14 | 0 | 6587442.43 | 286479 | 6737530.28 | 0 | 71844824.36 | 0 | 0 | 0 | 9524815.7 | 0 | 4874802.48 | 0 | 8769437.88 | 0 | 686269.08 | 0 | 3696774.82 | 0 | 7335397.6667 | 0 | 1668811.6667 | 0 | 851084.6667 | 11 | 112577784.32 | 0 | 11.22 | 0 | 113091851.1 | 0 | -3784255.68 | 0 | 0
FINANCING FEE
| Bank fees |  | 0 |  | 0 |  | 0 | [27 empty] | 0 | [19 empty] | 0 |  | 0 |  | 0 |  | 0
| Escrow |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Legal Fees |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Insurance |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Other |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Subtotal Financing Fee |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
RESALE HANDLING FEES (.25%) |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
DEVELOPMENT EXPENSES
| Salaries |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Travel Expenses |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Deloitte & Touche |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Utility Consulting Services |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| HARC Development Service- Tom Young |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Engineering Assessment |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| ICF - Studies |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Maps |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Other |  | 375000 |  | 375000 |  | 0 |  | 1805.25 |  | 0 |  | 1397.02 |  | 4883.08 |  | 7430.27 |  | 15614.51 |  | 12657.16 |  | 20604.31 |  | 1219.95 |  | 3244.27 |  | 1324.73 |  | 4156.31 |  | 231655.07 |  | 305991.93 |  | 0 |  | 2548.75 |  | 11864 |  | 45998 |  | 8597.5 | [8 empty] | 0 | 375000.18 |  | 0 |  | 375000.18 |  | -0.18
DEVELOPMENT EXPENSE |  |  | 375000 |  | 328220 |  | 0 |  | 1805.25 |  | 0 |  | 1397.02 |  | 4883.08 |  | 7430.27 |  | 15614.51 |  | 12657.16 |  | 20604.31 |  | 1219.95 |  | 3244.27 |  | 1324.73 |  | 4156.31 |  | 231655.07 |  | 305991.93 |  | 0 |  | 2548.75 |  | 11864 |  | 4210 |  | -6394 |  | 1950 |  | 8049 |  | 1425 |  | 0 | 0 | 329644.68 |  | 0 |  | 375000.18 |  | -0.18
LEGAL EXPENSES | [34 empty] | 0 | [19 empty] | 0 |  | 0 |  | 0
| King, Spalding |  | 300000 |  | 300000 |  | 0 |  | 21898.53 |  | 6134.01 |  | 9917.44 |  | 0 |  | 0 |  | 43465.95 |  | 0 |  | 0 |  | 0 |  | 28510.25 |  | 0 |  | 104668 |  | 65033.33 |  | 279627.51 |  | 0 |  | 2036.4 |  | 0 |  | 15744 |  | 2592 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  |  | 300000 |  | 300000 |  | 0 |  | Included fees expensed on WO# E07A59
| Kilpatrick, Stockton |  | 150000 |  | 150000 |  | 0 |  | 31211.02 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2585.04 |  | 0 |  | 9442.62 |  | 2771.63 |  | 0 |  | 13549 |  | 59559.31 |  | 0 |  | 3255.75 |  | 0 |  | 0 |  | 14530.83 |  | 14530.83 |  | 14530.83 |  | 14530.83 |  | 29061.83 | 0 | 150000.21 |  | 0 |  | 150000.21 |  | -0.21 |  | Included fees expensed on WO# E07A59
| Other |  | 0 |  | 0 |  | 0 |  | 2705 |  |  |  | 934 | [5 empty] | 0 |  | -10271.2 | [7 empty] | 0 |  | 0 |  | 0 |  | -6632.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6632 | 0 |  |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| LEGAL EXPENSE |  | 450000 |  | 385319 |  | 0 |  | 55814.55 |  | 6134.01 |  | 10851.44 |  | 0 |  | 0 |  | 43465.95 |  | -10271.2 |  | 2585.04 |  | 0 |  | 37952.87 |  | 2771.63 |  | 104668 |  | 78582.33 |  | 332554.62 |  | 0 |  | 5292.15 |  | 0 |  | 39733 |  | 28642 |  | -19789 |  | 46138 |  |  |  |  | 0 | 392570.77 |  | 300000 |  | 450000.21 |  | -0.21
DEBT RESERVE |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
CONTINGENCY |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
WORKING CAPITAL |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Subtotal - Expense |  | 825000 |  | 713539 |  | 0 |  | 57619.8 |  | 6134.01 |  | 12248.46 |  | 4883.08 |  | 7430.27 |  | 59080.46 |  | 2385.96 |  | 23189.35 |  | 1219.95 |  | 41197.14 |  | 4096.36 |  | 108824.31 |  | 310237.4 |  | 638546.55 |  | 0 |  | 7840.9 |  | 11864 |  | 43943 |  | 22248 |  | -17839 |  | 54187 |  | 1425 |  | 0 | 0 | 762215.45 |  | 300000 |  | 825000.39 |  | -0.39
TOTAL DOYLE -- ENA |  |  | 112383988.15 |  | 118198188.86 |  | 2933388.07 |  | 21428869.8 |  | 4411803.49 |  | 3230174.65 |  | 1861449.2 |  | 3029549.27 |  | 4609975.96 |  | 2900713.48 |  | 731310.49 |  | 3340374.04 |  | 3343727.46 |  | 7196256.5 |  | 6696266.74 |  | 7047767.68 |  | 72483370.91 |  | 0 |  | 9532656.6 |  | 4886666.48 |  | 8813380.88 |  | 708517.08 |  | 3678935.82 |  | 7389584.6667 |  | 1670236.6667 |  | 851084.6667 | 11 | 113299999.77 |  | 300011.22 |  | 113916851.49 |  | -3784256.07
TARGET $$/MW |  |  | 328608.1525 |  | 345608.7394 | [53 empty] | 333090.209
Oglethorpe Payment | [34 empty] | 0 |  |  |  | -23500000 |  | -68405007.68 | [13 empty] | -91905007.68
OPC Deposit on Power Purchase Agreement | [20 empty] | -5000000 | [13 empty] | -5000000 | [19 empty] | -5000000
TOTAL DOYLE -- ENA ( Net of Payment Received ) |  |  | 112383988.15 | 0 | 118198188.86 | 0 | 2933388.07 | 0 | 21428869.8 | 0 | 4411803.49 | 0 | 3230174.65 | 0 | 1861449.2 | 0 | 3029549.27 | 0 | 4609975.96 | 0 | -2099286.52 | 0 | 731310.49 | 0 | 3340374.04 | 0 | 3343727.46 | 0 | 7196256.5 | 0 | 6696266.74 | 0 | 7047767.68 | 0 | 67483370.91 | 0 | 0 | 0 | -13967343.4 | 0 | -63518341.2 | 0 | 8813380.88 | 0 | 708517.08 | 0 | 3678935.82 | 0 | 7389584.6667 | 0 | 1670236.6667 |  | 851084.6667 | 11 | 16394992.09 | 0 | 300011.22 | 0 | 113916851.49 | 0 | -3784256.07
| ENA PDA -- Contract Amount |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
MOBILIZATION OF O&M
| Mobilization Fee | Mobilization Fee | 1128564 |  | 1128564 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  | 64112 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 64112 |  | 1064452 |  | 1128564 |  | 0
| EI Hourly Billing | EI Hourly billing | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1425 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1425 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 1425 |  | 0 |  | 1425 |  | -1425
| Other | Other | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| TOTAL MOBILIZATION OF O&M |  | 1128564 | 0 | 1128564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1425 | 0 | 0 | 0 | 0 |  | 64112 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 65537 |  | 1063027 | 0 | 1128564 | 0 | -1425
Subtotal Mobilization of O&M
INTEREST DURING CONSTRUCTION TO WALTON |  |  | 3921610 | 0 | 3921610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 3921610 |  | 3921610 |  | 0
OPC - SUBSTATION REIMBURSEMENT |  |  | 2000000 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 206888.81 |  | 206888.81 |  |  |  | 0 |  | 20832.78 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 227721.59 |  | 1772278.41 |  | 2000000 |  | 0
POWER TRANSFORMERS / OPC |  |  | 0 |  | 5800000 |  | 5800000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 57410.7 |  | 1073726 |  | 173025.67 |  | 1304162.37 |  | 0 |  | 25613 |  | 1787991.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 3117767.27 |  | 2682232.73 |  | 5800000 |  | 0
OPC REIMBURSEMENT FOR TRANSFORMERS |  |  | 0 |  | -5800000 |  | -5800000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | -5800000 |  | -5800000 |  | 0
TOTAL DOYLE |  |  | 119434162.15 | 0 | 125248362.86 | 0 | 2933388.07 | 0 | 21428869.8 | 0 | 4411803.49 | 0 | 3230174.65 | 0 | 1861449.2 | 0 | 3030974.27 | 0 | 4609975.96 | 0 | -2099286.52 | 0 | 731310.49 | 0 | 3340374.04 | 0 | 3343727.46 | 0 | 7253667.2 | 0 | 7769992.74 | 0 | 7427682.16 | 0 | 68995847.09 | 0 | 0 | 0 | -13941730.4 | 0 | -61645404.52 | 0 | 8813380.88 | 0 | 708517.08 | 0 | 3678935.82 | 0 | 7389584.6667 | 0 | 1670236.6667 |  | 851084.6667 | 11 | 19806017.95 | 0 | 3939159.36 | 0 | 120967025.49 | 0 | -3785681.07 | 0
TOTAL DOYLE EXPENSE --- ENA |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| ENA Output Bonus |  | 0 |  | -1725000 | [29 empty] | 0 | [17 empty] | 0 |  | -1725000 |  | -1725000 |  | 1725000
TOTAL DOYLE -- ENA |  |  | 112383988.15 |  | 116473188.86 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -1725000 |  | -1725000 |  | 1725000
Note on Y12: Lindsay Long: IBC Turbo invoices Warehouse 56,200, security - 10,121, other is reclass of amounts not belonging to Doyle.
Note on Y15: Lindsay Long: Doyle originally charged for all LEC burners. This amount to reclass excess over 3 LEC burners.
Note on Q16: Lindsay Long: Net of $2,850,000 and (1,200,000)= 1,650,000. $2.8MM was refunded 4/99.
Note on B71: nepco: 10% delivery 90% 30days
Note on K246: Lindsay Long: Includes $21,899 expensed on E07A59.
Note on M246: Lindsay Long: Expensed on WO# E07A59.
Note on O246: Lindsay Long: Expensed on WO# E07A59.
Note on U246: Lindsay Long: Expensed on WO# E07A59.
Note on K247: Lindsay Long: Includes $2,485 expensed on E07A59.
Note on W248: Lindsay Long: Reverse Ogden, Newell legal costs not belonging to Doyle.
Note on B284: awu3: Include Substation/Switchyard from Nepco Billing

## Non_WO_costs
Doyle I Project
Legal fees charged to Work Order # E07A59
1998 and 1999
|  |  | Invoice | Amount
1998 |  | Date | #
| King & Spalding | 1998-10-16 | 107043 | 14520.32
| King & Spalding | 1998-12-01 | 110023 | 7378.21
21898.53
| Kilpatrick & Stockton | 1998-10-20 | 10273443 | 1704.5
| Kilpatrick & Stockton | 1998-11-20 | 10280035 | 780.46
2484.96
|  | Total 1998 Legal fees |  | 24383.49
1999
| King & Spalding | 1999-01-26 | 113636 | 6134.01
| King & Spalding | 1999-02-09 | 114283 | 9917.44
| King & Spalding | 1999-05-14 | 120375 | 43465.95
|  | Total 1999 Legal fees |  | 59517.4
| Total Legal fees not included in WO# S80015 |  |  | 83900.89

## To Update
To Update:
1 | Save file as new name
2 | Go to Summary tab
in cell "Q4" drop in date of Project Tracking report used as backup
3 | Go to LLC tab
unhide all columns
update actuals for applicable month
check totals
tie budget and current estimate to report from week before; explain any changes on summary tab
make sure that sum of Actuals to Date Total Project + Estimate to Complete + variance = Current Estimate amount
4 | Go to Summary tab
update variance explanations to current estimate