## Sheet1
# | Description of Issue | Root Cause # | Description of Root Cause | Project Team
1 | Quality Levels of the 1.5 Components Delivered to the Site were Inadequate
| 1.1 Management of Quality Issues at Supplier Base | 1.1.1 | Lack of QC at Supplier (Audit by GEWE QC Personnel)
|  | 1.1.2 | Receiving Inspections Inadequate
|  | 1.1.3 | Testing Prior to Delivery
|  | 1.1.4 | Full Prototype Testing
|  | 1.1.5 | Lack of QC by our Suppliers
|  | 1.1.6 | Lack of Product Feedback to Drive Improvement
|  | 1.1.7 | Inadequate In-Process Inspections During MFG (Band Aide Only)
|  | 1.1.8 | Testing of Individual Components to their Maximum Capacity (e.g. generators for 1.5 tested only to 350 kW)
| 1.2 Information on the 1.5 Turbine | 1.2.1 | Inappropriate and Inadequate Design Specifications
|  | 1.2.2 | Lack of or Inaccurate Information from Europe
|  | 1.2.3 | Application Analysis - Lack of Modularity
|  | 1.2.4 | Lack of Exploded Bill of Materials
| 1.3 Compressed Schedules | 1.3.1 | Highly Compressed Schedule
|  | 1.3.2 | Engineering Design Delay
|  | 1.3.3 | Lack of Resources
2 | Safety Incidents Exceed Industry Standards
| 2.1 Safety Standards Training | 2.1.1 | Training Insufficient
|  | 2.1.2 | Ramp-up with Inexperienced Employees and Turnover
|  | 2.1.3 | Safety Meetings not Held Often Enough
|  | 2.1.4 | Lack of Closed-loop System to Drive Improvement - Root Cause Analysis
|  | 2.1.5 | Lack of Knowledge Transfer between Construction and O&M
| 2.2 Commitment to Safety by Senior Management down to the Individual Employee and Third Party Labor Personnel | 2.2.1 | Inadequate Project Safety Plans
|  | 2.2.2 | Poor Implementation of Safety Plan
|  | 2.2.3 | Lack of Goals and Objectives for Safety
|  | 2.2.4 | Accountability Driven to the Employee Level
|  | 2.2.5 | Near-Miss Program Not being Followed
|  | 2.2.6 | Lack of Construction Team Accountability
|  | 2.2.7 | Third Party Labor - Short Term Workers
|  | 2.2.8 | Meet Customer Safety Requirements in Contract
3 | Lack of Alignment of Company Goals
| 3.1 Mission Statement, Goals and Objectives | 3.1.1 | Lack of Leadership - CEO Oversight
|  | 3.1.2 | Ownership/Accountability
|  | 3.1.3 | Lack of Definition of Goals - What is the Business Model
|  | 3.1.4 | Poor Communication of goals and rationale
|  | 3.1.5 | No Global Plan, with Goals and Objectives.
4 | Contracting Process was Ineffective and Impacted Project Performance
| 4.1 Turbine Sale and EPC Agreements | 4.1.1 | Contracts Not Standardized
| 4.2 European Supplier Contracts | 4.2.1 | No Protections for GEWE in contracts - totally one-sided in favor of the supplier - some major components did not even have a written contract.
4.3 Contract Review and Approval Process
|  | 4.3.1 | No Written Procedure or Process
|  | 4.3.2 | Lack of Signature Authority for Project Managers or Procurement Leaders.
|  | 4.3.3 | Bottleneck in Legal Review
5 | Human Resources did not Perform at their Full Potential
| 5.1 Human Resources Planning and Training | 5.1.1 | Lack of Proper Training for Commercial Sales Personnel
|  | 5.1.2 | Improper Timing (Planning)
|  | 5.1.3 | Lack of Specific Job Definition
|  | 5.1.4 | No Standarization of Resource Plan
| 5.2 Production Definition | 5.2.1 | Lack of Product Definition and Specifications
| 5.3 Product Performance | 5.3.1 | Lack of Product Performance
| 5.4 Senior Management | 5.4.1 | Senior Management Not Committed
6 | Component Deliveries Did Not Meet Project Requirements
| 6.1 Planning and Scheduling | 6.1.1 | Lead Times Were Inadequate
|  | 6.1.2 | PTC Causes Peaks and Valleys - Scheduling
|  | 6.1.3 | Lack of Centralized Scheduling System
|  | 6.1.4 | Vendor Deliveries did not Meet Expectations
|  | 6.1.5 | Not Enough Carriers
|  | 6.1.6 | Planning for Tighter Delivery Dates with Carriers Needed
|  | 6.1.7 | Just-in-Time Delivery Not realistic in the US
|  | 6.1.8 | Customer Requirements versus Standard Lead-times
7 | Excessive Pain Throughout Organization relating to Contracts, Spec's, Exhibits, Processes and Procedures (Manuals)
| 7.1 Standardized System for Access and Control of Documentation | 7.1.1 | Operations and Maintenance Manual not designed to be effective for the Field Personnel
|  | 7.1.2 | No Single Point of Contact for Systems
|  | 7.1.3 | Lack of Standard BOP Specifications
|  | 7.1.4 | Consistency of Application - On Again, Off Again - Tribal in Nature
|  | 7.1.5 | No Central Standards Globally
|  | 7.1.6 | Supplier Contracts with Deviations from US Specification not forwarded to America's
|  | 7.1.7 | No Commitment from Senior Management
| 7.2 Training Program to Educate GEWE Personnel on Available Systems | 7.2.1 | Lack of Training to Current Systems - Systems exist, But Nobody Knows about Them
| 7.3 Coordination of Activities between Europe and America's | 7.3.1 | No Incentive to Use Systems that are Currently Available
|  | 7.3.2 | No Senior Management Commitment
|  | 7.3.3 | Lack of Communication with Europe - Team Building Needed
8 | Spare Parts Inventory does not Meet Project Requirements
| 8.1 Plan (global) for the Delivery of Spare Parts for Projects in the America's | 8.1.1 | Lack of Planning
|  | 8.1.2 | No Early Forecast for Spare Parts
|  | 8.1.3 | Spare Parts are unknown - No BOM
|  | 8.1.4 | Lead Time for Component Delivery
|  | 8.1.5 | No Life Cycle Analysis (NTBF) - Inventory Level
|  | 8.1.6 | Inventory does not Comply with Customer Contracts
|  | 8.1.7 | Force Majuere Events not taken into Consideration
| 8.2 Inventory Management and Control System. | 8.2.1 | No Ability to Expedite - Inventory Pool or Just-in-Time
|  | 8.2.2 | Inventory too Low for Projects
|  | 8.2.3 | Lack of Effective Inventory Management System
|  | 8.2.4 | No Documentation Accompanying Failed Parts
|  | 8.2.5 | Lack of Training
| 8.3 Component Failures in the Field | 8.3.1 | Component Reliability
|  | 8.3.2 | Lack of Training
| 8.4 Tooling requirements | 8.5.1 | Lack of Adequate Tooling (physical and calibrated)
9 | Wind Plant Subsystems Not Available in a Timely Fashion
| 9.1 Advance Preparation for Construction of Projects | 9.1.1 | Development process for wind project too fast
|  | 9.1.2 | Risk Level Acceptance too Low
|  | 9.1.3 | Identify Utility Interconnect Requirements Earlier
|  | 9.1.4 | Structured Project Lead-time - Training
|  | 9.1.5 | Inadequate Contract Review Process - Project Scope Definition
|  | 9.1.6 | Project Implementation - Need a Standard for
|  | 9.1.7 | Lack of Plan for Energization of the Substation
|  | 9.1.8 | Untimely SCADA Installation
|  | 9.1.9 | Lack of Modularity
|  | 9.1.10 | Communication Systems need to be in Place prior to Construction
|  | 9.1.11 | PTC Causes Peaks and Valleys - Scheduling
|  | 9.1.12 | Sufficient Lead-times required to design and build project
10 | Current Quality Levels for Balance of Plant (BOP) Construction are Inadequate
| 10.1 Balance of Plant (BOP) Quality Program | 10.1.1 | Lack of Acceptance/Rejection Criteria
|  | 10.1.2 | No audit to an Approved Acceptance/Rejection Criteria
|  | 10.1.3 | Audit Frequency or timing is not Defined
|  | 10.1.4 | Lack of Quality Processes - Verification/Deviation Process, Final Sign-Off
| 10.2 Supplier Audits in Advance of Selection of Supplier | 10.2.1 | Lack of Supplier Certifications
|  | 10.2.2 | Supplier Contracts need better definition
| 10.3 Resources | 10.3.1 | Lack of adequate Resources to review BOP Quality Documentation
| 10.4 Control of Subcontractor, who has Design Build responsibilities. | 10.4.1 | Legal Risk Associated with GE Wind Oversight and Sign-off - Supplier Design Build Contracts
|  | 10.5.1 | Scope of BOP - Better Definition of Interface Points
11 | Inaccurate Project Scope Definition Lead to Increased Costs and Dissatisfaction and Frustrated Customers
| 11.1 Defined Work Scopes | 11.1.1 | Miscommunication with Customer - lack of confirmation/feedback loop
|  | 11.1.2 | Miscommunication within Company
|  | 11.1.3 | Quote Assumptions Relayed to Customer
|  | 11.1.4 | Lack of Quality Data/Inputs
| 11.2 Cost Estimating Process | 11.2.1 | Standardization of Inputs
|  | 11.2.2 | Bulletproof estimating process - with cross checks
|  | 11.2.3 | Increase Training and Knowledge Base of Commercial Sales for improved inputs for estimate
|  | 11.2.4 | Learn better estimating processes from past transactions - synthesize and disseminate
12 | Communication between Field (O&M and Construction) and Tehachapi/Rheine is Ineffective
| 12.1 Coordination of Improvements to the Turbine and Related Infrastructure between the Field and Engineering Groups | 12.1.1 | Inadequate Follow-up action on Field suggestions (FAR's, etc.)
|  | 12.1.2 | Lack of QC/Engineering Resources to Follow-up Effectively
|  | 12.1.3 | Inadequate Field Response to Engineering Inquiries and inadequate process to follow through
| 12.2 Training of Field Personnel | 12.2.1 | Improved Training on FAR and other Field Documentation Processes
|  | 12.2.2 | Increased Field Experience/Evaluation required by Engineering/QC
| 12.3 Tracking System to handle Field Requests | 12.3.1 | Tracking Mechanism for Follow-up - Management Oversight Inadequate
| 12.4 Who are Our Customers | 12.4.1 | Lack of Understanding of Internal Customer Requirements, in addition to External Customer Requirements
|  | 12.4.2 | Supplier Input - Customer Requirements Concept either not recognized or ignored.