## Pipeline
2001-08-21
Pipeline Expansions - West Region
Pipe | Name | Receipt Region | Receipt City | Delivery Region | Delivery City | Quantity | In Service | Term | Rate | STATUS | COMMENTS | Cost (Millions) | Length (Miles)
CIG Ruby (PG&E bypass) | RUBY | Rockies | Uintah County, UT | Northern California | Sacramento, CA | 750 | 2003-12-01 | TBD | $.80/mmbtu hurdle, if > 500 M2/d, will build | OPEN SEASON CONCLUDED WAITING FOR PRECEDANT AGREEMENTS. | Will travel via: Reno, Yuba City, Sacremento,Wild Goose | 200 | 850
CIG | Raton Phase I | Rockies | Las Animas County, CO | Rockies | Baca County, CO | 85 | 2001-09-01 |  |  | FERC APPLICATION FILED | Length = 70+ compression |  | 70
CIG | Raton Phase II | Rockies | Las Animas County, CO | Rockies | Baca County, CO | 135 | 2002-09-01 |  |  | Announced | Start date sometime in fall 2002 |  | 70
CIG | Campo, Cucharas, Picketwire Laterals | Rockies |  | Rockies |  | 0 | 2002-10-01 |  |  | Announced | Volume TBD.
CIG | Coastal Connection (COCO) | Rockies | Cheyenne Hub | Mid-Continent | Greensburg, KS | 500 | 2003-01-01 |  |  | Announced | Estimated In Service Date. Better mid-continent access than Western Frontier.
CIG |  | Powder/Wind River Basins |  |  |  | 45 |  |  |  | Announced
El Paso | Line 2000 Power Up | Permian | Texas | Southern California | Ehrenberg, AZ | 320 |  |  |  | Dead | No interest. Compression addition to All American.
El Paso | Sacramento Valley | California Border |  | Southern California | Sacramento, CA | 0 | 2003-06-01 | TBD |  | OPEN SEASON CLOSED. BINDING INTEREST TBD. | TBD on Capacity
El Paso | Dagget to Ehrenberg | Bi-directional | Dagget, CA | Bi-directional | Ehrenberg, AZ | 500 |  |  |  |  | Dead
El Paso | Western Frontier | Rockies | Northeastern Colorado | Rockies | Southwestern Kansas | 540 | 2003-11-01 |  |  | OPEN SEASON CLOSED IN JULY. FERC FILING PLANNED FOR 2001Q4. | Williams central markets. |  | 320
El Paso | Dumas Gas Transmission | Southwest | Colfax County, NM | Mid-Continent | Moore County, TX | 175 | 2001-07-01 |  |  | Announced. Interconnect with Northern Natural for delivery to Mid-continent. |  |  | 185
El Paso | Gasoductos de Chihuahua |  |  | Mexico |  |  | 2002-01-01 |  |  | Announced | Samalayuca lateral to Chihuahua, Mexico. In service date some time in 2002.
El Paso | Wilcox Lateral | Arizona | Cochise County, AZ | Mexico | Mermosilla and Agua Prieta, Mexico | 130 | 2001-12-01 |  |  |  | Only 100 subscribed. | 30 | 70
El Paso | All American | Permian | McCarney, TX | Southern California | Bakersfield, CA | 230 | 2001-12-31 | NA | TBD | FERC APPROVED. CAPACITY TO FILL EXISTING NEEDS. AKA LINE 2000 | Augment existing shippers, no new cd. | 75 | 1088
Fort Union | Fort Union Expansion | Powder/Wind River Basins | Gillette, WY | Wyoming | Glenrock, WY | 200 | 2001-10-01 |  |  | Announced | Sponsors: CMS, Western Gas Resources, CIG, Barrett Resources |  | 106
Kern River | Emergency filing | Rockies | Opal | SoCal | Wheeler Ridge | 21 | July 1,2001 | April 30,2003 | $.820 Resv+.003 RGRI Com+$.06 Com+ACA | DONE
Kern River | Emergency filing | Rockies | Opal | SoCal | Wheeler Ridge | 114 | July 1,2001 | April 30,2002 | +GRI +4.2% thru 4/30/02 and 6.2% thereafter | DONE | +202 M2/d @ Wheeler
Kern River | 2002 Expansion | Rockies | Opal | SoCal | Wheeler Ridge | 10.5 | May 1,2002 | 10 or 15 yr | $.3374 Resv+$.002 RGRI+$.0573 Com+ACA | RESEARCHING FERC APPROVAL
Kern River | 2003 Expansion | Rockies | Opal | SoCal | Wheeler Ridge | 900 | May 1,2003 | 15 yr | TBD = estimate a demand charge of $.45 plus | FERC APPLICATION FILED AUGUST 7, 2001 | +Wheeler Ridge to 830 M2/d
Kern River | High Desert Lateral | Rockies | Kern River/Mojave | California | Victorville, CA | 282 |  |  |  |  | Will feed High Dester Power (720MW) near Victorville. | 28.9 | 31.6
KMIGT | Advantage | Cheyenne Hub |  | Mid-Continent |  | 330 |  |  | Calpine = 400 Phase 1, 500 Phase II | OPEN SEASON PROPOSED FOR FALL
Burlington Resources/Enron | Lost Creek | Wind River Basin |  |  | Wamsutter, WY | 275 |  |  |  | Announced |  | 54 | 124
North Baja | North Baja | Southern California | Ehrenberg, AZ | Mexico | Tijuana, Mexico | 500 | 2003-09-01 | variable (20 year) | $.35/mmbtu recourse rate (US and Mexico) | EXPECT FERC APPROVAL NOV 2001. RECEIVED MEXICAN PERMITS. | Cosponsors: PG&E, Sempra, Proxima Gas | 230 | 212
NWPL | Evergreen | PNW | Sumas, WA | PNW | Chehalis, WA | 244 | 2003-06-01 | 15 yr - 25 yr | Rate to be announced upon FERC filing | FERC FILING MADE. FULLY SUBSCRIBED. | (277 M2/d of K) | 200 | 26
NWPL | Displacement Fix | Rockies |  | Stanfield, OR |  | 175 | 2003-10-01 | N/A | Rolled in - TBD | SETTLEMENT APPROVED BY CUSTOMERS. | Displacement Fix. (Primary obligations only)
NWPL | Piggyback | Rockies |  | Stanfield, OR |  | 0 | 2003-10-01 | TBD | incremental | AWAITING OPEN SEASON.
NWPL | Gorge Expansion | Stanfield | Stanfield, OR | PNW |  | 50 | 2003-10-01 | TBD | incremental | 7,000 TO FILL EVERGREEN. 42,000 TO EXISTING SHIPPERS. EXPECT FERC FILING SOON.
PG&E | Backbone - Redwood | Malin |  | PG&E Citygate |  | 200 | 2003-12-01 | TBD | Incremental Rates: | 200 - 500 MILLION REDWOOD. OPEN SEASON POSTPONED.
PGT | 2002 Expansion | Canada | Kinsgate, ID | California | Malin, OR | 200 | 2002-11-01 | 30+ years | rolled in + incremental .5% fuel on path | DONE - INCREMENTAL FUEL TO BE ASSESSED TO NEW SHIPPERS.
PGT | 2003 Expansion | Canada | Kinsgate, ID | California | Malin, OR | 250 | 2003-11-01 | TBD | TBD - estimate of $.44-.46 + incremental fuel | OPEN SEASON CLOSED. EXPECT FILING FOR 125,000. DON'T KNOW FILING DATE YET.
PGT | Washington Lateral | Central WA |  | I-5 Corridor |  | 0 | 1905-06-26 | TBD |  | NON BINDING OPEN SEASON CLOSED. WORKING ON PRECEDANT AGREEMENTS. PGT MEETING ON AUGUST 21, 2001.
Questar | Mainline 104 | Rockies | Price, UT | Wasatch Front | Elberta, UT |  | 2001-11-01 |  |  | FERC APPROVED. CAPACITY TO FILL EXISTING NEEDS. AKA LINE 2000 | Interconnect with Kern. Questar is other project sponsor. | 62 | 75
Questar - California | Souther Trails (?) | Rockies | Four Corners Area | SoCal Border | Long Beach , CA | 120 | TBD | TBD | Regulatory block at CPUC | SOCAL PEAKING SERVICE THREATENS CONVERSION. |  | 155 | 751
Questar Southern Trails | Southern Trails | San Juan | San Juan | California Border | California Border | 80 | 2002-04-01 | TBD | $.52 hurdle/Questar finalizing Navajo agreement | HAS FERC APPROVAL. EXPECT MID 2002 START DATE. DELIVERY POINT ISSUES STILL UNRESOLVED. | Oil line conversion - has FERC approval. Could be on-line in May instead of April 02.
Questar Southern Trails | Southern Trails | San Juan | San Juan | California Border | California Border | 40 | 2002-06-01 | TBD | TBD | EARLY PLANNING PHASES. NOT ANNOUNCED YET. NO OPEN SEASON YET. | compression expansion of above. Could come on-line in July 2002
SoCal | Backbone | California | California | California | California | 175 | 2001-12-01 | TBD | rolled in: 85 M2/d @ Wheeler Ridge, 40 - 50 M2/d | ANNOUNCED |  | 15
SoCal | Kramer | California | Kramer Junction | California | California | 200 | 2001-12-01 | TBD | rolled in - new interconnect with Kern | RESEARCHING STATUS |  |  | 32
Sonora (Calpine&KN) | Sonoran Phase I | San Juan | Blanco, NM | SoCal Border | Topock, CA | 750 | 2003-06-01 | 20 YEARS | Phase I to Border - $.39/mmbtu + 1.3% fuel | OPEN SEASON COMPLETED. HAVING DIFFICULTY GAINING SIGNED COMMITMENTS. |  | 624 | 570
Sonora (Calpine&KN) | Sonoran Phase II | SoCal Border | Needles, CA | Northern California | Antioch, CA | 1000 | TBD | TBD | Phase II intrastate - TBD | OPEN SEASON COMPLETED. HAVING DIFFICULTY GAINING SIGNED COMMITMENTS. | Capacity anywhere from 1,000 - 1,500 MMcf/d | 1100 | 590
Tuscarora | Tuscarora Expansion | PNW | Malin, OR | Nevada | Tracy, NV | 96 | 2002-12-01 | 10 - 15 years | need to determine | Announced | Sponsors: Sierra Pacific and TCPL | 60 | 229
TWPL | Red Rock | Permian |  | PG&E | [7 empty] | 93 | 400
TWPL | Red Rock | Griffith/Southpoint |  |  |  | 150 | 2002-12-01 | TBD | One part rates: $.63-5yr/$.45-10yr/$.38-15yr+ | FERC FILING MADE ON 6/1/2001. FILED FOR 150,000, BUT ONLY 108,000 CONTRACTED. NEEDLES FULL. 42,000 REMAINS UNSUBSCRIBED AT OTHER DELIVERY POINTS. |  |  |  | (partial service in July 2002)
TWPL | Sun Devil | Blanco |  | Thoreau |  | 750 | 2004-01-01 | TBD |  | OPEN SEASON CLOSES 8/30/01. | Potential receipt points at Blanco include: BRT/Val Verde Plant, WFS Milagro, WFS/Kurtz Plan, and TransColorado/Blanco. Estimated max reservation rates: San Juan to Thoreau ($.0985 dth/d; thoreau to California ($0.24 dth/d); Thoreau to Phoenix ($.454 dth/d).
TWPL | Sun Devil | Blanco |  | Thoreau |  | 90 | 2004-01-01 | TBD |  | OPEN SEASON CLOSES 8/30/01. | Potential receipt points at Blanco include: BRT/Val Verde Plant, WFS Milagro, WFS/Kurtz Plan, and TransColorado/Blanco. Estimated max reservation rates: San Juan to Thoreau ($.0985 dth/d; thoreau to California ($0.24 dth/d); Thoreau to Phoenix ($.454 dth/d).
TWPL | Sun Devil | Thoreau |  |  | Phoenix, AZ | 450 | 2004-01-01 | TBD |  | OPEN SEASON CLOSES 8/30/01. | Potential receipt points at Blanco include: BRT/Val Verde Plant, WFS Milagro, WFS/Kurtz Plan, and TransColorado/Blanco. Estimated max reservation rates: San Juan to Thoreau ($.0985 dth/d; thoreau to California ($0.24 dth/d); Thoreau to Phoenix ($.454 dth/d).
WIC |  | Cheyenne Hub |  | Opal | [5 empty] | OPEN SEASON CLOSED. WAITING FOR PRECEDENT AGREEMENTS.
| NECO | NE Colorado Market |  | NE Colorado Market | [5 empty] | OPEN SEASON PROPOSED FOR FALL
WIC | Medicine Bow Lateral Looping | Powder River/Wind River Basins | Converse County, WY |  | Weld Country, CO | 675 | [5 empty] | 160 | 150
Trailblazer | Trailbazer Expansion |  | Rockport, CO |  | Gage County, NE | 300 | 2002-07-01 |  |  | Announced | Compression addition. Sponsors: Enron, Kinder Morgan
Williston Basin Interstate Pipeline | Line 14 Expansion | Powder River/Wind River Basins | Recluse, WY |  | Northern Border | 40 | 2001-11-01 |  |  | Announced | Capacity will be between 40 and 100 MMCF/d
Georges Straight Crossing | Georges Straight | PNW | Sumas, WA | Canada | Vancouver, BC | 100 | 2003-10-01 |  |  | FERC filing made |  | 159 | 85
NWPL | Grants Pass Lateral | PNW | Portland, OR | PNW | Grants Pass, OR |  |  |  |  | Announced | Sponsor: Williams |  | 260
BC Gas | Inland Pacific Connector | Canada | Southern Crossing Interconnect | Canada | Huntington, BC | 350 | 2003-11-01 |  |  | Announced |  | 307 | 150
Westcoast Energy | Southern Mainline | Canada |  | Canada |  | 100 | 2003-11-01 |  |  | Announced | 100 MMcf/d on Alberta Leg, 200 MMcf/d on mainline

## Storage
Pipeline Expansions - West Region
Sponsor | Name | Receipt Region | Storage City | Initial Storage Quantity (BCF) | Storage Quantity Increase | Final Storage Q | Initial Withdrawal Quantity (MMcf/d) | Withdrawal Quantity Increase (MMCF/d) | Final Withdrawal Quantity | Initial Injection Quantity | Injection Quantity Increase (MMCF/d) | Final Injection Quantity | In Service | Term | STATUS | COMMENTS
Alberta Energy (AEC) | Wild Goose | Northern California | Gridley, CA | 14 | 15 bcf | 29 | 200 | 500 | 700 | 80 | 370 | 450 | 2004-04-01 | 2 - 30 years | Open Season closed 5/22/01. CPUC Application Filed | Current capacity is 14BCF. Current withdrawal is 200 mmcf/d. Current injection is 80 mmcf/d. If regulatory approval is expedited, could be in service as early as 2003.
Western Hub Properties | Lodi | Northern California | Sacramento, CA | 0 | 9 | 9 | 0 | 300 | 300 | 0 | 300 | 300 | 2001-10-01 |  | Announced. Received special regulatory approval relief from Gov. Davis. | Will be used to store gas for new and existing power plants in California. Calpine singed a 10 yar deal to take up to 4 bcf of gas. Facility will ultimately have 12 bcf of capacity, which will come on-line about three months after the first 9.
AES | Colorado Gas Storage | Colorado | Denver, CO |  | 9 bcf | 9 | [6 empty] | 2002-11-01 |  | Approval received from Colorado Oil and Gas Conservation Commission, the Colorado PUC, and Adams County, CO officials. | Will have ability to cycle working gas more than 2x per year. Interconnect with CIG is in progress. Future connection with Xcel is under consideration.
SoCal | La Goleta | Southern California | Santa Barbara, CA | [12 empty] | Proposed removal of 7 bcf of base gas for sale into market. No impact on working gas capacity in field
SoCal | Aliso Canyon | Southern California | Los Angeles County | [12 empty] | Proposed removal of 7 bcf of base gas for sale into market. No impact on working gas capacity in field
CIG | Fort Morgan | [6 empty] | 102