## EPE
CHANGE ORDER LOG
EMPRESA PRODUTORA DE ENERGIA LTDA
Cuiaba 480 MW Power Plant
Change Order Number | Description | Model |  | Scenarios | 2000-11-11
|  | Category | Reason Behind difference (if any) between SCC Position and Owner's Estimate | SCC Position | "Owners Estimate"
Amounts in Yellow are expected but Not budgeted due to contingent nature of these amounts
Power Plant Pending / Forecasted Change Orders
Power Plant Pending / Forecasted Change Orders
EPE-PCO-013 | Siemens Ltda. Cancellation Charge, Phase II design |  |  |  | 0
EPE-PCO-014 | Relay protection duplication |  |  |  | 0
EPE-PCO-015 | T&D Communication Tower at Coxipo Substation |  |  |  | 0
EPE-PCO-042 | Change in Tax Law - COFINS | Scenario 3 in Model | To be issued, Probably can be used against SCC tax benefits or charge back to Furnas | 0 | 0
EPE-PCO-043 | Escalation of Unpaid Balance - Onshore Power Plant '98 | Update in Model | To be issued, is in the value from Monthly construction report. Accordingly, to onshore portion of the EPC contract is subject to inflation escalation. | 536522 | 536522
EPE-PCO-044 | Escalation of Unpaid Balance - Onshore Power Plant '99 | Update in Model | To be issued, is in the value from Monthly construction report. Accordingly, to onshore portion of the EPC contract is subject to inflation escalation. | 456823 | 456823
EPE-PCO-045 | Escalation of Unpaid Balance - Onshore Power Plant '00 | Scenario 3 in Model | Withdrawn as per SCC Change Order log | 0 | 0
EPE-PCO-046 | Escalation of Unpaid Balance - T&D | Scenario 3 in Model | Withdrawn as per SCC Change Order log | 0 | 0
EPE-PCO-047 | Interest on Late Payment of Offshore Invoices | Scenario 3 in Model | Withdrawn as per SCC Change Order log | 0 | 0
EPE-PCO-048 | Water Treatement Facility escalation - Inflation adjustment factor |  |  |  | 0
EPE-PCO-049 | Design of Sludge Lagoon |  |  |  | 0
EPE-PCO-054 | Design & Construction of Sludge Lagoon | Scenario 3 in Model | Taken away from SCC - Outside Scope, included in other engineering costs | 0 | 0
EPE-PCO-060 | Siemens Extension of Time Phase III | Scenario 3 in Model | Disputing/Negotiating with Siemens, together with EPE-PCO-072, together with Fuel Commissioning; expect total settlement value to be 6.5 MM (incl. EPE-072) | 13372476.31 | 5400000
EPE-PCO-061 | Steam Blows | Update in Model | Original scope contemplated steam blows. SCC has not provided background on this item. Suggested split 50/50 with SCC. | 58882 | 29441
EPE-PCO-062 | Transportation Damage, HRSG | Scenario 3 in Model | Cargo Ship sailed into Typhoon; Issue in mediation. Inprudent action by shipper. | 1661743 | 0
EPE-PCO-063 | Change in IPI Tax Law |  |  |  | 0
EPE-PCO-069 | Damage to Water Treatment Plant (warranty claim) | Scenario 3 in Model | Warranty Claim - no cost to Owner | 13108 | 0
EPE-PCO-070 | Preservation, Maintenance & Reinstatement Prior to Resumption of Commiss. Of Ph III | Scenario 3 in Model | Already included / Tied to EOT Claim Siemens | 99000 | 0
EPE-PCO-071 | Refund to Siemens for portion of Ph I LD's after re-measure and re-calculation |  |  |  | 0
EPE-PCO-072 | Downpayment towards Extension of Time Costs Related to Phase III Owner Delays | Scenario 3 in Model | Downpayment to Siemens EOT Claim to avoid suspension by Siemens | 1100000 | 1100000
EPE-PCO-079 | Grid Access Restrictions during Plant Combined Cycle Commissioning - Potential Claim TBD | Not included in Model | Included in Siemens Settlement Phase III EOT, see below | 0 | 0
EPE-PCO-081 | Amper Water Treatment Facility Claim for Additional Costs, Close-Out Settlement |  | Settlement directly with Amper related to increases in Scope because more materials used (e.g. Ownwer Request.) | 796451 | 796451
EPE-PCO-082 | EOT Claim SCC for delay in Final NTP Pipeline | Not included in Model | Claim issued by SCC who is convinced never received NTP pipeline; will go to dispute resolution. Enron gave NTP on 7/15/99. | 232007 | 0
EPE-PCO-083 | Compensation Siemens for Siemens' Consequential costs related to HRSG Modules damaged during transport |  | Cargo Ship sailed into Typhoon; Issue in mediation, No insurance received; same issue as EPE -062. | 247500 | 0
EPE-PCO-084 | No Cost Change Order to correct Power Plant Price noted in Exhibit C-2 |  | Issued; No cost change order; Owner okay except with onshore/offshore portion WTP | 0 | 0
EPE-PCO-085 | Road connecting Plant with WTP and Lagoon pumping house |  | Issued; Access road needed to be able to get to WTP and Pump House in rainy season. Owner Request as outside scope. | 93233 | 93233
| Subtotal: |  |  | 18667745.31 | 8412470
| Subtotal of Forecasted & Budgeted Amount |  |  |  | 8412470
Non-numbered items and exposures
Future EOT Claim SCC | Future EOT Claim SCC |  | SCC has mentioned $11 MM claim for total project (EPE, GasMat, GasBol); depends on Siemens EOT claim but will probably go to mediation | 3000000 | 1500000
Grid Access Restrictions during Plant Combined Cycle Commissioning - Potential Claim TBD | Grid Access Restrictions during Plant Combined Cycle Commissioning - Potential Claim TBD |  | Grid Access Restrictions based on experience October-00 where we had about 10% of time grid access problems. | 600000 | 600000
| Change in Tax Law - COFINS |  |  | 852000 | 426000
Siemens Technicians and CC commissioning support | Siemens Technicians and CC commissioning support |  | Combined Cycle Commissioning support from Siemens; 5 months commissioning; (avg. 2 guys @ 25,000 monthly) to accelarate commissioning. To be negotiated. | 250000 | 250000
Siemens Technicians onsite from end of CC commissioning Fuel Oil till arrival of gas | Siemens Technicians onsite from end of CC commissioning Fuel Oil till arrival of gas |  | 3 Siemens reps to assist plant operations after CC commissioning on diesel; rest of Siemens goes home until gas; (3 persons @25K 3 months). To be negotiated. | 250000 | 250000
Escalation of Unpaid Balance - Onshore Power Plant '00 and '01 and T&D | Escalation of Unpaid Balance - Onshore Power Plant '00 and '01 and T&D |  | Most of on-shore items were paid in 99; Exposure remains on outstanding amount; need to perform analysis, withdrawn as per SCC change order log. | 250000 | 125000
Auxiliary Boiler and Piping | Auxiliary Boiler and Piping |  | Boiler and Piping already installed, change order probably coming for additional work done. To be determined. | 125000 | 125000
Superheater | Superheater |  | Superheater likely will not be installed. To be determined. | 75000 | 75000
HRSG Platform Bridge | HRSG Platform Bridge | Scenario 3 in Model | Item that has been out there for a long time; hasn't been installed and not expected at this point. | 75000 | 75000
Changes in logics / Load shedding | Changes in logics / Load shedding |  | Items that may show up based on experience | 30000 | 30000
Installation of Eye-Hye Detectors | Installation of Eye-Hye Detectors | Scenario 3 in Model | Item that has been out there for a long time; hasn't been installed and not expected at this point. | 50000 | 50000
| Phase III T/L Tower Foundations |  | Claims have been settled and is included in Approved EPE-PCO-076
| WTP Road Interconnection |  | Claims have been settled and is included in Approved EPE-PCO-085
| WTP Lagoon Fencing / Safety Improvements |  | Claims have been settled and is included in Approved EPE-PCO-076
| WTP Claims |  | Claims have been settled and is included in Approved EPE-PCO-076
| Mulheim LD's in mediation |  | Mulheim LD's in mediation; reason for 50 cents on dollar | -1020000 | -510000
| Change in IPI Tax Law - Charge Back to Furnas |  | According to Celso, no chance to get IPI change reimbursed | 0 | 0
| Furnas Charge Back of grid access restrictions |  | Based on getting everything or nothing reimbursed; Combines with Grid Access Restrictions estimate of $600,000 | -250000 | -125000
| Subtotal: |  |  | 4287000 | 2871000
| Total SCC Claims in excess of "Owner's Estimate" |  |  | 14542275.31

## GasMat
CHANGE ORDER LOG
GasOcidente do Mato Grosso Ltda.
278 km natural gas pipeline
Change Order Number | Description |  | Scenarios | 2000-11-11
|  | Reason Behind difference (if any) between SCC Position and Owner's Estimate | SCC Position | Owner Estimate
Amounts in Yellow are expected but Not budgeted due to contingent nature of these amounts
Pipeline Pending / Forecasted Change Orders - GasOcidente do Mato Grosso Ltda.
GasMat Pending / Forecasted Change Orders
GOC-PCO-004 | Powercrete Pipe Coating 40 mil thickness for 1,700 LM |  |  | 0
GOC-PCO-005 | Supply and Installation of 12" Line Pipe at Power Plant | Not issued by SCC yet. | 65000 | 0
GOC-PCO-007 | Re-Route from KP606+167 to KP629+171 & KP587+447 to KP592+447 |  |  | 0
GOC-PCO-008 | Geotechnical Investigation of Rio Cuiaba due to Re-Route |  |  | 0
GOC-PCO-012 | Additional 4.051 KM of Line Pipe Purchase due to Re-Routes |  |  | 0
GOC-PCO-013 | Installation of Additional 4.051 KM due to ReRoutes |  |  | 0
GOC-PCO-020 | Additional Non-Pipe Materials for Environmental Issues |  |  | 0
GOC-PCO-025 | Brasil Pipeline Contractor Early Completion Bonus | There will no early completion. (However, SCC is of the opinion that they never received NTP. In fact they received NTP 7/15/99) | 1050000 | 0
GOC-PCO-028 | Interest Expense on Late Payment of Offshore Invoices Submitted by SCC to GasOcidente |  |  | 0
GOC-PCO-034 | Increase in Length due to Multiple Re-Routes adding 1,552 LM Between KP-417 and KP-616+632 |  |  | 0
GOC-PCO-040 | Installation of Screw Anchors |  |  | 0
GOC-PCO-042 | Additional Wetland Crossing Requirements |  |  | 0
GOC-PCO-043 | Lock-out at KP 381 to KP 397, Fazenda Santa Helena | Civil Unrest is FM Event. | 23328 | 0
GOC-PCO-044 | Lock-Out in the Ridges, Spread 3 Brazil |  |  | 0
GOC-PCO-045 | Changes on Meter Stations, Block Valves & Compressor Sites | SCC engineering mistake. | 160430 | 0
GOC-PCO-046 | Brazil 3, Ridges: Additional Line Length due to Re-Routes | To be issued by SCC; Value based on estimate by SCC; environmental requirement. | 1188000 | 1188000
GOC-PCO-047 | Brazil 3, Ridges: NTP Delay, EOT & overheads of Conduto | Have not seen back-up, to go to dispute resolution | 2180000 | 545000
GOC-PCO-048 | Brazil 3, Ridges: NTP Delay, EOT & overheads of SCC | Have not seen back-up, to go to dispute resolution | 3308472 | 827118
GOC-PCO-050 | Additional Restoration Measures outside ridges | Env. Mitigation is Contractor Responsibility | 300000 | 0
GOC-PCO-051 | Changes on revised aligment sheets | SCC engineering mistake | 898665 | 0
GOC-PCO-052 | Relocation around unforseen gullies at KP 522 |  |  | 0
GOC-PCO-056 | Mob, Demob & Equipment Standby Delay to NTP for Brazil Spread 3 | Examine Actual Stand-by Equipment; based on contractual values for mobilization and demobilization. In Dispute. | 9695838 | 3200000
GOC-PCO-057 | Modified Execution Plan/Acceleration Costs - Spread 3 | Claim has only partial merit because SCC has reduced costs of execution. | 1520000 | 380000
GOC-PCO-059 | Owner Directed Changes for 12" By-pass, MLV, Launcher, etc. | SCC engineering mistake | 132000 | 0
GOC-PCO-060 | Increased Difficulty in Ridges due to Re-route | SCC is claiming higher degree of difficulty; however in actuality there has been a reduction in difficulty. | 1000000 | 0
GOC-PCO-061 | Lock-outs and Re-Routes in Brazil Spread 4 | FM but also SCC engineering mistakes. To be negotiated. | 500000 | 250000
GOC-PCO-062 | Additional Brazilian Camp Accomodations for Owner | No additional camp accomodations provided. | 30000 | 0
GOC-PCO-063 | Supply of radios for SCC, Owner, D&M. | Only D&M Portion to Owner Account | 15000 | 9000
GOC-PCO-067 | Additional Drying & Caliper Run per Owner Change Directive | To be issued; require further backup. | 875140 | 0
GOC-PCO-068 | Security for SCC & Owner Personnel, Caceres to San Matias | Should be in SCC's scope | TBD | 0
GOC-PCO-069 | Additional ROW requirements due to Future Compressor Stations & Anode beds | In scope SCC | TBD | 0
GOC-PCO-070 | Inability to use Taquaral Access Road per Owner Directive, Additional costs alternative route | Have not seen back-up | 330846 | 0
GOC-PCO-071 | Additional Heavy Equipment Rental due to Owner Restrictions on Blasting of Karst/Limestone in Ridges | Included in modified execution plan | TBD | 0
GOC-PCO-072 | Additional Blasting Restrictions on Limited 20 m ROW | Reduced cost of blasting explosives, experts, Included in modified execution plan | TBD | 0
GOC-PCO-073 | Pipeline Contractor Standby Costs due to Materials being held by Customs at Bol/Bsl border | SCC mistake, they responsible for customs release | TBD | 0
GOC-PCO-074 | EOT Claim for Various Delays | Included in PCO-047, | TBD | 0
GOC-PCO-075 | Additonal Buoyance Control Measures above SCC recommendations | Have not seen claim so don't know value; see below in exposures | TBD | 0
GOC-PCO-076 | Additional Costs related to Dames and Moore's Addendum 1 Report | Assumed included in the Restoration of ridges below (one package) | TBD | 0
GOC-PCO-077 | Correction of Exhibit C-2 Contract Price to equal Exhibit C-1, No cost | No cost; Owner okay with correction | 0 | 0
GOC-PCO-078 | Additional Hydroseeding | Includes some double counting in ridges restoration. | 605000 | 151250
GOC-PCO-079 | Cost delta between estimated and actual - supplement to PCO-065 Powercrete J materials | Owner directive for pipe and materials for drilling | 124190 | 124190
| Subtotal: |  | 24001909 | 6674558
Contingency:
| Subtotal of Forecasted & Budgeted Amount |  |  | 6674558
Non-numbered items and exposure:
| Restoration Ridges | 8 ridges at half a million a piece to restore ridge. Completed 1/2 of restoration. | 4000000 | 4000000
| Contingency for Blasting Restrictions and increased equipment rental | Not issued, and no estimate or backup available. | 500000 | 250000
| Contingency for Bouyance Control Measures above SCC recommendations | Not issued, and no estimate or backup available. | 250000 | 125000
| Contingency for various lockouts due to landowner issues | Based on 5-10 days of crew standby for specific activity @ 52,982 / day | 1059638.4 | 529820
| Credit for Carve Out of Ridges from EPC Contract |  | 0 | -4744523
| Credit for Material, Freight, technicians in reroutes paid for by owner | Need to firm up. Have done analysis; some reroutes were caused by landowner lockouts | 0 | -900000
| Credit for Screw Anchors bought by owner | Total negative bouyancy bought by Owners for Brazil, share the cost 50/50 | 0 | -75000
Material testing 12" pipe
Relocation of ROW clear and grade crew KP 381.98
Increase in WT from 0.277" to 0.312"
Lock-out in the ridges - Spread 3
Increase in length of directional drilled crossings
FBE coating to joints before powercrete coating
Changes on revised aligment sheets
Increase in lenght of pipeline due to re-routes
Relocate entire spread from Spread 2 on completion of work to Spread 1B
Supply of repeaters for radios supplied to SCC
Trial Holes KP 503+200
Directional Drilling Ridges 6 & 9
SCC Extra Contingency
Error in formula 6-22 change order log:
| Subtotal: |  | 5809638.4 | -814703
| Total SCC Claims in Excess of "Owners Equity" |  | 23136989.4
Total Power Plant Pending / Forecasted Change Orders with contingency

## GasBol
CHANGE ORDER LOG
GasOriente Boliviano Ltda.
362 km natural gas pipeline
Change Order Number | Description | Reason Behind difference (if any) between SCC Position and Owner's Estimate | 2000-11-11 | 2000-11-11
|  |  | SCC Position | Owner Estimate
Amounts in Yellow are expected but Not budgeted due to contingent nature of these amounts
Pipeline Forecasted Change Orders - GasOriente Boliviano Ltda
Bolivia Pipeline Pending / Forecasted Change Orders
GOR-PCO-016 | Purchase and shipment additional pipeline materials due to Environmental reasons |  |  | 0
GOR-PCO-021 | Bolivia Pipeline Contractor Early Completion Bonus | There will no early completion. (However, SCC is of the opinion that they never received NTP. In fact they received NTP 7/15/99) | 1450000 | 0
GOR-PCO-025 | Interest Expense on Late Payment of Offshore Invoices Submitted by SCC to GasOriente |  |  | 0
GOR-PCO-031 | Changes on Revised Aligment Sheets | SCC responsibility. | 259086 | 0
GOR-PCO-032 | Changes in Above Ground Installations (AGI's) | SCC responsibility. | 416946 | 0
GOR-PCO-034 | Increase in Wetland Crossing Requirements - See PCO-061 |  |  | 0
GOR-PCO-053 | Installation of screw Anchors |  |  | 0
GOR-PCO-054 | Transport of Pipes from Taperas to San Matias by Existing Roads |  |  | 0
GOR-PCO-055 | Stand-by KP-155, ROW and Grade Crews | To be issued. (need to negotiate actual impacts.) | 116065 | 0
GOR-PCO-064 | Double handling pipe stored at San Matias |  |  | 0
GOR-PCO-065 | Exchange FBE Coated Pipe to Concrete Coated |  |  | 0
GOR-PCO-066 | Groundwater Investigations |  |  | 0
GOR-PCO-067 | Stand-by of Stringing Crew at KP 315+200 waiting details of location of Concrete Coated pipe |  |  | 0
GOR-PCO-071 | Disruption of Work at San Miguelito | Civil Unrest is FM Event. | 50000 | 0
GOR-PCO-082 | Disruption of Work at Canon de Fatima |  |  | 0
GOR-PCO-083 | Additional ROW Restoration Requirements | Env. Mitigation in SCC Scope, included in ridges restoration below | 750000 | 0
GOR-PCO-084 | Owner directed Changes for 12" By-pass, MLV, Launcher & Receiver | SCC engineering mistake. | 192000 | 0
GOR-PCO-085 | Pipe Damage During Anchor Installation | Contractor Fault | 66000 | 0
GOR-PCO-086 | Additional Bolivian Camp Accomodations | Contractor has not demonstrated any actual cost. | 100000 | 0
GOR-PCO-087 | Supply of Radios for SCC, Owner, and D&M use. | Only D&M Portion is for Owner Account | 20000 | 10000
GOR-PCO-090 | Relocate Welding Crew KP153 to KP159 | Owner Instruction was not given. | 22322 | 0
GOR-PCO-091 | Archaeological Investigations, December 1999 |  |  | 0
GOR-PCO-092 | Additional Works Resulting from Archaeological Investigations | Archeological is for Owners Account | 6359 | 6359
GOR-PCO-093 | Stringing Difficulty from KP153 to KP 159 | No Scope Change, so SCC responsibility. | 54134 | 0
GOR-PCO-094 | Relocate Stringing Crew KP153 to KP159 | Owner Instruction was not given. | 24323 | 0
GOR-PCO-095 | Variant Surveys | SCC engineering mistake | 48730 | 0
GOR-PCO-097 | Construction Signs for Archaeological Areas |  |  | 0
GOR-PCO-099 | Additional Cost at RVX KP120+380, Archaelogical investigation in spread 2 | Archeological is for Owners Account | 36521 | 36521
GOR-PCO-100 | Additional Drying and Caliper Run per Owner Change Directive | Drying and Caliper run total of 1.92/meter for 362.1 km, less than SCC claim. | 1184400 | 695232
GOR-PCO-101 | Additional ROW requirements due to Future Compressor Stations & Anode Beds | In scope of work / original design | TBD | 0
GOR-PCO-102 | Pipeline Contractor Standby Costs due to Materials being held by Customs and at Bol/Bsl border | SCC mistake, they responsible for customs release | TBD | 0
GOR-PCO-103 | Costs Associated with Additional Time for Pre-Drying | Should be included in PCO-100 | 31366 | 0
GOR-PCO-104 | Supply of Personnel to Assist Owner's Subcontractor, Parsons | To be issued. | 2574 | 2574
GOR-PCO-105 | Additional Hydrotest Costs due to SIRESE requirements, Increasing Test Section from 10 to 15 | It is SCC responsibility to verify initial requirement with SIRESE; they needed to verify the installation license. | 1128275 | 0
GOR-PCO-106 | Additional ROW Restoration Costs from KP 155 to KP 174 due to Owner Change Directive | Included in Rebuilding Chiquitano Hills as below | TBD | 0
GOR-PCO-107 | EOT Claim for Various Delays, Bolivia Pipeline | Captured below, avoid double counting | TBD | 0
GOR-PCO-108 | Additional Buoyancy Control Measures above SCC recommendations | Either included in approved above or unknown (equal to Brazil value) | TBD | 0
GOR-PCO-109 | Additional Costs Related to Dames and Moore's Addendum 1 Report | Included in Rebuilding KP66 & Chiquitano Hills as below | TBD | 0
GOR-PCO-110 | Hydrotest Valve Spools | SCC fault | 16853 | 0
GOR-PCO-111 | Change to Hydrotest Point Locations | SCC mistake. | 51470 | 0
GOR-PCO-113 | Survey at KP-66 | Needs verification. | 8165 | 8165
GOR-PCO-115 | Topographical Survey at KP 150+000 to KP 175+000 | Included in Chiquitano Hills restoration | 42857 | 0
GOR-PCO-116 | Cathodic Protection Crew Standby | Needs verification, no reason for standby given. | 100466 | 0
GOR-PCO-117 | Archaeological Investigation Support Under Direction of D&M at several locations Spread 1 | Directed by D&M - Owner review needed | 7490 | 7490
GOR-PCO-119 | Mechanical Crew Standby at San Juan Camp and At KP 174+310 Awaiting Release of Materials from Customs by Owner. | SCC mistake, they responsible for customs release | 36496 | 0
GOR-PCO-120 | Mechanical Crew Standby at KP0+000 and KP87+850 Awaiting Release of Materials from Customs by Owner | SCC mistake, they responsible for customs release | 45948 | 0
GOR-PCO-121 | Electrical Crew Standby at KP0+000 Awaiting Release of Materials from Customs by Owner. | SCC mistake, they responsible for customs release | 7255 | 0
GOR-PCO-122 | Pressurization of the Bolivian Pipeline Segment with 100 PSI of Dry Air | Owner Directive. | 27135 | 27135
GOR-PCO-124 | Stand-by of Restoration Crews at KP179+700 & KP218+200 | Needs verification, no reason for standby given. | 48035 | 0
GOR-PCO-125 | Stand-by of Hydrotest Crews at KP0+000 | Needs verification, no reason for standby given. | 77682 | 0
GOR-PCO-126 | Standby of our Owner requested Screw Anchor Support Crew at Bolivia Spread 2 while performing Owner’s Screw Anchor Installation scope of Work. | Needs verification, no reason for standby given. | 58842 | 0
GOR-PCO-127 | Correction of Exhibit C-2 Contract Price to equal Exhibit C-1, no cost change order | No cost change order - Owner okay | 0 | 0
| Subtotal: |  | 6487795 | 793476
| Subtotal of Forecasted & Budgeted Amount |  |  | 793476
Non-numbered items and exposure:
| Conduto Spread 3 & 4 EOT Claim due to water on ROW | Subcontractor is claiming reimb for being on standby 4-5 months. Claim has some merit, although owner removed subcontractor from ROW for environmental mitigation. | 4000000 | 2000000
| Rebuilding Chiquitano Hills | Best guess at about 500k to 1000k for restoration per ridge for 5 ridges. | 2500000 | 2500000
| Rebuilding ridge KP 66 (Bolivian Machu Pichu) | ESMS requirement. Based on best estimate of actuals spent | 2000000 | 1000000
| Future EOT Claim SCC | Claim has some merit because of delay in Bolivian pipeline. Related to Conduto Srpead claim above. | 2000000 | 1000000
| Civil Unrest - San Matias, Starting Mar. 20, 2000 | FM Event up to 10 days . | 2649096 | 500000
| Civil Unrest - Bolivia, September | FM Event up to 10 days | 2649096 | 0
| Contingency for Bouyance Control Measures above SCC recommendations | Not issued. | 500000 | 250000
| Warning letter - Bolivia | Warning should not be a reason for for SCC to shutdown and incur additional standby cost. | 100000 | 0
| SCC Pipeline Commissioning Support | Included in Contract section 3.25. | 100000 | 100000
Stand-by Charges and relocation due to lock-out at KP 347+222
| Stand-by Charges and relocation due to lock-out at KP 345+822 |  |  | -1101701
| Increase in wall Thickness from 0.277" to 0.312" |  |  | -400000
Revised Tie-in Design of KP242 facility
Additional Cost of Lagoon and Pond crossings KP 221+750 - KP 360+000
Additional Cost of Crossing Wetland and Minor River at KP 84
SCC Additional Staffing
SCC Extra Contingency
Credit for Material, Freight, technicians in reroutes paid for by owner
| Credit for Screw Anchors bought by owner | Hard Line Position is value paid by Owners including transportation, taxes | 0 | -1101701
| Credit for As-builts - GIS / Wetland Surveys | Approximate value for Wetland mapping (mostly) and GIS/As-builts by Turnstone | 0 | -400000
| Subtotal: |  | 16498192 | 5848299
| Total SCC Claim in Excess of "Owner's Estimate" |  | 22192511
Total GasBol Pending / Forecasted Change Orders |  |  | 22985987