## Sheet1
Enron Project - Status
Engine: |  | LM6000PC E-Sprint w/o VIGV’s
Climate: |  | Winterization to –10F, Noise to 85 dBA
Enclosures: |  | Water Injection Skid, Liquid Fuel Skid, and Gauge Panel
Items Not Enclosed: |  | Auxiliary Skid, Hydraulic Starter, Sprint Skid, and CO2 – (Winterized)
Gas/Water Units: |  | Two simplex LP Water Injection Pumps w/Enclosures and heaters, no heat tracing
Dual Fuel Units: |  | Standard LP/HP Water Injection Pump Skids w/Enclosures and heaters, no heat tracing
Single Liquid Fuel Pump Skid w/Enclosure and Heat Tracing
Unit | Ready to Ship Date | Contract Ship Date | Drawing Series | Unit Serial Number | Turbine Serial Number | Generator Serial Number | Product Sales Number | Fuel | Generator Manufacturer | Piping | Line Side | Lube Oil Cooling | Exhaust Stack | Expected Site Assignment | Unit Testing | Unit
1 | 2000-06-20 | 2000-07-30 | 559XXX | 308898 | 191-198 | 336X | 601134 | Gas | GE | RH | RH | Fin/Fan | 45 ft HVY | ESA | Static Test | 1
7 | 2000-06-22 | 2000-07-30 | 568XXX | 309101 | 191-192 | 290ERJT / 2979 | 601134B | Dual | Brush | RH | RH | Fin/Fan |  | *Florida | Full Test | 7
8 | 2000-06-30 | 2000-07-30 | 568XXX | 309123 |  | 290ERJT / 3210 | 601134B | Dual | Brush | LH | LH | Fin/Fan |  | *Florida | Static Test | 8
4 | 2000-07-05 | 2000-08-30 | 559XXX | 308999 |  |  | 601134 | Gas | GE | LH | LH | Fin/Fan | 45 ft HVY | ESA | Static Test | 4
5 | 2000-07-10 | 2000-08-30 | 559XXX | 309020 | 191-204 |  | 601134 | Gas | GE | RH | RH | Fin/Fan | 45 ft HVY | ESA | Static Test | 5
6 | 2000-07-21 | 2000-08-30 | 559XXX | 309073 | 191-212 | 336X636 | 601134 | Gas | GE | LH | LH | Fin/Fan | 45 ft HVY | ESA | Full Test | 6
2 | 2000-07-26 | 2000-09-30 | 559XXX | 308951 |  |  | 601134 | Gas | GE | LH | LH | Fin/Fan | 45 ft HVY | ESA | Static Test | 2
3 | 2000-08-15 | 2000-09-30 | 559XXX | 308972 |  |  | 601134 | Gas | GE | RH | RH | Fin/Fan | 45 ft HVY | ESA | Static Test | 3
9 | 2000-08-19 | 2000-10-20 | 581XXX | 309266 |  |  | 601134C | Gas | Brush | RH | RH | Shell/Tube | By Enron | Austin | Full Test | 9
10 | 2000-09-01 | 2000-10-20 | 581XXX | 309307 |  |  | 601134C | Gas | Brush | LH | LH | Shell/Tube | By Enron | Austin | Static Test | 10
11 | 2000-09-06 | 2000-10-20 | 581XXX | 309376 |  |  | 601134C | Gas | Brush | RH | RH | Shell/Tube | By Enron | Austin | Static Test | 11
12 | 2000-09-14 | 2000-11-30 | 581XXX | 309398 |  |  | 601134C | Gas | Brush | LH | LH | Shell/Tube | By Enron | Austin | Static Test | 12
13 | 2000-09-21 | 2000-11-30 | 562XXX | 309420 |  |  | 601134A | Gas | Brush | RH | RH | Fin/Fan | 45 ft | PSCO | Full Test | 13
14 | 2000-09-28 | 2000-12-30 | 562XXX | 309505 |  |  | 601134A | Gas | Brush | LH | LH | Fin/Fan | 45 ft | PSCO | Full Test | 14
15 | 2000-10-25 | 2000-12-30 | 562XXX |  |  |  | 601134A | Gas | Brush | LH | LH | Fin/Fan | 45 ft | PSCO | Static Test | 15
16 | 2000-11-01 | 2001-01-30 | 568XXX |  |  |  | 601134A | Gas | Brush | RH | RH | Fin/Fan | 45 ft | PSCO | Full Test | 16
17 | 2000-11-13 | 2001-01-30 | 568XXX |  |  |  | 601134B | Dual | Brush | LH | LH | Fin/Fan |  | *Florida | Full Test | 17
18 | 2000-11-20 | 2001-01-30 | 568XXX |  |  |  | 601134B | Dual | Brush | RH | RH | Fin/Fan |  | *Florida | Static Test | 18
19 | 2000-11-27 | 2001-02-28 | 568XXX |  |  |  | 601134B | Dual | Brush | LH | LH | Shell/Tube | By Enron | *Las Vegas | Static Test | 19
20 | 2000-12-10 | 2001-02-28 | 562XXX |  |  |  | 601134B | Dual | Brush | RH | RH | Shell/Tube | By Enron | *Las Vegas | Static Test | 20
21 | 2001-01-05 | 2001-03-30 | 581XXX |  |  |  | 601134C | Gas | GE | LH | LH | Fin/Fan | 45 ft HVY | ESA | Static Test | 21
22 | 2001-01-12 | 2001-03-30 | 581XXX |  |  |  | 601134C | Gas | GE | RH | RH | Fin/Fan | 45 ft HVY | ESA | Full Test | 22
23 | 2001-01-20 | 2001-04-30 | 581XXX |  |  |  | 601134C | Gas | Brush | LH | LH | Shell/Tube | By Enron | *Las Vegas | Full Test | 23
24 | 2001-03-13 | 2001-04-30 | 581XXX |  |  |  | 601134C | Gas | Brush | RH | RH | Shell/Tube | By Enron | *Las Vegas | Static Test | 24