## Power Projects
Project Name | Enron Business Unit | Project Type I | Project Type/Description | Originator(s) | Responsible EA Tech Services | Technical Support | Location | $$ Exposure | Assessment of Risk | Updated | Update/Comments
AMPS | North America - Principal Investing |  | Generation Technology - mobile power units | Michael Miller, Kyle Kitagawa | Bob Virgo | Grigory Zelondzhev | Various |  |  | 2001-06-14 | Working on the marketing questions/issues.
Austin | North America - East |  | Development/Construction - Simple Cycle Project (~180 MW) | Jeff Keenan | Bob Virgo | Eric Booth | Austin, TX |  |  | 2001-05-15 | Construction nearly complete. Estimated completion = May 31, 2001.
Electrobolt | South America | Greenfield | Development/Construction - Simple Cycle Project (386 MW) | Brett Wiggs | Rod Blackham | EEOS | Rio de Janeiro, Brazil |  |  | 2001-05-15 | Site is under development - initial foundations and temporary facilities. 2 of 6 gas turbines to be shipped today to construction site. EEOS/NEPCO are primary parties in construction. Target Operation date = November 1, 2001.
Fort Pierce | North America - East |  | Repower Steam Plant | Dave Fairley | Bob Virgo, Mike Coleman | Darrell Stovall | Ft. Pierce, FL |  |  | 2001-06-28 | Dave Duran to talk with TECO about a potential ENRON/Enron joint venture arrangement
Las Vegas Cogen | North America - West |  | Development/Construction - 4x2 LM6000's combined cycle plant | Ed Clark | Wayne Mays | Bob Williams, Bob Chmielewski, Ed Dannhaus | Las Vegas, NV |  |  | 2001-06-14 | Agreement signed with Modern Continental; expecting to finalize on 08/31. Noise mitigation still needs discussion. Sound walls and transmission hardware concerns need to be run to ground.
Longview | North America - West |  | Greenfield development of a GE 7FA combined cycle power plant at the Port of Longview leased site | Jake Thomas | Wayne Mays | Don Hammond, Mark Mullen, Bill Williams | Longview, WA |  |  | 2001-07-03 | Modern Continental South agreed to be EPC for a full project wrap on LED. They will manage four (4) sub-contractors. RCI will be the civil and possibly the mechanical on the project. Amec-Simons will be design engineer. Electric is YTBD. Draw down schedule is being prepared. Option Draft for E-Next EPC prepared and sent July 2. FNTP sometime in October if not sooner. Water issue is being resolved. Public meeting held 6-29-01. No opposition. Major equipment identified. E-Next contracts being prepared for Nooter-Ericksen (HRSG) and Alstom (ST). GSU is next. Expect EPC contract negotiations to begin end of 2nd week in July. Final draft of E-Next EPC being reviewed and sent (hopefully) by end of the week.
Roseville | North America - West |  | Site acquisition underway. Seeking to secure emission credits | Mike McDonald | Wayne Mays | Don Hammond | No. California - near Sacramento |  |  | 2001-05-15 | Working on 100% of emissions reduction credits on the 700 MW plant. In discussion with WAPA about transmission topics. Engineering is on the long-term horizon.
TexMex | North America - East |  | Development/Construction - Installation of AC/DC tie, power export to Mexico | Ozzie Pagan | Bob Virgo | Walter Coffer, Scott Laidlaw | Brownsville, TX |  |  | 2001-04-23 | Interface with Brownsville public utility and ABB Engineering. Currently on hold.
Vitro | Mexico | Greenfield | Development/Construction - Combined Cycle Cogen Project (245 MW) | Steve Irvin, Marc Sabine, Max Yzaguirre | Bob Virgo | Ed Elam | Monterrey, Mexico |  |  | 2001-06-18 | Const Mob 03/26/01. Sell down in progress. Contractor's change request under discussion. Applying for co-generation customs exemption.
Midway | North America - East |  | Development - up to 3 x 7FA simple cycle plant | Greg Krause, Raimund Grube | Bob Virgo |  | St. Lucie Co., FL |  |  | 2001-07-02 | Discussions are underway with TECO regarding a potential TECO/ENRON joint venture arrangement. Further discussions may be pursued with other potential counterparties interested in a 2002/3 COD.
Rio Gen |  |  |  |  | Rod Blackham
Westinghouse (W) 501D5A Turbines | Enron Americas |  |  | Ben Jacoby | Mike Coleman |  | Various |  |  | 2001-07-05 | Enron has one in storage (Ben Jacoby). Team inspected it last week. There are various potential offers referred to development for consideration.
Mitsubishi (MHI) 501F Turbines | Enron Americas |  |  | Brett Wiggs |  |  | Various |  |  | 2001-07-05 | Turbines assigned: #1 - Fort Pierce #2, #3, #4 - to Rio Gen or for sale Again, offers referred to development for consideration.
Ukrainian Turbines |  |  |  |  | Bob Virgo
EPC Negotiation Team | Enron Americas | Greenfield | Lead EPC and turbine purchase contract discussions | Lisa Bills, Ron Tapscott, Chip Schneider, John Schwartzenburg | Bob Virgo | Mike Coleman | ENA

## Gas Projects
Project Name | Enron Business Unit | Project Type I | Project Type/Description | Originator(s) | Responsible EA Tech Services | Technical Support | Location | $$ Exposure | Assessment of Risk | Updated | Update/Comments
Napoleonville | North America |  | Complete/Put in a new service well at Napoleonville. Remove from service two (2) Dow wells |  | David Owen, Garry Wilson |  | Assumption Parish, LA |  |  | 2001-07-03 | Coordination and planning of field activities underway. Currently responding to LA Department of Natural Resources permit information requests.
Crawfish | North America |  | Dismantle and remove Crawfish gas processing plant | Patrick Johnson | Dave Owen |  | Assumption Parish, LA |  |  | 2001-07-03 | All activities scheduled to begin by mid-July. Discussions with Bridgeline regarding the handling of pipeline liquids re ongoing, but not critical to proceeding with the project.
Crescendo | North America |  | Install a low-BTU gas processing plant in western Colorado. Includes a P/L interconnect, gathering system, electric power lines, and a substation | Scott Josey | Dave Owen |  | Mesa County, CO |  |  | 2001-07-03 | Project is currently on schedule and within budget. All major equipment has been ordered. Agreements for electric power supply and for the pipeline interconnect with NWPL are in place. Bids for gathering system construction are in preparation and will be let during July. Project risks include: (1) receipt of construction permits by mid-July; (2) delivery of vendor drawings to the engineering subcontractor; (3) fall and winter construction at start-up. None of these risks items are currently affecting cost or schedule.
Oakhill | North America |  | Replacement/Upgrade of two (2) 3,500 hp compressors | Mark Knippa | Dave Owen |  | Carthage, TX |  |  | 2001-05-14 | Executable pricing still not available. Notional value updated & Hanover's packaging & installation costs received. Meeting with customer on the week of 6/4.
Iroquois | North America |  | Greenfield installation of compressors. Either 17,500 hp or 25,500 hp depending on load | Andrew Miles | Dave Owen |  | Brookfield, CT |  |  | 2001-06-28 | Iroquois waiting for FERC approval on two (2) potential expansions. One expansion on Eastchester project, another to eastern Long Island, NY to serve new power plant load - will know by end of summer. Either expansion will trigger projects.
Nicor | North America |  | 80,000 - 100,00 HP replacement | Ned Higgins | Dave Owen |  | Troy Grove, IL |  |  | 2001-05-22 | Preliminary proposal (project specifications and cost estimate) given to commercial originator. Meeting scheduled for 6/12 to present first proposal. Waiting on follow-up technical meeting and additional data.
Anadarko | North America |  | Replacement/Upgrade - 12,500 hp | Ned Higgins | Dave Owen |  | Panola, TX |  |  | 2001-05-17 | ENA Facility Planning prepared a "first pass" scoping document and cost estimate. A meeting is scheduled for Monday 6/4 to present a proposed term sheet.
Questar | North America |  | Base gas monetization | Paul Bieniawski, Eva Rainer | Garry Wilson | Walter Coffer, Scott Laidlaw | Utah |  |  | 2001-04-18 | Early stage. Evaluating regulatory issues with ENA Regulatory Affairs.
Halliburton Energy Services (HES) I | North America |  | Manage HES' commodity positions derived from in-kind payments by Gas Storage operators | Paul Bieniawski | Garry Wilson |  | U.S. |  |  | 2001-07-05 | ENA and HES held an initial meeting with NNG. NNG is reviewing HES' proposal.
Halliburton Energy Services (HES) II | North America |  | Manage HES' commodity positions derived from in-kind payments by E&P operators | Paul Bieniawski | Garry Wilson |  | U.S. |  |  | 2001-07-05 | ENA will met with HES' senior executives.
Columbia Gas | North America |  | Base gas monetization | Miguel Vasques, Paul Bieniawski | Garry Wilson |  | Northeast U.S. |  |  | 2001-07-05 | Met with client and they indicated that they would be interested in transacting with ENA. However, only to the extent that they would not have to share sale proceeds of base gas.
Montana Power | North America |  | Base gas monetization | Eva Rainer | Garry Wilson |  | Montana |  |  | 2001-07-05 | Negotiating CA. Planning to meet next week to discuss financial aspects of the monetization. ¦ Sidenotes: MPC is being acquired by Northwestern Corp (est. completion Q3 2001). MPC is in the middle of hearings to determine how to allocate revenues from previous sales of unneeded base gas.