## Sheet1
Enron East Power Development
DRAFT - Site Bank Report
2001-04-23
Site | County | Acres | Developer | Status | Objective | Balance Sheet Cost Basis as of 4/18/01
Developer
FLORIDA*
Midway | St. Lucie County | 109.83 | Krause | Air permit and local approvals received; awaiting issuance of ERP. | Use site to attract turbines in order to gain summer '02 MWs and promote on site sale. In current discussions with TECO, Calpine, Mirant, and NRG. | 914244.45
Corbett | Palm Beach County | 40 | Stevens | Development work underway to support summer '03 start date. | Develop for site flip, additional MWs, or customer deal. | 514827.41
Pompano Beach - Thornborough | Broward County | 28 | Krimsky | Development work underway to support summer '02 start date. Likely to slip to '03 due to local opposition. | Develop for site flip, additional MWs, or customer deal. | 1129354.93
Homestead Area (Nitram Partners) | Miami-Dade County | 38.5 | Krause | Inactive - development efforts focused on Certosa Holdings (see below). | NA | 0
Deerfield Beach - Broward (Mancini) | Broward County | 30 | Krimsky | Development work underway to support summer '02 start date. Likely to slip to '03 due to local opposition. | Develop for site flip, additional MWs, or customer deal. | 975411.14
South Dade - Certosa Holdings | Miami-Dade County | 64 | Krause | Development work underway to support summer '02 start date. Likely to slip to '03 due to switch from GE7EA to MHI 501F turbines. | Develop for site flip, additional MWs, or customer deal. | 820900.2
Doral Kelley | Miami-Dade County | 18.6 | Krause | Inactive -- Option Agreement Terminated. | NA | 344882.45
Medley (Dunn) | Miami-Dade County | 20 | Krause | Continuing limited development work. Currently working to finalize long-term lease agreement. | Develop for site flip, additional MWs, or customer deal. | 205318.18
[5 empty] | Subtotal | 4904938.76
GEORGIA
Athens (Summerour) | Clarke County | 84 | Keenan / Grube | In active development to support a summer '03 combined cycle position. | Develop for site flip, additional MWs, or customer deal. In discussions with FPL, Calpine, AES, and TECO on site sale. | 157201.19
Athens (Tillman) | Clarke County | 83.634 | Keenan / Grube | In active development to support a summer '03 combined cycle position. | Develop for site flip, additional MWs, or customer deal. In discussions with FPL, Calpine, AES, and TECO on site sale.
Hartwell | Hart County | 83.92 | Keenan / Grube | In active development to support a summer '03 combined cycle position. | Develop for site flip, additional MWs, or customer deal. In discussions with FPL, Calpine, AES, and TECO on site sale. | 201904
[5 empty] | Subtotal | 359105.19
ILLINOIS
Chicago - Pontiac (Green) | Livingston County | 146.5 | Stevens | Initially secured as part of '00 JV with Peoples Gas. | Continuing limited development work in order to preserve site optionality. | 167512.74
Chicago - Plano (Konicek) | Kendall County | 120 | Mitro | Initially secured as part of '00 JV with Peoples Gas. | Continuing limited development work in order to preserve site optionality. | 227128.55
[5 empty] | Subtotal | 394641.29
INDIANA
East Fork (Stone Farms, Inc.) | Pike County | 79.5 | Tapscott | Inactive | Will continue land option payments. | 6000
Switzerland (Curry Exec. Of Cutter Est) | Switzerland County | 88 | Tapscott | Inactive | Will continue land option payments.
Lawrence (Jones & Jones) | Lawrence County | 60 | Tapscott | Inactive | Will continue land option payments.
IOWA
Boone (Bristle) | Boone County | 80 | Tapscott | Inactive | Will continue land option payments. | 0
Louisa (Farrier) | Louisa County | 80 | Tapscott | Inactive | Will continue land option payments. | 0
Washington (Ossman, Est of Kaufman) | Washington County | 80 | Tapscott | Inactive | Will continue land option payments. | 0
KENTUCKY
Calvert City (Riley) | Marshall County | 78.44 | Booth | All permits received, but will have to resubmit air permit depending on equipment configuration. Site was originally part of '00 peaker program, but was moved when interconnection disputes arose with TVA. | Renegotiate interconnection requirements in order to effect site sale. | 6715
LOUISIANA
Calcasieu (Palvest, Inc.) | Calcasieu Parish | 60 | Tapscott | Development in process. | Site initially developed to support additional MW position desired by desk. Limited development now being pursued to support customer deal or site sale. | 229694.21
St. Charles (3C Riverside Properties) | St. Charles Parish | 45 | Tapscott | Development in process. | Site initially developed to support additional MW position desired by desk. Limited development now being pursued to support customer deal or site sale. | 151751.34
Jefferson Davis (Brown & Guillory) | Jefferson Davis Parish | 120 | Tapscott | Development in process. | Site initially developed to support additional MW position desired by desk. Limited development now being pursued to support customer deal or site sale. | 67260.75
[5 empty] | Subtotal | 448706.3
MISSOURI
Stoddard (Bond, et al.) | Stoddard County | 60.5 | Tapscott | Development in process. | Site initially developed to support additional MW position desired by desk. Limited development now being pursued to support customer deal or site sale. | 112168.73
Cape Girardeau (AKA Lutesville) (Lorberg Trust) | Cape Girardeau County | 42 | Tapscott | Development in process. | Site initially developed to support additional MW position desired by desk. Limited development now being pursued to support customer deal or site sale. | 60560.65
Bollinger | Bollinger County | 43 | Tapscott | Development in process. | Site initially developed to support additional MW position desired by desk. Limited development now being pursued to support customer deal or site sale. | 21560.69
[5 empty] | Subtotal | 194290.07
NORTH CAROLINA
Edgecombe** | Edgecombe County, NC | 26.16 | Keenan | Inactive | Site initially developed to support VEPCO origination deal using SW501D5A which was damaged prior to delivery. Limited development now being pursued to support customer deal or site sale. | 284946.67
TENNESSEE
Haywood (Mann) | Haywood County, Tennessee | 80 |  | Continuing limited development work in order to complete site sale. | Site option sold to AES in Dec. '00 for $5 million. Minimum additional payment of $2.5 million to be received by Aug. '01. | -238223.58
Shelby (Rachel Ann Hays) | Shelby County, Tennessee | 97.214 |  | Continuing limited development work in order to effect site sale. |  | 107000
[5 empty] | Subtotal | -131223.58
WISCONSIN
Arpin (O'Shasky) | Wood County, Wisconsin | 59 |  | Inactive - jointly held with Great River Energy. | Will continue land option payments. | 1250
[5 empty] | Total | 6469369.7
Notes:
*Excludes Ft. Pierce
**100% of Cost to be allocated to Southeast orig.