## 2000
Doorstep schedule
Week | Location | Days | Risk operations | RAC - Ted M. | RAC - Lynn B.
3rd Q 2000
2000-08-28 | New York (in progress) | 1 | Shona Wilson | NA | Ken Horton
2000-09-25 | Portland EBS | 1 | Shona Wilson | Rebecca Phillips | NA
2000-09-26 | Portland Power | 2 | Shona Wilson | Rebecca Phillips | Ken Horton
4th Q 2000
2000-10-02 | Chicago | 3 | Mike Moscoso | Frank Hayden | 1
2000-10-10 | Panama City | 2 | Scott Earnest, Michelle Bruce | Tom Moran | 1 (deal test in Houston)
2000-10-23 | St. Louis | 3 | Mike Moscoso | NA | 1
2000-11-06 | Hamburg MG, Enron | 3 | Shona Wilson | Lloyd Fleming | 1
2000-11-06 | San Francisco | 2 | Sally Beck | Ted Murphy | NA
2000-11-13 | Stockholm | 2 | TBD | Manfred Roenz | NA
2000-11-20 | Montreal | 3 | Shona Wilson | Vlady Gorny | NA
2000-11-20 | Toronto | 3 | Shona Wilson | Vlady Gorny | NA
2000-12-04 | Bucharest | 2 | TBD | Oliver Gaylard | NA
1st Q 2001
2000-01-08 | Chicago Enron & MG | 4 | Mike Moscoso | Frank Hayden | 1
2000-01-08 | Monterrey (Mexico) | 2 | Scott Mills, Sally Beck | Xochitl Figueroa | 1
2000-01-08 | Mexico City | 2 | Scott Mills, Sally Beck | Xochitl Figueroa | 1
2000-01-15 | Denver | 4 | Shona Wilson | Manfred Roenz | 1
2000-01-15 | St. Louis | 3 | Bob Hall | Frank Hayden | 1
2000-01-15 | Houston - interest rate, fx | 8 | Jeff Gossett | Nick Paraschos | 1
2000-01-29 | NY MG & Enron | 8 | Brenda Herod | David Port | 1
2000-01-29 | Calgary | 5 | Shona Wilson, David Maxwell | Tom Moran | 1
2000-02-05 | Chicago Enron & MG | 4 | Mike Moscoso | Xochitl Figueroa | 1
2000-02-12 | Sao Paulo | 2 | Scott Mills, Mike Moscoso | Rodrigo Lamas | 1
2000-02-12 | Buenos Aires | 2 | Scott Mills, Mike Moscoso | Rodrigo Lamas | 1
2000-02-12 | Panama City | 2 | Leslie Reeves | Xochitl Figueroa | 1
2000-02-12 | St. Louis | 3 | Bob Hall | NA | 1
2000-02-12 | Rio de Janeiro | 2 | Todd Hall | Rodrigo Lamas | NA
2000-02-19 | Santiago | 2 | Todd Hall | Rodrigo Lamas | NA
2000-02-19 | Lima | 2 | Mike Moscoso | Xochitl Figueroa | NA
2000-02-19 | London - coal, global liquids, pulp & paper, weather | 7 | Stacey White | Oliver Gaylard | 2
2000-02-26 | London - power | 7 | Stacey White | Oliver Gaylard | 2
2000-03-05 | London - gas | 7 | Leslie Reeves | Oliver Gaylard | 2
2000-03-05 | Helsinki | 5 | Todd Hall | Bjorn Hagelmann | 1
2000-03-05 | Chicago Enron & MG | 4 | Mike Moscoso | Vlady Gorny | 1
2000-03-05 | Moscow MG & Enron | 4 | TBD | Manfred Roenz | NA
2000-03-12 | London - credit, metals | 7 | Brenda Herod | Oliver Gaylard | 2
2000-03-12 | Panama City | 3 | Jeff Gossett | Rodrigo Lamas | 1
2000-03-19 | Bogota (Electricity) | 3 | Jeff Gossett | Vlady Gorny | NA
2000-03-19 | Sydney | 8 | Brent Price, Stacey White | John Suttle | 1
2000-03-26 | Cologne, Germany (MG) | 1 | TBD | Manfred Roenz | NA
2000-03-26 | Tokyo | 3 | Shona Wilson | John Suttle | NA
2000-03-26 | Houston - global liquids, coal, emmissions | 10 | Leslie Reeves | Christian LeBroc | 4
2nd Q 2001
2000-04-02 | Seoul | 2 |  | Bjorn Hagelmann
2000-04-02 | Rome (MG) | 1 |  | Lloyd Fleming
2000-04-09 | Bilbao, Spain (MG) | 1 |  | Lloyd Fleming
2000-04-09 | Madrid | 1 |  | Homin Amiry
2000-04-09 | Barcelona | 1 |  | Homin Amiry
2000-04-09 | St. Louis | 2 | Bob Hall | NA
2000-04-09 | Panama City | 2
2000-04-16 | Oslo | 2 | Stacey White
2000-04-16 | Chicago Enron & MG | 4
2000-04-16 | Montreal | 2
2000-04-23 | Calgary | 4
2000-04-23 | Frankfurt | 2
2000-05-01 | Sofia, Bulgaria (MG) | 1
2000-05-08 | New Delhi (MG) | 1
2000-05-07 | Beijing | 1
2000-05-07 | Shanghai | 1
2000-05-14 | Hong Kong | 1
2000-05-14 | Johannesburg | 1 | Shona Wilson | Bjorn Hagelmann
May | Montreal | 2
May | Chicago Enron & MG | 4
June | Montreal | 2
2000-06-04 | Jakarta | 1
2000-06-04 | Taipei | 1
2000-06-11 | Ho Chi Minh, Vietnam | 1
2000-06-18 | Manila | 1
June | Chicago Enron & MG | 4
July | Montreal | 2
July | Chicago Enron & MG | 4
July | India EPEG
July | Mariner
July | Houston - pulp and paper, weather | 7 | Shona Wilson | Manfred Roenz | 2
July | Houston - gas | 10 | Brenda Herod | Frank Hayden | 2
July | Houston - power | 10 | Kristin Albrecht | Rebecca Phillips | 2
3rd Q 2001
2000-08-28 | St. Louis | 2 | Bob Hall
Aug | Chicago Enron & MG | 4
Sept | Chicago Enron & MG | 4
Aug | Montreal | 2
Sept | Montreal | 2
2000-09-18 | Portland | 3
2000-09-18 | Panama City | 2
2000-09-25 | Chicago Enron & MG | 4
2000-09-25 | Stockholm | 1
4th Q 2001
2000-10-02 | Houston | 5
2000-10-02 | Houston | 5
2000-10-09 | Houston | 5
2000-10-09 | St. Louis | 2 | Bob Hall
2000-10-09 | Brussels | 1
2000-10-16 | Denver | 3
2000-10-16 | Houston | 5
2000-10-23 | Houston | 5
2000-10-23 | Chicago Enron & MG | 4
2000-10-23 | St. Louis | 2 | Bob Hall
2000-10-30 | Montreal | 2
2000-10-30 | Houston | 5
2000-10-30 | St. Louis | 2 | Bob Hall
2000-11-06 | San Francisco | 2
2000-11-06 | Chicago Enron & MG | 4
2000-11-06 | Montreal | 2
2000-11-06 | Hamburg | 1
2000-11-13 | India EPEG | 4
2000-11-20 | Tokyo | 3
2000-11-20 | Nowa Saryna | 1
2000-11-27 | Toronto | 1
2000-11-27 | St. Louis | 2 | Bob Hall
2000-12-04 | Bucharest | 1
2000-12-11 | Panama City | 2
2000-12-18 | Budapest | 1
2000-12-25
MG offices (no visitation of warehouses) not reflected above:
Not to be reviewed in 2001 |  | date last reviewed
Tacke Wind |  | NA
Zurich |  | NA
Cremona |  | NA
Sardinia |  | NA
Moscow |  | NA
Warsaw |  | NA
Croatia |  | NA
Greece |  | NA
Teeside |  | NA
Wilton |  | NA
Chester |  | NA
Oxford |  | NA
Torpey |  | NA
Milan |  | NA
Brussels |  | NA
Nowa Saryna |  | NA
Trakya |  | NA
Amsterdam |  | NA
Budapest |  | NA