## summary
2001-05-18
MARINER ENERGY, INC.
APPENDIX
WEEKLY DRILLING AND COMPLETION SUMMARY
[7 empty] | PRESENT | PROPOSED
|  | PROSPECT | AREA | WELL | E/D | WI% | DEPTH | TD | COMMENT
| I. | WELLS CURRENTLY DRILLING
|  | Sandy Lake | Onshore, Tx | B-1 ST #2 | E | 40% | 10,680' | 10,720' | Completion made water. Unloading well
after water isolation treatment.
|  | Mississippi Canyon 561 | Deepwater | OCS-G #1 | E | 16.7% | 8,953' | 6,901' | Repairing BOPs.
(Hells Canyon)
| II. | WELLS REACHING TOTAL DEPTH, TESTING, OR TURNED TO SALES THIS WEEK
None to report.
| III. | WELLS ANTICIPATED TO SPUD WITHIN 90 DAYS
|  | Mississippi Canyon 322 | Deepwater | OCS-G 19936 #1 | E | 40% |  |  | Antiicpate June 1, 2001 spud.
(Crater Lake)
|  | Green Canyon 516 | Deepwater | OCS-G # 1 | E | 44% |  |  | Anticipate May 28, 2001 spud.
(Yosemite)
|  | Green Canyon 472 | Deepwater | OCS-G #2 | D | 50% |  |  | Anticipate May 21, 2001 spud.
(King Kong)
| IV. | OTHER
None to report.