## Sheet1
Logistics Issue Log
Vol. Mgmt |  | Region | Pipe |  | Prod. |  |  |  | Estimated
Coordinator | Scheduler |  |  | Meter | date | Issue | Status | Date Notified | Completion
Antoinette Beale | Cora Pendergrass | Central | Michigan Consolidated | Deal 271751 | 2000-05-01 | Deal was killed on Great Lakes side and apparently not on MichCon | Cora is diligently working on a solution | 2001-08-08 | maybe 10/19
Ryan Keith | Bonnie Chang | Central | NGPL | 9254 | 2001-09-01 | Pipeline statement for NGPL shows gas flow of 6 mmbtu (1 mmbtu Sept 1-6) at REC POI 9254. Volume not pathed in Unify. | E-mailed information to Bonnie. | 2001-10-08
Ryan Keith | Bonnie Chang | Central | NGPL | 900472 | 2001-09-01 | Pipeline statement for NGPL shows gas flow of 747 mmbtu at REC POI 900472. Volume not pathed in Unify. | E-mailed information to Bonnie. | 2001-10-08
Ryan Keith | Jessica White | Central | NGPL |  | 2000-11-01 | Select Point Usage was used resulting in an imbalance for Nov 2000 production of 2,329 mmbtu. | E-mailed information to Jessica. | 2001-08-27
Ryan Keith | Cora Pendergrass | Central | NGPL (Shipper: EMW) |  | 2001-06-01 | Have a cashout to process for NGPL EMW for an imbalance on K#117650 of 17 mmbtu. Contract is currently not in Unify so I am unable to process the cashout. | Contacted Cora. | 2001-08-16
Ryan Keith | Jessica White | Central | NGPL (Shipper: ENA Upstream) | 5449 | 2001-07-01 | Pipeline statement for NGPL shows gas flow of 398 mmbtu (199-7/30 & 199-7/31) at DEL POI 5449. Volume has not been pathed in Unify. | E-mailed information to Jessica. | 8/16/01 & 8/27/01
Marlo James | Cora Pendergrass | Central | NICOR | Minooka | 2001-08-01 | Notified Cora that there was more injections than withdrawals throwing the pool out of balance by 5,000 and asked her to take a look at it. |  | 2001-10-04
Marlo James | Tammy Gilmore | Central | TROK | Various | Various | Transok 4/99-12/99 needed repathing | 10/4/01 Lisa and Tammy will resume working on the reconciliation today. | 2000-11-01
Sherlyn Schumack | Mark Schrab | Central | UGL | Various |  | All exchange tickets need to be set up and pathed for prior months.
Sherlyn Schumack | Mark Schrab | Central | UGL | 35 | 2001-08-01 | E16 withdrawals need to be zeroed out. Injections only this month.
Sherlyn Schumack | Mark Schrab | Central | UGL | 35 | 2001-08-01 | E20 Storage injection paths need to be removed. Only withdrawals this month. (See Usage column in path manager. Paths 4179668 & 417669)
Sherlyn Schumack | Mark Schrab | Central | UGL | Various | 2001-08-01 | HUB210T not tracked forward entire month. Also HUB210T has same volumes as UGL HUB210E33
Sherlyn Schumack | Mark Schrab | Central | UGL
Sherlyn Schumack | Mark Schrab | Central | UGL | Various | 2001-08-01 | HUB210E33 Exchange from UG Dawn not pathed
Sherlyn Schumack | Mark Schrab | Central | UGL | Various | 2001-08-01 | HUB210E33 Exchange to UG PEPL FZ not pathed
Sherlyn Schumack | Mark Schrab | Central | UGL | Unknown | 2001-08-01 | Pipe statement shows a delivery to Union (ECTR) at PEPL FZ EXCH not sure where this should be pathed.
Sherry Anastas | Kelly Loocke | East | CGAS | H1 | 2000-01-01 | Contract 36907 is missing a supply for O.M. Roberts for days 1/1/00 - 1/31/00. |  | 11/08/01
Sherry Anastas | Kelly Loocke | East | CGAS | P10 | 2000-01-02 | Contract 36907 is missing a market for Orwell for days 1/22/00 - 1/31/00. |  | 11/08/01
Sherry Anastas | Kelly Loocke | East | CGAS | A03 | 2000-01-02 | Contract 39999 is missing a market for TCO for 01/01/00 - 01/31/00. May be the same as deal number 908358 for 3/00. |  | 11/08/01
Sherry Anastas | Kelly Loocke | East | CGAS | A03 | 2000-02-01 | Contract 39999 is missing a market for TCO for 02/01/00 - 02/29/00. May be the same as deal number 908358 for 3/00. |  | 11/08/01
Sherry Anastas | Kelly Loocke | East | CGAS | P10 | 2000-01-02 | Contract 48049 is missing a market for Easton Util for days 1/29/00 - 1/31/00. |  | 11/08/01
Sherry Anastas | Lia Halstead | East | KOCH | IMB-TRADE | 2000-02-01 | Imbalance Trade missing for UPR Energy for 10,283 mmbtu for contract 14834.. |  | 11/08/01
Sherry Anastas | Lia Halstead | East | KOCH | IMB-TRADE | 2000-05-01 | Imbalance Trade missing for Prior Interstate for 17,868 mmbtu for contract 26378. Please path using deal number 1120498. |  | 11/08/01
Sherry Anastas | Lia Halstead | East | KOCH | 017155 & 009921 | 2000-04-01 | Contract 28223 has a missing path for 4/6,4/7, 4/11, 4/-4/17 and 4/20/00. Receipt meter 017155 and Delivery meter 009921 (see statement for detail). |  | 11/08/01
Sherry Anastas | Lia Halstead | East | KOCH | 013090 & 009429 | 2000-06-01 | Contract 14834 has a missing path for 6/22/00. Receipt meter 013090 for 3,000 mmbtu, fuel of 48 mmbtu and Delivery meter 009429 for 2,978 mmbtu. |  | 11/08/01
Sherry Anastas | Lia Halstead | East | KOCH | 020938 & 009429 | 2000-06-01 | Contract 14834 has a missing path for 6/28/00 - 06/30/00. Receipt meter 020938 for 4,137 mmbtu, fuel of 66 mmbtu and Delivery meter 009429 for 2,978 mmbtu. |  | 11/08/01
Sherry Anastas | Lia Halstead | East | KOCH | 001228 & 011470 | 2000-11-01 | Contract 20963 has a missing path for 11/01/00 - 11/30/00 Receipt meter 001228 for 1 mmbtu/d and Delivery meter 011470 for 25 mmbtu/d. |  | 11/08/01
Sherry Anastas | Lia Halstead | East | KOCH | 011257 & 010506 | 2000-12-01 | Contract 14834 has a missing path for 12/06/00. Receipt meter 011257 for 2,447 mmbtu, fuel of 39 mmbtu and Delivery meter 009429 for 2,408 mmbtu. |  | 11/08/01
Sherry Anastas | Lia Halstead | East | KOCH | 012773 & 010506 | 2000-12-01 | Contract 14834 has a missing path for 12/06/00. Receipt meter 012773 for 0 mmbtu and Delivery meter 010506 for 16,129 mmbtu. |  | 11/08/01
Lee Ann Chance | Tamie Carter | East | Tenn | Various | 6/01 - 9/01 | Waiting on pathing on 3 contracts - k13274, k18314, k32748 | Per Tenn Pipeline volume analyst reversals should appear for all or some of these contracts | 2001-09-05
Lee Ann Chance | Jesse Villereal | Upstream | Tenn | 001527 & 001447 | 2001-06-01 | Need pathing on Tenn for ENA k 36521 / brokered paths related to this contract needed from Upstream as well | ENA completed. ENA Upstream neeeding brokered transactions at point 001447 & 001527 additional days need pathing | 9/6/01 & 9/26/01
Hakeem Ogunbunmi | Daniel Lisk | West | PGE | Various | 2001-08-01 | The following contracts are not scheduled in Unify for Aug. 2001: 0202PCG031, 0202LCG023, 0202LCG020, 020LCG033, 0202LCG034, 0202LCG037, & 0202LCG012 | CLEARED
Gloria Barkowsky | Stacey Brewer | West | Questar | Granger Plant | 2001-01-01 | Eprime deal #561306 volumes not in path manager, other. |  | 2001-08-06
Marlo James | Daniel Lisk | West | SoCal |  | Various | Sent Jan a list of production periods that need to have the dailies sent from SoCal in order to cleanup the imbalances in Unify and provided Settlements with support. | Jan stated she would be contacting Socal 9/5 9/14 Received the dailies for the EES acct #2587. Jan said she would be calling SoCal back on 9/20 for the #2527 volumes. 9/28 Jan stated she would be calling SoCal again since we still have not received them. 10/9 FW list to Ted Evans to get the dailies. | 2001-08-22
Marlo James | Jane Tholt/Matt Smith | West | SoCal | Imb Trade | Various | Missing Imbalance Trade tickets | Still missing 3/00 and 8/00 trades. 10/12 spoke with Kim Olinger and Patti. Kim was to look into what was missing. | 2001-09-06
Marlo James | Daniel Lisk | West | SoCal |  | 2001-07-01 | Requested missing volumes for EES be pathed | Due to scheduler change - forwarded information to Daniel to look into. | 2001-09-12
|  | West | SoCal |  | 2001-08-01 | Needed a zero nom entered for 8/01 Harbor Cogen. |  | 2001-09-17
Stephen Swisher | Stacey Brewer | West | WFSC | L57 | 2001-04-01 | Day 27 gas is being pulled from imbalance account from WFSC. Waiting on Deal from Stacey Brewer. |  | 2001-06-15
Stephen Swisher | Stacey Brewer | West | WFSC | L57 | 2001-06-01 | Gas Day 3,4,5,6,22 missing deal (El Paso Merchant). Stacey is currently working with trader to get deals in unify. |  | 2001-09-18
Stephen Swisher | Wes Dempsey | West | WFSC | G470KS | Jan 00-Jun01 | Need to path gathering to pay gathering volume so that I can pay invoice thru Unify instead of manual payment. | Met on 8/27/01 with Lisa Kinsey, Patti Sullivan, and Wes Dempsey and we came to a conclusion that G470KS needed to be repathed in Unify. Projected to be completed Sept 17. | 2001-06-26
[5 empty] | 08/01- 09/01 | Blue Dolphin -The entire months need to be pathed | George Smith said that he will get it pathed | 2001-10-25