## summary
2001-03-30
MARINER ENERGY, INC.
APPENDIX
WEEKLY DRILLING AND COMPLETION SUMMARY
[7 empty] | PRESENT | PROPOSED
|  | PROSPECT | AREA | WELL | E/D | WI% | DEPTH | TD | COMMENT
| I. | WELLS CURRENTLY DRILLING
|  | East Breaks 558 | Deepwater | OCS-G 17266 #1 | E | 33% | 13,341' | 13,657' | TA'd well.
(LaSalle)
|  | Garden Banks 240 | Deepwater | OCS-G 10342 #4 | D | 33% | 9,446' | 10,200' | Completing.
(Mustique)
|  | Sandy Lake | Onshore, Tx | B-1 ST #2 | E | 40% | 9,421' | 10,720' | Completing.
|  | Mississippi Canyon 305 | Deepwater | OCS-G #3 | D | 25% | 9,700' | 13,300' | Drilling.
(Aconcagua)
|  | East Breaks 579 | Deepwater | OCS-G 19026 #1 | E | 50% | 5,929' | 9,060' | Drilling.
(Falcon)
| II. | WELLS REACHING TOTAL DEPTH, TESTING, OR TURNED TO SALES THIS WEEK
None to report.
| III. | WELLS ANTICIPATED TO SPUD WITHIN 90 DAYS
|  | Mississippi Canyon 323 | Deepwater | OCS-G 19936 #1 | E | 40% |  |  | Spud 2nd Quarter 2001.
(Crater Lake)
|  | Mississippi Canyon 561 | Deepwater | OCS-G #1 | E | 16.7% |  |  | Spud 2nd Quarter 2001.
(Hells Canyon)
|  | Green Canyon 516 | Deepwater | OCS-G # 1 | E | 50% |  |  | Spud 2nd Quarter 2001.
(Yosemite)
|  | Green Canyon 472 | Deepwater | OCS-G #2 | D | 50% |  |  | Spud 2nd Quarter 2001.
(King Kong)
| IV. | OTHER
None to report.