## Thermal, Hydro Operational
Thermal, Hydro - Operational | [7 empty] | 2000-02-25
| Product | Details | To do list | Relationship Manager | Product Responsible | Expected date | NPV (R$ 1.000) | Status
CSN | PPA | 200 MW form co-gen plant (non-firm) from February to June | Analyze attractiveness. Negotiate price and conditions. | João Carlos Guimarães |  | Second quarter
D'Arcy Carroll | Asset Monetization | Physical by pass (aprox. US$ 25 mm) | meeting with CSN
Marcelo Parodi | Finance | 100 MW from Itá | Internal Consensus
João Carlos Guimarães | PPA | Volta Redonda, RJ. 10 to 15 years and potential from 100 to 350 MW
| Power Sale Agreement | Riogen supply
PPA
PARAIBUNA | PPA | Peak Power from sobragi Power Plant in Juiz de For a - Minas Gerais | Set up a meeting | João Carlos Guimarães |  | 28 Feb
Decide on pricing
João Carlos Guimarães

## Thermal, Hydro Greenfield
Thermal, Hydro - Greenfield
| Product | Details | To do list | Relationship Manager | Product Responsible | Expected date | NPV (R$ 1.000) | Status
Grupo Rede - Lajeado | PPA | 50 MW Peak, 50 off-peak (Firm) | Enron to pre-pay, finance (up to $150mm) for power |  |  | Second quarter
|  | We offered them R$35/MWh | (25% of 25% 850MW nameplate); R$600mm Sudan (U$25)
Brett Wiggs |  | Probably start in Feb 00 | Enron can secure power pre-pay from Q3 ’99, including potential
|  | Multiple location | to execute power swap to SE through equity participants– Rede, CVRD
Grupo Rede territory
Santa Laura | Greenfield PCH, PPA | PPA for 7 MW generated by a PCH (nameplate capacity of 15 MW) | Engevix reviewing our confidentiality agreement | Idel Metzger | Claudia Brun |  |  | In conversation
|  | Maybe buy equity or facility and maybe deal with some debt, Engevix holds the registration | Decide on pricing
Maria Inês Granado |  | Take hydrological risk and offer 45 reais per MWh | Model is ready to run sensitivities
Claudia Brun
Remi Collonges
Erwin Landivar
Bom Retiro | Greenfield PCH, PPA | 25 MW nameplate PCH | Negotiating commercial terms of BOOT with sponsor | Idel Metzger | Claudia Brun - PPA | 2000-03-30 |  | Proposal
|  | R$ 35 million investment needed | Have first draft of binding LOI to sign once sponsor agrees to |  | Maria Inês Granado - Financing
Idel Metzger |  | 17 MW firm | proposal.
Erwin Landivar |  | Currently looking at a BOOT structure with Sponsor | Compare our numbers with Engevix's numbers
Claudia Brun |  | AES territory
Remi Collonges
Maria Inês
Odebrecht, CSN - ITÁ | PPA | Up to 169 MW Peak | Transmission study
|  | Probably start in July 00 | Legal issue
Brett Wiggs |  | Prepay power | Enron to pre-pay, finance for $ or power; need to secure transmission (capacity constraints); Gerasul right of first refusal
|  | Equity investment | First Boston report on partners rights, Gerasul/Tractebel interests; Odebrecht needs to guaranty off-take
Frigoara - Alto Jauru |  | 10 MW peak and off peak (firm) | We will offer them something between 40 and 46 |  |  |  |  | Proposal
|  | Start in may 01 | PCH; plan to build 2 (20% equity 15MW and 30MW) additional on same
Claudia Brun |  | 10 years | river; 70km 138kV line to be built; propose purchase at center of gravity; credit & construction risk
|  | MT | pre-pay for 2 additional projects
|  | Cemat territory | Clarify who is going to be responsible for this kind of product

## Biomass Operational
Biomass - Operational
| Product | Details | To do list | Relationship Manager | Product Responsible | Expected date | NPV (R$ 1.000) | Status
Aracruz | PPA | 10 MW for 5 years | Setting up meeting with CEO and CFO to discuss PPA, Asset | D'Arcy Carroll |  | Second quarter | 150
| Asset Monetization | Operational and expansion facilities | Monetization, and Financing opportunities |  | Marcelo Parodi - Asset Mon
Claudia Brun | Finance | Loan physical pulp purchase | Setting up a meeting next week between Aracruz and Orlando |  | Claudia Brun - PPA
Erwin Landivar |  | Sale of Electrochemical facility to CXY completed Dec 20 '99; 10MWs surplus at Aracruz facility available | Contact Walter Nunes or Aguiar
D'Arcy Carroll |  | Need to contact prior to Aracruz sale to ESCELSA (and after purchase discussions below)
Marcelo Parodi |  | Note: CXY needs to resign with ESCELSA for supply (35MWs increasing to 80MWs, 5 years)
Cenibra | PPA | Purchase of 10-20MWs of surplus energy; clarify fuel source (Biomass or fuel oil) | contact Sandro Moraes | D'Arcy Carroll |  | 2000-02-18 |  | prepare a letter
D'Arcy Carroll |  | Clarify connection requirements to Grid | Decide on pricing
Idel Metzger | Asset Monetization | Asset Monetization premise
João Carlos Guimarães |  | Pulp trade and derivative, linked to expansion (possible financing) plans
Copersucar | PPA | Total of 14 MW Peak, 14 off-peak (Firm) for about 10-15 sugar mills | Planning site visits for Feb 16th with CPFL mills | Luiz Otavio | Claudia Brun |  | 10080 | Proposal
|  | Proposal of R$50/MWh for the 14 MW | Negotiating to close with Dedini, Pilon and Cresciumal (Elektro)
Luiz Otavio |  | Some of the 14 MW prefer negotiating with CPFL, but no deal has been closed yet. | totalling 3 MW of Biomass, 5 years
Claudia Brun
Claudio Marques
CPFL/Elektro territory
Moema | PPA | Done deal | Parodi needs to transfer responsibility | Luiz Otavio
|  | New opportunities: They say that they can increase the generation from 2 to 12 MW from 2001 on | Confirm regulatory approval
Marcelo Parodi |  | With that increase, an investment of R$ 70.000/KM would be needed in the distribution line | ECE will pay services this week to Elektro |  |  |  |  | Done
The distance needed is about 30 KM, so an investment of R$2.100.000
Rigesa | Asset Monetization | Currently generating 4MW | Presentation made today | Ricardo Lisboa | Marcelo Parodi
|  | Asking for bid to replace their power boiler and to install a cogeneration |  |  | Ricardo Lisboa
|  | EPC Co-management | [5 empty] | In conversation
Celesc territory
SC
Champion | Finance
In conversation
| Pre payment |  | Review proposal to pre pay Elektro's PPA
Carbocloro | PPA |  | Discuss short term supply | D'Arcy Carroll
D'Arcy Carroll | [7 empty] | In conversation
CST | Asset Monetization | New power plant construction based on steel mill gases and eventually Monetization of existing plants | Discuss with consultant and waiting to set up a meeting | João Carlos Guimarães
PPA
Maria Inês Granado | [7 empty] | In conversation
Erwin Landivar
Rodrigo Garcia
Idel Metzger
Cosipa | Monetization | Coke oven Monetization | Waiting for a meeting with the CFO | João Carlos Guimarães
| Coal supply | Coal supply | Waiting for the industrial director to answer the questionnaire we've sent
| Financing | Invest in a 130 Mw power plant | Meeting with CFO next wednesday |  |  |  |  | In conversation
|  | EBE territory | Check incremental impact
Cubatão
Dedini |  | 1,5 MW plus a possibility of a call option up to 7,0 MW in order to lock them with us in the | Plant visit next week with contract to close deal | Claudio Marques | Claudia Brun
Claudia Brun |  | case of buying not just the excess power;
Claudio Marques |  | Firm energy May-November | [5 empty] | In conversation
Santini (Elektro) |  | SP
Elektro territory
Pilon |  | 0,5 MW plus a possibility of a call option up to 3,2 MW | Plant visit next week with contract to close deal | Claudio Marques | Claudia Brun
Claudia Brun |  | Firm energy May-November
Claudio Marques |  | SP | [5 empty] | In conversation
Pedro Kurt (Elektro) |  | Elektro territory
Cresciumal |  | 0,7 MW | Meeting this week, we need to set up the proposal | Luiz Otavio | Claudia Brun
Claudia Brun |  | Firm energy May-November | basis to send.
Claudio Marques |  | SP | They asked for 6 years and we want 8. |  |  |  |  | In conversation
Luiz Otavio |  | Elektro territory
Riocell | Pre Payment | A Pre payment of pulp and paper of aprox; US$ 50 mm. | Presented a proposal and client came back asking for better pulp price | Idel Metzger | Corbin Barnes | 2000-02-23 | 3500
and interest rate.
Corbin Barnes | Asset Monetization | Biomass and Coal Generation | Currently working on revised proposal | Idel Metzger |  |  |  | In conversation
Idel Metzger |  |  | Also analyzing potential asset Monetization
Maria Inês Granado |  |  | Define hedge strategies and how to sell pulp and paper on best effort
Rodrigo Garcia |  |  | basis
Sugar Mills - Several |  | Up to 10 MW bagass of several mills that require investments in connections/transmissions | Visits scheduled for next week. | Several | Claudia Brun
Firm energy May-November
Claudio Marques |  | SP | [5 empty] | In conversation
Claudia Brun |  | Mostly in CPFL territory
Plants - Ester, Colombo, Nardini, Virálcool e Nova América.

## PCH Operational
PCH - Operational
| Product | Details | To do list | Relationship Manager | Product Responsible | Expected date | NPV (R$ 1.000) | Status
Belgo Mineira | PCH - PPA SWAP | Visited with Belgo this week | Expecting to receive more details on hydrological data in the next | João Carlos Guimarães | Claudia Brun | Second quarter
|  | Immediate opportunities include 2 PCH totaling 5 MW | few days
João Carlos Guimarães |  | Future opportunities involve another 9 MW PCH and inside the fence efficiency improvements | Send a proposal
Claudia Brun | Outsource services | 3 MW risk management | Proof to them that we can offer best liability
Valesul | PCH - PPA SWAP | Opportunities include 4 PCH in MG totalling 60+ MW | Analyzing data to make a proposal | João Carlos Guimarães | Claudia Brun
|  | Customer very interested in hydro risk mgmt | Decide on pricing
Claudia Brun |  | Another opportunity is their need for close to 1200 MW in the north - possibility of an FX swap | [5 empty] | Done
João Carlos Guimarães
Claudio Marques
Alcan |  | 22 off-peak (firm) | meeting on14-feb - negotiation of the operational agreement, contract | João Carlos Guimarães | Marcelo Parodi | 1st week of march |  | Almost closed
|  | Probably start in March 00 | and ICMS
Marcelo Parodi |  | MG | next meeting: 24-feb
João Carlos Guimarães |  | CEMIG territory | Penalties to be dicussed
Meeting with Beltran
Usina Jaçiara |  | 1MW peak and off peak (firm) | Technical visit needed | Luiz Otavio |  |  |  | Proposal
We offered them R$40/MWh
Claudia Brun
Samarco-Belgo Mineira |  | Power Swap and hydrological risk management | Questionnaire sent | João Carlos Guimarães |  |  |  | Proposal
|  | Escelsa is offering the same deal | Waiting for response for next week
João Carlos Guimarães |  | EBE involved for saving ICMS | Make a proposal
Santa Maria - P&Pulp | PPA | PPA for 0,7 MW interruptible power generated by a PCH. Total power generated around 10,8 MW. | Talk to upper management in order to set up visit in the plant. |  | Claudia Brun |  |  | In conversation
| Swap | 11 MW Power swap at VN. Require more explanations for their management about the swap concept. | Meeting "in loco" set for the next week.
Claudia Brun | Financing | 0,7 MW turbine financing (using Biomass as fuel).
D'arcy Carroll |  | 12 MW thermal expansion
Claudio Marques |  | The transmission line capacity is ready for everything and they are
connected at 69 KV and pay around R$ 50/MWh for the power.
Copel's area - Parana.
Irani - P&Pulp | PPA | Power generated: PCH: 9 MW, BIOMASS: 3 MW. | Talk to upper management in order to set up visit in the plant. |  | Claudia Brun |  |  | In conversation
Claudio Marques | Swap - In doubt | 8 MW swap at VN complicated because they are connected at 23 KV and pay high tariffs. Require more explanations | Understanding everything "in loco" and decide what should be done.
Claudia Brun | Financing | for their management about the concept. | Wait for the new Celesc's substation on May/2000.
D'arcy Carroll |  | Celesc - SC State owned company. | Require 28 km of transmission line at 23 kV that Celesc is not willing to do.
Idel Metzger |  | 0,7 MW turbine financing | Meeting for the next 2 weeks.
Marcelo Parodi |  | 12 MW thermal expansion
Orsa - P&Pulp | PPA - In doubt | Power generated: PCH: 4 MW, BIOMASS: 2,5 MW. | Talk to upper management in order to set up visit in the plant. |  | Claudia Brun |  |  | In conversation
Luis Otavio | Swap - In doubt | 4 MW swap at the VN. Require more explanations for their management about the concept. | Understanding everything "in loco" and decide what do we want to do.
Claudia Brun | Financing | 1,5 MW turbine financing (use Biomass as fuel) - R$ 1,500,000 | Meeting for the next week in "locco" to
Baccaro |  | 3,5 MW Greenfield PCH - R$ 6,000,000 | get the information to analyse the deals.
Claudio Marques |  | Elektro area.
Idel
Carrol
Parodi
Engecorps/Cachoeirão | PPA | PCH - 25 MW
MG
Idel Metzger |  | Escelsa/Cemig territory? | Meeting next Friday | Idel Metzger | Claudia Brun
Claudia Brun
Fazenda Pilar | PPA or Buy Facility | Nameplate 6.7 Peak and off peak, average generation of 3 - 3,5 MW | Regulatory proposal and process clarified by Waltemberg, Pilar's lawyers | D'Arcy Carroll | Claudio Marques |  |  | Waiting
|  | They consume about 1 - 1,5 MW | Remi/Esteban - do the pricing
D'arcy Carroll |  | They have 3 PCH in Elektro's territory | bankruptcy representation on Thursday, Jan 19
Vasco |  | Will require 6kms of lines to connect ($R250m cost) | Final meeting between Sami and Erasmo to determine legal proposal
|  | No hydrological data (as yet) available; Lucio has checked all 3 regulatory sources | Technically the deal has value, requires a download from the
|  | SP | external lawyer about the legal risks.
|  | Elektro territory | Waiting for the legal decision to go ahead or not.
| Energy Services | Opportunity to provide energy services
Votorantim |  | Multiple PPA both short- and long-term (ECE has not submitted bids on previous 2 offers, requests) | Letter sent 02/04/2000 | João Carlos Guimarães | Claudia Brun
|  | PCH facilities (9 with CBA, 4 others between Paper and Cement) | Meeting with CMM postponed - date to be fixed |  | Fernando Bacellar
D'arcy Carroll |  | Interest in Energy Services and Efficiency (EES) | Meeting with Itau de Minas 02/29/2000
Marcelo Parodi |  | Want a recommendation re load, efficiency, contracting for Cement businesses
João Carlos Guimarães
National Account (1000MWs generation, 1500MWs consumption)
Credibanco |  | Put Option
Claudia Brun
Klabin | PPA | 21 MW generated by a PCH for a period of 3 years | Make a more detailed presentation for the deal | Idel Metzger | Claudia Brun | 2000-02-10 |  | In conversation
|  | 28 MW generated by Biomass | Meeting on march 2
Idel Metzger | SWAP | Existing opportunity to make a swap
Copel territory
Paraná
| Asset Monetization |  | Make an asset Monetization viability study | Idel Metzger | Marcelo Parodi

## Wholesale Market
Wholesale Market
| Product | Details | To do list | Relationship Manager | Product Responsible | Expected date | NPV (R$ 1.000) | Status
Tradener |  | 60 MW peak and off peak (firm) | They want a 5 years deal |  |  | Second quarter
We will offer them 50 reais per MWh
Luiz Otavio |  | 3 years
Luis Berti |  | PR
Copel territory
Decide on pricing
Escelsa |  | 10 MW peak and off peak (firm) | They want a 1 year deal |  |  |  |  | They promised to send terms
|  | Up to 70 MW | [5 empty] | and conditions till 27/01
Luiz Otavio |  | We will offer 65
Luis Berti |  | ES
Escelsa
Jan-Apr or/and May-Dec
Eletronuclear |  | They will be short in January; 600.000 MWh, but they say that they are not going to buy in the short term market
Luiz Otavio
Luis Berti
CELG
They will be short in January; 60.000 MWh
Luiz Otavio
Luis Berti
Coelba |  | 40 MW peak and off peak (firm) | They have sold some energy lately for R$120/MWh
Luis Berti
| Product | Details | To do list | Relationship Manager | Product Responsible | Expected date | NPV (R$ 1.000) | Status
Coelce |  | 15 MW peak and off peak (firm)
Luis Berti |  | They have sold 20 MW in jan for AES for R$ 128/MWh

## Demand
Demand
| Product | Details | To do list | Relationship Manager | Product Responsible | Expected date | NPV (R$ 1.000) | Status
Nadir Figueiredo | PPA | 10 MW | We sent a letter | João Carlos Guimarães |  | Second quarter
|  | 2.5 m3 of natural gas | Wait Nadir response to the letter
João Carlos Guimarães |  | Energy management - saving sharing | Analyze the opportunities
Fernando Bacellar |  |  | Send proposal
Fosfértil | PPA | Tender to become a national supply | João Carlos Guimarães will set up a meeting | D'Arcy Caroll
|  | 6 facilities all over the country | Decide on pricing
D'Arcy Carroll | [7 empty] | In conversation
João Carlos Guimarães
FIAT | PPA | Energy Management - cost savings | Lunch with Ricardo Mele next week | João Carlos Guimarães
Consultancy power negotiations
João Carlos Guimarães | EES | [6 empty] | In conversation
White Martins | CO2 Cuiabá | Sale of CO2 from Cuiabá | Meeting with White Martin - 10/02/2000 | D'Arcy Caroll
| Utility Island | Integrated development project for increase energy related products sales in Mato Grosso | Term Sheet and Confidential Agreement - next tree weeks
João Carlos Guimarães | Power Sale | Development together Utility/energy island's projects | List of potential projects to develop together |  |  |  |  | In conversation
|  | Sales of Wmartins's short term surplus | Schedule of Wmartins's eventual short term surplus for 2000
DOW |  | Analysis of co gen project | Discuss internal coverage of industrial supply and wholesale | D'Arcy Carroll
Clarify coverage between industry team ands regional team
In conversation
ACESITA | Energy Efficiency | Energy management - saving sharing | Send a letter and questionnaire | João Carlos Guimarães | Fernando Bacellar | 2000-02-21
Set up a meeting to introduce EES approach
Make a proposal
João Carlos Guimarães
SADIA | Total Energy Outsourcing | Energy management - saving sharing | Prepare a proposal for Cogen in Rio, higher voltage connection in | João Carlos Guimarães | Fernando Bacellar | 2000-02-25
| PPA |  | Paraná, PPA in Santa Catarina and total outsourcing for the 28 |  | Edmundo Picucci
Edmundo Pecucci | Cogeneration Facility |  | facilities in Brazil |  | Rod Blackham
João Carlos Guimarães |  |  |  |  | Elektro
D'Arcy Carroll
Fernando Bacellar

## Others
Other Opportunities
| Product | Details | To do list | Relationship Manager | Product Responsible | Expected date | NPV (R$ 1.000) | Status
Rhodia | EES | Energy Outsourcing. | Define commitments |  |  | Second quarter
Term sheet to be complete next week for client review.
Maria Inês Granado |  |  | Technical due diligence to be complete on 2-21-00 |  |  |  |  | In conversation
Fernando Bacellar |  |  | Meeting next week
Flavio Silberberg
Corbin Barnes
Banco Santander |  | They want to make a swap operation with us offering floating Reais and getting Fixed US$ | [5 empty] | In conversation
Decide on pricing
Remi Collonges
José Esteban
Internet | Internet trading | Internet Trading
Meeting with Esteban, Remi, Steve Nagy and Joe Kishkill next month
Remi Collonges |  | Business plan almost done. We have also talked with some guys in Germany as a way to
José Esteban |  | understand the site that they have there.
VCP | Asset Monetization | Monetize their energy assets with exception to the Black Liqueur Boiler | Have them to sign the LOI this week and start a 4 month due diligence
|  |  |  | Marcelo Parodi | Marcelo Parodi
Ricardo Libsoa
Eletrobras Financing | Contract Monetization | Monetize part of existing supply contract between Elektro and Itaipu. | Should hear final results today - does not appear to be likely we win | Maria Inês Granado
|  | $250 mm, 5-yr term | against bond offers still possible to provide fund through this structure
in parallel with bonds
Maria Inês Granado
Corbin Barnes