## Project Schedule
2001 EWS Project Status
[5 empty] | Day |  | 5 Weeks |  |  |  |  | Day |  | 1 Week
| Project | Executing | Superv. | Kickoff | Opening |  |  | In Progress |  |  | Last Date Updated | Closing | Final Rpt.
Trading | # | Mgr. | Mgr. | Month | Conference | < 25% | 25% | 50% | 75% | 100% |  | Conference | Issued | Finalized
Liquids - London | 02 | Albaugh | Vickers | August | [6 empty] | 2001-10-31 |  |  | November
Paper and Steel | 03 | Boyer | Agnew | August | [6 empty] | 2001-10-31 |  |  | October
Canada | 04 | Boyer | Stevenson | August | [6 empty] | 2001-10-31 |  |  | August
Financial Products Trading | 07 | Albaugh | Vickers | July | [6 empty] | 2001-10-31 |  |  | November
Weather Derivatives | 08 | Abaugh | Agnew | August/September | [6 empty] | 2001-10-31 |  |  | November
Portfolio Management | 09 | Boyer | Albaugh | June | [6 empty] | 2001-10-31 |  |  | November
Liquids - Singapore | 10 | Vickers | Vickers | June | [6 empty] | 2001-10-31 |  |  | November
Enron Online | 11 | Albaugh | Stevenson/Schultz | June | [6 empty] | 2001-10-31 |  |  | August
Gas Trading | 12 | Meador | Agnew | May | [6 empty] | 2001-10-31 |  |  | August
Power | 13 | Meador | Stevenson | May | [6 empty] | 2001-10-31 |  |  | July
Coal/Emissions - Houston | 14 | Albaugh | Vickers | May | [6 empty] | 2001-10-31 |  |  | August
Coal - London | 15 | Vickers | Vickers | May | [6 empty] | 2001-10-31 |  |  | August
FX/IR | 16 | Albaugh | Vickers | October | [6 empty] | 2001-10-31 |  |  | November
Liquids - Houston | 18 | Albaugh | Vickers | September | [6 empty] | 2001-10-31 |  |  | November
FX/IR - London | 19 | Albuagh | Vickers | September | [6 empty] | 2001-10-31 |  |  | November
Settlements | 20 | Boyer/Meador | Agnew/Stevenson | September | [6 empty] | 2001-10-31 |  |  | November
Information Technology |  |  |  |  | Opening |  | In Progress |  |  |  |  | Closing |  | Finalized
Rate Server/Lim | 22 | Bouwhuis | Schultz | August | [6 empty] | 2001-10-31 |  |  | November
Market Data Network | 23 | Bouwhuis | Schultz | June | [6 empty] | 2001-10-31 |  |  | August
Middleware Risk Assessment | 24 | Bouwhuis | Latham | June | [6 empty] | 2001-10-31 |  |  | November
Database Systems | 25 | Bouwhuis | Schultz | May | [6 empty] | 2001-10-31 |  |  | June
TAGG/ERMS/Enpower/DCAF | 26 | Bouwhuis | Latham | October | [6 empty] | 2001-10-31 |  |  | November
Global Databases Apps | 27 | Bouwhuis | Latham | September | [6 empty] | 2001-10-31 |  |  | November
Networks IT | 28 | Bouwhuis | Latham | September | [6 empty] | 2001-10-31 |  |  | November
Standards Audit | 47 | Bouwhuis | Latham | September | [6 empty] | 2001-10-31 |  |  | November
Financial |  |  |  |  | Opening |  | In Progress |  |  |  |  | Closing |  | Finalized
Underwriting | 31 | Boyer | Albaugh | September | [6 empty] | 2001-10-31 |  |  | October
Flash to Actual | 32 | Meador | Agnew | July | [6 empty] | 2001-10-31 |  |  | October
Portfolio Reporting & Structuring | 33 | Albaugh | Albaugh | May | [6 empty] | 2001-10-31 |  |  | July
Financial Operations I | 34 | Meador | Agnew | May | [6 empty] | 2001-10-31 |  |  | July
Financial Operations II | 36 | Meador | Agnew | September | [6 empty] | 2001-10-31 |  |  | November
Financial Business Analysis & Reporting | 38 | Albaugh | Albaugh | August | [6 empty] | 2001-10-31 |  |  | November
Risk Management |  |  |  |  | Opening |  | In Progress |  |  |  |  | Closing |  | Finalized
GRMS/RisktRAC | 39 | Boyer | Boyer | July | [6 empty] | 2001-10-31 |  |  | September
Global Risk Operations | 40 | Boyer | Agnew | July | [6 empty] | 2001-10-31 |  |  | November
Market Risk Management | 41 | Boyer | Stevenson | August | [6 empty] | 2001-10-31 |  |  | November
Credit I - RAC | 42 | Boyer | Stevenson | June | [6 empty] | 2001-10-31 |  |  | September
Credit 2 | 43 | Boyer | Stevenson | October | [6 empty] | 2001-10-31 |  |  | November
Other |  |  |  |  | Opening |  | In Progress |  |  |  |  | Closing |  | Finalized
AR/AP | 44 | Stevenson | Stevenson | April | [6 empty] | 2001-10-31 |  |  | July
OA | 45 | Boyer | Boyer | June | [6 empty] | 2001-10-31 |  |  | September