## Upstream Changes
2000-04-26
Changes required by upstream process for SAP Interfacing
FIN | GAS | PWR
Remit to Address types – check or wire
 GBL_Address_Num is populated within the Address table
 Internal_Entity_Id is populated within the Address table
 SAP_Id is populated within the Address table
Bill to Address types– check (we should not have bill to a wire location)
 GBL_Address_Num is populated within the Address table
 Internal_Entity_Id is populated within the Address table
Wires – payment methods (PM Address role)
 Wire_Method_Id is populated within the Address table for statements identified within Unify as wires.
 GBL_SAP_Bank_Acct_Id is populated within the Address table for Service Verifications and Supply Verifications identified within Unify as wires.
 Wire_ABA_Number is populated within the Address table for statements identified as wires.
 Wire_Account_Number is populated within the Address table for statements identified as wires.
Desk Id / Book code information
 Power – That a Desk Company Id exists for each line item
 Gas – That a Desk Id exists for each line item
 Financial – That a book code & desk id exists for the line item.
Statement Final Process – GL Account Updates in Acct Trans table
Statement Final Process
Changes are needed to the statement final process that when inserted into the Accounting_Transaction table,
1) to derive the counterparty status from SAP_Intco_Matrix. Ie 3rd party, Intercompany, NonSAP, and populate the GL Account Number as such.
The field selected is derived from the GL_Account_Reference, based on
|  |  |  | 3rd party | GL_Account_Number
|  |  |  | InterCompany | GL_Intco_Account_Num
|  |  |  | NonSAP | GL_Non_SAP_Account_Num
Accrual Process
Changes added to front end DRAFT accrual to stop the accrual if any ‘lessor of’ transactions are encountered.
This will have to be identified based on Transaction_Type_Id hardcoded for Gas/ Pwr.
A message will have to be raised in the messagebox informing of a lessor identified. The user will then have to reselect the gl account on the statement and
redraft before accrual can start again.
Statement Final Process/ Accrual Process – Validation for different country codes
Statement Final Process/ Accrual Process – Validation for different country codes
Ensure that the statement does not have multiple country codes, based on the PL_Pt. SAP cannot handle this.
The user will have to create a new statement.

## Dependencies list
High priority INTERNAL dependencies for Unify to SAP interface
Responsible Party | System | High level change requirement/ implications | ManDays Estimate | Request Date | Coding Comp. Date | UA Test Complete | Implement.Deadline | Status | Issues
Harmon/ Glass | STL - Gas/ Pwr/ Fin | Statement approval process - validating SAP Ids |  | 2000-04-05 | 2000-04-25 | 2000-05-02 | 2000-05-31 | awaiting prod mig.
Harmon/ Glass | STL - Gas/ Pwr/ Fin | Statement approval process - validating Wire Method |  | 2000-04-05 | 2000-04-25 | 2000-05-02 | 2000-05-31 | awaiting prod mig.
Harmon/ Glass | STL - Gas/ Pwr/ Fin | Statement draft/approval process - validating Desk Id exists on every drafted, finalized invoice/ line items. |  | 2000-04-05 |  |  | 2000-05-31
Settlements -
Harmon/ Glass | STL - Gas/ Pwr/ Fin | Statement approval process - validating Profit Center exists (xref) |  | 2000-04-05 |  |  | 2000-05-31
Harmon/ Glass | STL - Pwr | Backend change to determine/ populate sub company id in source tables (pwr - for desk id). |  | 2000-04-05
Harmon/ Glass | STL - Gas/ Pwr/ Fin | Statement Group - not allow selection of any I/C intercompany estimate accounts. Only the generics are allowed, and in which we will accrue to. |  | 2000-04-05
Harmon/ Glass | STL - Gas/ Pwr/ Fin | Statement Final Process - GL Account Updates in Acct Trans table, based on I/C, third party, NonSAP. |  | 2000-04-05 |  |  |  | coding in progress/
Harmon/ Glass | STL - Fin | Financials coded to handle "Prepays" transactions. Needed for interfacing to SAP. |  | 2000-04-05 |  |  | 2000-05-18
Harmon/ Glass | STL - Gas/ Pwr/ Fin | Statement Final Process - validation for different country codes. |  | 2000-04-05
Harmon/ Glass | STL - Fin | Settlements needs the capability of changing information from Upstream Systems in the backend due to short Settlement deadlines. |  | 2000-04-15 |  |  | 7/1/200 |  | Audit Issues!!!
Smith/ Gupta | STL - Gas/ Pwr | Accrual Process - Not allow 'lessor of' transactions to be approved. Force a statement correction and redraft. | 2 days | 2000-04-20 | 2000-05-01 |  | 2000-05-25 | Completed coding. | Awaiting user test.
B. Kline | STL - Fin | Data needs: TestCases document for every transaction type to interface to SAP - AR/ AP, Prepays/ I/C
B. Kline | STL - Fin | Data provided: Intercompany Data for financials |  |  |  |  | 2000-05-03
S. Blaylock/ T. Le | STL - Gas/ Pwr | Manual line item process for taxes - test and implement the lockdown of manual tax line items. This prevents the SAP interface from determine needed elements. | [5 empty] | Testing - Trang Le | Testing - Trang Le
Greg Whiting | SAP | SAP Intercompany tables setup for Gas/ Pwr |  |  |  |  | 2000-05-03
Greg Whiting | SAP | SAP Intercompany tables setup for Financials |  |  |  |  | 2000-05-03
Tax Dept | SAP | GL Account 50001040 setup for input taxes |  |  |  |  | 2000-05-03
Harmon/Smith/Reeves | STL - Pwr and SAP | Process SO2 and NOX through Unify Settlements |  | 2000-04-01 |  |  |  | Waiting for Requirements Document | IT driving this instead of the User in documenting requirements.
Smith/Yawanoski | MSA/SAP | Build a Solomon Interface to Texaco for Bridgeline data |  | 2000-05-02 |  |  |  | Cancelled. Deferred to manually for now. | May not be able to do by 7/1/2000. What is the contingency plan?
Harmon | STL - Gas /Pwr | Still receiving requests for enhancements for end-user |  | 2000-04-01 |  |  |  | Ongoing. | If request has to be done prior to 7/1/2000.
Harmon/Smith | Production Support | With the Liaison group diffusing we may be receiving more calls on Production Support issues that could be time consuming. |  | 2000-05-01 |  |  |  |  | We have no plan in place to handle this currently. Could impact SAP coding efforts on Settlements side.

## New-Late Requirements
Major open issues & late requirements impacting overall schedule
Unify, SAP, or business change requirements
Requested Date | High level summary of change | Modules impacted | Time impact/ analysis/ coding | Status | Forecast for Implementation | Comments
2000-04-21 | Financials - Ability to process Inter-company transactions. The SAP intercompany logic was not scheduled for FIN. Awaiting Global data setup. | Inter-company | 3 weeks | Development | 2000-05-25 | Need SAP Inter-Co tables setup, Global data entry
*completed | Ken H.- resolve replication problems preventing datasetup into Unify
*completed | Ken H.- Unify problem with Remit to/ Bill to, causing incorrect data in Unify
Becky F./ Bob K. - enter I/C data transactions for testing
Jeff Z. - complete coding for I/C, test
Pamela L./ Bob K. - ensure the SAP I/C tables support the I/C data for FIN (ie bank to vndr/ profit ctr)
2000-04-01 | Financials - Ability to process Prepay invoices for financials. Late major requirement. Analysis/ Design/ Coding needed. | Inter-company, AP/AR | 3 weeks | Analysis only | 2000-05-25 | Global data entry needed
*completed | Ken H.- resolve replication problems preventing datasetup into Unify
*completed | Ken H.- Unify problem with Remit to/ Bill to, causing incorrect data in Unify
Becky F.- create prepayment examples into Unify for testing
Becky F./ Melissa W. - Audit transactions, ensure entries are correct
Jeff Z. - complete coding/ unit testing of SAP module
Pamela L./ Terry S.- test loading into SAP.
Bob K.- SAP confirmation - tie out with Unify
2000-05-09 | Immediate impact - Financials - Unify Address Sequence Number expansion needed - Due to the financial entry, and their address requirements, the current address sequence number (ie FIN01), needs to be expanded to accommodate the larger volume of addresses (ie FIN00001). This has impacts across all statement group processing (GAS/PWR/FIN), and will require a code review/ changes to accommodate the database change. | Upstream to SAP Interface - All Gas/ Pwr/ Fin | 2 weeks
Ken H. - coordinate the db change, code review changes needed.
2000-04-15 | Financials - profit center requirements overall. Method not developed to map a profit center (book code/ desk). Database changes, GUI changes, validations. | Inter-company, AP/AR | 2 weeks | 90% | 2000-05-25 | Conceptual defined; not tested
*completed | Becky F.- all known profit centers are mapped into Unify.
Phil G.- ensure we have a book code/ desk to generate a profit center
2000-05-04 | New Inter-Company Tax code logic. Continues to change. Requirements are not locked down. | Inter-company, AP/AR, Accrual | 1 week | Done |  | Need specification as this changes freq.
Glenn/ M. White - Need written specification of design of all possible scenarios.
2000-04-24 | SAP mandated - multi-country tax not allowed for a single invoice. Unify has many of these (Canada). Changes will be needed for upstream settlement processing to not allow. Alternatives will have to be produced. | Inter-company, AP/AR, Accrual | 1 week | Open |  | Options: (1) Force upstream to split out; (2) handle manually
Glenn/ Pamela - awaiting fix from SAP. Will this be here in time?
Glenn - Alternative - create another tax code to default to when multiple's exist. Prototype this example.
*completed | Chris - audit/ fix the incorrect assignments where multi-countries does not exist
2000-04-24 | Accrual Process - not allow 'lessor of' transactions to be sent to SAP. Validation added in ACRL approval/ final stage. Business change to remove this from accrued transactions. | Accrual | 1 week | Development | 2000-05-31 | Awaiting testing; need to communicate changes to business units
M. White - awaiting testing
2000-05-08 | MSA GL Account Number supplied in the allocation field on the cutover clearing account side of AR & AP entries | Conversion | 1 week | Open | ? | Late change. Value of this enhancement?
Regan - need to research the change, impacts, and report by Friday
2000-04-15 | Physical Unify - Collapse of Louisiana companies (LRP-496, ESC-362, LGP-495, Crawfish-505) into 489. This will be needed for PMA processing. | All | 2 weeks | Open | ? | Handle Manually
M. White/ Regan - Manual entry into SAP- 3rd party/ IC - Unify to block/ not send 496/362/495/505 to SAP
M. White/ Regan - Manual entry into SAP- Unify to block I/C data for LGM/ 488 if the external cp is 496/362/495/505
2000-05-08 | Financial tax codes - the exempt status for countries. For Unify, can we use the U.S. 'no tax' code. |  |  | Open | ? | Tax Dept
Glenn - for financials, 3rd party, Unify to send a blank/ or default
Glenn - for financials, I/C, Unify needs to send the tax code per I/C tax table setup by SAP
Regan - request the SAP I/C table from Global into Unify, replication logic needed
Chris - code change needed to use the SAP I/C table for financial I/C for multi-countries exempt code
2000-05-08 | SAP: Intercompany transactions, having a 95% failure rate in mapping the buyer's entry due to SAP I/C Xref tables. |  |  | Open | ?
*completed | Bill Hare/ Susan - Global entry of PM needed for SAP to have the Bank to Vndr data
*completed | Susan - resolution of missing SAPCO, as needed for buyer's side of I/C data
SAP Tech - rebuild of bank to vendor table, pushed to prod server.
Unify DBA - ensure replication back to Global/ Unify
SAP Tech - audit bank to vendor build scripts. Assist with auditing report of needed data
Resolved - Changes implemented
2000-05-04 | Non GST tax line item change, Initially severance taxes were treated as regular line items. Now, special formatting requirements is needed. | Inter-company, AP/AR, Accrual | 1 week | Done
2000-05-04 | Change requested to add baseline date for Accruals. | Inter-company, AP/AR, Accrual | 1 week | Done
2000-05-05 | Change to tax requirements for penny in/ out processing. Set Tax Code to blank for penny in/penny out | Inter-company, AP/AR, Accrual | 1 week | Done

## TimeLines
|  |  | Actual |  | Conversion Cutover Project
|  |  | AR/AP/Accrual/ IC |  | Unify - AR Conversion testing
SAP Schedule | SAP Planned | Duration | Start | End | Start | End
Complete Requirements | 2000-01-31 |  |  | 2000-03-31
Complete Specifications | 2000-02-04 |  |  | 2000-03-31
Complete Development & System-to-Sys. Test | 2000-03-31 |  |  | 2000-04-14
Unit Testing |  |  |  | 2000-04-14
FIT 1 |  | 10 days | 2000-04-17 | 2000-04-28
Unit Test/ Error Correction |  | 5 days | 2000-05-01 | 2000-05-05
FIT 2 |  | 10 days | 2000-05-08 | 2000-05-19 | 2000-04-24
FIT 3 |  | 5 days | 2000-05-26 | 2000-06-02 | 2000-05-15
FIT 4 ? - financials
SAP configuration lockdown - no testing |  |  | 2000-06-02 | 2000-07-02
SAP Production Implementation |  |  | 2000-07-03
Significant obstacles during the process:
2000-04-07 | Losing 2 1/2 testing days due to the SAP unit test environment being down
2000-04-10 | Started unit testing the inter-company logic this morning and I noticed that the SAP inter-company tables were not populated with data for our unit test cases
During FIT 1 testing, I/C data delayed for 3 days into the process, reducing the feedback process
2000-05-08 | Made the Monday 8:00am target for all Jan-Mar I/C, 3rd party files. However, the I/C tables do not have the correct data, resulting in downtime
from sending complete I/C data. This will add 2 days to turnaround on obtaining feedback.