## Detail
Project Summer Asset Transfer Matrix - July 9, 2000 11:30pm
* Note: Friction Costs assume NO partner friction costs
| Name | BU | Country; Asset; Stage | Asset | Stage | BV (mm$) | ABC Now | ABC C | ABC Y/E | Transfer Restrictions | Action Items | People/Timing | Alternative | Friction Costs* | Transfer Level (Not yet scrubbed by group) | EI Contracts w/ ENE companies
SOUTH AMERICA
1 | Arcor | sa | Argentina; Power Plant; Purchased | Power Plant | Purchased | 13 | A | C | C | P - 100% ENE owned L - No financing R - Contract for purchase signed, but not closed (no later than 9-30-00); Need regulatory approval for transfer of interests with substantial influence at any level (Determine exemption availability) | R - Need Court for the Defense of Competition approval | Weiland, Young, Brasher, Jose Martinez de Hoz (local councel) Timing: 45-75 business days [4 mo] |  | 0 | Transfer to EGPP? | None -
2 | BBPL - GTB | sa | Bolivia; Pipeline; Existing | Pipeline | Existing | 29.044 | C | C | C | P - Various rights in favor of Shell L - No lender (Petrobras/Shareholder subdebt, $283MM) issues R - Confirm SIRESE approval not necessary b/c sale of non-controlling minority interest | P - Determine to either move to EGPP or trigger/get waiver of pref right (allocation of purchase price issue) R - Notify SIRESE immediately after announcement and work to convince no approval necessary | LF - V&E - Roark, Brasher R - Romero Guevarra (LC), Shapiro, Weiland, Young Timing: Immediately upon announcement notify SIRESE | ok | 0 | Transfer to EHCLLC, then to EGPP; dispose of EGPP | None -
3 | BBPL - TBG | sa | Brazil; Pipeline; existing |  |  | see above | C | C | C | P - Various rights in favor of Shell L - Multilateral debt, but no issues b/c sovereign guarantees/local bank) | P - Determine either to move to EGPP or trigger/get waiver pref right (purchase price allocation issue) | LF - V&E - Roark, Brasher P - Young Timing: |  | 0 | Transfer to EHCLLC, then to EGPP; dispose of EGPP | None -
4 | CEG | sa | Brazil; Gas LDC; Existing | Gas LDC | Existing | 193.267 | A | C | C | P - Various rights in favor of partners L - No consent necessary R - Confirm no reg approval necessary | P - Determine either to move at certain level or trigger/get waiver of pref right (allocation of purchase price issue) - C now if trigger pref right (recommendation- trigger pref right) R - Notify ASP after announcement | LF - V&E - Roark, Brasher P & R - Tozzini (LC), Shapiro, Weiland, Young, Brasher, Waddel Timing: 7/17 whether or not to trigger pref right |  | 0 | Rawhide Asset - Transfer EIB1997Ltd and EIGBH Ltd
5 | CEG-Rio | sa | Brazil; Gas LDC; Existing | Gas LDC | Existing | 69.571 | A | C | C | same as CEG | same as CEG | LF - V&E - Roark, Brasher same as CEG |  | 0 | Rawhide Asset - Transfer EIB1997Ltd and EIGBH Ltd
6 | Copel | sa | Brazil; Electric LDC; Existing | Electric LDC | Existing | 134.69 | C | C | C | None - Stock position |  |  | ok | 0 | Transfer ENE Brazil Power Holdings XII Ltd. | None -
7 | Cuiaba - EPE | sa | Brazil; Power Plant; Existing | Power Plant | Existing | 119.8 | B | B | B | P - various rights in favor of Shell L - 1.ENE must own 25% economic interest 2. Before project completion date, can sell up to 15.625% of shares of EPE; otherwise, no transfers of any beneficial or voting interests in EPE, BasBol, GasMat, or TBS (Subject to nominal OPIC consent) 3. ENE must control ENE Power Corp during EPC contract duration 4. ENE/Shell must control for 10 yrs after completion R - Consent of ANEEL necessary unless bidding requirements can be maintained by EI; confirm ANEEL approval not necessary b/c transfer of IPP not regulated or b/c transfer above EPE Holdings | P - Need overall Shell resolution or must be in A (In B only b/c lender issues) L - Negotiate w/ OPIC/KFW to substitute EI for ENE in hold restrictions and no ENE hold requirement in EI (If obtain, can move to A) R - Confirm if ANEEL approval necessary (Believe not necessary but inform ANEEL); check satisfaction of bidding requirements by EI (Inform FURNAS) | LF - V&E - Barquin, Spradling, Novak, Brasher P - Taylor, MINT L - Gathmann, Gay, Lipshutz, Mellencamp (resolve before financial closing) R - Shapiro, Weiland, Barquin, Tozzini, Bestard Timing: 7/14 whether reg approval necessary | ok | P - Unknown L - 50 - 100bps upfront fee ($1.8 - $3.6MM) | Transfer to EHCLLC, then to EGPP; dispose of EGPP(may have problem w/ COC of EGPP - no "EGPP exemption" under original docs) | None -
8 | Cuiaba - Gas Bol | sa | Bolivia; Pipeline; Existing | Pipeline | Existing | 19.871 | B | B | B | P & L - see EPE R - SIRESE consent may be necessary; maintain original concession requirements | R - Confirm if upstream transfer will avoid SIRESE approval, EI satisfies original requirements | R - Guevarra, Weiland, Young Timing: 7/14 | no | see EPE | see EPE | None -
9 | Cuiaba - GasMat | sa | Brazil; Pipeline; Exisitng | Pipeline | Existing | 35.574 | B | B | B | P & L - see EPE R - ANP consent may be necessary; maintain original concession requirements | R - Confirm if ANP approval necessary, EI satisfies original requirements | R - Tozzini, Weiland, Young Timing: 7/14 | ok | see EPE | see EPE | None -
10 | Cuiaba - TBS | sa | Brazil; Gas Marketing; Existing | Gas Marketing | Existing | 72.55 | B | B | B | P & L - see EPE R - No approval necessary |  |  | ok | see EPE | Transfer ESA b/c of partner approval rights | None -
11 | Elektro | sa | Brazil; Power LDC; Existing | Power LDC | Existing | 1978.22 | C | C | C | R - Need ANEEL approval | L - Take out Firefly Equity and Debt R - Get ANEEL approval | LF - Skadden - Brasher; VE - Shouse L - Lipshutz (Firefly - 8/31/00) R - Shapiro, Tozzini, MINT - 4 months | ok | 0 | Transfer EBPH V Ltd. And EBPH XI Ltd.
12 | Gaspart | sa | Brazil; Gas LDC; Existing | Gas LDC | Existing | 171.913 | A | C | C | P - Pref rights | P - Determine to either move at certain level or trigger/get waiver of pref right - Will be C if pref right triggered | LF - V&E - Blumental, Brasher R - Tozzini (LC), Shapiro, Weiland, Young, Waddel Timing: 7/17 | ok | 0 | Rawhide asset - Transfer EIB1997Ltd | None - | `
13 | TGS | sa | Argentina; Pipeline; Existing | Pipeline | Existing | 451.92 | A | C | C | P - Pref rights/tag-along rights in favor of Perez Companc extend up to ENE L - Put of $220MM Notes if ENE and Perez Companc have less than 50.1% vote of CIESA shares R - ENARGAS consent needed for COC; may need Court of Competition consent (determine exemption availability) | P - Leave in A, trigger COC, trigger pref right and a consent to transfer, or get waiver of transfer restrictions L - Negotiate w/ Noteholders to substitute EI with ENE in hold restrictions and no future ENE hold restrictions R - Get ENARGAS approval and determine if new EI falls under Court of Competition exemption | LF - VE - Blumental, Brasher P - Brasher, Young L - Gathmann, Gay, Lipshutz, Mellencamp (6 weeks) R - Martinez de Hoz, Weiland, Young, Brasher Timing: Determine Court of Competition 7/17, ENERGAS approval (6 weeks) |  | L - 50-100bps ($1.1 - $2.2MM) | Rawhide asset - Prefer to transfer shares of EPCA and EACH | None -
14 | Transredes | sa | Bolivia; Pipeline; Existing | Pipeline | Existing | 153.822 | A | A | C | P - Various rights in favor of Shell L - No lender issues R - Confirm SIRESE approval not necessary b/c sale of non-controlling minority interest (Note: ENE is operator - look at Article 31) | P - Confirm Shell's acquisition of Transredes' interest in GasBol proir to closing (tp prevent default under Cuiaba OPIC financing); Move to EGPP R - Notify SIRESE immediately after announcement and work to convince no approval necessary | LF - VE - Roark, Brasher Guevarra, Shapiro, Weiland, Young, Brasher Timing: Immediately upon announcement notify SIRESE and confirm approval not necessary 2 weeks after notice |  | 0 | Transfer to EHCLLC, then to EGPP; dispose of EGPP | $10MM ENE loan
| Name | BU | Country; Asset; Stage | Asset | Stage | BV (mm$) | ABC Now | ABC C | ABC Y/E | Transfer Restrictions | Action Items | People/Timing | Alternative | Friction Costs | Transfer Level (Not yet scrubbed by group)
15 | Argentina Trading |  | Argentina |  |  | 15.34 | C | C | C | R - May need Court of Competition consent; Need to confirm COC issues regarding power broker license | R - Determine if CofC exemption applies; Confirm COC power broker isssues | R - Martinez de Hoz, Weiland, Shapiro, Young, Brasher Timing: 7/17 |  | 0
16 | Bom Retiro | sa | Brazil | PPA | Development |  | C | C | C | No issues |  |  |  | 0
17 | Dona Francisca | sa | Brazil | PPA-prepay | Adv Dev |  | C | C | C | No issues |  |  |  | 0
18 | ECE | sa | Brazil | Power Marketing |  |  | C | C | C | No issues |  |  |  | 0
19 | Electrobolt | sa | Brazil | IPP | Early |  | C | C | C | No issues |  |  |  | 0
20 | Grupo Rede | sa | Brazil | Power prepay | Adv Dev |  | C | C | C | No issues |  |  |  | 0
21 | Grupo Rede - EPA with Cuiaba II | sa | Brazil | EPA Enron/ Grupo Rede | Adv Dev |  | C | C | C | 100% ENE owned - Confirm no restrictions on upstream COC |  | LF - VE - Cerano |  | 0
22 | GTB - 2% Purchase | sa | Bolivia | Pipeline | Adv Dev |  | C | C | C | Dead deal |  |  |  | 0
23 | International E-Commerce | sa |  |  |  |  | C | C | C | No issues |  |  |  | 0
24 | Maxus Bolivia | sa | Bolivia | Gas Prepay | Adv Dev |  | C | C | C | No issues |  |  |  | 0
25 | Pactual | sa | Brazil | PPA | Development |  | C | C | C | No issues |  |  |  | 0
26 | Puerto Suarez | sa | Bolivia | IPP | Early |  | C | C | C | P - No documents executed |  |  |  | 0
27 | Rhodia | sa | Brazil | Energy Services | Development |  | C | C | C | No issues |  |  |  | 0
28 | Rio Geo | sa | Brazil | Seismic Study Project | Operating |  | C | C | C | Same as APACHI #17 |  |  |  | 0
29 | Riocell | sa | Argentina | Energy Services | Development |  | C | C | C | No issues |  |  |  | 0
30 | Rosal | sa | Brazil | Share purchase in Hydro | Development |  | C | C | C | No issues |  |  |  | 0
31 | Scraps Phase II | sa | Bolivia | Chaco (20,300 MMBtu/d) | Development |  | C | C | C | No issues |  |  |  | 0
32 | Scraps Phase III | sa | Bolivia | British Gas | Development |  | C | C | C | No issues |  |  |  | 0
33 | Scraps Phase IV | sa | Bolivia | Vintage (20,300 MMBtu/d) | Development |  | C | C | C | No issues |  |  |  | 0
34 | Software | sa | Company | Software Dev. | Advanced Dev. |  | C | C | C | No issues |  |  |  | 0
35 | South American Fiber |  | Fiber Build; In Dev |  |  |  | C | C | C | No issues |  |  |  | 0
36 | TBG | sa | Brazil | Gas Compression Service | Development |  | C | C | C | No issues |  |  |  | 0
37 | VCP | sa | Brazil | Energy Services | Development |  | C | C | C | No issues |  |  |  | 0
38 | Vintage | sa | Bolivia | Gas Supply Con. | Adv Dev |  | C | C | C | No issues |  |  |  | 0
CALME
1 | Accro | ca | Venezuela; Gas Plant; Existing | Gas Plant | Existing | 2.13 | B | C | C | P - Pref right for direct ENE ownership and COC issue in Members Agreement and for PDVSA and TransCanada L - OPIC Common Terms Agreement 25% voting and economic hold requirement | P - Transfer at ENE Caribbean Basin Ltd. to avoid pref right and COC issue L - Get OPIC consent to amend hold restrictions from ENE to EI, must also get Transcanada consent as part of Accroven board approval in order to amend financing docs (Move to C if obtained); Make sure no transfer restrictions in current EXIM financing R - Confirm no reg approval needed | LF - VE - Kamine, Brasher L - Gathmann, Castagnola, Lipshutz, Mellencamp (2 months) R - Travieso (LC), Weiland, Young Timing: Spradling to confirm no EXIM transfer restrictions by 7/17, confirm no reg approval needed by 7/17 |  | 50 - 100 bps ($1-$2MM) | Transfer at ENE Caribbean Basin Ltd. or ACFI | O&M Agreement w/ Accroven Sister Co
2 | Bachaquero | ca | Venezuela; Compression; Existing | Compression | Existing | 7.59 | C | C | C | P - Hanover Cayman pref purchase right L - Loan agreements prohibit COC of EI Venezuela Developments Ltd, other than to EPP, but lender is ENE entity (affiliate contracts) | P - Transfer upstream L - ENE Sub consent required R - Confirm no reg issues | LF - VE - Kornreich, Brasher L - Lipshutz, Walia (1 month) R - Blanco, Weiland Timing: Confirm regulatory by 7/17 | ok | 0 | Rawhide asset - Prefer transfer of EI Venezuela Holdings Ltd; also need to transfer Compresion Projects Finance Ltd. To move debt
3 | Bahia Las Minas | ca | Panama; IPP; Existing | IPP | Existing | 95.51 | B | C | C | P - ENE Caribe III must own 25% of EIPSA until 1/14/04; ECIII or EIPSA must control EGEMINSA until 1/14/04 under bid rules (Govt is partner) L - No issues R - Panama Ministry of Finance approval needed (sits on board); Ente Regulador consent needed | P & R - Get Ente Regulador Consent; Determine if Fuel Agreement will be transferred to EI | LF - VE - Cestero, Brasher R - D'Alba, Fabrica, Pinto leite, Shapiro Timing: 4-6 weeks after announcement | ok | 0 | Transfer Enron Caribe III Ltd
4 | Calife | ca | Venezuela; Electric LDC; Existing | Electric LDC | Existing | 31 | C | C | C | No issues |  | LF - VE - Kornreich, Brasher | ok | 0 | Likely to be transferred through transfer of upper tier entity in Ventane chain
5 | Caribbean Basin Power Fund | ca | CA; Investment; Existing | Investments | Existing | 20 | C | C | C | P - No board approval needed, but investor must be an accredited investor for US Securites Law purposes | P - Confirm accredited investor | LF - VE - Sasser P - Sayer; Castagnola Timing: Confirm accredited investor by 7/21 |  | 0 | Transfer above ownership of Class A & B shares
| Name | BU | Country; Asset; Stage | Asset | Stage | BV (mm$) | ABC Now | ABC C | ABC Y/E | Transfer Restrictions | Action Items | People/Timing | Alternative | Friction Costs | Transfer Level (Not yet scrubbed by group)
6 | Centragas | ca | Colombia; Pipeline; Existing | Pipeline | Existing | 36.75 | A/B | A/B | A/B | P - ENE must control GP interest; Need Tomen consent if ENE holds less than 25% L - ENE must control GP; ENE 25% hold requirement for 144a noteholders R - Ecopetrol (govt) approval required | P - Tomen consent to move to C L - Get 51% bondholder consent (very difficult b/c bonds trading at discount) so keep in B R - Get Ecopetrol consent | LF - VE - Geller P - Sayer; Geller L - Gathmann, Castagnola, Lipshutz, Mellencamp (2 months) R - Weiland, Young, LC Timing: R - 3 months | ok | Unknown | Rawhide asset - Transfer at ACFL or higher to avoid Colombia tax
7 | Citadel Venezolana | ca | Venezuela; Controls; Existing | Controls | Existing | 31.61 | C | C | C | P - Technical Assistance Agreement with GE - consent required?? | P - Confirm status of project and determine if any consents required | LF - VE - Kornreich Sayre |  | 0 | Transfer thru tranfer of Ventane chain
8 | Corinto | ca | Nicaragua; IPP; Existing | IPP | Existing | 4.06 | A/B | C | C | P - Equity ROFR (can transfer upstream); ENE Caribe must hold 15% under Technical Services Agreement; ENE must hold 15% all the way upstream under Assumption Agreement (can satisfy through interest in MINT) L - No hold restriction but ENE has obligation to purchase vessel if default; backstopped by pro rata obligations of partners so ENE exposure is 35% | P - Negotiate w/ Centrans and CDC to substitute EI for ENE in hold requirements in Assumption Agreements L - No MARAD consent or notice needed if sell above Corinto level; MARAD backstop likely to have to stay in place | LF - Skadden - ; VE - Geller P - Sayre, Castagnola |  | 0 | Transfer Enron Caribe VI Holdings Ltd. | ENE Gty of MARAD financing issues; Fuel Supply Agreement w/ ENE;
9 | Dolphin | ca | Middle East; Pipeline; Existing | Pipeline | Existing | 3.1 | B | B | C | P - ENE 51% hold requirement in JVA L - No issues R - No issues | P - Get Partner (Offsets and Elf) consent immediately after announcement | LF - VE - Deemer, Brasher P - Rogers - 2 weeks after announcement | ok | 0 | Parent comfort letter may need to be amended (wait to be asked)
10 | EcoElectricia | ca | Puerto Rico; IPP; Existing | IPP | Existing | 80.84 | B (b/c partnership) | C | C | P - No ENE hold requirement w/ partners other than GE b/c conversion occurred 6/15/00; GE pulls in hold restrictions from credit agreement (has independent vote) L - 12.5% ENE (all the way upstream) hold requirement in Credit Agreement; 25% hold requirement for all sponsors | P - Transfer upstream; GE - See lender strategy below L - Negotiate to substitute EI for ENE in lender and GE hold requirements; Confirm that Edison qualifies as a new sponsor, satisfying 25% hold requirement for sponsors (VE) or substitute EI for ENE in agreement | LF - VE - Sasser L - Gathmann, Castagnola, Lipshutz, Mellencamp Timing: 2 months | ok | 50 bps ($3.7-$7.5MM) | Transfer of Buenergia Gas & Power Ltd. Or higher level (ENE LNG Power Atlantic Ltd.) | ENE guaranty of a dividend of $20MM to GE for working capital purposes; ENE guaranty of EPC contract (in warranty); Phase 2 is LNG terminal and under construction
11 | Gaza | ca | Gaza; IPP; Existing | IPP | Existing | 14.11 | X/B | B | C | P - Need board of director/shareholder approvals of any transfer if transfer below ENE Palestine Inc; Shareholder Rights Agreement has ENE hold restriction re:100 shares (tax issues); ENE Corp transfer agreement (ENE can transfer only to 'controlled affiliates' and any other owners must satisfy reputation and expertise requirements L - ENE must hold 51% of ETIL R - No Consent required O - PPA may require ENE ownership; IPO on Palestinian Stock Market (ENE ownership becomes 33.5%) | P - Transfer at ENE Palenstine Inc. level to avoid some partner consent issues; Confirm tax implications (Sykes); Get PEC Plc consent; Consult w/ Local counsel re: Palestinian Securities Laws; Determine if PPA offtake consent needed L - Negotiate w/ Banks to substitute EI for ENE in hold restrictions | LF - Skadden - Hoghooghi P - Rogers, Brasher, Coles, Sykes L - Lipshutz, Mellencamp, Gathmann and Richardson (2 months) Timing: Confirm tax implications by 7/21, consult w/ local counsel by 7/14; PEC consent 4-6 weeks O: Put IPO on hold immediately; scrub PPA for ENE ownership - Skadden by 7/17 |  | 50-100bps ($250-$500MM | Transfer take place at ENE Palestine Inc. (CayCo)
12 | Haina | ca | Dom. Rep.; IPP; Existing | IPP | Existing | 57.83 | C | C | C | Sold 6/30/00 |  |  |  | 0
13 | Industrial Gases Limited (IGL) | ca | Jamaica; LPG Dist; Existing | LPG Dist | Existing | 29.89 | C | C | C | No issues |  | LF - VE - Kornreich, Brasher | ok | 0 | Transfer Citadel Corp. Ltd. Or above (probably through sale of Protane Corp)
14 | Land (Pakistan) | ca | Pakistan; Land; Existing | Land | Existing | 2 | C | C | C | No issues |  |  |  | 0
15 | PQPC/PQPL | ca | Guatemala; IPP; Existing | IPP | Existing | 33.07 | A | C | C | P - Restrictions on transfer at project level; Pref rights at shareholder level L - OPIC and MARAD refinancing imminent | P - Sell at EGPP level or above to alleviate pref rights/ all restrictions on transfer L - Confirm no ENE hold requirements in new docs | LF - VE - Byrd, Spivak; Brasher L - Gathmann, Castagnola, Lipshutz, Mellencamp (resolve before financial closing) | ok | 0 | Rawhide asset - Transfer EGPP and Enron Guatemala Holdings Ltd. | EFI Fuel Supply Agreement;
16 | ProCaribe | ca | Puerto Rico; LPG Dist; Existing | LPG Dist | Existing | 2.22 | B | A | C | R - Approval needed for COC at any level for PR Port Authority and PSC - need consent/approval | L - As result of COC, either sublease to EcoElectrica or get consent to waive sublease - (Get confirmation) R - Get PR Port Authority and PSC approval - Check whether only COC or any transfer triggers regulatory approval | LF - VE - Kornreich, Brasher L - Castagnola (1 month) R - Sayer, Curran, Dapena Timing: 2-4 months |  | 0 | Transfer Protane Corp.
17 | Progasco | ca | Puerto Rico; LPH Dist; Existing | LPH Dist | Existing | 14.58 | A | A | C | R - Need PSC approval | R - Get PSC Approval | R - Sayer, Curran, Da Pena Timing: 2-4 months |  | 0 | Transfer Progasco Inc. probably effected through transfer of Protane Corp.
18 | Promigas | ca | Colombia; Pipeline; Existing | Pipeline | Existing | 137.24 | C | C | C |  | R - Confirmed that no tender offer needed b/c part of larger transaction | LF - VE - Shouse, Brasher R - Weiland, Sayre, LC Timing: 7/21 | ok | 0 | Buy back from Condor first, then transfer ECT Colombia Pipeline Holdings 2 Ltd. To avoid Colombia tax
19 | Rio Hondo |  | Guatemala; IPP; Existing |  |  |  | C | C | C | Capitalized development costs | Determine how/when to unwind ENE guarantee of loan funded to EECC | Sommers, Walia Timing: 7/21 |  | 0
| Name | BU | Country; Asset; Stage | Asset | Stage | BV (mm$) | ABC Now | ABC C | ABC Y/E | Transfer Restrictions | Action Items | People/Timing | Alternative | Friction Costs | Transfer Level (Not yet scrubbed by group)
20 | San Juan Gas | ca | Puerto Rico; LPG Dist; Existing | LPG Dist | Existing | 9.42 | A | A | C | L - ENE must hold 51% stock (ENE retains litigation risk) R - Need PSC approval at any level | L - Get waiver from Chase for ENE hold requirement (ENE guaranty in place) R - Get PSC Approval | LF - VE - Cestero L - Gathmann, Lipshutz (2 months) R - Sayre, Curran, Dapena (LC) (2-4 months) | ok | 0 | Transfer shares of San Juan Gas
21 | SECLP | ca | Dom Rep; IPP; Existing | IPP | Existing | 41.05 | B/A | B/A/C | B/C | P - Consent required - difficult partner issues L - Determine whether 20% of Ventane ownership can be transferred to B, and remaining Ventane piece as well as other SECLP can go to C (Payment default; poor lender relations); ENE must maintain 50% ownership of EPP while IFC financing in place or indemnify EPP against all claims; ENE affiliate must perform as O&M manager | P & L - Strip out 4/7 of 35% FinVen interest and put in B; Allow remaining 3/7 to be transferred w/ Protane to A; Remaining 50% to C (Brasher/Spradling to confirm w/ tax); Verify the structure solution alleviates partner and lender (IFC, MARAD, DEG) issues; Determine whether O&M Co can be put into A to satisfy O&M hold restrictions | LF - VE - Byrd, Spivak P & L - Spradling/Brasher to determine structure given all contraints P&L - Sayre, Gathmann Timing: Determine O&M hold by 7/14 | ok | 0 | Transfer Enron Dom RepLtd. (co 822), ENE Dom Rep Operations Lrd. (co. 826), both held by ECB LLC (to be confirmed) and transfer Enron Dominicana Holding Ltd.
22 | Ventane | ca | Venezuela; LPG Dist; Existing | LPG Dist | Existing | 138.62 | C | C | C | R - Tender offer may be needed | R - No tender offer required if part of a larger sale; Check to verify that new tender rules do not require tender | LF - VE - Kornreich, Brasher R - Sayre; Baker McKenzie Timing: 7/17 | ok | 0 | Transfer at ACFI
23 | Colombia/ Panama Pipeline |  | Pipeline; Mid-Dev | [6 empty] | No issues |  |  |  | 0
24 | Dom Rep LNG | [5 empty] | C | C | C | MOU w/ Union Finosa for re-gas facility - No transfer restrictions |  |  |  | 0
25 | Elba Island Terminal Capacity | ca | USA | LNG Terminal | [5 empty] | Negotiating LNG put requirement - possible transfer restrictions - confirm upstream transfer avoids consent |  |  |  | 0
26 | ExMar/ 2ExMar | ca | LNG Ships | LNG Ships |  |  | C | C | C | Option may have transfer restrictions (but upstream transfer ok) - option prices are significantly in the money - ENE Corp Gty -Termination for Convenience $74.5 MM in first year and goes to $47.5 after 3 years (25 yr charter) |  |  |  | 0
27 | Hoegh Galleon (charter) Nov. 2000 | ca | LNG Ships | LNG Ships |  |  | C | C | C | Charter party w/ ENE LNG Shipping Company - no upstream restrictions - 3 years then novate into VLNG or MetGas projects - no COC - ENE Corp Gty to backstop termination for convenience agreement - $18MM for first 3 years then goes down |  |  |  | 0
28 | Israel Power |  | Israel; Electric Generation; Early Dev |  |  |  | C | C | C | No issues |  |  |  | 0
29 | Israel Telecom |  | Israel; Telecom; Early Dev |  |  |  | C | C | C | No issues |  |  |  | 0
30 | Jebel Ali Project UAE | [5 empty] | C | C | C | MOU - No transfer restrictions |  |  |  | 0
31 | Master LNG P&S Agreement w/ Adgas | [5 empty] | C | C | C | For spot market LNG - holds FERC LNG import licence which may have upstream transfer issues - confirm no other upstream transfer issues |  |  |  | 0 |  | Spot L/C w/ ENE
32 | Oman Gas Distn | ca | Dev | LNG Supply Contracts |  |  | C | C | C | No issues |  |  |  | 0
33 | PR LNG Expansion | [5 empty] | C | C | C | In Development |  |  |  | 0
34 | San Juan Gas Geo Fiber Bundle |  | Puerto Rico |  |  |  | C | C | C | No issues |  |  |  | 0
35 | Saudi Arabian IPP | [5 empty] | C | C | C | Sadaf inside the fence power plant - draft JDA - no restrictions on tranfser - MOU |  |  |  | 0
36 | Venezuela LNG Project | [5 empty] | C | C | C | No issues at present (agreement pending) |  |  |  | 0
37 | Westinghouse Turbine | [5 empty] | C | C | C |  | Need to determine if there are transfer restrictions | Sayre by 7/17 |  | 0
38 | International E-commerce |  | Venezuela; |  |  |  | C | C | C | P - ROFR and tag-along rights at ENE Caribe Level | P - Transfer at ACFI to alleviate partner issues |  |  | 0 | Transfer at ACFI
39 | Lakshmi (Greenfield Shipping) | in | India | LNG Ships |  |  | A | C | C | L - ENE Corp 20% voting hold requirement | L - Amend to replace ENE with EI in hold restrictions | LF - Linklaters - Gewirtz, Andrews, Rogers, Hoghooghi, Spradling L - Castagnola, Gathmann, Lipshutz, Mellencamp Timing: 2 months |  | 50 - 100 bps ($830M - $1.6MM) | Must transfer at ACFI or above
APACHI
1 | Advanced Agro | ap | Thailand; Bonds, Existing | Bonds | Existing | 4.094 | C | C | C | No transfer restrictions | Confirm bonds owned by ENE CTS International, a wholly-owned sub of ENE |  |  | 0 | Transfer entity that owns bonds
2 | Australia Trading |  | Australia |  |  | 5.11 |  |  |  | Need to investigate approvals when structure determined |  | Aronowitz |  | 0
3 | Barges | ap | Nigeria; IPP; Existing | IPP | Existing | 32.6 | C | C | C | P - Asset held by LJM | P - LJM structure needs to be unwound | Lipshutz, Lynn Timing: 1 day before close | ok | 0 | Transfer at project co or above | None
4 | BASF | ap | China; IPP; Active | IPP | Active | 2.98 | C | C | C | Capitalized development costs |  |  | ok | 0
| Name | BU | Country; Asset; Stage | Asset | Stage | BV (mm$) | ABC Now | ABC C | ABC Y/E | Transfer Restrictions | Action Items | People/Timing | Alternative | Friction Costs | Transfer Level (Not yet scrubbed by group)
5 | Batangas | ap | Philippines; IPP; Existing | IPP | Existing | 55.42 | A | C | C | P - No issues (100% owned) L - ADB and OPIC requirement for ENE to hold 50% voting interest | L - Negotiate w/ OPIC and ADB to replace EI with ENE in hold requirement or voluntarily prepay; Check L/C reserve requirements (May be most economic to just pay off) | LF - Skadden - Saba, Spradling L - Gathmann, Hunt, Lipshutz, Mellencamp (2 months) Timing: Hunt, Gathmann (repayment of loan/LCs analysis - 7/24) |  | 50 - 100 bps ($100-$200M) | ENE Power Phil Corp; Transfer EPP entity to transfer affiliate contracts
6 | Benin | ap | Benin; IPP; Early | IPP | Early | 3.285 | C | C | C | Capitalized development costs |  |  |  | 0
7 | Bulacan | ap | Philippines; IPP; Advanced | IPP | Advanced | 2.57 | C | C | C | P - No restrictions L - October 2000 FMO financing closing | L - Anticipate there are no hold requirements | L - Quek |  | 0
8 | East Java | ap | Indonesia; PRI Claim; Existing | PRI Claim | Existing | 15 | C | C | C | Claim paid - asset deleted |  |  |  | 0
9 | Eclipse | ap | China; IPP; Existing | IPP | Existing | 111.12 | C | C | C | P &R - Can sell upstream w/o consent L - No restrictions | P - Transfer above project co | LF - VE Blumental | ok | 0 | EI Chendu Power Holdings Ltd. (above project co)
10 | Encom | ap | Japan; Investment; Existing | Investment | Existing | -16.34 | C | C | C | P - Encom has business purpose restrictions not to compete with ENE trading business in Japan which fall away if ENE owns less than 1/3 voting stock of Encom, will review all ENE hold requirements further L - Investment has $26MM ENE demand note reflecting dollars distributed which will be used for investment | P - Determine structure of trading business in Japan to decide what amendments are necessary L - Note should be repaid, new note executed by EI, and dollars redistributed to EI | P - Baxter and Dr. Amin (Japan strategy) P - Lundstrom L - Gathmann Timing: P&L by closing; Lundstrom will review all ENE hold requirements by 7/17 | ok | 0
11 | Hainan | ap | China; IPP; Existing | IPP | Existing | 146.48 | C | C | C | P - Under termination agreement, 1 payment of $88MM remains (foreign exchange issues) |  | LF - VE - Blumental | ok | 0
12 | Humpus | ap | Indonesia; Bonds; Existing | Bonds | Existing | 17.299 | C | C | C | No transfer restrictions | Confirm bonds owned by ENE CTS International, a wholly-owned sub of ENE | Lundstrom Timing: 7/17 | ok | 0 | Transfer entity that owns bonds
13 | MISP | ap | Mozambique; Steel Plant; Early | Gas Supply | Early | 9.161 | C | C | C | Capitalized development costs |  | LF - VE - Curry, Brasher |  | 0
14 | Napa Napa | ap | PNG; Refinery; Early | Refinery | Early | 8.9 | C | C | C | Capitalized development costs P - No transfer restrictions; ceased funding and retained non-voting economic interest L - No obligation to fund additional amounts | Confirm no COC restriction in shareholder agreement no longer operative | P - Lundstrom, Hunt Timing: 7/17 | ok | 0 | ENE Papua New Guinea
15 | Pande | ap | Mozambique; Gas Field in Dev; Early | Gas Dev. | Early | 23.169 | C | C | C | Under contract to sell gas field to SASOL for $30MM (proceeds split 20% w/ EOG) R - No restrictions | Held by Enron Southern Africa Develpment, Ltd., a CAYCO established for activities in South Africa and Mozambique | LF- VE - Curry, Brasher Hughes Timing: 7/17 | ok | 0 |  | None
16 | Piti - Guam | ap | Guam; IPP; Existing | IPP | Existing | 29.34 | B | C | C | P - Cannot transfer any ownership interest in project co w/o consent of majority members; does not restrict transfers upstream L - 12.5% 'ownership interest' hold requirement | P - Transfer upstream L - Negotiate w/ ABN/AMRO to replace EI with ENE in hold requirements or ENE to purchase 2.5% ownership interest (20% of 50% = 10% + 2.5% = 12.5%) | LF - Skadden - Thompson, Spradling L - Gathmann, Lipshutz, Mellencamp Timing:Determine purchase or negotiate by signing; if consent needed 2 months |  | 0 - 10 bps ($365M) | ENE Dvlp Piti Holdings Corp; Transfer EI Guam Operations LLC (advisor) ENE Guam Piti Corp (Supervisor) to A
17 | Rio Geo (ApachiPortion) | ap | Brazil; Investment; Completed | Investment | Completed | 0.488 | C | C | C | P - No hold requirements if transfer above member level; ENE CTS International, wholly owned by ENE, owns 30% interest; ENE APACHI, a wholly owned sub of ENE APACHI LLC, owns a 30% interest | P - Transfer above member level | LF - VE - Coates, Brasher |  | 0 | Above member level | None
18 | Saipan | ap | Saipan; IPP; Early | IPP | Early | 0.08 | C | C | C | Capitalized development costs |  |  |  | 0
19 | SK | ap | South Korea; Gas LDC; Existing | Gas Distribution Company | Existing | 267.02 | A | C | C | P - Restriction on sale of project co interest for 3 yrs from closing date w/o SK consent (can transfer upstream); COC (reaches up to ENE) triggers buy-sell; SK will put price on table; ENE can buy or sell L - No restrictions R - No restrictions | P - Transfer upstream to satisfy restriction on sale of project co interest; For COC, try to obtain waiver or trigger buy/sell | LF - VE - Kornreich, Brasher McDonald, Lundstrom, Young Timing: 2 months |  | 0 | EI Korea Holdings Co. Ltd
20 | Soc Trang | ap | Vietnam; IPP; Early | IPP | Early | 3.59 | C | C | C | Capitalized development costs | Do not enter into transaction before closing. | LF - VE - Curry | ok | 0 | ENE Soc Trang Power Holdings II Ltd.
21 | Subic | ap | Phillippines; IPP; Existing | IPP | Existing | 26.6 | A | A | C | P - Cant sell at project co level w/o Yuchenko consent (can sell upstream); Yuchenko has Right of First Negotiation (no affiliate out); ENE must hold 51% voting stock of EGPP and other restrictions L - ENE 25% voting interest hold restriction | P - Get Yuchenko consent (believe easy to obtain) L - Put in A; Post closing, consider to either get lender consent or refinance bonds (can get neutral economics, but is a timing issue) | LF - Skadden - Brasher: VE - McGown P - Hughes, Hunt L - Gathmann, Hunt, Lipshutz, Mellencamp (4 months) Timing:After closing | ok | Unknown | ENE Power Phil Corp
22 | Subic Bonds | ap | Philippines; Bonds; Existing | Bonds | Existing | 4.483 | C | C | C | No transfer restrictions; Bonds are pwned by ENE CTS International, wholly owned sub of ENE |  |  | ok | 0 | Transfer entity that owns the asset
23 | SW Pipeline | ap | China; Pipeline; Early | Pipeline | Early | 7.544 | C | C | C | Capitalized development costs |  | LF - VE - Sasser, Brasher | ok | 0
24 | AEIA | ap | Africa | Inv. Fund | Early |  | C | C | C | No info |  |  |  | 0
25 | Bakrie | ap | Indonesia | Pipeline | Early |  | C | C | C | Early Development |  |  |  | 0
26 | Effasu | ap | Ghana | IPP | Early |  | C | C | C | Deal Dead |  |  |  | 0
27 | EGAT | ap | Thailand | Financing | Early |  | C | C | C | Deal Dead |  |  |  | 0
28 | Ghana Gas | ap | Ghana | Gas Sale | Early |  | C | C | C | Deal Dead |  |  |  | 0
| Name | BU | Country; Asset; Stage | Asset | Stage | BV (mm$) | ABC Now | ABC C | ABC Y/E | Transfer Restrictions | Action Items | People/Timing | Alternative | Friction Costs | Transfer Level (Not yet scrubbed by group)
29 | GNPower | ap | Philippines | LNG/Re-gas | Early |  | C | C | C | Deal Dead |  |  |  | 0
30 | Internet Web development Co |  | Korea/Thailand |  |  |  | C | C | C | No transfer restrictions; Equity held by ENE International Korea Resources LLC (No ownership is in Thailand) |  | Hughes, Hunt |  | 0
31 | Japan Trading | [5 empty] | C | C | C |  | Determine Japan structure | Baxter, Dr. Amin Timing: Whenever they want |  | 0
32 | Maputo Iron & Steel |  | Late dev |  |  |  | C | C | C | Duplicate to MISP |  |  |  | 0
33 | MIGA Claim |  | Insurance Claim |  |  |  | C | C | C | Duplicate to East Java |  |  |  | 0
34 | NSM | ap | Thailand | IPP | Early |  | C | C | C |  | Consider transfer to ENA; Claim in bankruptcy; Securities action pending against ENE for underwriting | Mellencamp Timing: 7/17 |  | 0
35 | Petroci Gaz | ap | Ivory Coast | Pipeline | Early |  | C | C | C | Deal Dead |  |  |  | 0
36 | Rio Geo (ApachiPortion) |  | Brazil; Investment; | [6 empty] | Duplicate to MISP |  | LF - VE - Coates, Brasher |  | 0
37 | Tema | ap | Ghana | IPP | Early |  | C | C | C | Deal Dead |  |  |  | 0
38 | TLP | ap | Thailand | IPP | Early |  | C | C | C | Deal Dead |  |  |  | 0
39 | TPI | ap | Thailand | IPP | Early |  | C | C | C | Deal Dead |  |  |  | 0
40 | WAGP | ap | West Africa | Pipeline | Early |  | C | C | C | Deal Dead |  |  |  | 0
WIND
1 | Aeolos/ Megalli | w | Greece; op | wind | operating | 12.3 | A | C | C | L - Consent required or trigger stiff prepayment penalty when ENE ownership is less than 50% in EWC | L - Obtain waiver to substitue EI for ENE in hold requirements R - Verify if there are any regulatory restrictions | LF - VE - Reilly, Hoghooghi L - Gathmann, Friedlander, Lipshutz, Mellencamp (2 months) R - Newell by 7/11 |  | $200M total friction costs for Wind
2 | Cabazon | w | USA; op | wind | operating | 27.88 | C | C | C | P - 100% equity in 'FOE' structure to preserve QF status; If all direct and indirect ownership interests transferred, stream of benefits true-up payment to 'FOE' L - No hold requirements or transfer restrictions | P - Transfer 99.999% to C, .001% to B to avoid true-up payment | LF - VE - Spradling, Hoghooghi |  | 0
3 | Chonos | w | Greece; dev right | wind | dev right | 0.5 |  |  |  | In development - Looking to be sold by 9-30-00 |  |  |  | 0
4 | Green Power I | w | USA; op | wind | operating | 19 | A | C | C | R - FERC approval required for COC | R - Section 203 filing immediately after announcement | LF - VE - Winner (FERC Filing) R - Newell, Winner Timing: 2 months |  | 0
5 | Lake Benton I | w | USA; op | wind | operating | -0.2 | C | C | C | ENE ownership 1% - no restrictions |  |  |  | 0
6 | Lake Benton II | w | USA; sale to FPL?? | Wind | Sale to FPL | -3.86 | C | C | C | Sold 6-30-00 |  |  |  | 0
7 | Megalli Vrissi | w | Greece; op | wind | operating | 6.8 | A | C | C | See Aeolos |  |  |  | 0
8 | Mesa Entities | w | USA; op | wind | operating | 9.01 | A | C | C | L - TCW $4.5MM debt - COC prepayment penalty $400K - runs upstream - get consent or pay off loan | L - Amend docs to substitute EI for ENE in hold restrictions | LF - VE - Reilly, Hoghooghi L - Friedlander, Gathmann, Lipshutz, Mellencamp (2 months) Timing:Determine payoff vs. seek consent by 7/24 |  | 0 |  | $2.5MM L/C as collateral for loan
9 | Owenreagh | w | Ireland; op | wind | operating | 0 | C | C | C | No issues |  |  |  | 0
10 | Painted Hills | w | USA; op | wind | operating | 1.1 | C | C | C | No issues |  |  |  | 0
11 | Project 251 | w | USA; op | wind | operating | 2.9 | C | C | C | No issues |  |  |  | 0
12 | San Antonio | w | USA; adv dev | wind | adv dev. | 0.3 | C | C | C | No issues |  |  |  | 0
13 | Sky River | w | USA; op | wind | operating | 0.41 | C | C | C | P - Reacquiring QF facility from 'FOE' structure L - Need CSFB consent for EWC to acquire 'FOE' interest in project; COC - CSFB | P - Buy 'FOE' out of the structure (7-15-00) L - Get CSFB consent for 'FOE' interest acquisition; Verify whether CSFB consent for COC needed | LF - VE - Reilly, Hoghooghi L - Freidlander, Gathmann, Lipshutz, Mellencamp (2 months) Timing: VE determine by 7/17 |  | 0
14 | Storm Lake I | w | USA; op | wind | operating | 0.25 | C | C | C | P - Edison Capital consent may be needed | P - Verify whether consent needed for sale upstream (EWC owns 1% interest) | LF - VE - Reilly P - Young Timing: 7/17 |  | 0
15 | Storm Lake II | w | USA; op | wind | operating | 0.13 | C | C | C | P - GE consent may be needed | P - Verify whether consent needed for sale upstream (EWC owns 1% interest) | LF - VE - Reilly P - Young Timing: 7/18 |  | 0
16 | Utgrunden | w | Sweden; adv dev | wind | adv dev. | 0.64 | C | C | C | Capitalized development costs |  |  |  | 0
17 | Victory Garden Phase IV | w | USA; op | wind | operating | 1.61 | C | C | C | No issues |  |  |  | 0
18 | Victory Garden Repower | w | USA; op | wind | operating | 8.15 | C | C | C | P - 100% equity in 'FOE' structure to preserve QF status; If all direct and indirect ownership interests transferred, stream of benefits true-up payment to 'FOE' L - No hold requirements or transfer restrictions | P - Transfer 99.999% to C, .001% to B to avoid true-up payment | LF - VE - Spradling, Reilly, Hoghooghi |  | 0
19 | Wind Resource Acreage | w | USA; land | land | land | 9.5 | C | C | C | No issues |  |  |  | 0
20 | Ardeche | w | France | wind | active dev. |  | C | C | C | No issues |  |  |  | 0
21 | Cefn Croes | w | UK | wind | active dev. |  | C | C | C | No issues |  |  |  | 0
22 | Christensen-Lazar | w | USA | wind | adv dev. |  | C | C | C | No issues |  |  |  | 0
23 | Cottonwood | w | USA | wind | adv dev. |  | C | C | C | No issues |  |  |  | 0
24 | Harwich | w | Offshore | wind | active dev. |  | C | C | C | Not yet closed | Confirm no issues w/ power contract |  |  | 0
25 | Honduras | w | Honduras | wind | active dev. |  | C | C | C | No issues |  |  |  | 0
26 | Indian Mesa II | w | USA | wind | adv dev. |  | C | C | C | No issues |  |  |  | 0
27 | Kahua | w | USA | wind | adv dev. |  | C | C | C | No issues |  |  |  | 0
29 | Maui | w | USA | wind | adv dev. |  | C | C | C | No issues |  |  |  | 0
30 | Nicaragua | w | Nicaragua | wind | active dev. |  | C | C | C | No issues |  |  |  | 0
31 | PSCO - Gobblers Knob | w | USA | wind | active dev. |  | C | C | C | No issues |  |  |  | 0
| Name | BU | Country; Asset; Stage | Asset | Stage | BV (mm$) | ABC Now | ABC C | ABC Y/E | Transfer Restrictions | Action Items | People/Timing | Alternative | Friction Costs | Transfer Level (Not yet scrubbed by group)
32 | Puerto Rico | w | Puerto Rico | wind | active dev. |  | C | C | C | No issues |  |  |  | 0
33 | SMUD 35 | w | USA | wind | adv dev. |  | C | C | C | No issues |  |  |  | 0
34 | Sweetwater | w | USA | wind | adv dev. |  | C | C | C | No issues |  |  |  | 0
35 | Tacke |  | Germany |  |  | 2.2 | C | C | C | Have not yet reviewed docs | Confirm there are no issues | LF - VE - Spradling Timing: 7/17 |  | 0 |  | Loan to EEL from Tacke
INDIA
1 | Capitalized Dev. Costs | in | India | N/A | N/A | 13 | C | C | C | No issues |  |  |  | 0
2 | Dabhol - Step 1(ENE owns 100% EMC, which owns 66% DPC; EIMC is a C entity to which 16% of DPC will be transferred by EMC by year end). At year end, EMC (100% vote and economics w/ ENE) in B; Operator and Fuel Manager must be B entities | in | India; IPP; Existing | IPP | Existing | 594.63 | B | TBD | 16%C, EMC in B | P - ROFR/tag-along rights unless EMC continues to hold 50% DPC; various intersponsor agreements L - GOI Gty requires ENE to hold 26% ownership interest (directly or through an affiliate); Bank Group - ENE must hold 50% economic interest prior to commercial service of Phase II and LNG facility and 26% thereafter; ENE, GE, and Bechtel must own 70% of DPC shares collectively until one year after completion of Phase II and then drops to 51% of DPC shares collectively (ENE can use 5/7 of the difference between 70% collectively owned now and the 51% hold requirement). Bank group must approve new investor but not transfer (parallel path to regulatory, 8 weeks): ENE must own 50% economic interest in Offshore Power Operations C.V. and Enron Fuels International Inc. (the Operator and Fuel Manager) R - FIPB (approval for new investor to make $ investment in India - 4-6 weeks) / RBI (Need approval for sale of shares, and permission for new investor to own shares of Indian co - 2 additional weeks) / Bank group (approval of new investor, not transfer - parallel path, 8 weeks) O - EECC and Bechtel Power Coordination Agreement has EECC COC restriction (confirm reaches upstream) triggering purchase right of Bechtel to take over EPC contract for Phase II (power) | P - Pref rights have 30 day notice No shareholder approval necessary L - OPIC Global Soln; Approval of transferee indentity for 50% in A (14% in C at closing) (4 months for step 1) R - Obtain FIPB and RBI consents for investment adn transfer and pledge of shares | LF - Skadden P - Gathmann, Cline, Bhatnagar L - Gathmann, Mukerji, Lipshutz R - Katwala Timing: P - Give notice at announcement; L - 4-6 mo; R - 3 months | ok | 50 - 100 bps ($10 - 20MM)
| Dabhol - Step 2 (Same as above but EMC will hold 26% DPC and EIMC would own 40% of DPC. Operator and Fuel Manager would be C entities at year end.) |  |  |  |  | 0 | B | B | 40%C, 26% EMC | Same as above | P - Trigger/obtain wiaver of shareholder rights; amend various intersponsor agreements L - Obtain lender consent to transfer shares and consent of lenders and MSEB (counterparty to contract) to assign fuel management contract to C entity and for operator to be a C entity R - Same as above | Timing: same as above (6 months if pursued first - 8 months if step 1 completed prior to step 2) |  | 0
3 | GAIL | in | India; Investment; Existing | Investment | Existing | 54.58 | C | C | C | Tax issue to moveout of EGEP - no transfer restrictions | Move out of EGEP | LF - Skadden | ok | 0
4 | Genesys | in | India; Investment; Existing | Investment | Existing | 1.5 | C | C | C | No issues if transfer upstream |  | LF - Skadden |  | 0 | Transfer above Enron India Regional Development Ltd.
5 | Ispat | in | India; IPP; Existing | IPP | Existing | 5 | C | C | C | P - ENE hold requirement of 23% applies upstream | P - Modify agreement to substitute EI for ENE and trigger or procure waiver of pref rights | LF - Skadden P - Gathmann Timing: 3 mo |  | 0
6 | Kannur | in | India; Power Plant; Lost Bid | Power Plant | Lost Bid | 7 | C | C | C | Capitalized development costs |  |  |  | 0
7 | Metgas | in | India; Pipeline; Existing | Pipeline | Existing | 20 | A/B | C | C | O - TIGA (LNG supplier) requires 26% ENE hold requirement in all Metgas entities | O - Restructure unsigned contracts to allow new EI 26% hold and guarantees | LF - Skadden O - Anando resolve before signing the SPA with TIGA) Timing: |  | 0
8 | Communications | in | India | Content | Providers |  | C | C | C |  |  |  |  | 0
9 | Data Center |  | Project; Development | Data Centers | Advanced Dev. |  | C | C | C | MOU only |  |  |  | 0
10 | ICO | [5 empty] | C | C | C | No issuses |  |  |  | 0
11 | India Fiber | [12 empty] | 0
13 | MSEB ROW | in | India | Fibre Optic Transmission | Advanced Dev. |  | X | C | C | P - Direct or indirect ENE Corp 100% hold requirement for 5 yrs | P - Evaluate possibility of obtaining waiver in context of the bid and then negotiate to obtain MSEB waiver to substitute EI for ENE in hold restrictions or wait for 5 years from to move into C | P - Katwala Timing: P - 2 weeks to determine if violates bid requirements; 2 months to get approval |  | 0
14 | Wockhardt Building | in | India | Hdqs. Bldg. | Definitive Agmt. |  | C | C | C | No issues |  |  |  | 0
15 | Rediff.com |  | India |  |  | 0.3 | C | C | C | No issues |  |  |  | 0
EE&CC
1 | EE&CC | ee |  |  |  | 284.56 | C | C | C | To be determined |  |  |  | 0

## Consents Needed
SIRESE Approval | Defense of Competition | Shell Pref Right | ASEP | ANEEL | ENERGAS | PR Port Authority/ PSC
GTB (maybe) | Arcor | GTB | CEG | EPE - maybe | TGS | Procaribe
Gas Bol (maybe) | TGS | TGB | CEG-Rio | Elektro |  | Progasco
Transredes (maybe) | Argentina Trading | Cuiaba - EPE |  |  |  | San Juan Gas