## Sheet1
Project Pueblo
To Do List
1/31/00
TASK |  | Accountable Party
1) Explore company wide relationship - Enron / PNM |  | Lorraine Lindberg
quantify the $ value PNM brings to Enron |  | LL
2) Research - Proposed generation projects in the surrounding area |  | Kevin Hyatt
Dave Delaney - ENA |  | KH
3) Political Landscape - Check out the current NMPRC and DOE |  | Tim Aron
positions |  | TA
4) Track ENA turbines for availability |  | KH
5) Market intelligence - new/projected load in Albuquerque area |  | KH/LL/TA
6) Research - PNM's current rate case |  | TA
FERC Form 1 and 2, elec load and rates, stranded costs
7) Enron Wind - Karras |  | Drew Fossum
forward info to Langley |  | DF
8) Put together a deal structure sheet for Project Pueblo |  | KH
9) Regulatory structure of project - structure of pipeline ownership |  | Susan Scott
pursue most attractive rate structure, optimal regulatory structure |  | SS
10)Schedule meeting to inform senior management |  | LL