## Sheet1
|  | Population | [6 empty] | Projects
Activity |  | total | Done | Power | Gas | IT | Process | People | Pheonix | Gas Solutions | Ranger | Genysis | Power Solution | Timeline | Comments
Data Accuracy:
Historical
| Review / rebook large deeals | 110 | 0 | X | X | X | X | X | X
| Industrial gas deals | 5000 | 0 |  | X |  |  |  |  | X
| Commercial Gas Deals |  |  |  | X |  |  |  |  | X
| Retail |  |  | X
| wholesale (EPMI/ENA) Intercompany Tie-up |  |  | X
| Contract / Trade Documentation | 16000 |  | X | X | [8 empty] | OCT | Ensure company has all contracual documents in robust, imaging / retention / system, Goals = Accessible, complete & maintained in livelink
Go Forward
Integration with Global Common Tables
| Global Counterparties | 15000 | 5000 | X | X |  | X | X | [5 empty] | OCT | Have Global Data systems , integrated into Gas & Power, trade,risk & billing systems. Input and Validate historical backlog..
| Global Contracts |  |  | X | X |  | X | X | [5 empty] | OCT | "
| Global Facility / Site |  |  | X | X |  | X | X | [5 empty] | G-Oct / P-Jan | Gas October / Power Jan-02 "
Capture all New Deals
Deal Ticket
| Complete Site Listings | [8 empty] | X |  |  | X | G - JUL P - AUG | Working to transition capture from Deal Mgmt / Prod Development to Risk
Validation
| Back to contract |  |  | X | X | X | X | X |  | X |  |  | X | G - JUL P - AUG | Need workflow tools and additional people. Have good support from Origination heads
| Fully Papered |  |  | X | X | X | X | X |  | X |  |  | X | G - JUL P - AUG
| Executed |  |  | X | X | X | X | X |  | X |  |  | X | G - JUL P - AUG
| Confirmation |  |  | X | X | X | X | X |  | X |  |  | X | G - JUL P - AUG
Risk System Limitations:
Global | Reliability / timming of market risk interface |  |  | X | X | X |  |  |  | X |  |  | X | G-Oct / P-Jan | Reduction of Spreadsheets (SEP), Stabalizing RGS / RPS (AUG)
| Reliability of credit agg system |  |  | X | X | X |  |  |  | X |  |  | X |  | Reduction of Spreadsheets (SEP), Stabalizing RGS / RPS (AUG). GCP system integration, Short Term Counterparty setup
| Risk Info not real-time |  |  | X | X | X | X |  |  | X | X |  | X |  | ST = Aggregate any existing measurement info from CSC; MT = Have CSC pull from additional utilities for Hourly/daily info on meter consumption; LT Gas Solution & Power Solution
| EAM (Energy Asset Management) |  |  | X | X | X | X | X |  | X |  |  | X | ST - SEP LTG-OCT LTP-JAN | ST - Create EAM Books on EES side of business (so DSM can manage), Rebook and hedge between EES & EWS; LT - GAS & POWER Solutions
Power Specific | Batch Dependencies |  |  | X |  | X | [6 empty] | X | MT - JAN / LT - ? | IT system build out, ST - batch processes continue to be maintained in short term, Quick hit RPS valuation build out to reduce batch usage.
| Validation Does Not Support all risk components |  |  | X |  | X | X | [5 empty] | X | ST - JUL MT - AUG LT-JAN | ST- Proof of concept on site profile; MT- Tariff curve database and Tariff reporting; LT- IT system build out.
No Intramonth
| Position |  |  | X |  | X | X | [5 empty] | X | MT - SEP LT - JAN | MT - Real Time solutions as above, load profiling / forcaseting at daily / hourly incroments; LT - Power Solution
| Valuation |  |  | X |  | X | X | [5 empty] | X | MT - SEP LT - JAN | MT - Real Time solutions as above, load profiling / forcaseting at daily / hourly incroments; LT - Power Solution
| No Liquidation |  |  | X |  | X | X | X |  |  |  |  | X | MT - JUL LT - JAN | MT - Pull liquatations from batches; LT - Power Solution
| No Actualization |  |  | X |  | X | X | X |  |  | X | X | X | MT - AUG LT - Q401 / Q102 | MT - Populate repository with CSC invoicing Data "Ranger Short Term Deliverables"; LT - Genysis, Ranger, EWS settlement support
| Book Structure - Non existent |  |  | X |  | X | X | X |  |  |  |  | X | MT - JUL LT - JAN | MT - Continue to "Shoe Horn" book structure; LT - Power Solution
| Intra Book Activity (Tariff vs. Retail Gen split out) Commodity vs. Consumption - Site Profile. |  |  | X |  | X | X | [5 empty] | X | MT - AUG LT - JAN | MT - Review feasability of deal rebooking to split out risks and on going maintenance; LT - Power Solution
| Option Valuation |  |  | X |  | X | X |  | X |  |  |  | X | MT - Q301 LT - JAN | MT - Spreadsheet models for day to day positions & P/L; LT - Power Solution
| Curve Database |  |  | X |  | X | X | [5 empty] | X | MT - AUG LT - SEP | MT - Implementation of the tariff curve database; LT - Implementation of commodity curve database
GAS Specific
| Validation Does Not Support all risk components |  |  |  | X | X | X |  |  | X |  |  |  | ST - JUL LT - OCT | ST- Proof of concept on site profile; MT- ; LT- IT system build out for Term, Physical bussiness issues will be resolved with Gas Solution.
No Intramonth
| Position |  |  |  | X | X | X |  |  | X |  |  |  | MT - SEP LT - OCT | MT - Develop position reports using Altra data; LT - Gas Solution
| Valuation |  |  |  | X | X | X |  |  | X |  |  |  | MT - SEP LT - OCT | MT - Develop position reports using Altra data; LT - Gas Solution
| No Actualization |  |  |  | X | X | X | X |  | X | X | X |  | LT - Q401 | LT - Genysis, Ranger, EWS settlement support
| Intra Book Activity Tariff, Commodity vs. Consumption - Site Profile. |  |  |  | X | X | X |  |  | X |  |  |  | LT - Q401 | LT - Gas Solution
| Option Valuation |  |  |  | X | X | X |  | X | X |  |  |  | MT-Q301 LT-Q401 | MT - Spreadsheet models for day to day positions & P/L; LT - Gas Solution
Billing System Consolidation: