## Pipeline
2001-10-16
Pipeline Expansions - West Region
Date Created | Pipe | Name | Receipt Region | Receipt City | Delivery Region | Delivery City | Quantity | In Service | Term | RESV | R.GRI | Comm | C GRI | ACA | fuel % | Rate | RATES | STATUS | COMMENTS | Cost (Millions) | Length (Miles)
| El Paso | Dagget to Ehrenberg | Bi-directional | Dagget, CA | Bi-directional | Ehrenberg, AZ | 500 | [9 empty] | $.10/mmbtu | Dead | Dead
| TWPL | Sun Devil | Thoreau |  | CA |  | 90 | 2004-01-01 | TBD | [7 empty] | $.24 Thoreau to CA + ? Fuel+commod | OPEN SEASON CLOSES 8/30/01. | Potential receipt points at Blanco include: BRT/Val Verde Plant, WFS Milagro, WFS/Kurtz Plan, and TransColorado/Blanco. Estimated max reservation rates: San Juan to Thoreau ($.0985 dth/d; thoreau to California ($0.24 dth/d); Thoreau to Phoenix ($.454 dth/d).
| SoCal | Backbone | California | California | California | California | 175 | 2001-12-01 | TBD | [6 empty] | rolled in: 85 M2/d @ Wheeler Ridge, 40 - 50 M2/d |  | ANNOUNCED |  | 15
| SoCal | Kramer | California | Kramer Junction | California | California | 200 | 2001-12-01 | TBD | [6 empty] | rolled in - new interconnect with Kern |  | RESEARCHING STATUS |  |  | 32
| PGT | 2002 Expansion | Canada | Kinsgate, ID | California | Malin, OR | 200 | 2002-11-01 | 30+ years | [6 empty] | rolled in + incremental .5% fuel on path | rolled in rate + incremental fuel | DONE - INCREMENTAL FUEL TO BE ASSESSED TO NEW SHIPPERS.
| PGT | 2003 Expansion | Canada | Kinsgate, ID | California | Malin, OR | 230 | 2003-11-01 | TBD | 0.445 |  | 0.0003 |  | 0.0022 |  | TBD - estimate of $.44-.46 + incremental fuel
| Kern River | High Desert Lateral | Rockies | Kern River/Mojave | California | Victorville, CA | 282 | 2003-07-01 | 21 tears | [7 empty] | $.0583/dth |  | Will feed High Dester Power (720MW) near Victorville. | 28.9 | 31.6
| Questar Southern Trails | Southern Trails | San Juan | San Juan | California Border | California Border | 80 | 2002-04-01 | TBD | [6 empty] | $.52 hurdle/Questar finalizing Navajo agreement |  | HAS FERC APPROVAL. EXPECT MID 2002 START DATE. DELIVERY POINT ISSUES STILL UNRESOLVED. | Oil line conversion - has FERC approval. Could be on-line in May instead of April 02.
| Questar Southern Trails | Southern Trails | San Juan | San Juan | California Border | California Border | 120 | TBD | TBD | [6 empty] | TBD |  | Socal RLS rate issue | compression expansion of above. Could come on-line in July 2002 |  |  | (partial service in July 2002)
| BC Gas | Inland Pacific Connector | Canada | Southern Crossing Interconnect | Canada | Huntington, BC | 350 | 2003-11-01 | [9 empty] | Announced |  | 307 | 150
| Westcoast Energy | Southern Mainline | Canada |  | Canada |  | 100 | 2003-11-01 | [9 empty] | Announced | 100 MMcf/d on Alberta Leg, 200 MMcf/d on mainline
| Georges Straight Crossing | Georges Straight | PNW | Sumas, WA | Canada | Vancouver, BC | 100 | 2003-10-01 | [9 empty] | FERC filing made |  | 159 | 85
| PGT | Washington Lateral | Central WA |  | I-5 Corridor | Stanfileld | 130 | 1905-06-26 | TBD | [8 empty] | NON BINDING OPEN SEASON CLOSED. WORKING ON PRECEDANT AGREEMENTS. PGT MEETING ON AUGUST 21, 2001.
| Williston Basin Interstate Pipeline | Grasslands System | Powder River | Gillette, WY | Killdeer, ND |  | 80 | 2002-10-01 | [9 empty] | Will make FERC filing in October 2001. With FERC approval, construction could begin as early as 2002Q3. | Initially pipe will have three compressor stations: one on the south end of the route in Wyoming, another in eastern Montana, and a third in North Dakota. Pipeline will transport to Midwestern markets. |  | 245
| El Paso | Wilcox Lateral | Arizona | Cochise County, AZ | Mexico | Mermosilla and Agua Prieta, Mexico | 130 | 2001-12-01 | [9 empty] | FERC approval received in 2000. Completed all construction in late August 2001. Also has received approval from Pemex to connect to Pemex facilities at border. As of Sep 17, 2001, it had not made a decision on the east leg expansion. Has yet to post an open season. The project could take up to two years to complete. | According to 9/17/01 NGI article, only 92.166 MMcf/d on the lateral is subscribed (37.834 available). The lateral runs 60 miles form the EPNG mainline in Cochise County, AZ to border crossing facilities and is aimed at serviing several existing and proposed gas-fired power plants in Sonora, Mexico. EPNG has received inquires regarding expanding the the east leg, which would connect the lateral to the discharge of the Willcox Compressor Station and looping the east leg of the lateral. EPNG contact is Jerry Strange, director for transport marketing, (719-520-4687). | 30 | 70
| North Baja | North Baja | Southern California | Ehrenberg, AZ | Mexico | Tijuana, Mexico | 500 | 2002-09-01 | variable (20 year) | [6 empty] | $.35/mmbtu recourse rate (US and Mexico) | $.13728 Dth US/$.2164 Mex + 1% fuel | EXPECT FERC APPROVAL NOV 2001. RECEIVED MEXICAN PERMITS. | Cosponsors: PG&E, Sempra, Proxima Gas | 230 | 212
| El Paso | Gasoductos de Chihuahua |  |  | Mexico |  |  | 2002-01-01 | [9 empty] | FERC filing made on 8/17/01. | Samalayuca lateral to Chihuahua, Mexico (Hueco Compressor to Border). Daily export capacity will increase from 208 mmcf/d to 308 mmcf/d. Will feed a new plant near northern city of El Encino (60 mmcf/d) that comes on-line in 10/1/01. Plant will add anohter 40 mmcf/d in early 2002. Six parties responded to open season, but only one, MGI Supply, was willing to sign on to long term contracts. On 8/31/01 NGI reported that the Chihuahua III power plant near the City of Juarez will require an additional 50 MMcf/d of transportation capacity by May 2003.
| KMIGT | Advantage | Cheyenne Hub |  | Mid-Continent |  | 330 | [8 empty] | Calpine = 400 Phase 1, 500 Phase II |  | OPEN SEASON PROPOSED FOR FALL
| CIG | Coastal Connection (COCO) | Rockies | Cheyenne Hub | Mid-Continent | Greensburg, KS | 500 | 2003-01-01 | 10 years | [7 empty] | $.28 +.8% fuel | Announced | Estimated In Service Date. Better mid-continent access than Western Frontier.
| El Paso | Dumas Gas Transmission | Southwest | Colfax County, NM | Mid-Continent | Moore County, TX | 175 | 2001-07-01 | [9 empty] | Announced. Interconnect with Northern Natural for delivery to Mid-continent. |  |  | 185
| WIC | NECO | NE Colorado Market |  | NE Colorado Market | [12 empty] | OPEN SEASON PROPOSED FOR FALL
2001-10-10 | Tuscarora | Wadsworth Lateral | Nevada | Washoe, NV | Nevada | Tracy, NV | 96 | 2002-12-01 | 10 - 15 years | [6 empty] | need to determine |  | In September 2001, FERC issued a favorable preliminary determination on non-environmental grounds. | Sponsors: Sierra Pacific and TCPL. Would extend from Tuscarora's mainline in northern Washoe County, NV to an interconnect with Paiute Pipeline in Nevada. The expansion would serve two new power generation facilities near Tracy and Wadsworth, NV. Duke is contructing a 540 MW pland near Wadsworth and Morgan Stanly is constructing a 360 MW facility near Tracy. | 60 | 229
| CIG Ruby (PG&E bypass) | RUBY | Rockies | Uintah County, UT | Northern California | Sacramento, CA | 750 | 2003-12-01 | 10 years | [6 empty] | $.80/mmbtu hurdle, if > 500 M2/d, will build | Recourse=$.5603/dth Z1, $.1793/dt Z2 +1% fuel | OPEN SEASON CONCLUDED WAITING FOR PRECEDANT AGREEMENTS. | Will travel via: Reno, Yuba City, Sacremento,Wild Goose | 200 | 850
| Sonora (Calpine&KN) | Sonoran Phase II | SoCal Border | Needles, CA | Northern California | Antioch, CA | 1000 | TBD | TBD |  | 0.45 |  |  |  | 1 | Phase II intrastate - | $.45 Resv + 1.0% fuel | OPEN SEASON COMPLETED. HAVING DIFFICULTY GAINING SIGNED COMMITMENTS. | Capacity anywhere from 1,000 - 1,500 MMcf/d | 1100 | 590
| WIC |  | Cheyenne Hub |  | Opal | [12 empty] | OPEN SEASON CLOSED. WAITING FOR PRECEDENT AGREEMENTS.
| PG&E | Backbone - Redwood | Malin | Malin, OR | PG&E Citygate |  | 200 | 2003-12-01 | TBD | [6 empty] | Incremental Rates: |  | 200 - 500 MILLION REDWOOD. OPEN SEASON POSTPONED.
| TWPL | Red Rock | Permian |  | PGE/Southpoint/Citizens |  | 100 | 2002-12-01 | 2 - 30 years | 0.63 | included | included | included | included |  | one part rates | $.63/$.45/$.38 one part 5/10/15 yr = rolled fuel |  |  | 93 | 400
| TWPL | Red Rock | Permian |  | PGE/Southpoint/Citizens |  |  |  |  | 0.45 | included | included | included | included |  | one part rates
| TWPL | Red Rock | Permian |  | PGE/Southpoint/Citizens |  |  |  |  | 0.38 | included | included | included | included |  | one part rates
| TWPL | Sun Devil | Thoreau |  | Phoenix | Phoenix, AZ | 450 | 2004-01-01 | TBD | [7 empty] | $.454 Thoreau to Phoenix + ? Fuel+commod | OPEN SEASON CLOSES 8/30/01. | Potential receipt points at Blanco include: BRT/Val Verde Plant, WFS Milagro, WFS/Kurtz Plan, and TransColorado/Blanco. Estimated max reservation rates: San Juan to Thoreau ($.0985 dth/d; thoreau to California ($0.24 dth/d); Thoreau to Phoenix ($.454 dth/d).
| NWPL | Evergreen | PNW | Sumas, WA | PNW | Chehalis, WA | 244 | 2003-06-01 | 15 yr - 25 yr | [6 empty] | Rate to be announced upon FERC filing | $.41 Resv + ? Commod + ? Fuel | FERC FILING MADE. FULLY SUBSCRIBED. | (277 M2/d of K) | 200 | 26
| NWPL | Grants Pass Lateral | PNW | Portland, OR | PNW | Grants Pass, OR | [11 empty] | Announced | Sponsor: Williams |  | 260
| NWPL | Gorge Expansion | Stanfield | Stanfield, OR | PNW |  | 50 | 2003-10-01 | TBD | [6 empty] | incremental | rolled in rate - fuel? | 7,000 TO FILL EVERGREEN. 42,000 TO EXISTING SHIPPERS. EXPECT FERC FILING SOON.
| CIG | Raton Phase I | Rockies | Las Animas County, CO | Rockies | Baca County, CO | 85 | 2001-09-01 | [9 empty] | FERC APPLICATION FILED | Length = 70+ compression |  | 70
| CIG | Raton Phase II | Rockies | Las Animas County, CO | Rockies | Baca County, CO | 135 | 2002-09-01 | [9 empty] | Announced | Start date sometime in fall 2002 |  | 70
| CIG | Campo, Cucharas, Picketwire Laterals | Rockies |  | Rockies |  | 0 | 2002-10-01 | [9 empty] | Announced | Volume TBD.
| El Paso | Western Frontier | Rockies | Northeastern Colorado | Rockies | Southwestern Kansas | 540 | 2003-11-01 | [8 empty] | $.32/dth + 1% fuel (verify fuel) | OPEN SEASON CLOSED IN JULY. FERC FILING PLANNED FOR 2001Q4. | Williams central markets. |  | 320
| TWPL | Red Rock | Permian |  | Socal |  |  |  |  | 0.63 | included | included | included | included |  | one part rates
| TWPL | Red Rock | Permian |  | Socal |  |  |  |  | 0.45 | included | included | included | included |  | one part rates
| TWPL | Red Rock | Permian |  | Socal |  |  |  |  | 0.38 | included | included | included | included |  | one part rates
| TWPL | Red Rock | Permian |  | Socal |  | 50 | 2002-12-01 | 2 - 30 years | [6 empty] | One part rates: $.63-5yr/$.45-10yr/$.38-15yr+ | $.63/$.45/$.38 one part 5/10/15 yr = rolled fuel | FERC FILING MADE ON 6/1/2001. FILED FOR 150,000, BUT ONLY 108,000 CONTRACTED. NEEDLES FULL. 42,000 REMAINS UNSUBSCRIBED AT OTHER DELIVERY POINTS.
| Kern River | Emergency filing | Rockies | Opal | SoCal | Wheeler Ridge | 21 | July 1,2001 | April 30,2003 | 0.8066 | 0.003 | 0.06 | 0.007 | 0.0022 | 6.2 | $.820 Resv+.003 RGRI Com+$.06 Com+ACA | $.8096/Dth Resv + $.0692 Com. + 6.2% fuel | DONE
| Kern River | Emergency filing | Rockies | Opal | SoCal | Wheeler Ridge | 114 | July 1,2001 | April 30,2002 | 0.8066 | 0.003 | 0.06 | 0.007 | 0.0022 | 4.2 | +GRI +4.2% thru 4/30/02 and 6.2% thereafter | $.8096/Dth Resv + $.0692 Com. + 4.2% fuel | DONE | +202 M2/d @ Wheeler
| Kern River | 2002 Expansion | Rockies | Opal | SoCal | Wheeler Ridge | 10.5 | May 1,2002 | 10 or 15 yr | [6 empty] | $.3374 Resv+$.002 RGRI+$.0573 Com+ACA | $.40 & $.45 for 10/15 yrs + 1.6% (add GRI) | RESEARCHING FERC APPROVAL
| Kern River | 2003 Expansion | Rockies | Opal | SoCal | Wheeler Ridge | 900 | May 1,2003 | 15 yr | [6 empty] | TBD = estimate a demand charge of $.45 plus | $.70 & .568 for 10/15 yrs + 3.05% fuel | FERC APPLICATION FILED AUGUST 7, 2001 | +Wheeler Ridge to 830 M2/d
| Sonora (Calpine&KN) | Sonoran Phase I | San Juan | Blanco, NM | SoCal Border | Topock, CA | 750 | 2003-06-01 | 20 YEARS |  | 0.39 |  |  |  | 1.3 | Phase I to Border - $.39/mmbtu + 1.3% fuel | $.39 Resv + 1.3% fuel | OPEN SEASON COMPLETED. HAVING DIFFICULTY GAINING SIGNED COMMITMENTS. |  | 624 | 570
| El Paso | Sacramento Valley | California Border |  | Southern California | Sacramento, CA | 0 | 2003-06-01 | TBD | [7 empty] | TBD | OPEN SEASON CLOSED. BINDING INTEREST TBD. | TBD on Capacity
| El Paso | Line 2000 Power Up | Permian | Texas | Southern California | Ehrenberg, AZ | 320 | [9 empty] | Rolled in rates plus 5% fuel | Dead | No interest. Compression addition to All American.
| El Paso | All American | Permian | McCarney, TX | Southern California | Bakersfield, CA | 230 | 2001-12-31 | NA | [6 empty] | TBD | Rolled in rates, including fuel | FERC APPROVED. CAPACITY TO FILL EXISTING NEEDS. AKA LINE 2000 | Augment existing shippers, no new cd. | 75 | 1088
| PGT | 2003 Expansion | Canada | Kinsgate, ID | Stanfield, OR | Malin, OR | 100 | 2003-11-01 | TBD | 0.2015 |  | 0.0001 |  | 0.0022 |  | TBD - estimate of $.44-.46 + incremental fuel |  | OPEN SEASON CLOSED. EXPECT FILING FOR 125,000. DON'T KNOW FILING DATE YET.
| NWPL | Displacement Fix | Rockies |  | Stanfield, OR |  | 175 | 2003-10-01 | N/A | [6 empty] | Rolled in - TBD | Rolled in rate - will cause $.02 increase | SETTLEMENT APPROVED BY CUSTOMERS. | Displacement Fix. (Primary obligations only)
| NWPL | Piggyback | Rockies |  | Stanfield, OR |  | 0 | 2003-10-01 | TBD | [6 empty] | incremental | TBD - incremental | AWAITING OPEN SEASON.
| TWPL | Sun Devil | Blanco |  | Thoreau |  | 750 | 2004-01-01 | TBD | [7 empty] | $.0985 SJ to thoreau + ? Fuel+ commod | OPEN SEASON CLOSES 8/30/01. | Potential receipt points at Blanco include: BRT/Val Verde Plant, WFS Milagro, WFS/Kurtz Plan, and TransColorado/Blanco. Estimated max reservation rates: San Juan to Thoreau ($.0985 dth/d; thoreau to California ($0.24 dth/d); Thoreau to Phoenix ($.454 dth/d).
2001-10-11 | Questar | Mainline 104 | Rockies | Price, UT | Wasatch Front | Elberta, UT | 272 | 2001-11-01 | [9 empty] | FERC APPROVED 6/13/01. CAPACITY TO FILL EXISTING NEEDS. AKA LINE 2000 | Interconnect with Kern. Questar is other project sponsor. | 62 | 75
| Fort Union | Fort Union Expansion | Powder/Wind River Basins | Gillette, WY | Wyoming | Glenrock, WY | 200 | 2001-10-01 | [9 empty] | Announced | Sponsors: CMS, Western Gas Resources, CIG, Barrett Resources |  | 106
| WIC | Medicine Bow Lateral Looping | Powder River/Wind River Basins | Converse County, WY |  | Weld Country, CO | 675 | [12 empty] | 160 | 150
| Williston Basin Interstate Pipeline | Line 14 Expansion | Powder River/Wind River Basins | Recluse, WY |  | Northern Border | 40 | 2001-11-01 | [9 empty] | Announced | Capacity will be between 40 and 100 MMCF/d
| CIG |  | Powder/Wind River Basins |  |  |  | 45 | [10 empty] | Announced
| Burlington Resources/Enron | Lost Creek | Wind River Basin |  |  | Wamsutter, WY | 275 | [10 empty] | Announced |  | 54 | 124
| Kern River | 2002 Expansion | [7 empty] | 0.4247 | 0.0033 | 0.06 | 0.007 | 0.0022 |  | 10 year ETR
| Kern River | 2002 Expansion | [7 empty] | 0.3731 | 0.0033 | 0.06 | 0.007 | 0.0022 |  | 15 year ETR
| Kern River | 2002 Expansion | [7 empty] | 0.6043 | 0.0033 | 0.06 | 0.007 | 0.0022 |  | Recourse
| Trailblazer | Trailbazer Expansion |  | Rockport, CO |  | Gage County, NE | 300 | 2002-07-01 | [9 empty] | Announced | Compression addition. Sponsors: Enron, Kinder Morgan

## Storage
Pipeline Expansions - West Region
Sponsor | Name | Receipt Region | Storage City | Initial Storage Quantity (BCF) | Storage Quantity Increase | Final Storage Q | Initial Withdrawal Quantity (MMcf/d) | Withdrawal Quantity Increase (MMCF/d) | Final Withdrawal Quantity | Initial Injection Quantity | Injection Quantity Increase (MMCF/d) | Final Injection Quantity | In Service | Term | STATUS | COMMENTS
Alberta Energy (AEC) | Wild Goose | Northern California | Gridley, CA | 14 | 15 bcf | 29 | 200 | 500 | 700 | 80 | 370 | 450 | 2004-04-01 | 2 - 30 years | Open Season closed 5/22/01. CPUC Application Filed | Current capacity is 14BCF. Current withdrawal is 200 mmcf/d. Current injection is 80 mmcf/d. If regulatory approval is expedited, could be in service as early as 2003.
Western Hub Properties | Lodi | Northern California | Sacramento, CA | 0 | 12 | 12 | 0 | 500 | 500 | 0 | 300 | 400 | 2001-12-01 |  | Announced. Received special regulatory approval relief from Gov. Davis. As of 10/9/01 awaiting tariff approval from CPUC. | Will be used to store gas for new and existing power plants in California. Calpine singed a 10 yar deal to take up to 4 bcf of gas. Facility will ultimately have 12 bcf of capacity, which will come on-line about three months after the first 9. Will be able to cycle gas up to six times a year. Aquila is in the process of acquiring Western Hub. Facility will provide service directly to PG&E Line 401. See http://www.cpuc.ca.gov/Environment/info/lodi-gas.htm. On 10/9/01 I spoke with Kevin O'Tool (281-679-3591). He told me the following: 1) They will have a Nov 1, 2001 start date for the first 9 bcf of capacity; they will have an April 1, 2002 start date for the subsequent 3 bcf of capacity. November 1 will have a 300 MM injection and withdrawal quantity. April 1 will have a 400 MM injection and 500 MM withdrawal quantity. The are currently (as of October 9, 2001) injecting pad gas. On 10/12/01, NGI published an article contradicting O'Tool's Nov 1, 2001 start date. Now, Jim Fossum, in-state manager for Western Hub, predicts a start date of Dec. 1, 2001.
AES | Colorado Gas Storage | Colorado | Denver, CO |  | 9 bcf | 9 | [6 empty] | 2002-11-01 |  | Approval received from Colorado Oil and Gas Conservation Commission, the Colorado PUC, and Adams County, CO officials. | Will have ability to cycle working gas more than 2x per year. Interconnect with CIG is in progress. Future connection with Xcel is under consideration.
SoCal | La Goleta | Southern California | Santa Barbara, CA | [12 empty] | Proposed removal of 7 bcf of base gas for sale into market. No impact on working gas capacity in field
SoCal | Aliso Canyon | Southern California | Los Angeles County | [12 empty] | Proposed removal of 7 bcf of base gas for sale into market. No impact on working gas capacity in field
CIG | Fort Morgan | [6 empty] | 102

## LNG
Date Added to List/Modified | Sponsor | Name | Location | In-Service Date | Sendout Capacity (Bcf/d) | Cost (Millions) | Status | Comments
2001-10-10 | CMS and Sempra |  | 60 Miles South of Border near Ensenada in Baja, CA | 2005-10-01 | 1 | 500 | Will file an application with Mexican regulatory officials in late 2001. | Regasified gas would flow north into Baja, CA and the SW U.S. via a new proposed pipeline that would connect the terminal to existing intersttes.