## Sheet1 (2)
BGE Market Entry
Target Origination Sales Effort Start Date: August 27, 2001
Requirement | Responsibility | Week of
|  | 2001-07-30 | 2001-08-06 | 2001-08-13 | 2001-08-20 | 2001-08-27 | 2001-09-03 | 2001-09-10 | 2001-09-17
Verify load shape with site profile desk | Product Development | bar: 2001-07-30
Produce batch to analyze various cash flows | Product Development | bar: 2001-07-30
Determine best product alternatives and prepare Product Approval Template | Product Development/ Product Delivery | bar: 2001-07-30 to 2001-08-06
Prepare draft Transaction Confirmation | Legal | bar: 2001-07-30; 2001-08-13
Initiate financial billing set up procedures | Product Delivery/ Services Group | bar: 2001-08-06 to 2001-08-13
Prepare marketing materials | Product Delivery/ Product Marketing | bar: 2001-07-30; 2001-08-13 to 2001-08-20
Finalize target list | Product Delivery | bar: 2001-08-13 to 2001-08-20
Get approval from EWS and Deal Management | Product Development/ Product Delivery | bar: 2001-07-30; 2001-08-13 to 2001-08-20
Finalize contract | Legal | bar: 2001-07-30; 2001-08-20
Introduce product(s) to Commodity Structuring | Product Delivery/ Commodity Structuring | bar: 2001-08-20
Introduce product(s) to Origination Groups | Product Delivery/ Origination | bar: 2001-08-20
Begin sales efforts | Origination | bar: 2001-07-30; 2001-08-27 to 2001-09-03
Generate market feedback from customers | Origination/ Product Delivery | bar: 2001-07-30; 2001-09-03
If necessary, adjust product | Product Development/ Product Delivery | bar: 2001-07-30; 2001-09-10 to 2001-09-17
Negotiate remaining agreements with BGE | Government Relations | 2001-07-30: WILL COMMENCE IN DECEMBER TO MEET JULY 2002 PHYSICAL DELIVERY TARGET
.

## Sheet1
BGE Market Entry | Week of
 | time axis 2001-08-03 to 2001-10-08
Negotiate remaining agreements with BGE | bar: 2001-08-06 to 2001-09-14
Verify load shape with site profile desk | bar: 2001-08-03; 2001-09-06
Produce batch to analyze various cash flows | bar: 2001-09-06
Determine best product alternative and prepare Product Approval Template | bar: 2001-08-06 to 2001-08-10; 2001-09-06
Prepare draft Transaction Confirmation | bar: 2001-08-13 to 2001-08-17; 2001-09-06
Prepare marketing materials | bar: 2001-08-13 to 2001-09-14
Get approval from Deal Management and Power Desk | bar: 2001-08-13 to 2001-08-31; 2001-09-06
Finalize contract | bar: 2001-08-30 to 2001-09-06
.