## Sheet1
2001-08-09
Pipeline Expansions - West Region
Pipe |  | Route | Quantity (MMBTU) | In Service | Term | Rate | STATUS
El Paso | LINE 2000 | PERMIAN TO SOUTHERN CALIFORNIA | 230000 | 2001-12-31 | NA | TBD | FERC APPROVED. CAPACITY TO FILL EXISTING NEEDS.
EL PASO | POWER UP 2000 | PERMIAN TO SOUTHERN CALIFORNIA | DEAD
EL PASO | SACRAMENTO VALLEY | BORDER TO SACRAMENTO | TBD | MID 2003 | TBD |  | OPEN SEASON CLOSED. BINDING INTEREST TBD.
EL PASO | DAGGET TO EHRENBERG | DAGGET TO EHRENBERG | DEAD
Kern River |  | Opal - Wheeler Ridge | 21000 | July 1,2001 | April 30,2003 | $.820 Resv+.003 RGRI Com+$.06 Com+ACA | DONE
Emergency filing |  | +202 M2/d @ Wheeler | 114000 | July 1,2001 | April 30,2002 | +GRI +4.2% thru 4/30/02 and 6.2% thereafter | DONE
(thru 4/30/03)
Kern River |  | Opal - Wheeler Ridge | 10500 | May 1,2002 | 10 or 15 yr | $.3374 Resv+$.002 RGRI+$.0573 Com+ACA | RESEARCHING FERC APPROVAL
+GRI+$.051 Daggett Comp+1.6%
Kern River |  | Opal - Wheeler Ridge | 900000 | May 1,2003 | 15 yr | TBD = estimate a demand charge of $.45 plus | FERC APPLICATION FILED AUGUST 7, 2001
|  | +Wheeler Ridge to 830 M2/d |  |  |  | incremental fuel
Questar Southern Trails | SOUTHERN TRAILS | San Juan to Border | 80000 | April or May 2002 | TBD | $.52 hurdle/Questar finalizing Navajo agreement | HAS FERC APPROVAL. EXPECT MID 2002 START DATE. DELIVERY POINT ISSUES STILL UNRESOLVED.
Oil line conversion - has FERC approval | [5 empty] | Duke has contracted full volume
Questar Southern Trails | SOUTHERN TRAILS | San Juan to Border | 40000 | June or July 2002 | TBD | TBD | EARLY PLANNING PHASES. NOT ANNOUNCED YET. NO OPEN SEASON YET.
compression expansion of above
Questar - California | SOUTHERN TRAILS(?) | Border to Long Beach | 120000 | TBD | TBD | Regulatory block at CPUC | SOCAL PEAKING SERVICE THREATENS CONVERSION.
PGT | 2002 EXPANSION | Kingsgate to Malin | 200000 | November 2002 | 30+ years | rolled in + incremental .5% fuel on path | DONE - INCREMENTAL FUEL TO BE ASSESSED TO NEW SHIPPERS.
PGT | 2003 EXPANSION | Kingsgate to Malin | 125000 | November 2003 | TBD | TBD - estimate of $.44-.46 + incremental fuel | OPEN SEASON CLOSED. EXPECT FILING FOR 125,000. DON'T KNOW FILING DATE YET.
PGT | WASHINGTON LATERAL | CENTRAL WA TO I-5 CORRIDOR. | TBD | 2004 | TBD |  | NON BINDING OPEN SEASON CLOSED. WORKING ON PRECEDANT AGREEMENTS. PGT MEETING ON AUGUST 21, 2001.
TWPL | RED ROCK. | Permian to PGE,
|  | Griffith and Southpoint | 150000 | late Q2 - 2002 | TBD | One part rates: $.63-5yr/$.45-10yr/$.38-15yr+ | FERC FILING MADE ON 6/1/2001. FILED FOR 150,000, BUT ONLY 108,000 CONTRACTED. NEEDLES FULL. 42,000 REMAINS UNSUBSCRIBED AT OTHER DELIVERY POINTS.
5% fuel
TWPL | SUN DEVIL | BLANCO TO THOREAUX | 780000 | 2004-01-01 | TBD |  | OPEN SEASON CLOSES 8/30/01.
|  | THOROUEX | 90000 | 2004-01-01 | TBD
|  | THOROEUX TO PHOENIX | 450000 | 2004-01-01 | TBD
NWPL | EVERGREEN | Sumas to Chehalis | 244000 | June 1, 2003 | 15 yr - 25 yr | Rate to be announced upon FERC filing | FERC FILING MADE. FULLY SUBSCRIBED.
(277 M2/d of K)
NWPL | DISPLACEMENT FIX | Displacement fix | 175000 | October 1, 2003 | N/A | Rolled in - TBD | SETTLEMENT APPROVED BY CUSTOMERS.
(Primary obligations only)
NWPL | PIGGYBACK | Northbound to Stanfield | TBD | October 1, 2003 | TBD | incremental | AWAITING OPEN SEASON.
NWPL | GORGE EXPANSION | Stanfield to I-5 (Gorge) | 50000 | October 1, 2003 | TBD | incremental | 7,000 TO FILL EVERGREEN. 42,000 TO EXISTING SHIPPERS. EXPECT FERC FILING SOON.
CIG Ruby (PG&E bypass) | RUBY | Rockies to Northern CA | 750000 | late 2003 | TBD | $.80/mmbtu hurdle, if > 500 M2/d, will build | OPEN SEASON CONCLUDED WAITING FOR PRECEDANT AGREEMENTS.
|  | (Reno, Yuba City, Sacremento,Wild Goose) |  |  |  | access to Cheyenne!
WIC |  | CHEYENNE TO OPAL |  |  |  |  | OPEN SEASON CLOSED. WAITING FOR PRECEDENT AGREEMENTS.
QUESTAR NORTH |  | TBD
QUESTAR SOUTH |  | TBD
Socal | BACKBONE | Backbone | 175000 | 2001-12-01 | TBD | rolled in: 85 M2/d @ Wheeler Ridge, 40 - 50 M2/d | RESEARCHING STATUS
at Line 85 and 50 M2/d @ N. Needles
SOCAL | KRAMER | Kramer Junction | 200000 | 2001-12-01 | TBD | rolled in - new interconnect with Kern | RESEARCHING STATUS
PG&E |  | Backbone | TBD | late 2003 | TBD | Incremental Rates: | 200 - 500 MILLION REDWOOD. OPEN SEASON CLOSES 8/31/01.
Redwood loops - 200 m2/d = $.08/mmbtu
Redwood Compression - 200 m2/d = $.24/mmbtu
Baja - 200 m2/d = $400 MM
North Baja (PG&E/Sempra) |  | Ehrenberg to Tijuana | 500000 | September 2003 | variable | $.35/mmbtu recourse rate (US and Mexico) | EXPECT FERC APPROVAL NOV 2001. RECEIVED MEXICAN PERMITS.
|  |  |  | (partial service in |  | $.29 min negotiated rate for > 20 yrs.
|  |  |  | July 2002) |  | negotiated rate higher for shorter term
Tuscarora |  | Malin to Reno | 96000 | late 2002 | 10 - 15 years | need to determine | RESEARCHING STATUS.
Sonora (Calpine&KN) |  | San Juan to Border | 750000 | mid 2003 | 20 YEARS | Phase I to Border - $.39/mmbtu + 1.3% fuel | OPEN SEASON COMPLETED. HAVING DIFFICULTY GAINING SIGNED COMMITMENTS.
|  | Topock to SFO | 1 - 1.5 Bcf/day | TBD | TBD | Phase II intrastate - TBD | OPEN SEASON COMPLETED. HAVING DIFFICULTY GAINING SIGNED COMMITMENTS.
Calpine = 400 Phase 1, 500 Phase II