## Sheet1
DATE: November 26, 2001 |  |  | Assigned
Issue | Description | Status | To
BPCG GT Modeling Issue A
BPCG GT Modeling Issue B
BPCG Start Up
BPCG Start Up | Hours off line not calculated correctly
BPCG Group Units | Not paying grouped units when OOM for billing dates run May 2001
BPCG | Not pro-rating the mingen $ when a generator is operating
below mingen.
BPCG | Exclusion when LBMP negative
Transactions Import curtailment
PURPA Class 1 balancing at generator
PURPA Class 2 balancing date sensitive
Reserves | Synchronous LOC calc change
Reserves | 10-min non-sync LOC
Data | Various internal NYISO and external TO data
Regulation performance penalties | Regulating units not charged performance penalties
LBMP | SCD/PTS interval mis-match
ECA-B | Price corrections not in billing
Mitigation - Incorrect mitigation parameters
BPCG April 2001 Code error
DAM contract balancing | Code desing issue regarding weighting of on-dispatch time
DAM contract balancing | BAS doesn't distinguish between a derate called in by
generator or NYISO/TO. BAS being modified to read MIS
DAM contract balancing | When subtracting savings not capped at zero thus negative bids
receive large CBP
Curtailed transactions | Balancing incorrectly due to conflicting data from MIS
Hourly advisory statements | When BME fails no data for the hour gets printed in CSV
PTS-LBMP Mismatch | SCD intervals for PTS and LBMP calc not agree
Invoice Format | NYISO uplift charges reported under LRR uplift charges
Invoice Labeling | Billing summary label adjustments as prior period but monthly
statements labels adjustments as current adjustment
Mapping of transactions with grandfathered rights | Drives which bilaterals excused TUC & balance shortfall
External MWh grandfathering for TO ext TSC billing
Action with NYISO to send letter to TO's?
R. S. 1 invoice adjustments for new uplift billing code? | Are the nov 99 - oct 00 all getting proper invoide adjustments
Niagara Mohawk observation of September 2000 adjustment
Why is there a significant change in congestion
balancing with each True Up?
NYPA BPCG refund in September 2000 True Up
LBMP prices & posting
sign convention for congestion?
Gilboa pumping errors in "last" Nov 99
Nov 99 & Dec 99 backcasting for missing PTS | BAWG agreed to "straight" backcast
Interger vs decimals for scheduling/billing | At S&PWG
Negative unaccounted energy | some subzones require retail loads reduced
other subzones require retail loads increased
Suspicious of B-matrix loss allocation problem
DADRP | In production with preliminary curtailment data
Actual data will be used at 4-month true up
EDRP | Not in production, no payments to CSP yet
Voltage Support | In place for 2001
New VSS rates approved by MC for 2002
VSS long term at MSWG
Need ideas for uplift diagnostic reporting
uplift (socialized & TO), SRE's, etc.
Need ideas for residaul energy diagnostic reporting | Pool inadvertant
Need ideas for losses diagnostics reporting
Need ideas for BPCG diagnostics reporting
Need ideas for congestion balancing reporting
Update Billing & Accounting Manual
Virtual bidding
External TSC MWh for TO billing | Waiting on letter from ISO?
Why changing so much in true ups | March 2000 value to NM for NYPA was originally 2651 MWh
March 2000 true up has it at 30,018 MWh
R.S. 1 fixed change for collecting additional W.C. | Forecast for $.90/MWh to drop back $.66/MWh by 12-01
Nov 99-Mar 00 True up vs "opld" rebill issue?
Out-of-merrit billing & group billing issues | (Kathy to fill in)
Generator Performance penalties? | Non-regulationg units not invoked gen perf pen
TSC discounting?
March 2000 reserves | Per Nov 8, 2001 FERC ruling, NYISO to rebill reserves
at market prices. Assume bids were only in billing
Quality assurance & audits | Invite Mark Rubin to BAWG
LBMP Prices in billing | This has been presented by BAWG to BIC as fixed (twice)
NMPC & Barney Farnsworth have observations of hourly RT
time-weighted integrated prices on web site not equal to
RT prices used in bills. These are in January 2000
Appears to be for price corrections
Virtual Load bidding?
Future NYISO Billing Workshops
Transmission Owner Task Force
State Estimted subzones | NYISO has December 2001 comletion date in Project List |  | TOTF, NYISO
SZ tie, gen, D load visability |  | Complete
SZ tie, gen, M load visability |  | Complete
LSE & Power Supplier visabilty | Training or documentation |  | NYISO
Capabilty to "Fix" data through web site |  |  | NYISO
NYISO PTS corrections to add value to anomalies
Unaccounted between subzones | Investigate B-Matrix loss allocation |  | NYISO, TOTF
Need NYISO to initiate a project to use "8" control area mapping
Subzone tie metering inventory
Investigate improvements in daily review of sz tie data | Wes Y to present to SOAS |  | Wes Y
Missing PTID's | NYISO working with TO's |  | NYISO, TOTF
NYISO Customer Relations involved
NYISO to fix in True Up process
TO metering requirements | Are these in B&A Manual appendix? |  | NYISO, TOTF
Similar/same as Control Room Requirements Manual?
Consideration to modify 3,6,12,24 process |  |  | NYISO, TOTF
NYISO to consider modifying backcast process |  |  | NYISO
ISO to perform analysis on state estimator difference |  |  | NYISO
Load data measurements for DADRP
Load data measurements for EDRP
Billing Data & Format Task Force, BDFTF
Format change & centralized invoice | Functional Requirement Specification | complete
| On target for end Nov 2001 |  | NYISO
Provision of data availability | BDFTF provided specification for five minute SCD data | complete
| Confirmed NYISO retention period is 4 years | complete
| NYISO released some SCD data, BDFTF providing comments |  | NYISO,BDFTF
Out-of-Merit flagging, RPU flag, ramp rate const. | Availability of such data | complete
Regulation, mitigation data
Company-wide daily statements | MTD provision and CSV format discussions |  | NYISO,BDFTF
Version Log | Needs additional discussion |  | NYISO.BDFTF
Elimination of Column headings | No longer an issue | complete