## 6.5% - Swap (hidden)
Enron Capital & Trade Services
Business Analysis & Reporting |  | Last updated: February 23, 1999 | [17 empty] | O:\Fin_Ops\Engysvc\PowerPlants\TVA Plants\TVA Weekly Summary\[TVA Wkly Anal - 121499.xls]Brownsville
Power Plants - 2000 | [19 empty] | 1999-12-13 10:55
| 1998 | 1999 | [11 empty] | 2000
| Total | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | Total | Person Responsible
Wilton Center IL
( Dev Owner: Scott Healy)
GE 7EA's (8ea) | 6800000 | 0 | 32884800 | 13650278 | 6825139 | 6825139 | 6825139 | 6825139 | 6825139 | 6825139 | 8531424 | 12790310 | 16869995 | 0 |  |  |  |  | 6825139 | 139302780 | Mike Miller
ABB | 0 | 1999 April: 670000; 1999 June: 5360000; 1999 July: 2680000; 1999 August: 670000; 1999 September: 670000; 1999 October: 670000; 1999 November: 670000; 1999 December: 670000; 2000 January: 670000; 2000 February: 670000 | 13400000 | Mike Miller
EECC | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Mike Miller
NEPCO | 0 | [7 empty] | 1642664 | 1558726 | 1558726 | 1558996 | 2620773 | 4676732 | 4676732 | 4676732 | 4676732 | 3176732 | 3176455 | 34000000 | Mike Miller
EI (Mobilization of O&M) | 0 | 2000 January: 125000; 2000 February: 125000; 2000 March: 125000; 2000 April: 125000; 2000 May: 125000; 2000 June: 125000 | 750000 | Kevin Presto
PARTS | 0 | 2000 April: 500000; 2000 May: 500000; 2000 June: 204000 | 1204000 | Mike Miller
LAND | 0 | 1999 April: 1668400; 1999 May: 0; 1999 September: 350000 | 2018400 | Scott Healy
ENVIR PERMITTING | 0 | 1999 March: 100000; 1999 April: 100000; 1999 May: 100000; 1999 June: 100000 | 400000 | Scott Healy
GAS INTERCONNECT | 0 | 2000 January: 1750000; 2000 February: 500000; 2000 March: 500000; 2000 April: 500000; 2000 May: 250000 | 3500000 | Chris Meyer
ELECT INTERCONNECT | 0 | 1999 March: 100000; 1999 April: 100000; 1999 December: 1000000; 2000 January: 850000; 2000 February: 750000; 2000 March: 600000 | 3400000 | Scott Healy
START UP FUEL | 0 | 2000 April: 500000; 2000 May: 500000; 2000 June: 0 | 1000000 | Kevin Presto
SALES TAX | 0 | 2000 January: 0; 2000 February: 0; 2000 March: 4500000; 2000 April: 1500000; 2000 May: 1500000; 2000 June: 1500000 | 9000000 | Scott Healy
INSURANCE | 0 | 1999 September: 150000 | 150000 | Scott Healy
SALARIES | 0 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 200000 | Scott Healy
DEVELOPMENT | 0 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 45000 | 300000 | Scott Healy
LEGAL | 0 | [5 empty] | 12500 | 5000 | 5000 | 5000 | 5000 | 5000 | 162500 | 5000 | 5000 | 5000 | 5000 | 5000 | 175000 | 400000 | Scott Healy
Total Plant | 6800000 | 26111.1111 | 32910911.1111 | 13876389.1111 | 9389650.1111 | 6951250.1111 | 12323750.1111 | 9536250.1111 | 9168914.1111 | 9584976.1111 | 10791261.1111 | 15050417.1111 | 21349379.1111 | 8102843.1111 | 6752843.1111 | 10432843.1111 | 7832843.1111 | 6082843.1111 | 12061705.1111 | 209025180
Cumulative Total Plant | 6800000 | 6826111.1111 | 39737022.2222 | 53613411.3333 | 63003061.4444 | 69954311.5556 | 82278061.6667 | 91814311.7778 | 100983225.8889 | 110568202 | 121359463.1111 | 136409880.2222 | 157759259.3333 | 165862102.4444 | 172614945.5556 | 183047788.6667 | 190880631.7778 | 196963474.8889 | 209025180
$$/Kw | [19 empty] | 348.3753
IDC | 187366 | 42500 | 38219.876 | 216694.3355 | 293031.8709 | 345479.7316 | 385003.6849 | 453842.768 | 507955.7711 | 560372.1496 | 623451.1193 | 685280.8106 | 770515.841 | 890331.9387 | 939044.9702 | 980709.364 | 1042532.7732 | 1090607.7259 | 1129463.9179 | 11182404.6484 | Rodney Malcolm
FINANCING FEE | 0 | 1999 September: 1500000 | 1500000 | Rodney Malcolm
CONTINGENCY (5%) | 0 | 2000 June: 7970755.4 | 7970755.4 | Mike Miller
Subtotal | 187366 | 42500 | 38219.876 | 216694.3355 | 293031.8709 | 345479.7316 | 385003.6849 | 453842.768 | 507955.7711 | 2060372.1496 | 623451.1193 | 685280.8106 | 770515.841 | 890331.9387 | 939044.9702 | 980709.364 | 1042532.7732 | 1090607.7259 | 9100219.3179 | 20653160.0484
Cumulative subtotal | 187366 | 229866 | 268085.876 | 484780.2116 | 777812.0824 | 1123291.814 | 1508295.4989 | 1962138.2669 | 2470094.038 | 4530466.1876 | 5153917.307 | 5839198.1175 | 6609713.9586 | 7500045.8972 | 8439090.8674 | 9419800.2314 | 10462333.0046 | 11552940.7305 | 20653160.0484
Total Wilton Center | 6987366 | 68611.1111 | 32949130.9871 | 14093083.4466 | 9682681.982 | 7296729.8427 | 12708753.796 | 9990092.8791 | 9676869.8822 | 11645348.2607 | 11414712.2305 | 15735697.9217 | 22119894.9521 | 8993175.0498 | 7691888.0813 | 11413552.4751 | 8875375.8843 | 7173450.837 | 21161924.429 | 229678340.0484
Cumulative Total | 6987366 | 7055977.1111 | 40005108.0982 | 54098191.5449 | 63780873.5269 | 71077603.3696 | 83786357.1656 | 93776450.0447 | 103453319.9269 | 115098668.1876 | 126513380.4181 | 142249078.3398 | 164368973.2919 | 173362148.3417 | 181054036.423 | 192467588.898 | 201342964.7823 | 208516415.6194 | 229678340.0484
$$/Kw | [19 empty] | 382.7972
IDC 6.5% - Swap | 6.5%
600 | bar: 1999 January
DEBT RESERVE | 0 | 2000 June: 7340000 | 7340000 | Rodney Malcolm
Total Current month less IDC | 6800000 | 26111.1111 | 32910911.1111 | 13876389.1111 | 9389650.1111 | 6951250.1111 | 12323750.1111 | 9536250.1111 | 9168914.1111 | 11084976.1111 | 10791261.1111 | 15050417.1111 | 21349379.1111 | 8102843.1111 | 6752843.1111 | 10432843.1111 | 7832843.1111 | 6082843.1111 | 20032460.5111 | 218495935.4
CALVERT CITY, KY
( Dev Owner: Ben Jacoby)
WH501FD (2 ea) | 11990800 | 1999 January: 29977000; 1999 February: 2997700; 1999 March: 2997700; 1999 April: 2997700; 1999 May: 2997700; 2000 February: 2997700; 2000 June: 4531100 | 61487400 | Mike Miller
WH 501F (1 ea) | 17151750 | 1999 January: 0; 1999 February: 12474000; 2000 June: 1559250 | 31185000 | Mike Miller
ABB | 0 | 1999 April: 440000; 1999 June: 3520000; 1999 July: 1760000; 1999 August: 440000; 1999 September: 440000; 1999 October: 440000; 1999 November: 440000; 1999 December: 440000; 2000 January: 440000; 2000 February: 440000 | 8800000 | Mike Miller
NEPCO | 0 | [7 empty] | 600000 | 1000000 | 1000000 | 1000000 | 1500000 | 4206667 | 3866666.6667 | 3866666.6667 | 2986666.6667 | 2986666.6667 | 2986666.6667 | 26000000.3333 | Mike Miller
EI (Mobilization of O&M) | 0 | 2000 January: 150000; 2000 February: 150000; 2000 March: 150000; 2000 April: 150000; 2000 May: 150000 | 750000 | Kevin Presto
PARTS | 0 | 2000 April: 500000; 2000 May: 500000 | 1000000 | Mike Miller
LAND | 0 | 1999 August: 250000 | 250000 | Ben Jacoby
ENVIR PERMITTING | 0 | 1999 March: 100000; 1999 April: 100000; 1999 May: 150000; 1999 June: 150000 | 500000 | Ben Jacoby
WATER LINE | 0 | 1999 May: 200000; 1999 June: 200000 | 400000 | Ben Jacoby
GAS INTERCONNECT | 0 | 1999 December: 375000; 2000 January: 125000; 2000 February: 125000; 2000 March: 125000; 2000 April: 250000 | 1000000 | Chris Meyer
ELECT INTERCONNECT | 0 | 1999 December: 200000; 2000 January: 600000; 2000 February: 600000; 2000 March: 600000 | 2000000 | Ben Jacoby
START UP FUEL |  | 2000 April: 500000; 2000 May: 500000 | 1000000 | Kevin Presto
RESALE AND HANDLING FEE |  | 2000 June: 256000 | 256000 | Patrick Maloy
SALES TAX | 0 | 1999 December: 20000; 2000 March: 30000 | 50000 | Ben Jacoby
INSURANCE | 0 | 1999 September: 200000 | 200000 | Ben Jacoby
SALARIES | 0 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 200000 | Ben Jacoby
DEVELOPMENT | 0 |  | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 |  |  |  | 400000 | Ben Jacoby
LEGAL | 0 | [5 empty] | 25000 | 10000 | 10000 | 10000 | 10000 | 10000 | 325000 | 10000 | 10000 | 10000 | 10000 | 10000 | 50000 | 500000 | Ben Jacoby
Total Plant | 29142550 | 29988111.1111 | 15511382.5397 | 3137382.5397 | 3577382.5397 | 3387382.5397 | 3934682.5397 | 1809682.5397 | 1339682.5397 | 1689682.5397 | 1489682.5397 | 1489682.5397 | 2899682.5397 | 5571349.5397 | 8229049.2063 | 4821349.2063 | 4407777.7778 | 4157777.7778 | 9394127.7778 | 135978400.3333
Cumulative Total Plant | 29142550 | 59130661.1111 | 74642043.6508 | 77779426.1905 | 81356808.7302 | 84744191.2698 | 88678873.8095 | 90488556.3492 | 91828238.8889 | 93517921.4286 | 95007603.9683 | 96497286.5079 | 99396969.0476 | 104968318.5873 | 113197367.7937 | 118018717 | 122426494.7778 | 126584272.5556 | 135978400.3333
$$/Kw | [19 empty] | 283.2883
IDC | 184443 | 182141 | 322276.7444 | 408042.3988 | 427246.7839 | 448938.5261 | 469718.5985 | 493575.7713 | 506051.7538 | 516049.4813 | 536122.1964 | 547095.3054 | 558127.852 | 576857.6583 | 610160.4473 | 658039.4996 | 687719.5218 | 715320.1321 | 741716.0791 | 9589642.7501 | Rodney Malcolm
FINANCING FEE | 0 | 1999 September: 1500000 | 1500000 | Rodney Malcolm
CONTINGENCY (5%) | 0 | 2000 June: 5379352.0267 | 5379352.0267 | Ben Jacoby
Subtotal | 184443 | 182141 | 322276.7444 | 408042.3988 | 427246.7839 | 448938.5261 | 469718.5985 | 493575.7713 | 506051.7538 | 2016049.4813 | 536122.1964 | 547095.3054 | 558127.852 | 576857.6583 | 610160.4473 | 658039.4996 | 687719.5218 | 715320.1321 | 6121068.1058 | 16468994.7768
Cumulative subtotal | 184443 | 366584 | 688860.7444 | 1096903.1432 | 1524149.927 | 1973088.4531 | 2442807.0516 | 2936382.8229 | 3442434.5768 | 5458484.0581 | 5994606.2544 | 6541701.5598 | 7099829.4119 | 7676687.0702 | 8286847.5175 | 8944887.0171 | 9632606.5388 | 10347926.671 | 16468994.7768
Total Calvert City | 29326993 | 30170252.1111 | 15833659.284 | 3545424.9385 | 4004629.3236 | 3836321.0657 | 4404401.1382 | 2303258.311 | 1845734.2935 | 3705732.021 | 2025804.7361 | 2036777.8451 | 3457810.3917 | 6148207.198 | 8839209.6537 | 5479388.706 | 5095497.2995 | 4873097.9099 | 15515195.8836 | 152447395.1101
Cumulative Total | 29326993 | 59497245.1111 | 75330904.3951 | 78876329.3336 | 82880958.6572 | 86717279.723 | 91121680.8611 | 93424939.1721 | 95270673.4657 | 98976405.4866 | 101002210.2227 | 103038988.0678 | 106496798.4595 | 112645005.6575 | 121484215.3111 | 126963604.0171 | 132059101.3166 | 136932199.2265 | 152447395.1101
317.5987
IDC 6.5% - Swap | 6.5%
$$/Kw | 480 | bar: 1999 January
DEBT RESERVE | 0 | 2000 June: 6338000 | 6338000 | Rodney Malcolm
Total Current month less IDC | 29142550 | 29988111.1111 | 15511382.5397 | 3137382.5397 | 3577382.5397 | 3387382.5397 | 3934682.5397 | 1809682.5397 | 1339682.5397 | 3189682.5397 | 1489682.5397 | 1489682.5397 | 2899682.5397 | 5571349.5397 | 8229049.2063 | 4821349.2063 | 4407777.7778 | 4157777.7778 | 14773479.8044 | 142857752.36
WHEATLAND, INDIANA
( Dev Owner: Steve Dowd)
WH 501D5A (4) | 16673404 | 1999 January: 40778500; 1999 February: 4077852; 1999 March: 4077852; 1999 April: 4077852; 1999 May: 4077852; 1999 June: 4077852; 2000 June: 4077852 | 81919016 | Mike Miller
ABB | 0 | 1999 May: 440000; 1999 June: 3520000; 1999 July: 1760000; 1999 August: 440000; 1999 September: 440000; 1999 October: 440000; 1999 November: 440000; 1999 December: 440000; 2000 January: 440000; 2000 February: 440000 | 8800000 | Mike Miller
NEPCO | 0 | [7 empty] | 1600000 | 1440000 | 1440000 | 1440000 | 2400000 | 4426666.6667 | 4426666.6667 | 4426666.6667 | 4426666.6667 | 2986666.6667 | 2986666.6667 | 32000000 | Mike Miller
EI (Mobilization of O&M) | 0 | 2000 January: 125000; 2000 February: 125000; 2000 March: 125000; 2000 April: 125000; 2000 May: 125000; 2000 June: 125000 | 750000 | Kevin Presto
PARTS | 0 | 2000 April: 500000; 2000 May: 500000 | 1000000 | Mike Miller
LAND | 0 | 1999 August: 770000 | 770000 | Steve Dowd
ENVIR PERMITTING | 0 | 1999 March: 112500; 1999 April: 112500; 1999 May: 112500; 1999 June: 112500 | 450000 | Steve Dowd
GAS INTERCONNECT | 0 | 2000 February: 500000; 2000 March: 166666.6667; 2000 April: 166666.6667; 2000 May: 166666.6667 | 1000000 | Chris Meyer
ELECT INTERCONNECT | 0 | 2000 January: 1000000; 2000 February: 500000; 2000 March: 500000 | 2000000 | Steve Dowd
START UP FUEL | 0 | 2000 April: 500000; 2000 May: 500000; 2000 June: 0 | 1000000 | Kevin Presto
RESALE HANDLING FEE |  | 2000 June: 236000 | 236000 | Patrick Maloy
SALES TAX | 0 | 2000 June: 50000 | 50000 | Steve Dowd
INSURANCE | 0 | 1999 September: 200000 | 200000 | Steve Dowd
SALARIES | 0 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 200000 | Steve Dowd
DEVELOPMENT | 0 |  | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 |  |  |  | 400000 | Steve Dowd
LEGAL | 0 | 1999 November: 10000; 1999 December: 290000; 2000 January: 10000; 2000 February: 10000; 2000 March: 10000; 2000 April: 10000; 2000 May: 10000; 2000 June: 50000 | 400000 | Steve Dowd
Total Plant | 16673404 | 40789611.1111 | 4117534.5397 | 4230034.5397 | 4230034.5397 | 4670034.5397 | 7750034.5397 | 1799682.5397 | 2849682.5397 | 2119682.5397 | 1919682.5397 | 1929682.5397 | 3169682.5397 | 6041349.2063 | 6041349.2063 | 5268015.873 | 5739444.4444 | 4299444.4444 | 7536629.7778 | 131175016
Cumulative Total Plant | 16673404 | 57463015.1111 | 61580549.6508 | 65810584.1905 | 70040618.7302 | 74710653.2698 | 82460687.8095 | 84260370.3492 | 87110052.8889 | 89229735.4286 | 91149417.9683 | 93079100.5079 | 96248783.0476 | 102290132.254 | 108331481.4603 | 113599497.3333 | 119338941.7778 | 123638386.2222 | 131175016
$$/Kw | [19 empty] | 285.1631
IDC | 146354 | 104209 | 312615.2148 | 336611.8593 | 361347.8606 | 386217.8486 | 413605.8824 | 457825.6013 | 470053.7704 | 488035.6754 | 510285.8158 | 523448.1444 | 536735.9356 | 556812.369 | 592552.4108 | 628486.0446 | 660425.43 | 695091.3918 | 722145.1276 | 8902859.3823 | Rodney Malcolm
FINANCING FEE | 0 | 1999 September: 1500000 | 1500000 | Rodney Malcolm
CONTINGENCY (5%) | 0 | 2000 June: 5535250.48 | 5535250.48 | Steve Dowd
Subtotal | 146354 | 104209 | 312615.2148 | 336611.8593 | 361347.8606 | 386217.8486 | 413605.8824 | 457825.6013 | 470053.7704 | 1988035.6754 | 510285.8158 | 523448.1444 | 536735.9356 | 556812.369 | 592552.4108 | 628486.0446 | 660425.43 | 695091.3918 | 6257395.6076 | 15938109.8623
Cumulative subtotal | 146354 | 250563 | 563178.2148 | 899790.074 | 1261137.9346 | 1647355.7832 | 2060961.6656 | 2518787.2669 | 2988841.0374 | 4976876.7128 | 5487162.5286 | 6010610.6729 | 6547346.6085 | 7104158.9774 | 7696711.3883 | 8325197.4329 | 8985622.8629 | 9680714.2547 | 15938109.8623
Total Calvert City | 16819758 | 40893820.1111 | 4430149.7545 | 4566646.399 | 4591382.4003 | 5056252.3883 | 8163640.4221 | 2257508.141 | 3319736.3101 | 4107718.2151 | 2429968.3554 | 2453130.684 | 3706418.4752 | 6598161.5753 | 6633901.6172 | 5896501.9176 | 6399869.8744 | 4994535.8362 | 13794025.3854 | 147113125.8623
Cumulative Total | 16819758 | 57713578.1111 | 62143727.8656 | 66710374.2645 | 71301756.6648 | 76358009.0531 | 84521649.4751 | 86779157.6161 | 90098893.9262 | 94206612.1414 | 96636580.4968 | 99089711.1808 | 102796129.6561 | 109394291.2314 | 116028192.8486 | 121924694.7662 | 128324564.6406 | 133319100.4769 | 147113125.8623
319.8111
IDC 6.5% - Swap | 6.5%
$$/Kw | 460 | bar: 1999 January
DEBT RESERVE | 0 | 2000 June: 5842000 | 5842000 | Rodney Malcolm
Total Current month less IDC | 16673404 | 40789611.1111 | 4117534.5397 | 4230034.5397 | 4230034.5397 | 4670034.5397 | 7750034.5397 | 1799682.5397 | 2849682.5397 | 3619682.5397 | 1919682.5397 | 1929682.5397 | 3169682.5397 | 6041349.2063 | 6041349.2063 | 5268015.873 | 5739444.4444 | 4299444.4444 | 13071880.2578 | 138210266.48
Cumulative total w/o Debt reserve | 53134117 | 124266800.3333 | 177479740.3589 | 199684895.143 | 217963588.8489 | 234152892.1456 | 259429687.5019 | 273980546.833 | 288822887.3188 | 308281685.8156 | 324152171.1376 | 344377777.5884 | 373661901.4075 | 395401445.2306 | 418566444.5827 | 441355887.6813 | 461726630.7396 | 478767715.3228 | 529238861.0208
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19520000
Cumulative total with Debt reserve | 53134117 | 124266800.3333 | 177479740.3589 | 199684895.143 | 217963588.8489 | 234152892.1456 | 259429687.5019 | 273980546.833 | 288822887.3188 | 308281685.8156 | 324152171.1376 | 344377777.5884 | 373661901.4075 | 395401445.2306 | 418566444.5827 | 441355887.6813 | 461726630.7396 | 478767715.3228 | 548758861.0208

## Brownsville
Enron Capital & Trade Services
Business Analysis & Reporting |  | Last updated: Actuals through December 10, 1999 | [11 empty] | O:\Fin_Ops\Engysvc\PowerPlants\TVA Plants\TVA Weekly Summary\[TVA Wkly Anal - 121499.xls]Brownsville
Power Plants - 1999 | [13 empty] | 1999-12-13 10:55
| 1998 | [5 empty] | 1999
| Total | January | February | March | April | May | June | July | August | September | October | November | December | Total
Capital
Brownsville, TN
( Dev Owner: Clay Spears)
WH 5D's (4ea) | 58899539 | 48600 | 3567810 | 3342088 | 338722 | 840995 | 276019 | 136426 | 3337741 | 172832 | 16019 | 0 | 1637615 | 72614406 | 72614405.8 | -0.2
ABB | 2998569 | 2951629 | 137615 | 0 | 1229873 | 747040 | 692016 | 174000 | 0 | 227783 | 0 | 0 | -273278 | 8885247 | 8885247.14 | 0.14
EECC | 182376 | 0 | 0 | 0 | 0 | 0 | 324238 | 125335 | 30644 | 0 | 21103 | 42455 | 8572 | 734723 | 734722.72 | -0.28
NEPCO | 1415805 | 3042655 | 1851195 | 3966412 | 1481773 | 4260335 | 4701685 | 4762777 | 4478140 | 983532 | 775246 | 287383 | 1242562 | 33249500 | 33249499.7 | -0.3
EI (Mobilization of O&M) | 6111 | 25337 | 0 | 0 | 74417 | 173681 | 225874 | 95732 | 68947 | 26337 | 1079 | 775 | -1 | 698289 | 698289.4 | 0.4
PARTS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238231 | 16621 | 1062895 | 0 | 0 | 1317747 | 1317746.81 | -0.19
LAND | 458107 | 0 | 0 | 0 | 0 | 3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461440 | 461440.33 | 0.33
ENVIR PERMITTING | 220810 | 59942 | 30441 | 125058 | 24442 | 66861 | 204010 | 84200 | 0 | 0 | 37358 | 0 | 12247 | 865369 | 865369.28 | 0.28
GAS INTERCONNECT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ELECT INTERCONNECT | 0 | 73862 | 0 | 0 | 717411 | 0 | 379197 | 353836 | 91393 | 52976 | 5188 | 133605 | 165021 | 1972489 | 1972489.012 | 0.012
START UP FUEL | 0 | 0 | 0 | 0 | 0 | 121528 | 58914 | 47610 | 0 | 0 | 0 | 0 | -1 | 228051 | 228051.11 | 0.11
SALES TAX | 0 | 0 | 5853 | 0 | 27412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192684 | 225949 | 225949 | 0
RESALE HANDLING FEE | 69936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 69937 | 69937 | 0
INSURANCE | 0 | 117600 | 0 | 0 | 0 | 0 | 0 | 14699 | 0 | 22048 | 0 | 0 | 10001 | 164348 | 164348 | 0
SALARIES | 0 | 0 | 5869 | 0 | 4276 | 14353 | 6434 | 4128 | 0 | 0 | 0 | 0 | 0 | 35060 | 35060.42 | 0.42
DEVELOPMENT | 200157 | 3386 | 4412 | -19953 | 3514 | 147966 | 41583 | 64584 | 77226 | 25706 | 3272 | 3463 | -1 | 555315 | 555315.14 | 0.14
LEGAL | 181515 | 5254 | 128603 | 0 | 3491 | 265297 | 0 | 27841 | 0 | 146514 | 7904 | 0 | -2 | 766417 | 766416.75 | -0.25
OTHER | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
Total Plant | 64632925 | 6328265 | 5731798 | 7413605 | 3905331 | 6641389 | 6909970 | 5891168 | 8322322 | 1674349 | 1930064 | 467681 | 2995420 | 122844287
Cumulative Total Plant | 64632925 | 70961190 | 76692988 | 84106593 | 88011924 | 94653313 | 101563283 | 107454451 | 115776773 | 117451122 | 119381186 | 119848867 | 122844287
$$/Kw | [13 empty] | 268.219
IDC | 2084749 | 441000 | 374381.8296 | 391590.4572 | 467674.2924 | 256005 | 683274 | 598297 | -598297 | -290628 | 0 | 0 | 0 | 4408046.5792 | 4408047 | 0.42076
IDC Credit on Unused Cash |  | April: -123964 | -123964 | -123964 | 0
Commitment Fee | 0 | 6251.0121 | 5254.994 | 4060.8751 | 3911.4188 | 3727 |  |  |  | 0 |  | 0 | 0 | 23205.3 | 23205.3 | 0
FINANCING FEE | 68386 | 761038 | 0 | 0 | 0 | 83333 | 0 |  |  |  |  | 83333 | 107680 | 1103770 | 1103769.7233 | -0.27667
SWAP | 0 | April: 2666; May: -18334 | -15668 | -15667.94 | 0.06
CONTINGENCY | 0 | [12 empty] | 0
Subtotal | 2153135 | 1208289.0121 | 379636.8236 | 395651.3323 | 350287.7112 | 324731 | 683274 | 598297 | -598297 | -290628 | 0 | 83333 | 107680 | 5395389.8792
Cumulative subtotal | 2153135 | 3361424.0121 | 3741060.8357 | 4136712.1681 | 4486999.8792 | 4811730.8792 | 5495004.8792 | 6093301.8792 | 5495004.8792 | 5204376.8792 | 5204376.8792 | 5287709.8792 | 5395389.8792
Total Capital | 66786060 | 7536554.0121 | 6111434.8236 | 7809256.3323 | 4255618.7112 | 6966120 | 7593244 | 6489465 | 7724025 | 1383721 | 1930064 | 551014 | 3103100 | 128239676.8792
Cumulative Total | 66786060 | 74322614.0121 | 80434048.8357 | 88243305.1681 | 92498923.8792 | 99465043.8792 | 107058287.8792 | 113547752.8792 | 121271777.8792 | 122655498.8792 | 124585562.8792 | 125136576.8792 | 128239676.8792
$$/Kw | [13 empty] | 279.9993
DEBT RESERVE | 0 | 1999 June: 0 | 0 |  | 0
Total Current month less IDC | 64701311 | 7095554.0121 | 5737052.994 | 7417665.8751 | 3787944.4188 | 6710115 | 6909970 | 5891168 | 8322322 | 1674349 | 1930064 | 551014 | 3103100 | 123831630.3
Monthly Draw, including accr int and comm fee | 70991903 | 7968145 | 9552951 | 1195651 | 250000 | 0 | 0 | 0 | 0
Cumulative Outstanding Balance | 70991903 | 78960048 | 88512999 | 89708650 | 89958650 | 0 | 0 | 0 | 0
Total Project Cost (w/o Debt Reserve) | 66786060 | 7536554.0121 | 6111434.8236 | 7809256.3323 | 4255618.7112 | 6966120 | 7593244 | 6489465 | 7724025 | 1383721 | 1930064 | 551014 | 3103100 | 128239676.8792 |  | 0.81609
Total Cumul Project Cost (w/o Debt Reserve) | 66786060 | 74322614.0121 | 80434048.8357 | 88243305.1681 | 92498923.8792 | 99465043.8792 | 107058287.8792 | 113547752.8792 | 121271777.8792 | 122655498.8792 | 124585562.8792 | 125136576.8792 | 128239676.8792
Total Project Cost (with Debt Reserve) | 66786060 | 7536554.0121 | 6111434.8236 | 7809256.3323 | 4255618.7112 | 6966120 | 7593244 | 6489465 | 7724027 | 1383721 | 1930064 | 551014 | 3103100 | 128239676.8792 | 128239676.6953 | -0.18391
IDC 5.75% (Actuals through April) | 10% | 6.368% | 5.69% | 5.688% | 5.687% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5%
+ 15 Bps Com Fee (thru 5/21/99 only) | 0.15%
458 | bar: January
| Blue | January: Actuals
Input from WestLB statements for each month's actuals (1/99 - 5/99)

## Caledonia
Enron Capital & Trade Services
Business Analysis & Reporting |  | Last updated: Actuals through December 10, 1999 | [11 empty] | O:\Fin_Ops\Engysvc\PowerPlants\TVA Plants\TVA Weekly Summary\[TVA Wkly Anal - 121499.xls]Brownsville
Power Plants - 1999 | [13 empty] | 1999-12-13 10:55
| 1998 | 1999
| Total | January | February | March | April | May | June | July | August | September | October | November | December | Total
Capital
Caledonia, MS
( Dev Owner: Clay Spears)
GE 7EA's (6ea) | 37377776 | 6859220 | 6859220 | 12326714 | 12919710 | 15213392 | 0 | 0 | 3280101 | 0 | 0 | 4852796 | 1940179 | 101629108 | 101629107.92 | -0.08
ABB | 1897561 | 4007308 | 0 | 615000 | 1398550 | 821775 | 445570 | 0 | 0 | 1100956 | 0 | 0 | 1 | 10286721 | 10286721 | 0
EECC | 232364 | 0 | 0 | 0 | 0 | 0 | 316915 | 143865 | 41523 | 0 | 27419 | 10884 | 12984 | 785954 | 785954.21 | 0.21
NEPCO | 167072 | 899776 | 810086 | 1831143 | 0 | 3372514 | 2932107 | 9360536 | 4662889 | 2317012 | 1167995 | 960719 | 829651 | 29311500 | 29311500.15 | 0.15
EI (Mobilization of O&M) | 0 | 0 | 0 | 0 | 72162 | 162075 | 232977 | 64037 | 17168 | 19696 | 464 | 0 | 0 | 568579 | 568579.44 | 0.44
PARTS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157467 | 525706 | 11614 | 1988 | 91025 | 787800 | 787800 | 0
LAND | 532310 | 0 | 0 | 22050 | 0 | 3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 557693 | 557693.33 | 0.33
ENVIR PERMITTING | 207085 | 0 | 0 | 0 | 0 | 29791 | 0 | 0 | 227 | 0 | 250 | 0 | 0 | 237353 | 237352.65 | -0.35
GAS INTERCONNECT | 738500 | 0 | 242359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 981000 | 981000 | 0
ELECT INTERCONNECT | 0 | 110523 | 0 | 0 | 1651484 | 0 | 59847 | 230834 | 864906 | 146302 | 0 | 3218 | 440706 | 3507820 | 3507819.876 | -0.124
START UP FUEL | 0 | 0 | 0 | 0 | 10000 | 53741 | 61014 | 11281 | 0 | 0 | 0 | 0 | 0 | 136036 | 136036.07 | 0.07
SALES TAX | 280627 | 6383 | 0 | 0 | 0 | 0 | 0 | 85968 | 0 | 0 | 0 | 0 | -272978 | 100000 | 100000 | 0
RESALE HANDLING FEE | 94021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94021 | 94021 | 0
INSURANCE | 0 | 145042 | 0 | 0 | 0 | 0 | 0 | 38633 | 0 | 38633 | 0 | 0 | 2615 | 224923 | 224923 | 0
SALARIES | 0 | 0 | 8735 | 0 | 5963 | 23696 | 9719 | 5091 | 0 | 0 | 0 | 0 | 0 | 53204 | 53203.58 | -0.42
DEVELOPMENT | 81639 | 27824 | 3701 | -21839 | 2188 | 205652 | 74162 | 109970 | 67695 | 29497 | 3271 | 163989 | -6113 | 741636 | 741635.96 | -0.04
LEGAL | 105274 | 6484 | 150776 | 0 | 0 | 221475 | 0 | 51987 | 0 | 33731 | 3474 | 8180 | 1 | 581382 | 581382.25 | 0.25
OTHER | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Total Plant | 41714229 | 12062560 | 8074877 | 14773068 | 16060057 | 20107444 | 4132311 | 10102202 | 9091976 | 4211533 | 1214487 | 6001774 | 3038212 | 150584730
Cumulative Total Plant | 41714229 | 53776789 | 61851666 | 76624734 | 92684791 | 112792235 | 116924546 | 127026748 | 136118724 | 140330257 | 141544744 | 147546518 | 150584730
$$/Kw | [13 empty] | 340.6894
IDC | 1013050 | 342824 | 321299.9189 | 443917.8536 | 528055.6849 | 124517 | 725143 | 684126 | -684126 | -326769 | 0 | 0 | 0 | 3172038.4574 | 3172038.28 | 0.17737
IDC Credit on Unused Cash |  | 1999 March: -309104; 1999 April: -117884 | -426988 | -426988 | 0
Commitment Fee | 0 | 1999 January: 11785.189; 1999 February: 10279.4176; 1999 March: 6207.3998; 1999 April: 6088.6341; 1999 May: 5897; 1999 November: 0; 1999 December: 0 | 40257.6405 | 40258 | -0.3595
Swap Gain/Loss |  |  |  | -5266 | 13200 | -18334 | 0 |  | 0 | 0 | 0 | 0 | 1 | -10399 | -10399.47 | 0.47
FINANCING FEE | 68386 | 942288 | 0 | 0 | 0 | 83333 | 0 | 0 | 0 | 0 | 0 | 83333 | 107680 | 1285020 | 1285019.7133 | 0.28667
CONTINGENCY | 0 | [12 empty] | 0
Subtotal | 1081436 | 1296897.189 | 331579.3365 | 135755.2534 | 429460.319 | 195413 | 725143 | 684126 | -684126 | -326769 | 0 | 83333 | 107681 | 4059929.0979
Cumulative subtotal | 1081436 | 2378333.189 | 2709912.5255 | 2845667.7789 | 3275128.0979 | 3470541.0979 | 4195684.0979 | 4879810.0979 | 4195684.0979 | 3868915.0979 | 3868915.0979 | 3952248.0979 | 4059929.0979
Total Capital | 42795665 | 13359457.189 | 8406456.3365 | 14908823.2534 | 16489517.319 | 20302857 | 4857454 | 10786328 | 8407851 | 3884764 | 1214487 | 6085107 | 3145893 | 154644660.0979
Cumulative Total | 42795665 | 56155122.189 | 64561578.5255 | 79470401.7789 | 95959919.0979 | 116262776.0979 | 121120230.0979 | 131906558.0979 | 140314409.0979 | 144199173.0979 | 145413660.0979 | 151498767.0979 | 154644660.0979
$$/Kw | [13 empty] | 349.8748
DEBT RESERVE | 0 | 1999 June: 0 | 0
Total Current month less IDC | 41782615 | 13016633.189 | 8085156.4176 | 14464905.3998 | 15961461.6341 | 20178340 | 4132311 | 10102202 | 9091977 | 4211533 | 1214487 | 6085107 | 3145893 | 151472621.6405
Monthly Draw, including accr int and comm fee | 55718488 | 12046171 | 32576143 | 950125 | 250000 | 0 | 0 | 0 | 0
Cumulative Outstanding Balance | 55718488 | 67764659 | 100340802 | 101290927 | 101540927 | 0 | 0 | 0 | 0
Total Project Cost (w/o Debt Reserve) | 42795665 | 13359457.189 | 8406456.3365 | 14908823.2534 | 16489517.319 | 20302857 | 4857454 | 10786328 | 8407851 | 3884764 | 1214487 | 6085107 | 3145893 | 154644661.0979 |  | 1.0105
Total Cumul Project Cost (w/o Debt Reserve) | 42795665 | 56155122.189 | 64561578.5255 | 79470401.7789 | 95959919.0979 | 116262776.0979 | 121120230.0979 | 131906558.0979 | 140314409.0979 | 144199173.0979 | 145413660.0979 | 151498767.0979 | 154644660.0979
Total Project Cost (with Debt Reserve) | 42795665 | 13359457.189 | 8406456.3365 | 14908823.2534 | 16489517.319 | 20302857 | 4857454 | 10786328 | 8407851 | 3884764 | 1214487 | 6085107 | 3145893 | 154644661.0979 | 154644660.9593 | -0.13854
IDC 5.75% (Actuals through April) | 10% | 6.368% | 5.69% | 5.688% | 5.687% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5%
+ 15 Bps Com Fee (thru 5/21/99 only) | 0.15%
442 | bar: 1999 January
| Blue | 1999 January: Actuals
Input from WestLB statements for each month's actuals (1/99 - 5/99)

## New Albany
Enron Capital & Trade Services
Business Analysis & Reporting |  | Last updated: Actuals through December 10, 1999 | [11 empty] | O:\Fin_Ops\Engysvc\PowerPlants\TVA Plants\TVA Weekly Summary\[TVA Wkly Anal - 121499.xls]Brownsville
Power Plants - 1999 | [13 empty] | 1999-12-13 10:55
| 1998 | [5 empty] | 1999
| Total | January | February | March | April | May | June | July | August | September | October | November | December | Total
Capital
New Albany, MS
( Dev Owner: Ben Jacoby)
GE 7EA's (6ea) | 52751407 | 13494013 | -1000500 | 1214720.4 | 5942931 | 5639430 | 518483 | 761820 | 807720 | 295000 | 115737 | 56819 | 2157008 | 82754588.4 | 82754588.73 | 0.33
PARTS | 7430171 | 3111381 | 0 | -5415746 | 248257 | 1334950 | 92004 | 13613 | 20000 | 1036626 | 20000 | 0 | 1 | 7891257 | 7891256.53 | -0.47
ABB | 2041028 | 1118578 | 293815 | 1817629 | 783550 | 3531431 | 853259 | 300000 | 6600 | 724514 | 0 | 0 | -133528 | 11336876 | 11336875.91 | -0.09
EECC | 134978 | 36683 | 0 | 0 | 15908 | 0 | 541378 | 174321 | 66961 | 0 | 107095 | 8577 | 113778 | 1199679 | 1199679 | 0
NEPCO | 270744 | 392941 | 674363 | 1756963 | 0 | 4390660 | 4408350 | 7502651 | 5239722 | 3901236 | 1735395 | 1149530 | 2102445 | 33525000 | 33525000.17 | 0.17
EI (Mobilization of O&M) | 6111 | 11487 | 0 | 0 | 91858 | 166373 | 242196 | 108546 | 112784 | 37105 | 7825 | 2323 | 1 | 786609 | 786608.59 | -0.41
SPARE PARTS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39923 | 689524 | 18842 | 0 | 64761 | 813050 | 813050 | 0
LAND | 169276 | 0 | 0 | 0 | 0 | 3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172609 | 172609.34 | 0.34
ENVIR PERMITTING | 209531 | 205 | 12317 | 0 | 0 | 11450 |  | 14830 | 130 | 0 | 106440 | 0 | 0 | 354903 | 354903.46 | 0.46
GAS INTERCONNECT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ELECT INTERCONNECT | 0 | 71060 | 0 | 0 | 719016 | 0 | 644133 | 169598 | 185299 | 72188 | 12905 | 156684 | 119924 | 2150807 | 2150806.664 | -0.336
START UP FUEL | 0 | 0 | 0 | 0 | 50000 | 54684 | 131581 | 138751 | 0 | 0 | 0 | 0 | 0 | 375016 | 375015.74 | -0.26
SALES TAX | 162185.68 | 64952 | 4730 | 0 | 0 | 0 | 0 | 85968 | 0 | 0 | 0 | 0 | -217836 | 99999.68 | 100000 | 0.32
RESALE HANDLING FEE | 63535 | 0 | 0 | 0 | -826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62709 | 62709.15 | 0.15
INSURANCE | 0 | 0 | 0 | 201497 | 0 | 22112 | 0 | 0 | 0 | 67030 | 0 | 0 | 35888 | 326527 | 326527 | 0
SALARIES | 0 | 0 | 11127 | 0 | 3775 | 29108 | 13554 | 6060 | 0 | 0 | 0 | 0 | 0 | 63624 | 63623.9 | -0.1
DEVELOPMENT | 186836 | 29347 | 4798 | -13959 | 5324 | 148591 | 42813 | 89041 | 78710 | 55226 | 8094 | 3363 | -2 | 638182 | 638181.85 | -0.15
LEGAL | 112431 | 5498 | 133167 | 0 | 0 | 190115 | 0 | 54871 | 0 | 33731 | 2974 | 6180 | -1 | 538966 | 538966.38 | 0.38
OTHER | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Total Plant | 63538233.68 | 18336145 | 133817 | -438895.6 | 7859793 | 15522237 | 7487751 | 9420070 | 6557849 | 6912180 | 2135307 | 1383476 | 4242439 | 143090402.08
Cumulative Total Plant | 63538233.68 | 81874378.68 | 82008195.68 | 81569300.08 | 89429093.08 | 104951330.08 | 112439081.08 | 121859151.08 | 128417000.08 | 135329180.08 | 137464487.08 | 138847963.08 | 143090402.08
$$/Kw | [13 empty] | 369.7426
IDC | 1362241 | 436078 | 434033.2176 | 422737.6996 | 505583.1356 | 264883 | 738348 | 659904.5 | -659904 |  |  |  |  | 4163904.5527 | 4163904.83 | -0.27726
IDC Credit on Unused Cash |  | March: -94899; April: -64384 | -159283 | -159283 | 0
Commitment Fee | 0 | 7392.7297 | 4682.3761 | 4180.8308 | 4002 | 3814 |  |  |  | 0 |  | 0 | 0 | 24071.9366 | 24072.18 | -0.24338
FINANCING FEE | 68386 | 811038 | 0 | 0 | 0 | 83333 | 0 | 0 | 0 | 0 | 0 | 83333 | 107680 | 1153770 | 1153769.7033 | 0.29667
Swap | 0 | April: 2666; May: -18334; 1999 July: 0; 1999 August: 0 | -15668 | -15668 | 0
CONTINGENCY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal | 1430627 | 1254508.7297 | 438715.5937 | 332019.5304 | 447867.1356 | 333696 | 738348 | 659904.5 | -659904 | 0 | 0 | 83333 | 107680 | 5166795.4894
Cumulative subtotal | 1430627 | 2685135.7297 | 3123851.3234 | 3455870.8538 | 3903737.9894 | 4237433.9894 | 4975781.9894 | 5635686.4894 | 4975782.4894 | 4975782.4894 | 4975782.4894 | 5059115.4894 | 5166795.4894
Total Capital | 64968860.68 | 19590653.7297 | 572532.5937 | -106876.0696 | 8307660.1356 | 15855933 | 8226099 | 10079974.5 | 5897945 | 6912180 | 2135307 | 1466809 | 4350119 | 148257197.5694
Cumulative Total | 64968860.68 | 84559514.4097 | 85132047.0034 | 85025170.9338 | 93332831.0694 | 109188764.0694 | 117414863.0694 | 127494837.5694 | 133392782.5694 | 140304962.5694 | 142440269.5694 | 143907078.5694 | 148257197.5694
$$/Kw | [13 empty] | 383.0935
DEBT RESERVE | 0 | 1999 June: 0 | 0
Total Current month less IDC | 63606619.68 | 19154575.7297 | 138499.3761 | -529613.7692 | 7802077 | 15591050 | 7487751 | 9420070 | 6557849 | 6912180 | 2135307 | 1466809 | 4350119 | 144093293.0166
Monthly Draw, including accr int and comm fee | 69858162 | 21682829 | 4012363 | 1426919 | 250000 | 0 | 0 | 0 | 0
Cumulative Outstanding Balance | 69858162 | 91540991 | 95553354 | 96980273 | 97230273 | 0 | 0 | 0 | 0
Total Project Cost (w/o Debt Reserve) | 64968860.68 | 19590653.7297 | 572532.5937 | -106876.0696 | 8307660.1356 | 15855933 | 8226099 | 10079974.5 | 5897945 | 6912180 | 2135307 | 1466809 | 4350119 | 148257197.5694 |  | 0.11003
Total Cumul Project Cost (w/o Debt Reserve) | 64968860.68 | 84559514.4097 | 85132047.0034 | 85025170.9338 | 93332831.0694 | 109188764.0694 | 117414863.0694 | 127494837.5694 | 133392782.5694 | 140304962.5694 | 142440269.5694 | 143907078.5694 | 148257197.5694
Total Project Cost (with Debt Reserve) | 64968860.68 | 19590653.7297 | 572532.5937 | -106876.0696 | 8307660.1356 | 15855933 | 8226099 | 10079974.5 | 5897945 | 6912180 | 2135307 | 1466809 | 4350119 | 148257197.5694 | 148257197.1273 | -0.44203
IDC 5.75% (Actuals through April) | 10% | 6.368% | 5.69% | 5.688% | 5.687% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5%
+ 15 Bps Com Fee (thru 5/21/99 only) | 0.15%
387 | bar: January
| Blue | January: Actuals
Input from WestLB statements for each month's actuals (1/99 - 5/99)

## Draw Summary
Enron Capital & Trade Services
Business Analysis & Reporting
Power Plants
Outstanding Balance Summary
| Date of | Interest
Description | Funding | Rate | Brownsville | Caledonia | New Albany | Total
(30day LIBOR
+ 75 bps)
Initial Funding | 1998-12-21 |  | 61516763 | 43104549 | 63865968 | 168487280
First Draw | 1998-12-24 |  | 9309496 | 12435707 | 5818345 | 27563548
Transaction Expenses |  |  | 126458.5 | 150775 | 133166.5 | 410400
Interest |  | 7.75% | 39185.34 | 27457.01 | 40681.75 | 107324.1
CM Activity |  |  | 9475139.84 | 12613939.01 | 5992193.25 | 28081272.1
Cumulative O/S balance |  |  | 70991902.84 | 55718488.01 | 69858161.25 | 196568552.1
Second Draw | 1999-01-25 |  | 6803830 | 10781519 | 20473789 | 38059138
Transaction Expenses |  |  | 756250 | 937500 | 806250 | 2500000
Interest |  | 6.367% | 401814.17 | 315366.64 | 395397.19 | 1112578
Commitment Fee |  | 0.35% | 6251.01 | 11785.19 | 7392.73 | 25428.93
CM Activity |  |  | 7968145.18 | 12046170.83 | 21682828.92 | 41697144.93
Cumulative O/S balance |  |  | 78960048.02 | 67764658.84 | 91540990.17 | 238265697.03
Third Draw | 1999-02-24 |  | 9173314 | 32244564 | 3573648 | 44991526
Transaction Expenses |  |  | 0 | 0 | 0 | 0
Interest |  | 5.69% | 374381.83 | 321299.92 | 434033.21 | 1129714.96
Commitment Fee |  | 0.35% | 5254.99 | 10279.42 | 4682.38 | 20216.79
CM Activity |  |  | 9552950.82 | 32576143.34 | 4012363.59 | 46141457.75
Cumulative O/S balance |  |  | 88512998.84 | 100340802.18 | 95553353.76 | 284407154.78
Fourth Draw | 1999-03-24 |  | 800000 | 500000 | 1000000 | 2300000
Transaction Expenses |  |  | 0 | 0 | 0 | 0
Interest |  | 5.688% | 391590.46 | 443917.85 | 422737.7 | 1258246.01
Commitment Fee |  | 0.35% | 4060.88 | 6207.4 | 4180.83 | 14449.11
CM Activity |  |  | 1195651.34 | 950125.25 | 1426918.53 | 3572695.12
Cumulative O/S balance |  |  | 89708650.18 | 101290927.43 | 96980272.29 | 287979849.9
Fifth Draw | 1999-04-26 |  | 1000000 | 1000000 | 1000000 | 3000000
Transaction Expenses | [5 empty] | 0
Interest |  |  | 467674.29 | 528055.69 | 505583.13 | 1501313.11
Commitment Fee |  | 0.35% | 3911.42 | 6088.63 | 4002.47 | 14002.52
CM Activity |  |  | 1471585.71 | 1534144.32 | 1509585.6 | 4515315.63
Cumulative O/S balance |  |  | 91180235.89 | 102825071.75 | 98489857.89 | 292495165.53
Sixth Draw | 1999-05-21 |  | 0 | 0 | 0 | 0
Transaction Expenses |  |  | 0 | 0 | 0 | 0
Interest |  |  | 358547.28 | 404338.17 | 387290.85 | 1150176.3
Commitment Fee |  | 0.35% | 3727.47 | 5896.87 | 3813.77 | 13438.11
Breakage Costs |  |  | 83333.3333 | 83333.3333 | 83333.3333 | 250000
CM Activity |  |  | 445608.0833 | 493568.3733 | 474437.9533 | 1413614.41
Cumulative O/S balance |  |  | 91625843.9733 | 103318640.1233 | 98964295.8433 | 293908779.94
Payback West LB |  |  | -91550734.42 | -103477083.01 | -98880962.51 | -293908779.94
Total Commitment |  |  | 121000000 | 150000000 | 129000000 | 400000000
Remaining balance |  |  | 29374156.0267 | 46681359.8767 | 30035704.1567 | 106091220.06