## Sheet1
Enron Transportation Services
System Outage Request/Notification
[6 empty] | Submittal Date: ____ | 2002-01-11
|  |  |  | Planned: X |  | Late: | Unplanned:
| Region/Location: |  | Transwestern pipeline Station 4
| Reported By: |  | Robert Stearns |  |  |  |  | New: | x | Revised
| Telephone No: |  | 928-871-4266 or3038 |  |  | If a Revision Enter outage ID#
or the Original Est. Start Date
| FAX No: |  | 928-871-5784
| Starting Date: |  | 2002-04-08 | Time: | 08;00 | Completion Date: |  | 2002-04-14 | Time: | 19:00
| Descripition of Work: |  |  | Shut unit 402 down and change 2 piston and cyl. Liners, both after coolers all fuel valves, lifters, spark plugs, finfan motors, compressor valves, compressor rods and piston, packings, and pocket loaders, and calabrate and check all safty devices.
Facilities Affected
| Compressor Station: |  | Station 4 |  |  |  |  | Estimated Volume: |  | 250 to 400 mcf
|  | Units: | Unit 402 |  |  |  |  | Horse Power: |  | 4000 hp
Services Affected
| Mainline: |  | na |  |  |  |  | Aprox. Mile Post: |  | na
| Branchline/Transmission: |  | na |  |  |  | Reduced Operation Pressure: |  |  | na
|  | TBS: | [5 empty] | Farmtap: |  | na
| Comments: |  | This is part of our annual April outage
| All Outages Fax Or E:mail To (Jerry Graves) |  |  |  | fax# (713)-345-3478 Houston
| Facility Planning (Outage Coordinator) |  |  |  |  | fax# (402)-3987041 Omaha
For Unplanned Outages Add these Burst FAX Numbers ( Project Link):
( For unplanned outages in the Holcomb, Liberal, Mullinville & Amarillo Regions Only)
| Oneok - Tulsa |  | Delaine Kruth |  |  | (918) 732-1355 |  | ET&S Gas Control (Houston): |  |  | 7138539155
| Oneok - Bushton |  | Alan Siemer |  |  | (316) 562-4373 |  | ET&S Gary Spraggins: |  |  | 7136468000
| Exxon-Mobil-Liberal |  | Ulysses |  |  | (316) 356-7580
[8 empty] | Anadarko: |  |  | 3166294505
| OXY-Liberal |  | Jay Muse |  |  | (316) 624-7014
| ETS - Liberal Operatons |  |  |  |  | (316) 626-2251