## Merge
TASK | DATE DUE | Revised Completion Date | Complete | RESPONSIBLE PARTY | ISSUES | WEEK 1-8/14-18 ACTIVITY | WEEK 2-8/21-25 ACTIVITY | WEEK 3-8/28-9/1 ACTIVITY | WEEK 4-9/4-6 ACTIVITY | WEEK 5-9/11-15 ACTIVITY | WEEK 6-9/18-22 ACTIVITY | WEEK 7-9/25-29 ACTIVITY | WEEK 8-10/2-6 ACTIVITY | WEEK 9-10/9-13 ACTIVITY | WEEK 10-10/16-20 ACTIVITY | WEEK 11-10/23-27 ACTIVITY | WEEK 10-10/16-20 ACTIVITY | WEEK 12-10/30-11/3 ACTIVITY | WEEK 13-11/6-10 ACTIVITY | WEEK 14-11/13-17 ACTIVITY | WEEK 15-11/20-24 ACTIVITY | WEEK 16-11/27-12/1 ACTIVITY | WEEK 17-12/4-12/8 ACTIVITY
COMMUNICATION PLAN
1) Method of Communication | 2000-10-01 |  | Done | Dave Schafer | Content of memo, What, Why
1st Memo to Operations | 2000-08-16 |  | Done | Stan Horton/Phil Lowry | When to say it | Two general announcements were sent to GPG and Eott employees on 8/16
2nd Memo to Operations | 2000-09-15 |  | Done | Stan Horton/Phil Lowry | Names and explanations
3rd Memo to Operations | 2000-10-06 |  | Complete | Mary Ellen Coombe | Transition from EOTT employment and benefits
ORGANIZATION
1) Identify Vice Presidents | 2000-09-15 |  | Done | Phil Lowry
2) Director selection | 2000-09-15 |  | Done | Phil Lowry/Vice Presidents | [10 empty] | Directors have been selected
3) Advisor Selection | 2000-11-01 |  | Done | Directors | [10 empty] | Recommendations for Advisor Organization due to Wilson 11/1
4) Teams make-up & boundaries identified | 2000-12-31 |  | Complete | Directors | [10 empty] | SE Operations - In the process of identifying boundaries, career paths and team make-up. Midwest and SW are completed.
Note: Current weeks revisions in red. | Past Due Dates in Blue
5) Develop a career path for all employees | 2000-12-31 |  |  | Directors | [10 empty] | Underway
6) Staff Support Defined |  |  | Complete | Directors
Environmental, | 2000-09-15 |  | Done | John Shafer |  |  |  | Furnished list to Human Resources of EOTT employees to be assigned to EH&S Activity.
Communication, Control, Corrosion, Measurement, Mechanical, Over/Short | 2000-09-15 |  | Done | Rick Craig |  |  | Meeting w/Cutty and Don to review Tech Services organizational proposal and get names of candidates for vacant slots. Cutty to provide candidates. |  | Meeting with Don & Rick - Identified 8 individuals involved with ticketing and over/short coming to Measurement department. | No Personnel Relocating.
Regulatory | 2000-09-15 |  | Done | Dave Johnson |  | Requested system maps and info regarding inspections and open issues | Provided Dave with a color coded (state and DOT) PL map and a binder with specific 3 year history of Federal and state audit inspection reports |  |  | Records - other than GPG will require EOTT to maintain.
Field and home office administration | 2000-09-15 | 2000-10-01 | Complete | Larry Fenstad |  |  |  | Requested a lsit of field administration for review. | Eott HR submitting list of field administration employees. 9/5/00; Larry has list of 16 cost centers for EOTT. | Cost Allocation; Do not change allocations Oct. 1. Don Bruce will be officing in 3AC morning of Oct. 8th.
Over/Short Review & address Eott Process | 2000-09-15 |  | Complete | Rick Craig |  |  |  | Meeting with Klemish 9/6/00
Engineering, Planning/Optimization | 2000-09-15 |  | Done | John Keller |  |  | Had meeting with Cutty and Don and agreed on the transfer of 7 or 8 employees |  |  | Eott Staff Mtg.; EPS will not use existing EOTT Service Contracts.
Control Center
1) EOTT Control Center | 2000-09-15 |  | Done | Cutty Cunningham/Nick Rahn | Identify function & key employees |  | Had two meetings, one with Cutty and Don and the other with Don and David Hultsman
2) Eott & Phoenix Control Center/Location | 2000-09-15 |  | Done | Phil LowryDon Bruce/Julia White |  |  |  |  | Contact Julia White to discuss. 9/5/00
3) Integration of SCADA systems | 2000-09-01 |  | Done | Nick Rahn/Paul Anderson | Conduct due diligence review on 9/1 |  |  |  | N Rahn to meet with Paul Anderson 9/14-17
TRANSITION EMPLOYEES TO NEW ORGANIZATION
1) Implementation plan in place | 2000-09-15 |  | Done | Wilson Barbee | Benefits, Variable Pay, Actual transfer date of employees of employees | Had 1st GPG & Eott meeting to develop plan to handle HR issues
2) Employee Meetings | 2000-09-15 |  | Done | Wilson Barbee | Visit with Eott employees on GPG HR process |  |  | Schedule template to be provided by week of 9/5/00 |  | Meetings Scheduled.
3) Identify SME for controls, plant ops, corrosion, mechanics and measurement | 2000-10-01 |  | Done | Wilson Barbee/Mary Ellen Coombe |  |  |  | Renda Angel provided list to HR on 8/28
4) EOTT Skill Base Pay Transition/program plan | 2000-09-15 |  | Done | Wilson Barbee | EOTT Employees skill qualified by 10/1/02, (Grandfathered until then) |  |  | Set up meeting to review measurement on 9/5 with Cliff McPherson & Don | Met and enlarged list of SMEs', scheduled Houston work session for 9/14-15/00 | Transition Plan Complete; skill block meeting this week.
1) Identify office needs for Eott personnel relocating downtown | 2000-09-15 |  | Done | Larry Fenstad/Cutty Cunningham | Determine who & how many will be relocating |  |  |  | need verification of any any additional space requirements…IT and UAF staff
IMPLEMENTATION OF SDWT & ADVISORS
1) Identify support required to implement | 2000-12-31 |  | Complete | Roger Sumlin/SDWT Task Force |  |  | Set up special SDWT Task Force meeting for 9/6-7
2) Training requirements | 2000-12-31 |  | Done | Roger Sumlin |  |  | Set up special SDWT Task Force meeting for 9/6-7
3) EOTT Task Force Members identified | 2000-12-31 |  | Done | Roger Sumlin
4) How to handle Variable Pay eligibility | 2000-10-31 |  | Done | SDWT Task Force |  |  | Set up special SDWT Task Force meeting for 9/6-7
5) Training & development plan to start up & charter teams | 2000-11-01 |  | Complete | Roger Sumlin/SDWT Task Force |  |  | Set up special SDWT Task Force meeting for 9/6-7
FINANCIAL PLAN
1) Plan
Plan in place | 2000-09-15 |  | Complete | Rod Hayslett |  |  |  | Meeting 8/30/00 work to continue week of 9/5/00
By Business Unit | 2000-11-01 | 2000-11-12 | Complete | Larry Fenstad/Barney Brasher/David Clements |  |  |  |  | review plan w/ P/L operations planning & Tracy | [9 empty] | North Area Plan submitted on 11/6/00. Business Unit Plan being reviewed with Phil Lowry and V.P.'s.
Consolidated | 2000-11-27 |  | Complete | Tracy Geaccone
2) Define "SAP" Application for EOTT | 2000-09-15 |  | Done | Larry Fenstad |  |  |  |  | CC review by Jon Trevelise & Tracy underway. Setup planned to be complete 9-8
P Card EOTT/ETS Transition Issues | 2000-12-31 |  |  | Morris Brassfield | [18 empty] | Cards are due to us on 12/8/00. Distribution will occur as soon as training can be scheduled.
EOTT/ETS Field Office A/P | 2000-11-30 | 2000-12-31 |  | Morris Brassfield | [18 empty] | Training has been completed. Security Access for each trained employee has been requested and is in the process of being set up.
"IT" STRATEGY
1) Define GPG & EOTT duplicate processes | 2000-09-01 |  | Done | Don Bruce/Nick Rahn |  | Gathered detailed list of applications. Will meet with Don 8/23 to discuss next step. | Had meeting with Don & David Hultsman about SCADA & Tech Support
2) Identify Issues/Opportunities | 2000-09-15 |  |  | Nick Rahn/ Cutty Cunningham | Review Eott tank measurement projects |  |  | Had a meeting with GSI and reviewed 3 tank projects | [7 empty] | On going effort |  |  | (not part of Cutty Cunningham's current duties) Noted as on-going effort 9/15
3) Handle Eott work station move/Custody of work stations | 2000-09-15 |  | Done | Nick Rahn | Save hard drive info./ Determine Ownership | [10 empty] | CD's burned for users and finally completed. There are still numerous issues including ENTRIX access and AutoCAD file transfer. Working with Steve Findley and Tom Sampson (Enron) to resolve.
6) Oracle upgrade for Eott | 2000-09-15 |  | Complete | Nick Rahn/David Hultsman | Conduct parallel test (2 ticket entry process) during Oct. | [10 empty] | Continuing as planned. The dual ticket entry portion for the field has been completed. The expected cutover date is Nov 4th with first ticket close. |  |  | Conversion complete
EOTT ENVIRONMENTAL
ISSUES
1) Interview Entrix | 2000-09-15 |  | Complete | John Shafer |  |  |  | Meeting held with Entrix on 8/31. Complete overview of contractual provisions reviewed. Agreed with Legal Department that they should issue a "thirty day notice of termination" of the agreement with Entrix by September 2. Good review of other permitting issues and remediation activities. Next meeting to be held 9/13/00. |  | Meeting scheduled 9/13/00
2) Define results/needs | 2000-09-15 | 2000-12-31 | First Phase Complete Second Phase On-going | John Shafer |  |  |  | Basic understanding of services being provided by Entrix discussed. Contract to be renegotiated to include limited scope of services to be provided as of Oct. 2. Probably areas of service for Entrix will include expansion needs of OPA 90 and remediation of approximately 360 known EOTT sites. Next meeting on 9/13/00 will reveal more definition of needs. | [10 empty] | Awaiting EOTT approval of 4Q00 Remediation activities. Some work authorizations have been submitted and approved. Remainder on-going.
3) Revise Kniffen Estates memo with current status and expenditures forecast. | 2000-11-03 |  | Completed 11/6/00 | Cutty Cuningham | [14 empty] | Submitted to EOTT Management
4)Set up W.O. and coding for the Kniffen Estates project. | 2000-11-10 |  | Complete | Bill Kendrick | [13 empty] | ETS work order established Nov. 3.
5) Refine 4th quarter 2001 budget numbers for presentation to Dana Gibbs. | 2000-11-15 |  | Complete | Bill Kendrick | [13 empty] | Meetings to be held in Midland during week of Nov. 3rd to refine budget
6) Prepare and submit 2001 annual budget numbers for presentation to Dana Gibbs. | 2000-11-30 |  | Complete | Bill Kendrick | [11 empty] | See above | [5 empty] | Meeting scheduled week of 12/12.
7) Prepare a report of where EOTT presently stands with their insurance claims. | 2000-11-15 |  | Complete | Susan Ralph
8) Memo to the field informing them of the reporting procedures and the criticality of reporting to the insurance company within 15 days on non-Texas/New Mexico assets. | 2000-11-30 |  |  | Susan Ralph | [17 empty] | Training session held for Houston EPSC employees Nov. 27.
9) Schedule of environmental site visits to determine accuracy of current estimates for the 1st quarter, 2001. | 2000-11-15 |  | Completed 11/10/00 | Bill Kendrick/Cutty Cunningham | [13 empty] | Trip to Midland scheduled week of Nov. 6th.
OPERATING PROCEDURES
1) Determine existing manuals | 2000-08-15 |  | Done | Randy Belyeu |  | Manuals in place but all needing modifications. Safety, Operating Procedures, Engineering Stds, Emergency Plan. No Environmental Plan
2) Comprehensive Manuals
Operating Procedure | 2000-10-01 |  | Done | Dave Johnson | Obtain Liquid Ops Manual |  |  |  |  | On-going |  | Combined Operating Procedures completed and posted on intranet
Environmental | 2000-10-01 |  | Complete | John Shafer | Obtain Liquid Env. Manual |  |  | Most of the environmental procedures manual for GPG is applicable. However, areas such as OPA 90 requirements will have to be enhanced. Bill Kendrick to work with Cutty Cunningham on these issues. |  | On-going
Engineering Standards | 2000-10-01 |  | Complete | Dave Johnson | [7 empty] | Several standards updated. No significant additional needs identified. Modifications to be made on an ongoing basis.
Safety | 2000-10-01 |  | Complete | John Shafer | Procedures | The Safety portion of Eott manuals are basically in compliance and no major concerns presented. While three procedures (asbestos, lead, fire retardant clothing) are needed, we need only make minor changed to the corresponding GPG safety procedures to incorporate Eott particulars.
OPERATIONS/ASSET MANAGEMENT
1) Determine the proper method for the field teams to answer the telephone. | 2000-11-15 |  | Complete | Randy Rice/Mike Nelson/Danny Pribble | Consideration must be given to the fact that some of the field teams operate more than one company's assets.
2) Ensure there is an adequate process for assessing the relative risk factors associated with operating particular segments of pipeline prior to shutting them down. In conjunction with this initiative an effort to locate segments of pipe that have little volume and are candidates to close down would be undertaken. | 2000-12-15 |  |  | John Keller/Terri Gallasini/Robin Border/Ron Davenport/David Odneal | Typically these pieces of pipe are small diameter lines that have possibly one lease at the end with 100 BD or less of production on it. The economics versus risk would typically indicate discontinuing operations on that segment of pipe. | [13 empty] | Orginal group contact made with the transmittal of the Risk Assessment document from R Davenport to the group. |  |  |  | Border and Davenport preparing statement of procedure to distribute to the field.
ADMINISTRATION
1) Define the procedure and develop a flow chart for ETS securing EOTT approval authorizations and project tracking. | 2000-11-15 | 2000-12-31 |  | Morris Brassfield/Barney Brasher/Randy Belyeu | [14 empty] | Met and discussed the project tracking for initiation to completion. Work is in progress for tracking and entering into SAP. Flow chart being formatted presently. Project scope document being standardized throughout ETS. | Teams were designated to develop the processes from initial project scope to level "A" estimate, from level "A" to AFE development plus tracking and from the AFE through input into SAP. |  | Moving forward, strawman sent to the team for review and comments.
1A) Scoping/AFE approval Team; |  | 2000-12-31 |  | Randy Belyeu, Terry Galassini, Talbert Loyd, Larry Steward, David Stroin, Deaun Trayer | [17 empty] | Strawman sent to the team for review and comments.
1B)SAP/Financial Team |  | 2000-12-31 |  | Randy Belyeu, Barney Brasher, Morris Brassfield | [17 empty] | PA form has been modified and is ready for distribution to the office and field.
1C)Project Estimating/Scheduling/ Tracking Team |  | 2000-12-31 |  | Randy Belyeu, Earl Chanley, Rick Johnson, Greg Mathews, Frank Osburn, Joe Richards, Mike Smith, Norm Spalding | [17 empty] | Strawman sent to the team for review and comments. Meeting held to discuss the E & C e-STAT tracking system. The team feels that this is the program that services our needs and it can be migrated to ETS expediently. IT will have a cost estimate by 12/08 to have migration ready for January 1.
2) Develop a procedure to improve the present process to ensure prompt handling EOTT invoices from the field. | 2000-11-15 | 2000-11-16 |  | Morris Brassfield/Barney Brasher/David Clements/Larry Fenstad/Randy Belyeu | [14 empty] | Meeting between L.Fenstad and D. Clements set 11/13/00 to discuss process for all reoccurring type invoices and invoices for Field purchases in the SW and North Area.
ENGINEERING
1) Develop a schedule of engineering charges for estimates on projects. | 2000-11-15 |  |  | Jerry Martin/Joe Richards/Lori Maddox
2) Conduct an analysis, make a recommendation and develop a cost estimate to address the Hunt #1 line located in Mississippi. Prepare a presentation for management. | 2000-11-15 |  |  | Jerry Martin/Norm Spalding/Rick Johnson
FLEET (Light Duty) MANAGEMENT
1) Review Differences | 2000-10-01 | 2000-11-01 | Complete | Morris Brassfield/Keller |  |  |  |  | Auto Ins. Emps. Driving vehicles will not be covered Oct. 1; GPG - Lease/Purchase light duty vehicles. | [9 empty] | Standardized on spec's reviewing Runzheimer program
2) Recommended Plan | 2000-10-01 | 2000-11-01 | Complete | Morris Brassfield
3) Ownership of Light Duty Vehicles | 2000-10-01 |  | Complete | Cutty Cunningham/Phil Lowry | Determine Ownership |  |  | Vehicles to remain titled in owning company's name | [10 empty] | Operation and Service Agreement leased those vehicles form EOTT to Enron for the term of the service agreement.
ASSETS
1) Identify Assets | 2000-09-15 |  | Done | Randy Belyeu/Don Bruce |  |  | Had an EOTT meeting on 8/24 to develop format for asset identification | Met 8/30/00, Identified various EOTT databases. In process of merging into one. Gathering list of GPG assets by team. |  | Fenstad custodian of asset lists
Active | 2000-09-15 |  | Done | Randy Belyeu/Don Bruce
Inactive | 2000-09-15 |  | Done | Randy Belyeu/Don Bruce |  | Scheduled 1st meeting for 8/30
Abandoned | 2000-09-15 |  | Done | Randy Belyeu/Don Bruce
Redundant Facilities | 2000-09-15 |  | Done | Randy Belyeu/Don Bruce |  | Scheduled 1st meeting for 8/30 |  | Developing map of office locations, ready for Thursday meeting
2) Custody of Maintenance Equipment | 2000-09-15 |  | Complete | Cutty Cunningham/Phil Lowry | Determine Ownership
3) Develop a process for identifying and developing a list of present EOTT assets and designate a ETS focal person for communicating with Advalorem Taxes. | 2000-11-30 |  | Complete | Warren Schick/Randy Belyeu | There is presently some uncertainty as to what current assets are attached to the EOTT system. | [13 empty] | Meeting set for 11/16/00 | Presently there is not an accurate list of assets. An effort should be made to take the conveyance document presented at closing on the Koch and Texas/New Mexico acquisitions to verify that the assets operated match this document. Advalorem Tax is unsure as to what properties taxes are due and have been notified of delinquent taxes. It is recommended that the ROW department be given funds to clear the issue by March 1, 2001 |  | Project Authorization to conduct the reconciliation submitted for management approval. To be completed by 3/1/01. | Workorder has been approved.
CRISIS MANAGEMENT
1) Emergency Response | 2000-10-01 | 2000-11-30 | Complete | John Shafer/Stephen Allen | Must have a consistent response procedure | Continued effort to develop the electronic emergency plan will ensure that major elements and expectations of emergency plans will be accomplished. Training on Regional/company reporting requirements will be required and could be conducted during the transition period. |  | Emergency Response - Will begin work on 10/1 with EHS Coordinators for EOTT to ensure necessary training is being conducted. |  | Meeting with Shafer, Cunningham, Allen & Lowry week of 8/11/00 | [9 empty] | Waiting on EOTT Management notification matrix |  | Contact names and numbers were recieved from EOTT. This data has been entered into a data base in the Operations Communication Center, who will notify anyone on the list when requested to do so in an Emergency or Crisis Event. (Consolidated contact listing will be presented to ETS Vice Presidents at the Operations Staff Meeting to be conducted on December 7).
Legal Review
Service Agreement | 2000-09-15 |  | Complete | Mike Moran/Molly Sample/Kelley | Develop Service Agreement |  |  |  |  | Being drafted | [8 empty] | Complete
Contract Review | 2000-10-01 |  | Done | Lou Soldano/Molly Sample | Determine the contracts that need amended
Ownership/lease office space | 2000-10-01 |  | Done | Molly Sample/Annette Vogel |  |  |  | EOTT Legal scoped out a plan to put together a list of relevant information on the ownership and applicable agreements for each field office location. This is a more specific subset of the facilities list and pertains only to locations where people office or are based, even if only a few days per week. Will put together a booklet, hopefully all the info needed to decide which field offices to keep or shut down and the associated costs. Since most of info is in Annette's data base, we hope to have by the end of next week.
Human Resource Process | 2000-09-15 |  | Done | Wilson Barbee/Mary Ellen Coombe
Accounting Process | 2000-09-15 | 2000-12-15 |  | Lawrence Clayton/Lori Maddox/Jon Trevelise/Rod Hayslett/David Hultsman