## ERMS-TAGG-TDS Request (Top 5) (hidden)
Priority | Task ID | System | Tech/ Func | Application / Project | Function/Purpose | Business Unit | Requested By | Request Date | Priority | Key IT Contacts | Key Bus. Contacts | Start Date | Estimated Complete Date | Status | Comments / Key Issues
1 | 21 | ERMS | Tech | PortCalc | Increase post ids from 6 digits | ENA |  | 2000-07-27 | H | Sanjesh Pathak Jeremy Wong |  |  |  | In Development
2 | 63 | TAGG | Func | MetaCalc | Locks up easily; slow performance | ENA | Risk Management | 2000-08-03 | H | Francis Lim, Truong Vu Cap Gemini | Risk Management |  |  | In Development
3 | 30 | TAGG ERMS TDS | Func | PortCalc Deal Capture Position Manager P&L Manager | Add logic to handle spread options in TAGG/ERMS (First phase will be for Basis/Location Spread. The Second phase will be for Calendar Spread.) | ENA | Trading | 2000-07-27 | H | Jeremy Wong | Trading Dutch Quigley |  |  | In Development/in Enpower | Using Enpower for the time being.
3 | 56 | TAGG ERMS Sitara | Func | Deal Manager | Ability to capture term transport deals and related hedges | ENA | Risk Management | 2000-07-27 | H | TAGG ERMS Sitara | Risk Management Sitara Development |  |  | In Development/in Enpower | Dependent on the integration of Basis Options in port calc (Task # 30)
4 | 36 | ERMS | Func | Reporting | Create additional exception reports /PostID Compare | ENA | Dutch Quigley | 2000-07-27 | M | Sanjesh Pathak | Dutch Quigley |  |  | Pending | These reports need to be defined! Will Kelly will provide example report layout. This report should skip new deals.
4 | 39 | ERMS | Func | Reporting | Create better Gas Daily and Intramonth Changed Deal Reports | ENA | Kathy Reeves | 2000-07-27 | M | ERMS | Kathy Reeves |  |  | Pending
4 | 47 | TDS | Func | Position Manager P&L Manager | Changed Deals: Ability show details about changed deals (before, after -what changed) | ENA | Keith Holst | 2000-07-26 | M | TDS | Trading Risk Management Bill Kasemervisz |  |  | Pending
4 | 53 | TDS | Func | Position Manager P&L Manager | Net Aggregated Changes to Prior Day Position: Resulting from new and changed deals This report should also have drill down capability to see net changes due to just new deals or due to just changed deals. The layout of this report would be exactly like the regular position report. | ENA | Phillip Allen | 2000-08-08 | M | TDS | Trading Risk Management |  |  | Pending | Further review with Phillip Allen required; meeting scheduled week of 08/14-08/18
5 | 41 | CPR ERMS Unify | Func | Operational Analysis Improvements | Move OA data out of Access to Oracle -Improve timeliness of the process (current process takes 3 to 5 hours to accumulate) -Need ability to do OA Analysis at Deal level; new reporting requirements | ENA | Risk Management | 2000-07-27 | H | Nagesh Kavi Zhiyong Wei Unify | Risk Management VM/Logistics Settlements |  |  | In Development | Leslie Reeves' group is going to looking into the issues before proceeded by us.
Tasks sharing the same priority number are either dependent on each other or are being consolidated because they are similar.

## Newly Completed
Date Completed /Closed | Task ID | System | Tech/ Func | Application / Project | Function/Purpose | Business Unit | Request Date | Key IT Contacts | Key Bus. Contacts | Commodity | Scope | Start Date | Estimated Complete Date | Status | Comments / Key Issues | Priority | Requested By
2001-06-01 | G22 | ERMS | Tech | GUI Reports | Fix Basis Download process - the portfolio and commodity order sequences are running out ( #54), Increase pub_cd_order and portfolio_order from 1 character to two characters | Global Products | 2001-04-10 | Farid, Francis | Carol Chew | Global Markets |  | 2001-04-23 | 2001-05-25 | Completed | Done the database changes. Done fixing the form. Waiting for +-5 days to move form to production
2001-06-08 | G33 | TAGG ERMS | Func | Excel | Modification of the Excel program to have more than one post_id and a Strategy Code Filter (Task #56). This is to provide London with the Vessel information in the Strategy Code field. | Global Products | 2001-05-08 | Samer, Francis | Dimitri Taylor | Global Markets |  | 2001-05-25 | 2001-06-15 | Completed | Samer informed Dimitri on the completion and asked Dimitri to call back if any questions.
2001-06-08 | G34 | ERMS | Tech | Excel | Broker Fee Change report in excel (Task #57) | Global Products | 2001-05-08 | Samer, Francis | Susan Trevino, Chris Abel | Global Markets |  | 2001-05-25 | 2001-06-15 | Completed | Samer will show Susan Trevino how to run
2001-06-08 | G38 | TAGG ERMS | Func | Database | Move deals from 15 existing books to a new set of books (Task #58) | Global Products | 2001-05-24 | Sanjeev | David Oliver | Global Markets |  | 2001-05-25 | 2001-06-15 | Completed | We made the change on one of the books. David Oliver is testing it and we will do the rest when David says everything is OK.
2001-06-18 | NG51 | ERMS | func | Reporting | Data Extract from AEP HPL | ENA | 2001-05-24 | Margie | Tommy Yanowski | Natural Gas |  | 2001-05-25 | 2001-05-31 | Cancelled | AEP will tell us which report they want. We will get the sql from the report. Margie created the SQL in Toad. Will be migrated over to ASP when SQL is perfect. After performing a detailed analysis of the ERMS data and reports, we have decided to hold off on the P&L and Price Risk Position data extracts. The primary reason for suspension of these interfaces is that the ERMS data has to be significantly scrubbed prior to reporting our numbers to management. Thank you for your support. I'm sure we'll be needing your services again in the future. We'll be in touch. Kurt D. Wissner
2001-06-13 | NG37 | TAGG/ERMS | Func | PortCalc | Add new Gas Daily Ostrip model with Vega1 and Vega2 to PortCalc (Task #13) | ENA | 2001-03-23 | Shouan | Larry May | Natural Gas |  | 2001-03-23 | 2001-05-18 | Completed
2001-06-20 | NG55 | ERMS | Func | Excel | Please add the book name corresponding to the (internal) counterparty_cd. Excel forward detail new version | ENA | 2001-05-11 | Cecilia | Brian Gillis | Natural Gas |  | 2001-06-20 | 2001-06-20 | Completed | URGENT New request
2001-06-18 | NG50 | ERMS | Func | Reporting | Open Position Download from Tagg (Task #25) | ENA | 2001-05-24 | Cecilia | James Barrett | Natural Gas |  | 2001-05-25 |  | Completed
2001-06-18 | IM14 | ERMS | Func | Excel | The following "books" all have the same book code:Paper-IDX JLNP-NEWENGLAND JLNP-ESCT JLNP-CANADAEAST JLetc.They allow for us to run book to book transactions within a book. I consider the first the primary book, and the last three subbooks, since when I enter the book code in ERMS Paper-IDX pops up. When I calculate Paper-IDX, all the deals in the last three "books" show up in the results. When I run a query from TAGG, selecting "NP-CANADAEAST" as my book, I will show the deals that I have entered with that book, but when I run a forwards detail, I can't decipher which book it was entered with. I would like to add a column to my forwards detail to show which book it was entered in. (Task # 9) | Industrial Markets | 2001-05-07 | Cecilia, Francis | Shari Mao | IM - Pulp, Paper, Lumber, and Steel |  | 2001-05-11 | 2001-05-14 | Completed
2001-06-27 | NG56 | ERMS | Bug Fix | PortCalc screen | Increase the length of the the PUB_CODE list on the form rsr0028.fmb so that more pub codes can be entered. | ENA | 2001-06-20 | Farid | Jeremy Wong | Natural Gas |  | 2001-06-26 | 2001-06-27 | Completed | Length has been increased to 255 characters
2001-06-28 | NG57 | ERMS | Func | Excel | Create Excel macro to fetch/update swaption volatility matrix from database | ENA | 2001-06-25 | Margie | John Griffith | Natural Gas |  | 2001-06-25 | 2001-06-27 | Completed
2001-06-29 | GTV10 | ERMS | Func | Report | Modifications of Larry May's existing Gas Daily prompt and and forward months excel report so that it does not use sqlplus anymore. Move the entire sql into the internal VB. I had encountered several problems with it because everytime the excel is given to another user it no longer works because they do not have a local install of the sqlplus program. To get the program to work they have to send a request to e-request for a local install of sqlplus. If we move the SQL inside the excel program then we do not need the sqlplus program anymore. The program will run a little slower. | ENA | 2001-06-21 | Francis, Margie | George Huan and Sean | Natural Gas |  | 2001-06-28 | 2001-06-29 | Completed | Moved sql codes in vb.
2001-06-29 | NG55 | ERMS | Func | Excel | re-code Options premium VB spreadsheet so that Jennifer Blay can run it for two weeks time span. Re-code it again to that it does not take a long time to run. | ENA | 2001-06-21 | Francis | George Huan and Sean | Natural Gas |  | 2001-06-28 | 2001-06-29 | Completed | Entirely new prem upload spreadsheet created from scratch to run two weeks time span and good speed.
2001-07-10 | NG56 | ERMS | Func | Reporting | provide in excel post_id informations for a given set of post_ids | ENA | 7/3/201 | Margie | Edgar Castro | Natural Gas |  |  |  | Completed | gave the excel to Edgar Castro
2001-06-29 | 82.3 | ERMS | Func | Price Down Load | Get Gas Daily prices from MKM. Upload and download curves to/from MKM/Rate Server and insert into our database (Task # 06) | ENA | 2000-11-03 | Cecilia | Willie Harrell | Applies to ALL |  | 2001-01-15 | 2001-05-11 | Completed
2001-07-09 | C15 | TAGG | Func | Deal Capture | For Commodity Logic, modify Deal Capture to allow user to identify if a deal is multi-legged (Task # 07) | ENA Global Products | 2001-03-02 | Sanjeev | Ron Nolte | Applies to ALL |  | 2001-04-13 | 2001-07-06 | Completed | Waiting for user approval
2001-07-09 | G39 | TAGG ERMS | Func | Database | Create new calendar (combination of NYMEX + IPE) for common pricing commodities | Global Products | 2001-05-23 | Jeremy, Cecilia | Shifali Sharma | Global Markets |  | 2001-06-18 | 2001-06-29 | Completed
2001-07-09 | G43 | TAGG | Func | Deal Capture | Allow negative strike prices for Swaps/Forwards/Options in TAGG OTC Deal Capture | Global Products | 2001-06-18 | Sanjeev | Victor Guggenheim | Global Markets |  | 2001-07-02 | 2001-07-13 | Completed
2001-07-09 | NG52 | TAGG ERMS | Func | Database | Move deals from 5 existing books to a new set of books | ENA | 2001-06-11 | Sanjeev | Darron Giron | Natural Gas |  | 2001-06-25 | 2001-07-02 | Completed
2001-07-09 | NG53 | TAGG ERMS | Func | Database | Move deals from 1 existing book to another existing book | ENA | 2001-06-18 | Sanjeev | Carlos Torres | Natural Gas |  | 2001-06-25 | 2001-07-02 | Completed
2001-07-09 | NG48 | ERMS | Func | Database | create a new curve mapping for the Intramonth portcalc. (Task #23) | ENA | 2001-05-24 | Francis | Russ Severson | Natural Gas |  |  |  | Completed
2001-07-09 | NG49 | ERMS | Func | Reporting | create a new report for the Curve Shift Report so that it will require 4 post ID's to run. This is because of the N post id and the M postid. Form Modification, report modification, shell script modification. (Task# 24) | ENA | 2001-05-24 | Farid, Francis | Chuck Aimes | Natural Gas |  | 2001-05-24 |  | Completed | Farid did the form changes and report changes but the result was not exactly what was wanted. crvshft C program, modified script, modified form.
2001-07-16 | G45 | TAGG | Func | Deal Capture | For Exchange Deal Capture, allow more than 1 price curve to be mapped to a commodity | Global Products | 2001-07-02 | Oscar | Richard Cross | Global Markets |  |  |  | Dropped
2001-07-23 | C12 | ERMS | Func | Project | Executive Report Viewer Rewrite with History, Audit, Security, and Improved looks ( #Task 22) |  | 2001-01-09 | Hal, Sanjesh, Kirti | Chris Abel | Applies to ALL |  | 2001-01-15 | 2001-05-31 | Completed | Completed Phase I
2001-07-23 | C30 | ERMS | Func | Project | Trader Report Viewer with History, Audit, and Security |  |  | Hal, Sanjesh, Kirti | Chris Abel | Applies to ALL |  |  |  | Completed
2001-07-16 | IM06 | TAGG ERMS | Func | Database | Change UOM from TONNE to MTON for Pulp and Paper deals (task #5) | Industrial Markets | 2001-02-16 | Sanjeev, Cecilia | David Lowicki | IM - Pulp, Paper, Lumber, and Steel |  | 2001-03-19 | 2001-04-20 | Completed
2001-07-16 | IM07 | TAGG ERMS | Func | Database | Change UOM from TONNE to STON for Pulp and Paper deals (task #6) | Industrial Markets | 2001-02-20 | Sanjeev, Cecilia | David Lowicki | IM - Pulp, Paper, Lumber, and Steel |  | 2001-03-19 | 2001-04-20 | Completed
2001-07-17 | G42 | TAGG | Func | Reports | Brokerage Report in Excel spreadsheet to generate a report with counterparty, deal number, deal date, Phy/Fin, Deal type, Period, Monthly Quantity, Broker, and Brokerage Amount | Global Products | 2001-06-22 | Margie, Francis | Maya Beyhum | Global Markets |  | 2001-06-23 | 2001-07-01 | Completed | Completed. Excel reports are in O:\erms\docs\excel\reports
2001-07-26 | NG61 | ERMS | Func | Reporting | converting our reports from Oracle to Excel. P&L Summ tab: Hedge Quantities - rsr0500 P&L Detail Page - rsr0512 Sensitivity Detail - rsr0503 Option Risk by Mo - rsr0515s4 Canadian tab: Implicit Pos Rep - rsr0950is and rsr0950io Explicit Pos Rep - rsr0950e | ENA | 2001-07-17 | Margie, Francis | Brian Gillis | Natural Gas |  | 2001-07-13 | 2001-07-26 | Completed | Completed. Excel reports are in O:\erms\docs\excel\reports
2001-07-24 | NG62 | ERMS | Func | Excel | I have noticed that EOL deal #'s are not included on the Option Premium Invoices- (and don't think they have ever been for Options-)Would it be possible and fairly easy to include the EOL deal #'s within the option query, so that the Unify invoices will reflect this information? | ENA | 2001-07-24 | Francis | Jennifer Blay | Natural Gas |  |  |  | Completed
2001-08-08 | IT18 | TAGG | Tech | Upgrade | post_id_info report. report all post_id entries from egs_posn_def and egs_posn_errors. | ENA Global Products | 2000-12-20 | Margie | Mike Clifford | Applies to ALL |  |  |  | COMPLETED
2001-08-08 | IT19 | TAGG | Tech | Upgrade | Deal_info_report | ENA Global Products | 2000-12-20 | Margie | Mike Clifford | Applies to ALL |  |  |  | COMPLETED
2001-08-08 | C23 | TAGG | Tech | Deal Capture | Fix TAGG Deal Capture not to save a blank price as a blank pub. Code (Task #24) | ENA | 2001-05-01 | Sanjeev | Jeremy Wong | Applies to ALL |  |  |  | Completed
2001-08-03 | C31 | ERMS | Func | PortCalc | Redo discount logic of physical deals to discount to last day rather than first day of month | ALL | 2001-06-21 | Jeremy, Jennifer | Sheila Glover, Chris Abel, Jeff Gossett, Todd Hall | Applies to ALL |  | 2001-06-25 | 2001-08-01 | Completed | Completed and cancelled
2001-08-22 | G08 | ERMS | Func | PortCalc | Modify Asian options (with 1 underlying) from using business days to calendar days ( #23) | Global Products | 2000-12-15 | Jennifer | John Swinney | Global Markets |  | 2001-01-25 | 2001-05-11 | Completed
2001-08-08 | G44 | TAGG | Func | Deal Capture | Allow for entering of pub. code in place of strike price for Options/Swaptions in TAGG OTC Deal Capture | Global Products | 2001-06-26 | Sanjeev | Victor Guggenheim | Global Markets |  | 2001-07-02 | 2001-07-13 | Completed
2001-08-08 | NG58 | TAGG | Func | Deal Capture | Provide a warning message in TAGG OTC Deal Capture when the start date of a deal is not in the same month or later as the deal date | ENA | 2001-07-03 | Sanjeev | David Baumbach | Natural Gas |  | 2001-07-09 | 2001-07-13 | Completed
2001-07-28 | NG63 | TAGG ERMS | Func | Database | Move deals from FT-CENTRAL to FT-ONTARIO | ENA | 2001-07-23 | Sanjeev | Phillip Love | Natural Gas |  |  |  | Completed
2001-08-18 | NG64 | TAGG ERMS | Func | Database | Move deals from 9 West desk books | ENA | 2001-07-23 | Sanjeev | Anne Bike | Natural Gas |  |  |  | Completed
2001-08-08 | NG65 | ERMS | Func | PortCalc | Modify Copy PostId application to handle new Gas Daily Index "Y" risk type | ENA | 2001-07-16 | Sanjeev | Kam Keiser | Natural Gas |  | 2001-07-16 | 2001-08-09 | Completed
2001-08-20 | NG70 | TAGG | Func | Excel | Attached are two excel files (example and end result). The example spreadsheet is what I think this new fetch macro should look like. The end result spreadsheet is what we are ultimately trying to produce for our traders and I think the new fetch macro will get us there. Our current process is to manually type this information in, requireing too many man hours. Give me a call tomorrow and let me know how long something like this might take to build, if it is not already available. | ENA | 2001-08-17 | Mike Clifford | Matt Brown | Natural Gas |  |  | 2001-08-20 | COMPLETED
2001-08-20 | NG68 | TAGG | Func | Excel | settlement problem Rhonda Washington (3-7734) has a spreadsheet that she needs someone to look at the logic behind it - to see why some numbers are not correct. Would you have someone to help her ? | ENA | 2001-08-16 | Margie, Francis | Rhonda Washington | Natural Gas |  |  |  | COMPLETED
2001-08-18 | NG66 | ERMS | Func | Reporting | add a column referencing the TAGG number in the forwarddetailwsitara.xls Excel file when running the Fetch Detail with Sitara macro. The name of the columns is external_sys_id on egs_intra_month_price_book table | ENA | 2001-06-28 | Margie, Francis | Scott Palmer | Natural Gas |  | 6/31/2001 |  | COMPLETED
2001-08-24 | NG69 | TAGG | Func | Excel | I used the above Excel query to extract data from ERMS and it works great but have a Windows 2000 problem with Column S (Index_Cd). Since installing Windows 2000, the default for this column in zero (0) not blank. When I link this results page into Access it cannot distinquish between alpha/numeric and errors out this field. Can you have someone just format ONLY Column S (Index_cd) to load a blank instead of zeros. I need the rest of the columns to report zeros instead of blank. | ENA | 2001-08-17 | Syed Ishaq | Sony Wilson. 3-7729 | Natural Gas |  |  |  | COMPLETED
2001-08-24 | NG67 | ERMS | Func | Excel | have the ability for Stewart to enter the post_ids into the Excel basis_liquidation download Excel sheet rather then use the forms4.5 screen. | ENA | 2001-07-06 | Sanjesh, Francis | Stewart Range | Global Markets |  | 2001-07-27 |  | COMPLETED
2001-08-31 | G46 | TAGG | func | Reports | Shifali Sharma (EGM, x3-5170) is requesting a new report similar to the TAGG (IQ) report Exchange Options MTM - Calls and Puts Together (RSXEOCE3) but for OTC options. | Global Products | 2001-07-24 | Kirti, Francis | Shifali Sharma | Global Markets |  |  |  | COMPLETED but Shifali decided to drop this report.
2001-08-31 | NG70 | TAGG | Func | Excel | I have a request from the East desk originations head. He would like to be able to see the following....Number of new deals done each month and the volumes associated w/ those deals...absolute volumes (not liquidated volumes but the new deals done each month) broken out by month and physical vs. financial. He would like to go back three years if possible. Can you or someone in your group help me with this request from the TAGG/ERMS data stored? | ENA | 2001-08-28 | Syed, Francis | Kam Keiser | Natural Gas |  |  |  | COMPLETED
2001-09-07 | NG71 | TAGG | Func | Reporting | We need to pull only those deals which falls under these books. FT-NY East-NorthEast,East-MktEast,East-gulf1,East-gulf2,East-gulf3,East-gulf4,East-New-Eng,East-CNG,East-NEWYORK,East-TP1, East-TP2,East-TP3, Intra-Northeast | ENA | 2001-07-16 | Syed | Kam Keiser | Natural Gas |  |  |  | COMPLETED
2001-09-10 | NG71B | TAGG | Func | Reporting | more information needed as Torrey Moorer requested | ENA | 2001-07-16 | Syed | Torrey Moorer | Natural Gas |  |  |  | COMPLETED
2001-09-14 | NG72 | TAGG | Func | Database | We need to write a script to move all of the existing deals from FT-CAND-EGSC-BC into FT-CAND -EGSC. Note that both of these books are in the C4 book, EGSC-BC being the "CANADA" region and EGSC being the "DESK" region. We would like to have these moved this week - which day it happens on isn't important, we just need to know in advance when you are doing it so that we can make the necessary preparations. As in the past, there will be interbook deals between these two books - as I recall, you had your script automatically kill those deals - could you confirm that? | ENA | 2001-09-10 | Sangeev, Truong | Brian Gillis | Natural Gas |  |  |  | COMPLETED
2001-09-18 | G09 | ERMS | Func | PortCalc | Enhance predictive rolloff reporting of futures ( #48) | Global Products | 2000-09-25 | Jennifer | Shifali Sharma | Global Markets |  |  |  | COMPLETED
2001-09-20 |  | TAGG | Func | Excel | have a curve fetch macro in excel that was created some time in the past. This macro will pull a curve from ERMS over a date range and show how the curve was set each day. However this macro does not pull the prompt month (first month of the curve). I was wondering who in your group might be able to help adjust this file so it would list the prompt month prices. I have attached the file below. If you have any questions please ask. | ENA | 2000-09-18 | Dan Arellano | Victor Guggenheim | Natural Gas |  |  |  | COMPLETED
2001-09-20 |  | TAGG | Func | Excel | .2% Gasoil MTM @ 09_14.xls macro changes because it stopped working after the upgrade to Oracle 8i | Global Products | 2001-06-22 | Cecilia Cheung | Maya Beyhum | Global Markets |  | 2001-09-24 | 2001-09-24 | COMPLETED
2001-08-31 |  | TAGG | Func | Excel | kevin lee would like to get a list of the books with non-expired swaptions in them | Global Products | 2001-08-31 | Syed, Micheal Clifford | Kevin Lee | Global Markets |  | 2001-09-18 | 2001-09-18 | COMPLETED
2001-09-24 |  | TAGG | Func | bridge | I have noticed a recurring problem with EOL that has just started occuring in the last week. What is happening is when someone trades with John Disturnal's NGMR-AECO/C options online, TAGG is populating a 0 in the basis field, which should be there. I have been erasing that value, and also going into the Details screen and erasing it there. However, the value returns even after I save and exit the trade. And then it causes a Translation Error screen to keep appearing on my TAGG screen with these deal numbers. The two deals that are having this problem are Y35763 (legs 1,2,3,4) There is another deal today (Y50858) which I also tried to correct but it is already starting to error as well. | EOL | 2001-09-24 | Sanjeev and Oscar | Chad Brad | EOL |  | 2001-09-24 | 2001-09-24 | COMPLETED | cause of the problem was the EOL.
2001-09-26 |  | ERMS | Func | Database | Todd Hall would like us to get zinc curves from the rmsprod database and insert it into egsprod database because he needs these curves loaded everyday. | Todd Hall | 2001-09-24 | Francis | Todd Hall | Todd Hall |  | 2001-09-25 | 2001-09-26 | COMPLETED
2001-09-28 | G50 | ERMS | func | Report | Speed up of the canadian gas daily report because it is taking two hours to run.The reason why this query is too slow is because egs_sensitivities and egs_price basis are both views. Joining these two views together will be very slow. Egs_price_book has 8 table joins and egs_sensitivites has three table joins Solution: re-write the query so that it uses the minimum amount of table joins using base tables. You do not need all the 8 tables from egs_price_book. You only need egs_price_basis, egs_price_basis_dtls, and egs_common_cmd_uom_convs. same thing goes with egs_sensitivities. | Global Products | 2001-09-25 | Dan, Francis | [5 empty] | COMPLETED | Cause of the problem was by an improper join to the two views egs_sensitivities and egs_price_book on the /prod/egs-home/clc/bin/canada_gd_pos.sql query that creates the temp table for the report. I added a one line join to the query which should greatly speed it up. How fast? I don't know but it should NOT run for 3 to 5 hours anymore. My quesstimate should be less than 10 minutes.
2001-10-08 | EOL1 | Tagg | Func | Excel | I work with Marc on EnronOnline. I'm just getting started in helping him to define the attributes we need to create a valuable database for trend analysis. We'd actually like to start with gas. Can you send me a dump of the gas deals similar to the power dump you sent Marc? | EOL | 2001-09-19 | Mike Clifford | Brad Harris |  | medium | 2001-09-24 |  | COMPLETED | Mike was able to give everything that user needs
2001-10-19 | NG83 | ERMSHPL | Func | curves | Users in AEP would like us to extend the interest rates INTNS and INT up to end of the year next year. | AEP | 2001-10-11 | Dan, Francis | Russll Long | Natural Gas |  |  |  | COMPLETED
2001-10-14 | NG78 | ERMS | Tech | Excel | I have attached a copy of an Excel spreadsheet that downloads Total Sensitivities for a Post-ID and was wondering whether it would be possible to amend this to give the detail by product type as seen on the print-out ? This would be particularly useful for verifying the greek changes by product, particularly Exchange & OTC options. | ENA | 2001-09-26 | Syed | Jason Harding | Natural Gas |  |  |  | In Test | a volley of emails between jason and syed
2001-10-10 | NG73 | ERMS | Func | PortCalc | Enable volatility skew for non-NYMEX NG options | ENA | 2001-09-17 | Jennifer | Bradley Jones | Natural Gas |  | 2001-09-17 |  | COMPLETED
2001-10-10 | NG74 | ERMS | Func | PortCalc | Enable volatility skew for NGGJ options | ENA | 2001-09-17 | Jennifer | Chad Bruce | Natural Gas |  | 2001-09-17 |  | COMPLETED
2001-10-22 |  | TAGG | Tech | Request for Info | would like to see all deals that was done this year from jan-2001 for COAL. This is a one time deal that is to be given to him in Excel. Contact Jae for the columns that he needs. He justs wants deal information. |  |  | Syed | Jae Cho ext: 3-1872 |  |  |  | 2001-10-22 | COMPLETED | all information requested has been given

## Common
Priority | Task ID | System | Tech/ Func | Application / Project | Function/Purpose | Business Unit | Request Date | Key IT Contacts / Developers | Key Bus. Contacts | Commodity | Scope | Start Date | Estimated Complete Date | Status | Comments / Key Issues
H | 68 | ERMS Deal Capture | Func | Deal Capture | Link between NYMEX reference on Deal Capture screen to the Option Expiration Date on the Detail Screen. ( Task # 13) |  | 2000-08-22 | Oscar, Sanjeev | Dutch Quigley/Everyone | Applies to ALL |  |  |  | Needs to be started | Needs to be discussed at bi-weeky meeting as Dutch Quigley is no longer in this organization (04/18/01 -TD)
H | 72 | ERMS | Func | PortCalc | Improve option valuation precision in PortCalc (Task # 19) | ENA Global Products | 2000-08-24 | Sandy | Stinson Gibner | Applies to ALL |  | 2001-07-16 | 2001-09-12 | Pending | With the new "Options Manager" available in EOL the week of Jul 16, this project becomes High priority
H | 134 | ERMS | Func |  | Enhance curve granularity so that prices can be added for days and weeks as opposed to only months (helps capture intramonth differences) (Task# 15) |  | 2000-10-12 | Dave | Everyone | Applies to ALL |  |  |  | Needs to be started
M | 58 | ERMS TAGG | Func | PortCalc Exchange | Correctly liquidate futures activity daily. Liquidate transactions as they actualize rather than at month end such as futures when positions are closed out or when deals finish pricing or when physical volumes updated rather than at month end (Task # 18) | ENA Global Products | 2000-07-27 | Sandy | Everyone | Applies to ALL |  | 2001-07-02 | 2001-07-13 | Needs to be started
| 41 | CPR ERMS Unify | Func | Operational Analysis Improvements | Move OA data out of Access to Oracle (Task # 7) -Improve timeliness of the process (current process takes 3 to 5 hours to accumulate) -Need ability to do OA Analysis at Deal level; new reporting requirements | ENA | 2000-07-27 | Nagesh, Zhiyong Unify | Risk Management VM/Logistics Settlements | Applies to ALL |  | 2000-10-02 | 2001-12-31 | On Hold | Leslie Reeves' group is going to looking into the issues before proceeded by us.
| 59 | ERMS | Func | PortCalc | Redo discount logic to discount to correct payment date for Reserve PortCalc | ALL | 2001-06-21 | Jeremy, Jennifer | Sheila Glover, Chris Abel, Jeff Gossett, Todd Hall | Applies to ALL |  | 2001-06-25 | 2001-08-28 | On Hold | See ERMS discounting document for detailed timeline and project plan
| 75 | TAGG ERMS | Tech | Database | Modify TAGG/ERMS to use TIBCO to access Global data | ENA Global Products |  | Oscar | Jun Lu | Applies to ALL |  |  |  | Pending
| 116 | ERMS | Func | Database | Change from using short counterparty name to using duns_link_id in ERMS ( Task # 21) | ENA Global Products | 2000-10-02 | Sanjeev, Oscar |  | Applies to ALL |  | 2001-06-01 | 2001-07-30 | Pending
| 117 | TAGG | Func | Deal Capture | Change from using short to long counterparty name, and remove inactive counterparties (Task # 22) | ENA Global Products | 2000-09-26 | Oscar, Sanjeev | Corey Hollander | Applies to ALL |  | 2001-06-01 | 2001-07-30 | In Development | Need to test together with task #57.
| C13 | ERMS | Func | Price Down Load | Get exchange futures and option prices from MKM. Upload and download curves to/from MKM/Rate Server and insert into our database (Task # 06) | ENA Global Products |  | Cecilia | Willie Harrell | Applies to ALL |  |  |  | Development COMPLETED. MKM has issues. | there is no more development on this project. We have already done our part. We are waiting for MKM. They have issues.
| C16 | TAGG | Func | PortCalc | Rollout copy postid application as part of theTAGG group of applications (Task # 08) | ENA | 2001-02-23 | Sanjeev | Brian Kristjansen | Applies to ALL |  | 2001-03-01 | 2001-06-30 | In Development | 50% done. More changes being done.
| C17 | TAGG ERMS | Tech | Price download | Telerate being replaced by TIBCO (Task# 16) | ENA | 2001-02-23 | Cecilia | Danielle Marcinkowski | Applies to ALL |  |  |  | Pending
| C22 | TAGG ERMS | Tech | All | Running out of available deal numbers (Task # 23) | ENA Global Products |  | Sanjeev, Oscar | Everyone | Applies to ALL |  | 2001-05-25 |  | In progress
| C24 | TAGG ERMS | Func | MetaCalc PortCalc | Add org. region code as an input field to MetaCalc and PortCalc (Task #25) | ENA Global Products | 2001-05-01 | Sanjeev, Truong, Dave | Jeremy Wong | Applies to ALL |  |  |  | New Request
| C26 | TAGG | Tech | Deal Clearing | Restore archived confirmations (Task #27) | ENA Global Products | 2001-04-25 | Truong | Ron Nolte | Applies to ALL |  |  |  | New Request
| C29 | ERMS | Func | PortCalc | Improve ERMS valuation feed to RisktRAC | ALL |  | Jeremy, Dave | Ramesh Ganapathy | Applies to ALL |  | 2001-10-05 |  | In Development | See ERMS Feed to Downstream Risk Systems document for project plan
| C33 | ERMS | Func | Reporting | Move all of our existing oracle 6i reports over to the web | ALL | 2001-07-27 | Kirti, Francis | ALL | Applies to ALL |  |  |  | New Request | On-Hold until we have all reports on the Client-server running
| C34 | ERMS | Func | Portcalc screen | modification of the port_calc screen rsr0028 so that the two where clause (Regular where clause and the Gas Daily where clause) is combined into one where clause. This change was requested by Zhiyong Wei so that the port_calc can also be done from metacalc | ALL | 2001-09-05 | Farid, Francis | ALL | Applies to ALL |  |  |  | In Development
| C35 | ERMS | BUG | pub posting | I found a SEVERE problem with the rsr0072 form that is use for the pub_posting. If you enter a wrong date on the expiration date on top of the screen. The form will generate an endless loop of error about the date and you can not exit out of the form anymore. This happens on the UNIX version as well at the PC version. | ALL | 2001-10-01 | Mustafa, Francis | ALL | Applies to ALL |  |  |  | In Development
| C36 | TAGG | Func | deal entry | I work in confirmations and I was wondering if we could input a special window in Tagg deal Capture. This window would help with a human error situation. It would pop up when entering a trade that had the same terms as the month it is done in. For example today's trade date is Oct 11 and the trader enters the trade for the month of Oct 01. This is an impossible trade being that it is already the 11th. But it should also note that a trade term for Oct 12-31 is a good deal. I have come across these types of trades and I was hoping this idea could helpful to many of us. If this idea is unclear or if you have any questions please let me know. | Deal Compliance | 2001-10-11 | Sanjeev, Francis | Kristine Best | Applies to ALL |  |  |  | New Request
| NG81 | TAGG | Tech |  | Develop a new feed from TAGG to provide the correct "Price-to-the-Customer" for future months deals to the Credit Risk gorup. | ENA |  | Francis, Felicia | Debbie Brackett, Sue Vasan |  |  | 2001-10-08 | 2001-11-09 | In Development | See Statement of Work on "Pricing Info for Credit Aggregation" project.

## Global Mkt
Priority | Task ID | System | Tech/ Func | Application / Project | Function/Purpose | Business Unit | Request Date | Key IT Contacts / Developers | Key Bus. Contacts | Commodity | Scope | Start Date | Estimated Complete Date | Status | Comments / Key Issues
C | 133 | ERMS | func | Report | Report changes for deals at movement level (Task #18) | Global Products | 2000-10-12 | shouan, cecilia | Everyone | Global Markets |  | 2000-12-28 | 2001-05-17 | On Hold | 100% coding done. Need users to populate data into tables and test reports.
H | G02 | ERMS | Func | PortCalc | Event-driven pricing calculations (eg. 5-d BOL averaging on weekends, holidays, etc.) ( #53) | Global Products | 2000-10-16 | Jennifer Song | Kevin Sweeney | Global Markets |  |  |  | On Hold
M | G03 | ERMS | Func | PortCalc | Enhance option sensitivity reporting for greeks so that users can specify different movements for gamma in P/L and for vega in both position and P/L reporting similar to gamma position reporting today ( #47) | Global Products | 2000-09-27 | Jennifer Song | Mark Fondren | Global Markets |  |  |  | On Hold | This request was found in old GM list. Entered into TAGG/ERMS list 11/29/00.
| 13 | ERMS | Func | PortCalc | Modify averaging logic to handle monthly in addition to daily averaging for Global Products ( #52) | Global Products | 2000-07-27 | Jennifer Song | Chris Connelly | Global Markets |  | 2001-05-14 | 2001-07-06 | On hold, per Kevin Sweeney (4/25/01) | #13, 99, and G2 are resource dependent on completion of #131, 79, 71. Estimate 8 weeks total for 13, 99, and G2.
| 71 | TAGG ERMS | Func | PortCalc | Add Floating Fixed Price logic to Financial Forwards in addition to Physical Forwards in PortCalc (Task # 44) | Global Products | 2000-08-09 | Cecilia | Mark Fondren | Global Markets |  | 2001-04-23 | 2001-05-11 | On Hold | Put on hold, per Kevin Sweeney (4/25/01).
| 74 | TAGG ERMS | Func | Deal Capture Translator PortCalc | Restructure portfolio/book definition in TAGG/ERMS, by region, product and desk, and business unit (#45) | Global Products | 2000-08-28 | Alex, Francis | Eric Groves | Global Markets |  | 2001-03-19 | 2001-05-14 | On hold, per Kevin Sweeney (4/25/01). | Prelim est. 8 weeks if we just change the mapping structure, the security, the GUI and PortCalc pieces to reflect this, with the assumption that OLAP reporting tools will be used by Global Markets to create their own reports. PortCalc piece est. 2 weeks, and dependent on resource completion of #13, 99, and G2 (scheduled on 4/30). Slicing, and dicing reporting
| 79 | ERMS | Func | PortCalc | Handling FX deals in ERMS properly for UK office ( #42) | Global Products | 2000-09-13 | Jennifer Song | Cindy Horn | Global Markets |  | 2001-04-02 | 2001-04-20 | On Hold | Put on hold, per Kevin Sweeney (4/25/01). Per Dimitri Taylor, project cancelled due to some work is underway from the FX group to provide them with the necessary information.
| 80 | TAGG ERMS | Func | Reports | Handling FX hedges in TAGG/ERMS ( #43) | Global Products | 2000-09-13 | Shouan | Cindy Horn | Global Markets |  | 2001-04-23 | 2001-05-11 | On hold, per Kevin Sweeney (4/25/01). | Need more definitions and researches to bring the FX reporting together. Related to #79.
| 81 | ERMS | Func | PortCalc | Deal Costs Reporting. Include Brokerage and other costs in P&L such as freight, storage, inspection, brokerage so that they are part of top page and P/L explanatories ( #36) | Global Products | 2000-09-13 | Cecilia, Francis | Cindy Horn | Global Markets |  | 2001-01-08 | 2001-05-17 | On hold, per Kevin Sweeney (4/25/01). | 100% coding done. Cecilia will write a script to run reports for user testing purpose.
| G13 | TAGG ERMS | Func | Portcalc, Translator, Reports | Capture ThunderBall info in TAGG and bring Pub Code to Movement Level ( # 49) | Global Products | 2001-02-13 | Cecilia, Jennifer | Kevin Sweeney | Global Markets |  | 2001-03-12 | 2001-05-11 | On Hold | Per team discussion with Kevin on 05/08/01, the PubCodes at Deal movement is running into a big design issue during analysis. This will take a big effort to implement. Kevin will be checking with Dana Docherty on Global Valuation progress/timeline and get back to TAGG/ERMS on whether to proceed with the effort.
| G14 | TAGG | Func | MetaCalc | Allow setting of Position by Hedge Month flag by post id instead of meta id ( # 50) | Global Products |  | Sanjeev, Truong | Joel Bennett | Global Markets |  | 2001-10-29 |  | Needs to be started
| G23 | TAGG ERMS | Func | Database | Move S02 and NOX deals from EnPower back to TAGG/ERMS (Task #55) | Global Products | 2001-05-01 | Sanjeev | Frank Prejean | Global Markets |  | 2001-05-08 |  | In Development | Waiting for Frank Prejean's answer
| G41.1 | TAGG ERMS | Func | Reports | Regarding the changes you had requested for RSR0501 (Forwards Detail) and RSXEOCE3 (Exchange Options) reports, here are our thoughts: 1. In the PortCalc screen, you can change the "Output UOM" and "Output Currency" fields to pull the price in gallons and the volume in barrels - this way, the report that you run for your Post ID will reflect the changes immediately. 2. If the option above is not befitting your requirements, then we'll need to hard-code the specified changes in ERMS for EGM, and that will take up longer time. | Global Products | 2001-06-18 | Farid, Francis | John Swinney | Global Markets |  | 2001-06-18 |  | In Development
| G41.2 | TAGG ERMS | Func | Reports | Same request but for the RSR0501 (Forward Detail) report only. | Global Products |  | Farid, Francis | John Swinney | Global Markets |  | 2001-06-18 |  | In Development
| G47 | TAGG | func | MetaCalc | Allow setting of Use Optlib for Exchange flag in MetaCalc by post id | Global Products | 2001-07-24 | Sanjeev, Truong | Stewart Range | Global Markets |  |  |  | New Request
| G48 | ERMS | func | PortCalc | Enable volatility skew in PortCalc for EGM commodities | Global Products | 2001-08-20 | Jennifer | Stewart Range | Global Markets |  |  |  | In Development | EGM has a different skew table format versus the current table used for NG
| G49 | ERMS | Func | Excel | Have the ability for Stewart to enter the post_ids into the Excel basis_liquidation download Excel sheet rather then use the forms4.5 screen. | Global Products | 2001-07-06 | Sanjesh, Francis | Stewart Range | Global Markets |  | 2001-07-27 |  | In Development

## Nat Gas
Priority | Task ID | System | Tech/ Func | Application / Project | Function/Purpose | Business Unit | Request Date | Key IT Contacts / Developers | Key Bus. Contacts | Commodity | Scope | Start Date | Estimated Complete Date | Status | Comments / Key Issues
| 31 | TAGG | Func | MetaCalc | Enhance PowerBuilder front-end to enable gas daily calcs, etc. ( Task # 04) | ENA |  | Dominique, Sanjeev | Jeff Gossett | Natural Gas |  | 2001-08-14 |  | In Development
H | 70 | ERMS | Func | PortCalc | Basis/Index Rolloff by Pub. Code Mapping (Task #02) | ENA | 2000-08-20 | Dave | Brian Gillis | Natural Gas |  | 2001-02-01 | 2001-04-06 | Completed | Dave sent test to Brian Gillis, Jeff Gossett. Leave item here if need to revisit together with Price/Basis move into TAGG/ERMS
M | 62 | CPR, ERMS, Sitara | Func | Valuation | Imbalance Valuation in CPR using actual transport balances from Unify (Task #03) | ENA | 2000-07-27 | Dave Wei | Jeff Gossett | Natural Gas |  |  |  | New Request | Need more info
| 118 | ERMS | Func | PortCalc | Enhance PortCalc to provide implicit positions for options, in addition to swaps (on TopPage report also) (Task #05) | ENA | 2000-09-29 | Dave Wei | Brian Gillis | Natural Gas |  | 2001-10-01 | 2001-12-31 | Pending | Working on understanding the swaps part
| NG10 | TAGG | Func | Deal Capture | Bianca's Broker Issue. Enhance logic in TAGG Deal Capture to verify that there are not two rows in PINSTR_CP_DEAL_CD with the same deal number for which the broker on the instr is the same. (Task # 01) | ENA | 2000-12-13 | Oscar, Francis | Bianca Ornelas | Natural Gas |  |  |  | Pending | Here's an example. A deal is created and the broker is EDF Mann. A clearing user calls the Broker and enters a broker deal number of 16576 into TAGG Deal Clearing. A second deal is created and the Broker is Gerald, Inc. The same broker deal number is put into Tagg Deal Clearing, 16576. Then someone discovers that the Broker on second deal is incorrect and changes the Broker in TAGG Deal Capture to EDF Mann. Now there are two deals brokered though EDF Mann with the same deal number.
| NG20 | TAGG/ERMS | Tech |  | Restructuring Canada Books ( Task #10) | ENA | 2001-02-08 | Thu Dang and Jeremy | Kathy Reeves | Natural Gas |  |  |  | On Hold | In analysis phase. Alternative being evaluated for consensus from all stakeholders. Waiting for Chris Abel will talk to Zhiyong and business users.
| NG26 | TAGG/ERMS | Func | PortCalc | Index Roll-In ( Task #09) | ENA | 2001-02-15 | Dave | Jeff Gossett | Natural Gas |  |  |  | On Hold | Related to the Price/Basis Split Alternative project being evaluated.
| NG34 | TAGG/ERMS | Func | PortCalc | Allow both consolidated price/basis and gas daily PortCalcs in the same book (Task #12) | ENA | 2001-03-12 | Dave | Kathy Reeves | Natural Gas |  |  |  | Pending
| NG39 | TAGG | Func | MetaCalc | Work with Calgary to test running MetaCalc there (Task #15) | ENA | 2001-02-23 | Sanjeev | Brian Kristjansen | Natural Gas |  |  |  | Pending
| NG43 | ERMS | Func | PortCalc | Use avg FX rate for the month for liquidating deals, instead of the spot rate (Task #19) | ENA |  | Dave | Kathy Reeves | Natural Gas |  |  |  | New Request
| NG59 | ERMS | Func | Option Grid | Automate daily run of Option Grid for the NG options (Mike Maggi's) book | ENA |  | Sanjeev, Oscar | John Griffith | Natural Gas |  |  |  | In Test | I have modified the Option Grid Application and the process is mostly automated. Please let me know when you have time to test it. I will explain you the same time how it is going to work. I will be happy to implement any new suggestions you may have.
| NG61 | ERMS | Tech | toppage | canadian top page repor shows large amount of value even when there are no rows for the post id. Some values are not cleared by the C program | ENA | 2001-09-17 | Dominique, Francis | Albert Luc | Natural Gas |  | 9/17.2001 |  | In Test
| NG62 | TAGG | Tech | Deal Capture | Said that on the deal entry screen for basis option normally the pubcode 1 is NX1 and pubcode 2 is IF-<something> Inside ferc. He said that the selection on pubcodes for 1 and 2 is only NX1D and there is no NX1 or NX2 or NX3. | ENA | 2001-09-25 | Oscar, Sanjeev, Francis | Bradley Jones | Natural Gas |  | 2001-09-25 |  | IN TEST and DEVEL | Item number 1 has been put to stage and test so that NX1,2,3 appears on the tagg deal entry. Item 2 is currently being looked at by sanjeev
| NG75 | ERMS | Func | PortCalc | Replace Gas Daily expert clause with the regular expert clause | ENA | 2001-09-24 | Jennifer | Jeff Gossett | Natural Gas |  | 2001-09-25 |  | In Development
| NG76 | ERMS | Tech | PortCalc | Speed up Gas Daily "Y" calc. - Research Group's Ostrip model is slow | ENA | 2001-09-27 | Jennifer | Errol McLaughlin | Natural Gas |  | 2001-10-03 |  | In Development
| NG77 | ERMS | Tech | PortCalc | Fix bug in Canadian Implicit Position code | ENA | 2001-09-27 | Jennifer | Carlos Torres | Natural Gas |  | 2001-09-28 |  | In Test
| NG79 | ERMS | Tech | Excel | would like to pull in volatily into a spreadsheet for put and call that they have in the book by their respective strike price for the heating book and the gas book. | ENA | 2001-10-04 |  | Errol McLaughlin | Natural Gas |  | 2001-10-22 |  | In Development
| NG80 | ERMS | Func | Reporting | Problem with the current month P&L Effect Report. Report number rsr0241 was originally written in Oracle report writer 1.1. The problem occurs when he runs the report using a post_id that has portfolio_type_cd of "[" or book_type_cd of "[". The UNIX operating system takes the parameter [ as a UNIX command and the report does not come out. We need to fix the problem by creating a c-shell script to run the report with quotes between the portfolio_type_cd and book_type_cd. Also, we need to modify the form that calls the report and change it so that it runs the c-shell script. | ENA | 2001-10-04 | Farid, Francis | Brian Gillis | Natural Gas |  | 2001-10-17 |  | In Development
| NG84 | ERMS | Tech | Reporting | Per our meeting last week, we are requesting that a report option be set-up for pub_posting. The screen no. in ERMS is rsr0072. We would like to capture publication prices posted in here, including Gas Daily, Inside FERC, Natural Gas Weekly, Natural Gas Intelligence, Canadian Gas Price Reporter, some NX & PWR prices, and our only variables will be the BookType, CurveType, and Exp Date. If you need a listing of some of the pub_codes, I can provide that. Please let me know what other information is needed from our group. | ENA | 2001-10-17 | Sanjeev, Francis | Kelly@5.8491 | Natural Gas |  |  |  | new project
| CPR2 | CPR | Tech |  | CPR reports through the web | ENA |  | Don Adam, Felicia | Russ Severson | Natural Gas |  | 2001-10-15 |  | In development | Prototype will be rolled out to users in early November.
|  | CPR | Tech |  | CPR database table partitioning | ENA |  | Alex, Francis, Felicia | Russ Severson | Natural Gas |  | 2001-10-12 |  | In development

## Industrial Markets
Priority | Task ID | System | Tech/ Func | Application / Project | Function/Purpose | Business Unit | Request Date | Key IT Contacts / Developers | Key Bus. Contacts | Commodity | Scope | Start Date | Estimated Complete Date | Status | Comments / Key Issues
| IM04 | TAGG | Func | Settlement | Migrate from manual process to using TAGG Settlement Report application | Industrial Markets |  | Truong | Kris Hanson | IM - Pulp, Paper, Lumber, and Steel |  | 2001-01-16 | 2001-04-20 | In Test | Key Bus. Contacts change from Tracy Beardmore to Kris Hanson
| IM08 | TAGG | Func | Database | Update GCC product codes in TAGG (Task #7) | Industrial Markets | 2001-02-23 | Cecilia Cheung | Stiles Anderson | IM - Pulp, Paper, Lumber, and Steel |  | 2001-02-26 | 2001-04-13 | On Hold | Waiting for codes to put in
| IM12 | TAGG ERMS | Func | Database | Change commodity code from NW45 to NWSP for Paper deals (Task #7) | Industrial Markets | 2001-04-26 | Sanjeev, Cecilia | Shari Mao | IM - Pulp, Paper, Lumber, and Steel |  |  |  | On Hold | Waiting for some clarifications from user.