## OCT 3
Project No. 22834, Implementation Activities Related to Retail Competition Pilot Projects
October 3, 2001 Status Report
|  |  | AEP-CPL | AEP-WTU | Reliant TDSP | TNMP TDSP | TXU TDSP
Enron Energy Services
| Pre-8/30 Backlog | 1a. |  |  |  |  | 9
|  | 1b. |  |  |  |  | 6
| Switching (814_05, 867_02) | 2a. |  |  |  |  | 70%
|  | 2b. |  |  |  |  | 70%
| Intial Meter Read (867_04) | 3a. |  |  |  |  | 10%
|  | 3b. |  |  |  |  | 17%
| Monthly Usage (867_03) | 4a. |  |  |  |  | N/A
|  | 4b. |  |  |  |  | N/A
| TDSP to CR Invoice (810_02) | 5a. |  |  |  |  | N/A
|  | 5b. |  |  |  |  | N/A

## Justification
ESI ID | 814-01 Sent | 814-05 Received | 867-02 Received | 867-04 Received | Initial Meter Read
10443720003625902 | 2001-08-29 | 2001-09-07 | 2001-09-09 |  | 2001-10-05
10443720003630335 | 2001-08-29 | 2001-09-07 | 2001-09-09 |  | 2001-10-04
10443720006522263 | 2001-08-29 | 2001-09-07 |  |  | 2001-10-04
10443720006871343 | 2001-08-29 | 2001-09-07 | 2001-09-09 |  | 2001-09-27
10443720007738300 | 2001-08-29 | 2001-09-07 | 2001-09-09 |  | 2001-10-05
10443720004233186 | 2001-08-30 | 2001-09-07 | 2001-09-09 |  | 2001-09-28
10443720005335270 | 2001-08-30 | 2001-09-07 |  |  | 2001-10-08
10443720003001397 | 2001-08-30 | 2001-09-07 |  |  | 2001-09-24
10443720004431331 | 2001-08-30 | 2001-09-07 | 2001-09-09 | 2001-09-14 | 2001-09-12
10443720005335301 | 2001-08-30 | 2001-09-07 | 2001-09-09 |  | 2001-10-08