## North Anna 01
Owner Name | Dominion Virginia Power
Station Name | North Anna Nuclear Power Station
Unit Name | North Anna 01
NERC Region | SERC
State | VA
Fuel Type | Nuclear
Capacity | 980 MW
Start Date | 2001-09-08
End Date | 2001-10-11
Prv. Start Date | 2001-09-08
Prv. End Date | 2001-10-11
Comments | We have spoken to our contact at the plant. The unit went in to start up yesterday and they are online today at 50% and moving up.
SIC | 4911
Plant ID | 1012052
Unit ID | 1006140
Outage ID | 11071

## Blackstone 01
Owner Name | American National Power Company
Station Name | Blackstone Power Plant
Unit Name | Unit 01 CT / HRSG
NERC Region | NPCC
State | TX
Fuel Type | Natural Gas
Capacity | 290 MW
Start Date | 2001-09-01
End Date | 2001-10-15
Prv. Start Date | 2001-09-01
Prv. End Date | 2001-10-12
Comments | Design Issues
SIC | 4931
Plant ID | 1033441
Unit ID | 1012822
Outage ID | 18240

## Riverbend 01
Owner Name | Entergy Gulf States Inc.
Station Name | Riverbend Nuclear Power Station
Unit Name | River Bend 01
NERC Region | SERC
State | LA
Fuel Type | Nuclear
Capacity | 1,036 MW
Start Date | 2001-09-23
End Date | 2001-10-10
Prv. Start Date | 2001-09-23
Prv. End Date | 2001-11-04
Comments | Refueling. Unit connected to the grid last night, is currently at 20% power, still doing turbine testing. Hoping to be at full power by Sunday.
SIC | 4911
Plant ID | 1004408
Unit ID | 1004548
Outage ID | 7495

## Palo Verde 02 R7
Owner Name | Arizona Public Service Company
Station Name | Palo Verde Nuclear Power Station
Unit Name | Palo Verde 02 R7
NERC Region | WSCC
State | AZ
Fuel Type | Nuclear
Capacity | 1403 MW
Start Date | 2001-10-11
End Date | 2001-11-09
Prv. Start Date | 2001-10-11
Prv. End Date | 2001-10-14
Comments | Replacement of control element asseblies.
SIC | 4911
Plant ID | 1015283
Unit ID | 10078741
Outage ID | 18635

## Cromby 01
Owner Name | Exelon Power
Station Name | Cromby Power Station
Unit Name | Unit 01
NERC Region | MAAC
State | PA
Fuel Type | Coal
Capacity | 188 MW
Start Date | 2001-10-26
End Date | 2001-11-09
Prv. Start Date | 2001-10-05
Prv. End Date | 2001-10-19
Comments | Boiler and Superheater work
SIC | 4931
Plant ID | 1514989
Unit ID | 1005109
Outage ID | 17466

## San Juan 03
Owner Name | Public Service Company of New Mexico
Station Name | San Juan Generating Station
Unit Name | San Juan 03
NERC Region | WSCC
State | NW
Fuel Type | Coal
Capacity | 534 MW
Start Date | 2001-10-10
End Date | 2001-10-11
Prv. Start Date | 2001-10-10
Prv. End Date | 10/12/1/01
Comments | Tube leak was not as extensive as first thought.
SIC | 4911
Plant ID | 1016385
Unit ID | 1007771
Outage ID | 18630

## Sommers 02
Owner Name | San Antonio City Public Service Board
Station Name | O W Sommers Power Station
Unit Name | Sommers 02
NERC Region | ERCOT
State | TX
Fuel Type | Natural Gas
Capacity | 446 MW
Start Date | 2001-10-12
End Date | 2001-12-06
Prv. Start Date | 2001-10-05
Prv. End Date | 2001-11-29
Comments | Control Upgrade
SIC | 4911
Plant ID | 1002208
Unit ID | 1005825
Outage ID | 15811