## Sheet1
For Internal Use Only
Interstate Pipeline Capacity to California Report
Revised: 08/17/01
| Date: |  |  |  |  | Contract
Pipeline/ | Announced (A) | Docket | Capacity |  | Estimated | Status | Projected
Project | Filed (F) | No. | (Mmcf/d) | Del. Pt. | Costs (Millions) | (Mmcf/d) | In-Service Date | Status/Comments
Transwestern Pipeline Co. | 03/29/01 (F) | CP01-115 | 150 | Topock, Calpine & | 93.3 | 106.7 | 2002-06-01 | Accepted 7/16 Order on 7/19/01. Filed Affirmative Statement on 7/27/01.
Red Rocks Expansion |  |  |  | Needles
Transwestern Pipeline Co. | 08/08/01 (A) | N/A | 780 | Phoenix & CA |  |  | 2004-05-01 | Open Season ends 8/30/01
Sun Devil Expansion
El Paso Line No. 2000 | 07/31/00 (F) | CP00-422-000 | 230 | Ehrenberg | 153.1 | None | 2001-08-01 | Certificate Issued 5/7/01. On 7/19/01 received approval to clean line.
| 03/15/01 (F) | CP00-422-001
PG&E GT NW | 04/02/0l (F) | CP01-141 | 211 | Malin | 122 | 200 | Ph. I Nov-01 | Order approving project issued on 8/6/01.
2002 Expansion | [6 empty] | Ph. II Sum. 02
Questar - Southern Trails | 01/19/99 (F) | CP99-163-000 | East Zone 87.5 | Topock | 155 |  | 2001-12-01 | Received Commission Order 7/28/00. Updated Env. Plan filed on 7/2/01.
|  | CP99-163-001 | West Zone 120 |  |  |  | 2002-07-01
Kern River 2002 | 11/15/00 (F) | CP01-31-000 | 124 | Wheeler Ridge | 80 |  | 2002-05-01 | Amended Certificate issued 7/26/01 to add emergency capacity on a perm basis.
| 05/11/00 (F) | CP01-31-001
North Baja Pipeline | 11/1/00 (F) | CP01-22 | 500 | Ehrenberg to | 213 |  | 2002-09-01 | FERC issued a Draft EA finding the project to have limited adverse impact.
Ogilby, MX
Otay Mesa Gen. Co. | 4/6/01 (F) | CP01-145 | 110 | MX/CA Border | N/A |  | 2002-09-01 | FERC issued a Presidential Permit to import gas.
Kern River | 7/18/01(F) | CP01-405 | 282 | Victorville | 28.9 | 282 | 2002-09-01 | Deliveries will be to the High Dessert Power Project. Interventions are due 8/17/01.
High Dessert Lateral
Kern River | 08/01/01 (F) | CP01-422 | 885 | CA Border | 1.26 Billion | 885 | 2003-05-01 | Requested PD by 2/1/02 & Full Cert. Order by 5/1/02.
2003 Expansion
Kern River--Kramer | 6/15/01 (A) | N/A | 500 | Kramer Junc. | N/A |  | 2001-12-01 | New meter station if 2002 -2003 expansion shippers move to Kramer Junction Del. Point from Wheeler Ridge.
Junction Interconnect
Kinder-Morgan/ | 05/03/01 (A) | N/A | Ph. I 750 | Needles | Ph. I $624 | Ph. I 400 | Summer 2003 | Open season ended June 1. Rec'd requests for 1 Bcf in Ph. I and l.5 Bcf in Ph. II.
Calpine-Sonoran Pipeline |  |  | Ph II 1000 |  | Ph. II $1.1 billion | Ph. II 500 | Yet TBD
El Paso Line 2000 | 07/09/01(A) | N/A | 320 | Ehrenberg | N/A | N/A | Mid-2003 | Open Season ends Aug. 2.
Power-up Expansion
PG&E GT NW | 05/07/01 (A) | N/A | 300-500 | Malin |  | N/A | 2003-11-01 | Open Season ended June 19, 2001. Rec'd binding agreements for 250MMcf/d.
2003 Expansion
CIG - Ruby Pipeline | 11/19/98 (A) | N/A | 750 | Northern Ca. & Wild Goose Storage. | N/A |  | Late-03 | Extended open season ended June 22.