## Turbine Allocation
LM 6000 Turbine Allocation
# | Turbine Unit # | Delivery Date | Project Name | Change Orders
1 | 308898 | 2000-07-08 | Enron South America | #3
2 | 308951 | 2000-07-26 | Enron South America | #3
3 | 308972 | 2000-08-15 | Enron South America | #3
4 | 308999 | 2000-07-09 | Enron South America | #3
5 | 309020 | 2000-07-10 | Enron South America | #3
6 | 309073 | 2000-07-21 | Enron South America | #3
7 | 309101 | 2000-07-26 | PSCO/Fountain Valley | #1 - Dual Fuel
8 | 309123 | 2000-08-15 | PSCO/Fountain Valley | #1 - Dual Fuel
9 | 309266 | 2000-08-19 | Austin
10 | 309547 | 2000-09-01 | Austin
11 | 309575 | 2000-09-06 | Austin
12 | 309578 | 2000-09-14 | Austin
13 | 309420 | 2000-09-21 | PSCO/Fountain Valley | #2
14 | 309505 | 2000-09-28 | PSCO/Fountain Valley | #2
15 | 309573 | 2000-10-25 | PSCO/Fountain Valley | #2
16 | 309601 | 2000-11-01 | PSCO/Fountain Valley | #2
17 | 309604 | 2000-11-13 | Coral Energy | #1 - Dual Fuel
18 | 309719 | 2000-11-20 | Coral Energy | #1 - Dual Fuel
19 | To be assigned | 2000-07-21 | Las Vegas
20 | To be assigned | 2000-07-24 | Las Vegas
21 | 309898 | 2001-02-01 | Enron South America | #3
22 | 309988 | 2001-01-27 | Enron South America | #3
23 | To be assigned | 2000-07-30 | Las Vegas
24 | To be assigned | 2000-09-01 | Las Vegas

## Change Orders
West LB Change Orders
Amount Invoiced
Change Order # | Project/Description | Total Amount | December, 2000
1 | Dual Fuel - Units 7,8, 17, 18 | 1120000 | 840000
2 | PSCO - Units 13,14,15,16 | 792000 | 594000
3 | ESA - Units 1-6, 21, 22 | 12649400 | 9487050
| TOTAL | 14561400 | 10921050

## Contract Payment Summary
LM 6000 Contract Payment Summary
| # of | Contract | Paid Through |  | Dec '00 Change
Project Name | Turbines | Value | October | Nov. Pymt. | Order Pymt. | 2001-01-15 | 2001-05-15 | 2001-07-30 | 2001-08-15 | TOTAL
Austin - Units 9 -12 | 4 | 56288000 | 42216000 | 14072000 | 0 | 0 |  |  |  | 56288000
PSCO - Units 13-16 | 4 | 56288000 | 42216000 | 7036000 | 594000 | 6442000 |  |  |  | 56288000
PSCO - Units 7 & 8 | 2 | 28144000 | 21108000 | 3518000 | 420000 | 4450000 |  |  |  | 29496000
Coral - Unit 17 | 1 | 14072000 | 10554000 | 1759000 | 210000 | 1829000 |  |  |  | 14352000
Coral - Unit 18 | 1 | 14072000 | 10554000 | 1759000 | 210000 | 1829000 |  |  |  | 14352000
ESA - Units 1-6 | 6 | 84432000 | 63324000 | 4221600 | 7115287.5 | 19258162.5 |  |  |  | 93919050
ESA - Units 21 & 22 | 2 | 28144000 | 22019200 | 3310400 | 2371762.5 | 3604987.5 |  |  |  | 31306350
LV Cogen - Units 19-20 & 23-24 | 4 | 56288000 | 5628800 | 0 | 0 | 0 | 16886400 | 16886400 | 16886400 | 56288000
TOTAL | 24 | 337728000 | 217620000 | 35676000 | 10921050 | 37413150 | 16886400 | 16886400 | 16886400 | 352289400
1 Contract Value represents GE's allocation of the total costs of the 24 turbines and options D, I, J, and Y (excludes Change Orders).
Please note that although only 16 turbines have Option D, GE has split the cost over all 24 turbines.
2 Dec. '00 Change Order Payment represents 75% of the total amount due.