## Sheet1
Prepared by
Energy Operations
Updated: 3/29/01
AEP-HPL TRANSITION ISSUES *
System |  | Activity | Point Person | Point Person | Due Date
|  |  | Enron | AEP
Global Counterparty
| 1 | Web page development | Tommy Yanowski IT |  | 2001-04-30
| 2 | Procedures for counterparty updates | Bill Hare EO |  | 2001-04-15
| 3 | Amendment to Service Agreement | Tommy Yanowski IT |  | 2001-04-15
| 4 | Filtering Information in comments/notes | Bill Hare EO |  | 2001-04-15
| 5 | DUN's number for AEP-HPL | Sandi Braband LG/Mike Eiben EO |  | 2001-04-15
| 6 | Banking info from AEP |  | Steve Jackson/Jan with AEP | 2001-05-15
| 7 | Cross reference table for counterparty | Tommy Yanowski IT | Steve Jackson/Don Simpson | 2001-04-30
| 8 | Enron credit information on counterparty | Bill Hare EO/Tommy Yanowski IT
Global Facilities
| 1 | Global facilities maintenance group split | Mike Eiben EO/Sundar Chitradurga IT |  | 2001-04-30
| 2 | Resolve new pipeline question | Mike Eiben EO/Matt Pena IT |  | 2001-04-15
Global Contracts
| 1 | Script to copy contract data | Cheryl Dudley EO |  | 2001-03-20
| 2 | Contracts being transferred | George Weissman PS |  | 2001-04-15
| 3 | Contract to be terminated before close | George Weissman PS |  | 2001-04-15
| 4 | Contracts to be terminated after close | George Weissman PS |  | 2001-04-15
Global Rates
| 1 | Cross reference table for rates | Tommy Yanowski IT | Don Simpson | 2001-04-30
* This document was conceived by Bob Hall
Key: | IT Information Services |  |  | with the intent to follow the life of a
| EO Energy Operations |  |  | transaction from system to system in
| LG Legal |  |  | order to identify tasks to be completed
| PS Producers Services |  |  | before AEP fully utilizes our systems.
Deal Entry
| 1 | Bridge from AEP trade blotter to Sitara | Tommy Yanowski IT | Don Simpson | 2001-04-30
| 2 | Bridge Error report |  | Don Simpson
| 3 | New Desks created in Sitara | Russ Severson EO |  | 2001-04-30
| 4 | Base Gas bridge and updates | Tommy Yanowski IT
| 5 | Separate copy of ERMS and CPR | Tommy Yanowski IT
Confirmations
| 1 | Will AEP use our confirmation system | Bob Hall EO | Steve Jackson | 2001-04-15
Scheduling/Allocations/Settlements
| 1 | Bridge Error-Feedback monitor training | Kathryn Bussell EO |  | 2001-05-01
| 2 | Bridge to Sitara not to trade blotter follow-up | Bob Hall EO | Steve Jackson | 2001-04-15
| 3 | Cash accounts amendment | Sandi Braband LG/Bob Hall EO |  | 2001-04-15
| 4 | Hard coding of Name for settlements | Chris Schomer IT |  | 2001-05-01
| 5 | HUB & EDI contracts after four months | Tommy Yanowski IT | Don Simpson | 2001-04-15
| 6 | Notice to counterparties on banking change | Bob Hall EO/Leslie Reeves EO | Steve Jackson | 2001-06-01
Transportation Rates
| 1 | HPL transport rates through Sitara only | Kim Olinger EO/Matt Pena IT |  | 2001-05-01
| 2 | Security for transport rates | Kim Olinger EO/Matt Pena IT |  | 2001-05-01
MISC
| 1 | Operational Data Web Site amendment to service agmt | Mike Eiben EO/Tommy Yanowski IT |  | 2001-05-01
| 2 | Tariff filing system amendment to service agmt | Mike Eiben EO/Tommy Yanowski IT |  | 2001-05-01
| 3 | A/R collections | Leslie Reeves EO |  | 2001-04-30