## summary
2000-11-10
MARINER ENERGY, INC.
APPENDIX
WEEKLY DRILLING AND COMPLETION SUMMARY
[7 empty] | PRESENT | PROPOSED
|  | PROSPECT | AREA | WELL | E/D | WI% | DEPTH | TD | COMMENT
| I. | WELLS CURRENTLY DRILLING
None to report.
| II. | WELLS REACHING TOTAL DEPTH, TESTING, OR TURNED TO SALES THIS WEEK
None to report.
| III. | WELLS ANTICIPATED TO SPUD WITHIN 90 DAYS
|  | East Breaks 832 |  | OCS-G #1 | E | 100% |  |  | Drill Key West 4th Quarter 2000.
(Key West)
|  | East Breaks 558 |  | OCS-G #1 | E | 33% |  |  | Expect well proposal from Anadarko to drill initial
|  | (LaSalle) | [6 empty] | well in 4th Quarter 2000.
|  | Garden Banks 367 |  | OCS-G | D | 42% |  |  | Spud in November 2000.
(Sidetrack well updip)
|  | Mississippi Canyon 323 |  | OCS-G # | E | 45% |  |  | Spud in December 2000.
(Crater Lake)
|  | Garden Banks 240 |  | OCS-G #2 | D | 33% |  |  | Spud in January 2001.
(Development Well)
|  | East Breaks 580 |  | OCS-G #1 | E | 50% |  |  | Spud in February 2001.
(Falcon)
| IV. | OTHER
None to report.