## Green Light
No. | Project Name | Project Type | Project Description | Status | Comments | Prty | Resources |  | Expected Benefits
[7 empty] | Business | IT
| Data Validation | [5 empty] | TBD
| Validate current RiskTrac configuration |  | Portfolio clean-up (verify there are no duplicates, that all positions are being captured) Re-design hierarchy structure for easier maintenance Verify usage of other root portfolios (AGG_CREDIT, Discounting, etc) Check curve mappings | Inception |  | High | Burton / Nancy | Ramesh's team | - Ensures accurate position and VaR reporting - Eliminate entries in multiple portfolios - Promotes flexibility when moving portfolios (due to trader movements, DPR changes, etc)
| Enhance exception reporting across systems and processes |  | - Officialization loads - VaR diagnostic report - business rules around exceptions (eg. Materiality) | Team to be identified | add timestamp / Credit columns in Active/Inactive | High | Gary | Ramesh's team | - Ensures completeness - Ensures accuracy - Reduce time/effort in resolving daily issues
| Prevent book/portfolio duplications |  | Develop checks to prevent duplicate books and portfolio criteria | Current approach being enhanced |  | High | Burton | Ramesh's team | - Prevents duplicate capture of positions
| Enhance RiskTrac reporting capabilities |  | Benchmark reporting and DPR loads VaR reporting and DPR loads | Team to be identified |  | High | Tom / Chris / Zakkiyah | Ramesh's team / Won? | - Eliminate need to reconcile benchmark file with RMS - Faster benchmark processing - Simplifies benchmark reporting, encouraging risk groups/users to run benchmark reports themselves (vs. GRO)
| Book archiving / aging |  | Process to archive books and prevent use in all upstream systems Book aging functionality | Inception | May be able to use GCP inactivation to drive archiving process | High | Nancy | Ramesh's team | - Clean-up books/portfolios (leads to better system performance) - Prevents use of Archived books
| Online book creation |  | Online form with input validation; Automatic back-end table updates; Audit trail database | Inception | Online form created; no database yet Back-end update currently not in scope | High | Tom / Jennifer | Ramesh's team / Won? | - Make GRO user process more efficient - Provides audit trail - Encourages book admins to submit complete and accurate book requests
| Tool for assigning a book to a portfolio/s |  | To eliminate tedious process in VB app, specially if book needs to be entered in multiple portfolios | Requirement identified |  | Med | Tom / Jennifer | Ramesh's team | Make GRO user process more efficient
| Moving sub-portfolios |  | Highlighting a group of portfolios and copying to another portfolio; currently, user can only move portfolios one at a time | Requirement identified |  | Low | Susan | Ramesh's team | Make GRO user process more efficient
| Renaming books (with no trading history yet) |  | Currently, the process is to create a new book with the correct name (since we also cannot delete books, old book ends up being unused) | Requirement identified |  | Low | Susan | Ramesh's team | Make GRO user process more efficient
| Document current RiskTrac set-up procedures and develop checklists |  |  | Creating draft | No IT role here | Low | Susan / Jennifer | None | - Minimize user errors when setting up books - Facilitate knowledge transfer within GRO
| Re-design application that calculates monthly reserves |  | The application uses book Ids from Discounting UK and Discounting USD portfolios. The re-design of the application will make use of one of the production portfolios (maybe AGG-PROD_BU?) | Requirement identified |  | Low | Chris / Anita | Ramesh's team / Won? | - Eliminates the need to maintain Discounting UK and Discounting USD
| Business Process | [5 empty] | Keith Considine (PM)
| Re-define RiskTrac user roles and responsibilities |  | Identify user groups and define different levels of access to data groups and functionalities | Inception | User group definitions submitted to IT; start with UK risk group | High | James / Fergus | Ramesh's team | - Decentralizes some RiskTrac functions, reducing GRO workload and promoting risk groups to take more responsibility for risk processes
| Re-define risk controls processes and segregation of responsibilities | [5 empty] | Tom / Keith
| Source Feeds Processing | [5 empty] | Greg Couch (PM)
| Faster ERMS position capture process in RiskTrac |  |  | Inception phase | ERMS and RiskTrac IT groups setting up a project; Steve Stock will provide status of meetings | High | Greg | RiskTrac IT, ERMS IT | Faster RiskTrac loads
| Document current state of position capture |  | Some groups' positions are not being captured in RiskTrac Some groups' have separate loads to RiskTrac and CAS (eg. Canada) | Requirement identified | Need to determine % of positions not captured through RiskTrac Need to determine % of positions on RiskTrac but failed to load | High | Greg | TBD
| Address inconsistent un- and re-officialization processes across RiskTrac, CAS, Infinity |  | Need to document differences in RiskTrac, CAS, Infinity, and make sure that we're not missing, duplicating positions | Team to be identified |  | High | ?? | ?? | Ensures capture of same positions in RiskTrac, CAS, Infinity
| Address inconsistent processes when system finds no post-id (eg. Infinity takes previous day's data, RiskTrac does not) |  | Need to document differences in RiskTrac, CAS, Infinity; if differences cannot be addressed, then we need to develop a way to tack the differences | Team to be identified |  | Med | ?? | ?? | Ensures capture of same positions in RiskTrac, CAS, Infinity
| Document any hardware-related issues impacting system performance (as well as any plans to address these) |  |  | Team to be identified |  | Med | ?? | ?? | Identify opportunities for improving system performance
| Running parallel RiskTrac load processes (from ERMS) |  |  | Running in production | Significant improvement in RiskTrac load times; need to monitor impact on ERMS processing times | Med | None | Ramesh's team | Faster RiskTrac loads
| ERMS function to prevent officialization of empty books (similar to EnPower) |  | There are a large number of empty books that are being calc'd and officialized through Meta-calc stream | Requirement identified | Per Ramesh, impact will be low on RiskTrac load times (more of a clean-up project) | Low | Nancy | ERMS IT | - Improved peformance in RiskTrac loads (minimal impact, per Ramesh) - Eliminates unnecessary ERMS processing

## Source feeds
|  | ERMS |  |  |  |  | EnPower |  | Spreadsheets
|  | Gas | EGM | EIM | EES | Canada | Power | EES | Gas | Power | EGM | EIM | S. America | Canada | UK
DPR
Benchmark positions
Maturity gap
VaR
P&L
Validation
Exception reporting
RiskTrac
Officialized
Positions
MTM
Curve shift P&L
Curves
Validation
Exception reporting
CAS
Officialized
Positions
MTM
Validation
Exception reporting
Infinity
Officialized
Positions
MTM
Curves
Validation
Exception reporting

## RiskTrac
Project Name |  |  | Comments | Responsibility | Timing
RiskTrac clean-up
Hierarchies / Books
|  | What are the relevant porftolios? -- which portfolios do groups need VaR for (DPR, commodity risk, traders) | Ask VaR users which portfolios they look at for VaR. How do they look at VaR (SQL queries?)
|  | Are all necessary books in each portfolio? | Generate list of books per portfolio (web tool)
|  | Are there any duplicates? (sub-portfolios, books, criteria) | IT tests for duplicates
|  | Which books can be archived? | Implement aging ERMS_OLD
Other root portfolios
Other root portfolios -- who uses them?, for what?
Curves
|  | Identify unused curves | Aging
|  | Identify unmapped curves | Curve mapping tool
Benchmark reports
How do commodity risk groups check their positions? Which reports do they look at? Which portfolios/books?
Do risk groups look at position reports from RMS? If so, how (sql queries?)? If not, how are DPR positions confirmed?
Design RMS report to confirm position reports from source systems
RiskTrac user processes
Book set-up
Web front-end -- input validation, multiple entries)
RMS database updates
ERMS database updates
| Tool to Assign books to portfolio/s |  | automatic check for duplicates
Exception reporting
Officialization exceptions
Gross positions (source vs. RMS)
MTM (source vs. RMS), check with DPR