## summary
2001-09-21
MARINER ENERGY, INC.
APPENDIX
WEEKLY DRILLING AND COMPLETION SUMMARY
[7 empty] | PRESENT | PROPOSED
|  | PROSPECT | AREA | WELL | E/D | WI% | DEPTH | TD | COMMENT
| I. | WELLS CURRENTLY DRILLING
|  | Green Canyon 136 | Deepwater | OCS-G 4508 #8 | D | 25% | 2,140' | 7,600' | Drilling.
(Shasta)
| II. | WELLS REACHING TOTAL DEPTH, TESTING, OR TURNED TO SALES THIS WEEK
|  | Green Cayon 516 | Deepwater | OCS-G 20074 #1 | E | 50% |  |  | Completing.
(Yosemite)
| III. | WELLS ANTICIPATED TO SPUD WITHIN 90 DAYS
|  | Viosca Knoll 962 | Deepwater | OCS-G #1 | E | 15% |  | 4,478' | Expected spud date third week October 2001.
(Swordfish)
|  | Visoca Knoll 962 | Deepwater | OCS-G #2 | E | 15% |  | 3,835' | Expected spud date fourth week November
|  | (Swordfish) | [6 empty] | 2001
|  | Mississippi Canyon 205 | Deepwater | OCS-G #1 | E | 25% |  | 3,500' | Expected spud date mid December 2001.
(Piston)
| IV. | OTHER
None to report.