## Logistics
Priority | Change Description | Change Type | Requestor | Responsible Party | Delivery Date
1 | SIRP00365/Fix - Event Status shows QR late but has been received on EPNG. | Fix | T. Jaquet | H. Ahsan | 2001-11-14
2 | QR, why some schedulers not receiving | Fix | T. Jaquet | H. Ahsan | 2001-11-14
3 | SIRP00067/Enhance - Automate Load of Scheduled Quantities | Enhancement | T. Jaquet | H. Ahsan | Estimating
4 | EDI Rewrite | Operations | T. Jaquet | R. Virnau / H. Ahsan / C. Tonks | Estimating
5 | Path Manager Rewrite | Operations | All Schedulers | M Pena, B. Tung, B. Nguyen, N. Boukris, R. D'Souza | Phase I testing, Phase II - late November
6 | Drivetrain / Sybase Replication replacement | Operations | All Unify Users | R. Hiarcher, M. Kaspereit | 2001-11-20
7 | Bridge Rewrite | Operations | All Schedulers | S. Macphail, A. Jang | 2002-02-01
8 | EES Bridge Changes | Enhancement | EES | C. Pham | 2001-11-14
9 | EES Interfaces | Enhancement | EES | M Pena, A. Ravat, G. Edminson | ???
10

## Volume Management
Priority | Change Description | Change Type | Requestor | Responsible Party | Delivery Date
1 | Booking Statement | Enhancement | Rita/Mark | Jay Sengupta, M. Kaspereit, J. Tat, M. Cuccia, N. Davis, M. Pena | Testing initial load / other milestones to be discussed along with dates
2 | SIRP00235/Bug when transport contracts changed between ENA and ENA Upstream on Koch Midstream Services | Fix | Rita/Mark | Steve Roberts / Matt Pena | Testing / 11/14/01
3 | Pipeline Actualization Project | Enhancement | Rita/Mark | J. Heinlen, H. Ahsan, K. Gillispie, M. Pena | Febuary 2002
4 | Bridge Changes for Bookable vs. NonBookable volumes | Enhancement | Rita/Mark | C. Pham | Testing / 11/14/01
5
6
7
8
9
10

## Settlements
Priority | Change Description | Change Type | Requestor | Responsible Party | Delivery Date
1 | Rate Server rounding problem | Fix | Bryce's team | Anwar Melethil | 2001-11-09
2 | Rate Server performance problem | Operations | Settlements | Anwar Melethil | 2001-11-14
2 | Pay Lessor of Logic for Supply Verifications | Enhancement | Settlements | K. Gillispie | Testing / 11/14/2001
3 | Invoice Logic | Enhancement | Bryce's team | S.Roberts | 2001-11-30
4 | Due Dates problem with Canada contract | Fix | Cheryl Dawes | Danny Martinez | 2001-11-14
5 | Sales Invoice not showing one of the tiers | Fix | Cheryl Dawes | Danny Martinez | 2001-11-12
6 | Create new OA extract | Enhancement | Kim Wilbanks | S.Roberts | 2001-11-30
7 | Phoenix to MKM migration | Operations | MKM | Anwar Melethil | 2001-12-14
8 | Settlements Database Split | Operations | Matt Pena | Romeo D'Souza | Q1 2002
9 | Service Draft EJB conversion | Enhancement |  | Anwar Melethil, Darren Stokes, Mutaz Mallak, Robert Laurel | Deferred / 2002
10 | Automate Calculation of Penalties on Supply | Future Enhancement | Bryce Baxter | Anwar Melethil | <no date>