## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - April 1, 2002 Through May 31, 2002
Amarillo Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted March 13, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18528 | AMA | BEAVER 2 | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 |  | OPS |  | 5 | 0.8 | Annual ESD. |  |  |  | 0 | P | N | N
2 | 18460 | AMA | BEAVER 6 | ALL | ANNUAL ESD | 2002-05-08 10:00 | 2002-05-08 12:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD. Will blind flange and not blow the station down. |  |  |  | 0 | P | N | N
3 | 18589 | AMA | BEAVER 7 | 1 | COMPRESSOR CYLINDER | 2002-03-10 07:00 | 2002-03-12 16:00 | 2.4 |  | OPS |  | 3 | 7.1 | Unit down with a knock in the #1 compressor. Not sure what they have unitl they tear into it. |  | 2002-03-10 07:00 |  | 0 | U | N | N
4 | 18367 | AMA | BEAVER PLANT | 12 | OVERHAUL | 2002-04-01 08:00 | 2002-04-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major enigne & compressors. (Subject to Dynegy approval). |  |  |  | 0 | P | N | N
5 | 18522 | AMA | BEAVER PLANT | ESD | ESD | 2002-05-02 08:00 | 2002-05-02 16:00 | 0.3 |  | OPS |  | 600 | 200 | Annual ESD. (7 to 8 hours). |  |  |  | 0 | P | N | N
6 | 18583 | AMA | BEAVER PLANT | B LINE ORIFICE | REMOVE ORIFICE PLATE | 2002-05-02 08:00 | 2002-05-03 16:00 | 1.3 |  | OPS |  | 0 | 0 | They believe the orifice plate is bent on the B line measurement at Beaver. They need to remove it when Beaver has their ESD. Actual time table for the work is estimated. It could be more or less. Flow affect is Spearman volumes. Estimated(68 mmfcd). |  |  |  | 0 | P | N | N
7 | 18459 | AMA | ELLIS 1 | ALL | ANNUAL ESD | 2002-05-07 09:00 | 2002-05-07 11:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD. Will blind flange and not blow the station down. |  |  |  | 0 | P | N | N
8 | 18513 | AMA | ELLIS 2 | ALL | ESD | 2002-05-15 09:00 | 2002-05-15 11:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
9 | 18524 | AMA | NORTHRUP | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 20:00 | 0.5 |  | OPS |  | 10 | 5 | Annual ESD. |  |  |  | 0 | P | N | N
10 | 18525 | AMA | PERRYTON BARLOW | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 20:00 | 0.5 |  | OPS |  | 7 | 3.5 | Annual ESD. |  |  |  | 0 | P | N | N
11 | 18523 | AMA | SPEARMAN | ESD & A LINE | ESD & A LINE LEAKS | 2002-05-02 08:00 | 2002-05-03 16:00 | 1.3 |  | OPS |  | 68 | 90.7 | Annual ESD. Need to repair several A Line leaks. |  |  |  | 0 | P | N | N
12 | 18526 | AMA | SUNRAY | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 20:00 | 0.5 |  | OPS |  | 144 | 72 | Annual ESD. |  |  |  | 0 | P | N | N
1 | 17151 | BEA | BUSHTON | 26 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
2 | 18527 | BEA | BUSHTON | ALL | ESD | 2002-05-07 07:30 | 2002-05-07 20:00 | 0.5 |  | OPS |  | 300 | 162.5 | Annual ESD. We should be able to bypass some volumes through the station using Clifton H.P. |  |  |  | 0 | P | N | N
3 | 17154 | BEA | CUNNINGHAM | 5 | OVERHAUL & CRACKED MANIFOLD | 2002-03-04 07:00 | 2002-03-25 15:30 | 21.3 |  | OPS |  | 50 | 1066.7 | Major overhaul MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. Repair Manifold. (Flow affect is about 50 mmcfd depending on the needs on the pipeline). |  | 2002-03-04 07:00 |  | 0 | P | N | N
4 | 18567 | BEA | CUNNINGHAM | 1 2 3 | ELECTRIC CO. SERVICE | 2002-03-21 07:00 | 2002-03-21 16:00 | 0.4 |  | OPS |  | 200 | 75 | The electric company needs to perform maintenance on their service. This work is being done due to their equipment failure on 03/01/02. (Unit #4 & #6 will still be available). The electric units will be down. |  |  |  | 0 | P | N | N
5 | 18569 | BEA | CUNNINGHAM | ALL | MAIN PLANT DRIPS | 2002-04-30 07:00 | 2002-04-30 16:00 | 0.4 |  | OPS |  | 0 | 0 | Repair/replace 1" line on Main Plant Drips. This is a consolidated audit action item. (It will affect max Inj. and Wdl). |  |  |  | 0 | P | N | N
6 | 18568 | BEA | CUNNINGHAM | ALL | ESD | 2002-06-06 07:00 | 2002-06-06 16:00 | 0.4 |  | OPS |  | 0 | 0 | Annual ESD test. (Will affect max Inj. and Wdl. |  |  |  | 0 | P | N | N
7 | 18512 | BEA | NGPL | TRAILBLAZER | NGPL TRAILBLAZER I/C | 2002-04-09 08:00 | 2002-04-11 16:00 | 2.3 |  | OPS |  | 450 | 1050 | NGPL is having a complete outage on their side. |  |  |  | 0 | P | N | N
1 | 17521 | DES | BELLEVILLE | 1 2 3 | ESD TEST | 2002-05-07 10:00 | 2002-05-07 12:00 | 0.1 |  | OPS |  | 0 | 0 | ESD test. 3300 HP |  |  |  | 0 | P | N | N
2 | 18497 | DES | EARLVILLE | 1 | WATER WASH | 2002-04-17 06:00 | 2002-04-17 16:00 | 0.4 |  | OPS |  | 0 | 0 | Water wash turbine and change air filters. |  |  |  | 0 | P | N | N
3 | 17161 | DES | GALENA | 1 | OVERHAUL | 2002-05-06 08:00 | 2002-05-17 16:00 | 11.3 |  | OPS |  | 0 | 0 | Solar Centaur Turbine exchange based on analysis and run hours. |  |  |  | 0 | P | N | N
4 | 17520 | DES | GALENA | 1 2 | ESD TEST | 2002-05-14 09:00 | 2002-05-14 11:00 | 0.1 |  | OPS |  | 0 | 0 | ESD test. 8000 HP |  |  |  | 0 | P | N | N
5 | 17164 | DES | OGDEN | 15 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Dresser Clark TLA-6 based on preventative maintenance data analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
6 | 17229 | DES | OTTAWA | N MANHATTAN | N MANHATTAN CV | 2002-04-17 08:00 | 2002-04-21 16:00 | 4.3 |  | 453 | C.014802 | 0 | 0 | North Manhattan CV replacement. Remove existing control valve and install a new quieter valve. |  |  |  | 0 | P | N | N
7 | 18449 | DES | PLATTEVILLE | HWY 151 | REPLACE 8" SAVANNA BL | 2002-04-26 08:00 | 2002-04-26 16:00 | 0.3 |  | 453 |  | 0 | 0 | Hwy 151 Dubuque Co- Replace and lower approx. 450 feet of 8" pipe of the Savanna BL at Hwy 151 in Dubuque Co. Iowa. |  |  |  | 0 | P | N | N
8 | 18557 | DES | WATERLOO | 1 | PIPING TRANSITIONS | 2002-03-18 07:00 | 2002-03-22 16:30 | 4.4 |  | OPS |  | 0 | 0 | Piping transitions that penetrate building 1 and building 2 will be knocked out around the pipe for inspecton and any needed maintenance to the pipe. Piping in the yard will be hand dug inspected and recoated with some sort of protection. |  |  |  | 0 | P | N | N
9 | 18558 | DES | WATERLOO | 2 | PIPING TRANSITIONS | 2002-03-25 07:00 | 2002-03-29 16:30 | 4.4 |  | OPS |  | 0 | 0 | Piping transitions that penetrate building 1 and building 2 will be knocked out around the pipe for inspecton and any needed maintenance to the pipe. Piping in the yard will be hand dug inspected and recoated with some sort of protection. |  |  |  | 0 | P | N | N
10 | 18559 | DES | WATERLOO | 3 | PIPING TRANSITIONS | 2002-04-01 07:00 | 2002-04-05 16:30 | 4.4 |  | OPS |  | 0 | 0 | Piping transitions that penetrate building 1 and building 2 will be knocked out around the pipe for inspecton and any needed maintenance to the pipe. Piping in the yard will be hand dug inspected and recoated with some sort of protection. |  |  |  | 0 | P | N | N
11 | 18560 | DES | WATERLOO | 4 | PIPING TRANSITIONS | 2002-04-08 07:00 | 2002-04-12 16:30 | 4.4 |  | OPS |  | 0 | 0 | Piping transitions that penetrate building 1 and building 2 will be knocked out around the pipe for inspecton and any needed maintenance to the pipe. Piping in the yard will be hand dug inspected and recoated with some sort of protection. |  |  |  | 0 | P | N | N
12 | 18561 | DES | WATERLOO | 5 | PIPING TRANSITIONS | 2002-04-15 07:00 | 2002-04-19 16:30 | 4.4 |  | OPS |  | 0 | 0 | Piping transitions that penetrate building 1 and building 2 will be knocked out around the pipe for inspecton and any needed maintenance to the pipe. Piping in the yard will be hand dug inspected and recoated with some sort of protection. |  |  |  | 0 | P | N | N
13 | 18562 | DES | WATERLOO | 6 | PIPING TRANSITIONS | 2002-04-22 07:00 | 2002-04-26 16:30 | 4.4 |  | OPS |  | 0 | 0 | Piping transitions that penetrate building 1 and building 2 will be knocked out around the pipe for inspecton and any needed maintenance to the pipe. Piping in the yard will be hand dug inspected and recoated with some sort of protection. |  |  |  | 0 | P | N | N
14 | 18499 | DES | WATERLOO | ALL | ESD | 2002-05-21 07:00 | 2002-05-22 16:00 | 1.4 |  | OPS |  | 0 | 0 | Annual ESD test rebuild ESD regulators test ESD relief valves Motor Control center wiring clean-up install ESD system quick fill assembly replace unit #6 suction and discharge lead-line valves (Valve replacement pending funding). |  |  |  | 0 | P | N | N
1 | 18465 | LIB | BEAVER 1 | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 |  | OPS |  | 14 | 2.3 | Annual ESD. |  |  |  | 0 | P | N | N
2 | 18408 | LIB | BURDETT | ALL | ANNUAL ESD | 2002-05-14 08:00 | 2002-05-14 12:00 | 0.2 |  | OPS |  | 0 | 0 | Annual ESD will shut down during the same time as Holcomb's ESD. |  |  |  | 0 | P | N | N
3 | 18468 | LIB | CLARK 1 | 1 | BORESCOPE | 2002-03-15 08:00 | 2002-04-26 16:00 | 42.3 |  | OPS |  | 2 | 84.7 | Borescope the power cylinder. |  |  |  | 0 | P | N | N
4 | 18467 | LIB | CLARK 1 | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 20:00 | 0.5 |  | OPS |  | 6.5 | 3.3 | Annual ESD. |  |  |  | 0 | P | N | N
5 | 18469 | LIB | CLARK 2 | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 20:00 | 0.5 |  | OPS |  | 6 | 3 | Annual ESD. |  |  |  | 0 | P | N | N
6 | 18570 | LIB | FINNEY 1 | ALL | ESD | 2002-05-14 07:30 | 2002-05-15 16:00 | 1.4 |  | OPS |  | 10 | 13.8 | Annual ESD. Finney 1 will need to be down 2 days for Holcomb south's outage. Cleaning their VTECH. |  |  |  | 0 | P | N | N
7 | 18368 | LIB | FINNEY 2 | 1 | OVERHAUL | 2002-04-15 08:00 | 2002-04-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Inframe engine & compressor OH. |  |  |  | 0 | P | N | N
8 | 18511 | LIB | FINNEY 2 3 4 | ALL | ANNUAL ESD | 2002-05-14 07:30 | 2002-05-14 16:00 | 0.4 |  | OPS |  | 0 | 0 | Annual ESD's for the Finney Co. Stations. 2 3 and 4. |  |  |  | 0 | P | N | N
9 | 18364 | LIB | FINNEY 3 | 1 | ENGINE EXCHANGE | 2002-04-01 08:00 | 2002-04-15 16:00 | 14.3 |  | OPS |  | 0 | 0 | Engine exchange. |  |  |  | 0 | P | N | N
10 | 18363 | LIB | FINNEY 4 | 4 | OVERHAUL | 2002-04-15 08:00 | 2002-05-10 16:30 | 25.3 |  | OPS |  | 3 | 76 | Unit will be pulled out and overhauled. (Unit Exchange if possible). |  |  |  | 0 | P | N | N
11 | 17836 | LIB | HOLCOMB | 10 | REPLACE PISTONS & RINGS | 2002-05-01 08:00 | 2002-05-31 16:00 | 30.3 |  | OPS |  | 0 | 0 | Replace pistons and rings overhaul 2 & 3 compressors. |  |  |  | 0 | P | N | N
12 | 17839 | LIB | HOLCOMB | ESD | ANNUAL ESD | 2002-05-14 08:00 | 2002-05-14 12:00 | 0.2 |  | OPS |  | 135 | 22.5 | Annual ESD and maintenance. |  |  |  | 0 | P | N | N
13 | 17840 | LIB | HOLCOMB | HOLCOMB SOUTH | ESD & CLEAN BETEX | 2002-05-14 08:00 | 2002-05-15 12:00 | 1.2 |  | OPS |  | 6 | 7 | Outage coordinated with Holcomb's Annual ESD. And also to clean their BETEX. Finney co. 1 will need to be down through this outage. |  |  |  | 0 | P | N | N
14 | 18089 | LIB | HUGOTON | ALL | ESD | 2002-05-07 07:30 | 2002-05-09 16:00 | 2.4 |  | OPS |  | 130 | 308.8 | Planned ESD. (Actual completion time depends on contractors). |  |  |  | 0 | P | N | N
15 | 17622 | LIB | MORTON 1 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-07 13:00 | 0.3 |  | OPS |  | 18 | 4.5 | Annual ESD. |  |  |  | 0 | P | N | N
16 | 17623 | LIB | MORTON 6 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-07 13:00 | 0.3 |  | OPS |  | 8 | 2 | Annual ESD. |  |  |  | 0 | P | N | N
17 | 18494 | LIB | MULLINVILLE | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 20:00 | 0.5 |  | OPS |  | 400 | 200 | Annual ESD. |  |  |  | 0 | P | N | N
18 | 18073 | LIB | STEVENS 1 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-07 10:30 | 0.1 |  | OPS |  | 30 | 3.8 | Annual ESD. |  |  |  | 0 | P | N | N
19 | 17842 | LIB | STEVENS 2 | ALL | ANNUAL ESD | 2002-05-07 08:00 | 2002-05-07 10:30 | 0.1 |  | OPS |  | 19 | 1.6 | Annual ESD |  |  |  | 0 | P | N | N
20 | 18493 | LIB | STEVENS 3 | ALL | ESD | 2002-05-07 07:30 | 2002-05-07 10:30 | 0.1 |  | OPS |  | 6 | 0.8 | Annual ESD. |  |  |  | 0 | P | N | N
21 | 17895 | LIB | STEVENS 4 | ALL | ANNUAL ESD | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 |  | OPS |  | 18 | 42 | Annual ESD. (Station will be back up when Hugoton comes back on). |  |  |  | 0 | P | N | N
22 | 18471 | LIB | STEVENS 6 | ALL | ESD | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 |  | OPS |  | 18 | 42 | Annual ESD. (The station will be back on line when the Hugoton plant comes back on). |  |  |  | 0 | P | N | N
23 | 18472 | LIB | STEVENS 7 | ALL | ESD | 2002-05-07 08:00 | 2002-05-07 10:30 | 0.1 |  | OPS |  | 30 | 2.5 | Annual ESD. |  |  |  | 0 | P | N | N
24 | 18473 | LIB | SUBLETTE | ALL | ESD | 2002-05-07 08:00 | 2002-05-07 14:00 | 0.3 |  | OPS |  | 0 | 0 | Annual ESD. (Flow affects are in Hugoton's outage). |  |  |  | 0 | P | N | N
25 | 17757 | LIB | TATE | ALL | ESD | 2002-05-14 08:00 | 2002-05-14 12:00 | 0.2 |  | OPS |  | 14 | 2.3 | Annual ESD test. |  |  |  | 0 | P | N | N
26 | 17624 | LIB | TEXAS 1 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-08 14:00 | 1.3 |  | OPS |  | 10 | 12.9 | Annual ESD. |  |  |  | 0 | P | N | N
27 | 17625 | LIB | TEXAS 2 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-08 14:00 | 1.3 |  | OPS |  | 15 | 19.4 | Annual ESD. |  |  |  | 0 | P | N | N
1 | 18325 | MID | PLAINS | 1 | ANNUAL ESD | 2002-03-19 08:00 | 2002-03-20 12:00 | 1.2 |  | OPS |  | 100 | 116.7 | Annual ESD & calibrate transmitters. Test all shut downs devices put in new battery charge. (Will put on @ 18:00 03/19/02 and take back down on 3/20/02 if needed). Will see if El Paso can work with us on the outage. |  |  |  | 0 | P | N | N
2 | 18319 | MID | SPRAYBERRY | ESD | ANNUAL ESD | 2002-05-22 08:00 | 2002-05-22 16:00 | 0.3 |  | OPS |  | 280 | 93.3 | Annual ESD and maintenance. |  |  |  | 0 | P | N | N
1 | 18577 | MIN | CHATFIELD | 1 | OUTBOARD BEARING SUPPORT | 2002-03-06 08:00 | 2002-03-15 16:00 | 9.3 |  | OPS |  | 0 | 0 | Re-enforce the rear outboard bearing support. The part needs to be machined. |  | 2002-03-06 08:00 |  | 0 | P | N | N
2 | 18537 | MIN | FARMINGTON | ALL | ESD | 2002-05-01 08:00 | 2002-05-01 16:00 | 0.3 |  | OPS |  | 0 | 0 | Annual ESD. (ESD will scheduled when Farmington goes down for the season). Depending on the north system loads it may be late April or early May. |  |  |  | 0 | P | N | N
3 | 18518 | MIN | NORTH BRANCH | BUFFALO B/L | BUFFALO 4 BLOCK VALVE RELOCATE | 2002-04-22 08:00 | 2002-04-22 16:00 | 0.3 |  | OPS |  | 0 | 0 | Remove existing block valve setting 67101BYB01.1 on the 4" Buffalo B/L at M.P. 6.812 and install new block valve setting. The pressure will reduced to 500-550 psig to allow proper seating of the stopples. |  |  |  | 0 | P | N | N
4 | 18519 | MIN | NORTH BRANCH | BUFFALO 6 BLOCK | BUFFALO 6 BLOCK VALVE RELOCATE | 2002-04-23 08:00 | 2002-04-23 16:00 | 0.3 |  | OPS |  | 0 | 0 | Remove existing block valve setting 67102BYB011.1 on the 6" B/L at M.P. 6.818 and install new 6" spool piece. Reduce pressure to 500-550 psig to allow proper seating of stopples. |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - April 1, 2002 Through May 31, 2002
Amarillo Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted March 13, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18528 | AMA | BEAVER 2 | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 |  | OPS |  | 5 | 0.8 | Annual ESD. |  |  |  | 0 | P | N | N
2 | 18460 | AMA | BEAVER 6 | ALL | ANNUAL ESD | 2002-05-08 10:00 | 2002-05-08 12:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD. Will blind flange and not blow the station down. |  |  |  | 0 | P | N | N
3 | 18589 | AMA | BEAVER 7 | 1 | COMPRESSOR CYLINDER | 2002-03-10 07:00 | 2002-03-12 16:00 | 2.4 |  | OPS |  | 3 | 7.1 | Unit down with a knock in the #1 compressor. Not sure what they have unitl they tear into it. |  | 2002-03-10 07:00 |  | 0 | U | N | N
4 | 18367 | AMA | BEAVER PLANT | 12 | OVERHAUL | 2002-04-01 08:00 | 2002-04-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major enigne & compressors. (Subject to Dynegy approval). |  |  |  | 0 | P | N | N
5 | 18522 | AMA | BEAVER PLANT | ESD | ESD | 2002-05-02 08:00 | 2002-05-02 16:00 | 0.3 |  | OPS |  | 600 | 200 | Annual ESD. (7 to 8 hours). |  |  |  | 0 | P | N | N
6 | 18583 | AMA | BEAVER PLANT | B LINE ORIFICE | REMOVE ORIFICE PLATE | 2002-05-02 08:00 | 2002-05-03 16:00 | 1.3 |  | OPS |  | 0 | 0 | They believe the orifice plate is bent on the B line measurement at Beaver. They need to remove it when Beaver has their ESD. Actual time table for the work is estimated. It could be more or less. Flow affect is Spearman volumes. Estimated(68 mmfcd). |  |  |  | 0 | P | N | N
7 | 18459 | AMA | ELLIS 1 | ALL | ANNUAL ESD | 2002-05-07 09:00 | 2002-05-07 11:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD. Will blind flange and not blow the station down. |  |  |  | 0 | P | N | N
8 | 18513 | AMA | ELLIS 2 | ALL | ESD | 2002-05-15 09:00 | 2002-05-15 11:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
9 | 18524 | AMA | NORTHRUP | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 20:00 | 0.5 |  | OPS |  | 10 | 5 | Annual ESD. |  |  |  | 0 | P | N | N
10 | 18525 | AMA | PERRYTON BARLOW | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 20:00 | 0.5 |  | OPS |  | 7 | 3.5 | Annual ESD. |  |  |  | 0 | P | N | N
11 | 18523 | AMA | SPEARMAN | ESD & A LINE | ESD & A LINE LEAKS | 2002-05-02 08:00 | 2002-05-03 16:00 | 1.3 |  | OPS |  | 68 | 90.7 | Annual ESD. Need to repair several A Line leaks. |  |  |  | 0 | P | N | N
12 | 18526 | AMA | SUNRAY | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 20:00 | 0.5 |  | OPS |  | 144 | 72 | Annual ESD. |  |  |  | 0 | P | N | N
1 | 17151 | BEA | BUSHTON | 26 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
2 | 18527 | BEA | BUSHTON | ALL | ESD | 2002-05-07 07:30 | 2002-05-07 20:00 | 0.5 |  | OPS |  | 300 | 162.5 | Annual ESD. We should be able to bypass some volumes through the station using Clifton H.P. |  |  |  | 0 | P | N | N
3 | 17154 | BEA | CUNNINGHAM | 5 | OVERHAUL & CRACKED MANIFOLD | 2002-03-04 07:00 | 2002-03-25 15:30 | 21.3 |  | OPS |  | 50 | 1066.7 | Major overhaul MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. Repair Manifold. (Flow affect is about 50 mmcfd depending on the needs on the pipeline). |  | 2002-03-04 07:00 |  | 0 | P | N | N
4 | 18567 | BEA | CUNNINGHAM | 1 2 3 | ELECTRIC CO. SERVICE | 2002-03-21 07:00 | 2002-03-21 16:00 | 0.4 |  | OPS |  | 200 | 75 | The electric company needs to perform maintenance on their service. This work is being done due to their equipment failure on 03/01/02. (Unit #4 & #6 will still be available). The electric units will be down. |  |  |  | 0 | P | N | N
5 | 18569 | BEA | CUNNINGHAM | ALL | MAIN PLANT DRIPS | 2002-04-30 07:00 | 2002-04-30 16:00 | 0.4 |  | OPS |  | 0 | 0 | Repair/replace 1" line on Main Plant Drips. This is a consolidated audit action item. (It will affect max Inj. and Wdl). |  |  |  | 0 | P | N | N
6 | 18568 | BEA | CUNNINGHAM | ALL | ESD | 2002-06-06 07:00 | 2002-06-06 16:00 | 0.4 |  | OPS |  | 0 | 0 | Annual ESD test. (Will affect max Inj. and Wdl. |  |  |  | 0 | P | N | N
7 | 18512 | BEA | NGPL | TRAILBLAZER | NGPL TRAILBLAZER I/C | 2002-04-09 08:00 | 2002-04-11 16:00 | 2.3 |  | OPS |  | 450 | 1050 | NGPL is having a complete outage on their side. |  |  |  | 0 | P | N | N
1 | 17521 | DES | BELLEVILLE | 1 2 3 | ESD TEST | 2002-05-07 10:00 | 2002-05-07 12:00 | 0.1 |  | OPS |  | 0 | 0 | ESD test. 3300 HP |  |  |  | 0 | P | N | N
2 | 18497 | DES | EARLVILLE | 1 | WATER WASH | 2002-04-17 06:00 | 2002-04-17 16:00 | 0.4 |  | OPS |  | 0 | 0 | Water wash turbine and change air filters. |  |  |  | 0 | P | N | N
3 | 17161 | DES | GALENA | 1 | OVERHAUL | 2002-05-06 08:00 | 2002-05-17 16:00 | 11.3 |  | OPS |  | 0 | 0 | Solar Centaur Turbine exchange based on analysis and run hours. |  |  |  | 0 | P | N | N
4 | 17520 | DES | GALENA | 1 2 | ESD TEST | 2002-05-14 09:00 | 2002-05-14 11:00 | 0.1 |  | OPS |  | 0 | 0 | ESD test. 8000 HP |  |  |  | 0 | P | N | N
5 | 17164 | DES | OGDEN | 15 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Dresser Clark TLA-6 based on preventative maintenance data analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
6 | 17229 | DES | OTTAWA | N MANHATTAN | N MANHATTAN CV | 2002-04-17 08:00 | 2002-04-21 16:00 | 4.3 |  | 453 | C.014802 | 0 | 0 | North Manhattan CV replacement. Remove existing control valve and install a new quieter valve. |  |  |  | 0 | P | N | N
7 | 18449 | DES | PLATTEVILLE | HWY 151 | REPLACE 8" SAVANNA BL | 2002-04-26 08:00 | 2002-04-26 16:00 | 0.3 |  | 453 |  | 0 | 0 | Hwy 151 Dubuque Co- Replace and lower approx. 450 feet of 8" pipe of the Savanna BL at Hwy 151 in Dubuque Co. Iowa. |  |  |  | 0 | P | N | N
8 | 18557 | DES | WATERLOO | 1 | PIPING TRANSITIONS | 2002-03-18 07:00 | 2002-03-22 16:30 | 4.4 |  | OPS |  | 0 | 0 | Piping transitions that penetrate building 1 and building 2 will be knocked out around the pipe for inspecton and any needed maintenance to the pipe. Piping in the yard will be hand dug inspected and recoated with some sort of protection. |  |  |  | 0 | P | N | N
9 | 18558 | DES | WATERLOO | 2 | PIPING TRANSITIONS | 2002-03-25 07:00 | 2002-03-29 16:30 | 4.4 |  | OPS |  | 0 | 0 | Piping transitions that penetrate building 1 and building 2 will be knocked out around the pipe for inspecton and any needed maintenance to the pipe. Piping in the yard will be hand dug inspected and recoated with some sort of protection. |  |  |  | 0 | P | N | N
10 | 18559 | DES | WATERLOO | 3 | PIPING TRANSITIONS | 2002-04-01 07:00 | 2002-04-05 16:30 | 4.4 |  | OPS |  | 0 | 0 | Piping transitions that penetrate building 1 and building 2 will be knocked out around the pipe for inspecton and any needed maintenance to the pipe. Piping in the yard will be hand dug inspected and recoated with some sort of protection. |  |  |  | 0 | P | N | N
11 | 18560 | DES | WATERLOO | 4 | PIPING TRANSITIONS | 2002-04-08 07:00 | 2002-04-12 16:30 | 4.4 |  | OPS |  | 0 | 0 | Piping transitions that penetrate building 1 and building 2 will be knocked out around the pipe for inspecton and any needed maintenance to the pipe. Piping in the yard will be hand dug inspected and recoated with some sort of protection. |  |  |  | 0 | P | N | N
12 | 18561 | DES | WATERLOO | 5 | PIPING TRANSITIONS | 2002-04-15 07:00 | 2002-04-19 16:30 | 4.4 |  | OPS |  | 0 | 0 | Piping transitions that penetrate building 1 and building 2 will be knocked out around the pipe for inspecton and any needed maintenance to the pipe. Piping in the yard will be hand dug inspected and recoated with some sort of protection. |  |  |  | 0 | P | N | N
13 | 18562 | DES | WATERLOO | 6 | PIPING TRANSITIONS | 2002-04-22 07:00 | 2002-04-26 16:30 | 4.4 |  | OPS |  | 0 | 0 | Piping transitions that penetrate building 1 and building 2 will be knocked out around the pipe for inspecton and any needed maintenance to the pipe. Piping in the yard will be hand dug inspected and recoated with some sort of protection. |  |  |  | 0 | P | N | N
14 | 18499 | DES | WATERLOO | ALL | ESD | 2002-05-21 07:00 | 2002-05-22 16:00 | 1.4 |  | OPS |  | 0 | 0 | Annual ESD test rebuild ESD regulators test ESD relief valves Motor Control center wiring clean-up install ESD system quick fill assembly replace unit #6 suction and discharge lead-line valves (Valve replacement pending funding). |  |  |  | 0 | P | N | N
1 | 18465 | LIB | BEAVER 1 | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 |  | OPS |  | 14 | 2.3 | Annual ESD. |  |  |  | 0 | P | N | N
2 | 18408 | LIB | BURDETT | ALL | ANNUAL ESD | 2002-05-14 08:00 | 2002-05-14 12:00 | 0.2 |  | OPS |  | 0 | 0 | Annual ESD will shut down during the same time as Holcomb's ESD. |  |  |  | 0 | P | N | N
3 | 18468 | LIB | CLARK 1 | 1 | BORESCOPE | 2002-03-15 08:00 | 2002-04-26 16:00 | 42.3 |  | OPS |  | 2 | 84.7 | Borescope the power cylinder. |  |  |  | 0 | P | N | N
4 | 18467 | LIB | CLARK 1 | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 20:00 | 0.5 |  | OPS |  | 6.5 | 3.3 | Annual ESD. |  |  |  | 0 | P | N | N
5 | 18469 | LIB | CLARK 2 | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 20:00 | 0.5 |  | OPS |  | 6 | 3 | Annual ESD. |  |  |  | 0 | P | N | N
6 | 18570 | LIB | FINNEY 1 | ALL | ESD | 2002-05-14 07:30 | 2002-05-15 16:00 | 1.4 |  | OPS |  | 10 | 13.8 | Annual ESD. Finney 1 will need to be down 2 days for Holcomb south's outage. Cleaning their VTECH. |  |  |  | 0 | P | N | N
7 | 18368 | LIB | FINNEY 2 | 1 | OVERHAUL | 2002-04-15 08:00 | 2002-04-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Inframe engine & compressor OH. |  |  |  | 0 | P | N | N
8 | 18511 | LIB | FINNEY 2 3 4 | ALL | ANNUAL ESD | 2002-05-14 07:30 | 2002-05-14 16:00 | 0.4 |  | OPS |  | 0 | 0 | Annual ESD's for the Finney Co. Stations. 2 3 and 4. |  |  |  | 0 | P | N | N
9 | 18364 | LIB | FINNEY 3 | 1 | ENGINE EXCHANGE | 2002-04-01 08:00 | 2002-04-15 16:00 | 14.3 |  | OPS |  | 0 | 0 | Engine exchange. |  |  |  | 0 | P | N | N
10 | 18363 | LIB | FINNEY 4 | 4 | OVERHAUL | 2002-04-15 08:00 | 2002-05-10 16:30 | 25.3 |  | OPS |  | 3 | 76 | Unit will be pulled out and overhauled. (Unit Exchange if possible). |  |  |  | 0 | P | N | N
11 | 17836 | LIB | HOLCOMB | 10 | REPLACE PISTONS & RINGS | 2002-05-01 08:00 | 2002-05-31 16:00 | 30.3 |  | OPS |  | 0 | 0 | Replace pistons and rings overhaul 2 & 3 compressors. |  |  |  | 0 | P | N | N
12 | 17839 | LIB | HOLCOMB | ESD | ANNUAL ESD | 2002-05-14 08:00 | 2002-05-14 12:00 | 0.2 |  | OPS |  | 135 | 22.5 | Annual ESD and maintenance. |  |  |  | 0 | P | N | N
13 | 17840 | LIB | HOLCOMB | HOLCOMB SOUTH | ESD & CLEAN BETEX | 2002-05-14 08:00 | 2002-05-15 12:00 | 1.2 |  | OPS |  | 6 | 7 | Outage coordinated with Holcomb's Annual ESD. And also to clean their BETEX. Finney co. 1 will need to be down through this outage. |  |  |  | 0 | P | N | N
14 | 18089 | LIB | HUGOTON | ALL | ESD | 2002-05-07 07:30 | 2002-05-09 16:00 | 2.4 |  | OPS |  | 130 | 308.8 | Planned ESD. (Actual completion time depends on contractors). |  |  |  | 0 | P | N | N
15 | 17622 | LIB | MORTON 1 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-07 13:00 | 0.3 |  | OPS |  | 18 | 4.5 | Annual ESD. |  |  |  | 0 | P | N | N
16 | 17623 | LIB | MORTON 6 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-07 13:00 | 0.3 |  | OPS |  | 8 | 2 | Annual ESD. |  |  |  | 0 | P | N | N
17 | 18494 | LIB | MULLINVILLE | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 20:00 | 0.5 |  | OPS |  | 400 | 200 | Annual ESD. |  |  |  | 0 | P | N | N
18 | 18073 | LIB | STEVENS 1 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-07 10:30 | 0.1 |  | OPS |  | 30 | 3.8 | Annual ESD. |  |  |  | 0 | P | N | N
19 | 17842 | LIB | STEVENS 2 | ALL | ANNUAL ESD | 2002-05-07 08:00 | 2002-05-07 10:30 | 0.1 |  | OPS |  | 19 | 1.6 | Annual ESD |  |  |  | 0 | P | N | N
20 | 18493 | LIB | STEVENS 3 | ALL | ESD | 2002-05-07 07:30 | 2002-05-07 10:30 | 0.1 |  | OPS |  | 6 | 0.8 | Annual ESD. |  |  |  | 0 | P | N | N
21 | 17895 | LIB | STEVENS 4 | ALL | ANNUAL ESD | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 |  | OPS |  | 18 | 42 | Annual ESD. (Station will be back up when Hugoton comes back on). |  |  |  | 0 | P | N | N
22 | 18471 | LIB | STEVENS 6 | ALL | ESD | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 |  | OPS |  | 18 | 42 | Annual ESD. (The station will be back on line when the Hugoton plant comes back on). |  |  |  | 0 | P | N | N
23 | 18472 | LIB | STEVENS 7 | ALL | ESD | 2002-05-07 08:00 | 2002-05-07 10:30 | 0.1 |  | OPS |  | 30 | 2.5 | Annual ESD. |  |  |  | 0 | P | N | N
24 | 18473 | LIB | SUBLETTE | ALL | ESD | 2002-05-07 08:00 | 2002-05-07 14:00 | 0.3 |  | OPS |  | 0 | 0 | Annual ESD. (Flow affects are in Hugoton's outage). |  |  |  | 0 | P | N | N
25 | 17757 | LIB | TATE | ALL | ESD | 2002-05-14 08:00 | 2002-05-14 12:00 | 0.2 |  | OPS |  | 14 | 2.3 | Annual ESD test. |  |  |  | 0 | P | N | N
26 | 17624 | LIB | TEXAS 1 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-08 14:00 | 1.3 |  | OPS |  | 10 | 12.9 | Annual ESD. |  |  |  | 0 | P | N | N
27 | 17625 | LIB | TEXAS 2 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-08 14:00 | 1.3 |  | OPS |  | 15 | 19.4 | Annual ESD. |  |  |  | 0 | P | N | N
1 | 18325 | MID | PLAINS | 1 | ANNUAL ESD | 2002-03-19 08:00 | 2002-03-20 12:00 | 1.2 |  | OPS |  | 100 | 116.7 | Annual ESD & calibrate transmitters. Test all shut downs devices put in new battery charge. (Will put on @ 18:00 03/19/02 and take back down on 3/20/02 if needed). Will see if El Paso can work with us on the outage. |  |  |  | 0 | P | N | N
2 | 18319 | MID | SPRAYBERRY | ESD | ANNUAL ESD | 2002-05-22 08:00 | 2002-05-22 16:00 | 0.3 |  | OPS |  | 280 | 93.3 | Annual ESD and maintenance. |  |  |  | 0 | P | N | N
1 | 18577 | MIN | CHATFIELD | 1 | OUTBOARD BEARING SUPPORT | 2002-03-06 08:00 | 2002-03-15 16:00 | 9.3 |  | OPS |  | 0 | 0 | Re-enforce the rear outboard bearing support. The part needs to be machined. |  | 2002-03-06 08:00 |  | 0 | P | N | N
2 | 18537 | MIN | FARMINGTON | ALL | ESD | 2002-05-01 08:00 | 2002-05-01 16:00 | 0.3 |  | OPS |  | 0 | 0 | Annual ESD. (ESD will scheduled when Farmington goes down for the season). Depending on the north system loads it may be late April or early May. |  |  |  | 0 | P | N | N
3 | 18518 | MIN | NORTH BRANCH | BUFFALO B/L | BUFFALO 4 BLOCK VALVE RELOCATE | 2002-04-22 08:00 | 2002-04-22 16:00 | 0.3 |  | OPS |  | 0 | 0 | Remove existing block valve setting 67101BYB01.1 on the 4" Buffalo B/L at M.P. 6.812 and install new block valve setting. The pressure will reduced to 500-550 psig to allow proper seating of the stopples. |  |  |  | 0 | P | N | N
4 | 18519 | MIN | NORTH BRANCH | BUFFALO 6 BLOCK | BUFFALO 6 BLOCK VALVE RELOCATE | 2002-04-23 08:00 | 2002-04-23 16:00 | 0.3 |  | OPS |  | 0 | 0 | Remove existing block valve setting 67102BYB011.1 on the 6" B/L at M.P. 6.818 and install new 6" spool piece. Reduce pressure to 500-550 psig to allow proper seating of stopples. |  |  |  | 0 | P | N | N