## Req-Chkist
[22 empty] | Origination Date: | 8-20-01
|  |  | Enron Transportation Services | [18 empty] | Revision Date: | 09-07-01
|  |  | Project Data Form | [20 empty] | Revision #: | 1
[20 empty] | Request Number: | West01033
General Information: | [18 empty] | Estimate Level:
Originator Name: |  |  |  | Kevin Hyatt | [9 empty] | Location/Dept.: | Asset Development
Date Estimate Required: | [14 empty] | Projected In-Service Date: | Jan, 2004
Project Name: |  |  | Sun Devil Project
Customer Rep.-Name/Company:
Customer Rep.-Contact Information:
Facility Planner: |  |  | Ron Matthews SW Planning Team
Type of Expenditure: | [10 empty] | Other:
Pipeline: | [10 empty] | Other:
Operations Representative: | [6 empty] | Various Teams | [8 empty] | Region/Team: | Albuquerque Region
Scope of Work:
Facilities:
|  | Measurement: | [7 empty] | Compression: | [7 empty] | Power:
|  | Regulation: | [7 empty] | Piping: | [7 empty] | SCADA:
[6 empty] | Gas Treating Fac. (select below): |  | Other: | [9 empty] | Pipeline:
Other:
Right-of-way:
|  | ROW Costs | [6 empty] | Predominate ROW Type | [8 empty] | Environmental
Estimated Costs:
|  |  |  | Materials, taxes & freight | 0 | [6 empty] | Engineering | 0 | [6 empty] | As-builts | 0
|  |  |  | Install Labor & Equipment | 0 | [6 empty] | Design/Drafting | 0 | [6 empty] | AFUDC | 0
|  |  |  | Construction Support | 0 | [6 empty] | Project Mgmt. | 0 | [6 empty] | Contingency | 0
|  |  |  | District Labor | 0 | [6 empty] | Envr./Surveying | 0 | [8 empty] | TOTAL
|  |  |  | Inspection & X-ray | 0 | [6 empty] | Right-of-Way | 0 | [5 empty] | 0
San Juan - Install 97 miles of 36" loop line from Bloomfield to the junction, install a 7000 Hp site rated unit at Bloomfield, replace units #1-3 compressors with Solar C40's, modify the Blanco Hub piping and measurement, install a 9500 Hp site rated unit at the proposed Standing Rock location, and modify the Gallup CS. Other station piping mods may be required to handle the new flow rates.
Mainline - Install 224 miles of 36" loop lines from the San Juan junction to a point about 35 miles west of Station #2, install new mid-point compressor stations between Stations #2 & #1(25,000 Hp site) and Station #1 & Needles(27,500 Hp site), and install new compression at Station #4 (25,000 Hp site).
Sun Devil Pipeline - Install approximately 126 miles of 30" pipeline starting about 35 miles west of Station #2 to Phoenix. This will parallel El Paso's existing pipeline.
Comments:
The following sheet (Cost Estimate Summary) is the Level A cost estimate prepared by Facility Planning. Costs were not broken down in the categories above but the pipeline was calculated using a "rule of thumb" of $28,000 per diameter-inch per mile method. Horsepower was based on past and present project costs. Note the interest and overheads for the pipeline were separated out upon request by the Financial group. Contingency used was 10% which is included. Existing gas cooling and scrubber capacities need to be reviewed. Potential additional cooling and scrubbers will be required on both the mainline and San Juan lateral. Existing Hub measurement will be reviewed after the location of the new gas supply is determined.
Note on AB4: NT: Generated by Planning
Note on M10: NT: Phone and/or email addr.
Note on F11: NT: Name and Team Location
Note on A15: NT: Brief scope if complete detail cannot fit in this text block. A detailed scope should be provided on the worksheet titled "Addt'l Info".

## Cost Estimate Summary
Sun Devil Project
San Juan to Phoenix
Estimated Costs of Facilities
CASE VII. | A. | 36" MAINLINE LOOP, AND HP
NO MAOP UPGRADE
SUN DEVIL FROM 35 MILE WEST OF STATION #2
810 MMCF/D EXPANSION (2020 MMCF/D TOTAL)
[9 empty] | Vol. Incr. | Total Vol. | Int., O/H, etc
From |  | To |  | Miles |  | Size (") |  | Est. Costs | MMcf/d | MMcf/d | Not Included
BLFD CS |  | SJCT |  | 96.83 |  | 36 | " | 107365104 |  |  | 19520928
|  | Bloomfield Hp (7000 Hp) | [5 empty] | 13000000
|  | Bloomfield Mods | [5 empty] | 1000000
|  | Bloomfield Compressor Mods | [5 empty] | 2400000
|  | Blanco Hub Mods | [5 empty] | 2000000
|  | Bisti CS Mods | [5 empty] | 1000000
|  | Standing Rock CS (9,500 Hp) | [5 empty] | 14000000
|  | Gallup CS Mods | [5 empty] | 5000000
|  |  | Total San Juan Expansion | 96.83 |  |  |  | 145765104 | 780 | 1630 | 19520928
SJCT | - | Sta. #4 |  | 43.9 |  | 36 | " | 48676320 |  |  | 8850240
Sta. #4 | - | Sta. #3 |  | 85.5 |  | 36 | " | 94802400 |  |  | 17236800
Sta. #3 | - | Sta. #2 |  | 59.11 |  | 36 | " | 65541168 |  |  | 11916576
Sta. #2 |  | Sta. #1 |  | 35.2 |  | 36 | " | 39029760 |  |  | 7096320
Sta. #1 |  | Needles |  | 0 |  | 36 | " | 0 |  |  | 0
|  | CS4 (25,000 Hp) | [5 empty] | 23000000
|  | CS15 (25,000 Hp) | [5 empty] | 23000000
|  | Kingman CS (30,000 Hp) | [5 empty] | 23000000
|  |  | Total Mainline Expansion | 223.71 |  |  |  | 317049648 | 810 | 2020 | 45099936
M/L | - | Phoenix |  | 126 |  | 36 | " | 139708800 |  |  | 25401600
|  |  | Total Sun Devil Pipeline | 126 |  |  |  | 139708800 | --- | 450 | 25401600
|  |  | Total Project Excl. Int., O/H, etc. | 446.54 |  |  |  | 602523552 |  |  | 90022464
|  |  | Total Project Incl. Int., O/H, etc. |  |  |  |  | 692546016
Note: | 1. | Interest and overheads are not included.
| 2. | Station #4 Hp changeout included in this project.
| 3. | Bloomfield Unit #4 service change to low side BRI Val Verde receipt required.
Bloomfield Unit #3 moved to the high side with compressor change out on Unit #1 - #3.

## MeterTap Data
Measurement Facilities Design Parameters:
Delivery |  |  | Receipt |  |  |  | Bidirectional
System/Line No.: | [10 empty] | Size: |  |  |  |  | Connection Mile Post:
Project Location(s):
Upstream Conditions | [6 empty] | minimum |  | normal |  | high |  | MAOP/max |  |  | Measurement Type
[5 empty] | Pressure (psig) | [9 empty] | No. of Runs: |  | Size:
[5 empty] | Volume (MMcfd) | [9 empty] | Run Switching
[5 empty] | Gas Quality(BTU, dry) | [9 empty] | Measurement
Analysis
Downstream Conditions | [6 empty] | minimum |  | normal |  | high |  | MAOP/max |  | Power Supply
[5 empty] | Pressure (psig) | [9 empty] | Flange Rating
Volume (MMcfd)
[5 empty] | Gas Quality(BTU, dry) | [10 empty] | Phone Drop
Cellular Modem
Gas Characteristics | [5 empty] | minimum |  | normal |  | high | [5 empty] | Radio/Tower
|  |  |  | H2O (lbs/MMcf) | [11 empty] | VSAT
| H2S | [14 empty] | Remote Control
| CO2 | [14 empty] | by:
other comp.-units | [15 empty] | Over Pressure Protection:
other comp.-units | [15 empty] | by:
Connection Information: | [13 empty] | Number of connections required
Description:
Hot Tap |  |  |  | Tee & side valve
Header pipe:
|  | Diameter | [5 empty] | Wall Thickness |  |  |  | Grade |  |  |  | MAOP
Branch pipe:
|  | Diameter | [5 empty] | Wall Thickness |  |  |  | Grade |  |  |  | MAOP
Description:
Hot Tap |  |  |  | Tee & side valve
Header pipe:
|  | Diameter | [5 empty] | Wall Thickness |  |  |  | Grade |  |  |  | MAOP
Branch pipe:
|  | Diameter | [5 empty] | Wall Thickness |  |  |  | Grade |  |  |  | MAOP
yes
no
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
Note on H8: NT: Should specify: - Nearest City/Zip Code, State(s) - County, Block, Quadrant, Section, RR Survey (TX) - County/Parish, Section, Township, Range (other states) - Area, Block (offshore) - Latitude/Longitude, Lambert Corrdinates (X,Y) - Use worksheet "Addt'l Info" if more space is needed. Attach maps or drawings in additional worksheet tabs provided. Drawings should be in common readable formats such as .tif, .jpg, or .bmp.
Note on A26: NT: Select and edit text as required. Include units.

## Pipeline 1
Pipeline Facilities Design Parameters
Delivery: |  |  | Receipt: |  |  | Bidirectional:
System/Line No.: | [10 empty] | Size: | 36" | [6 empty] | Connection Mile Post: | MP00
Project Location(s): |  |  |  |  | San Juan & McKinley Cos., NM
|  |  |  | Beginning point | Bloomfield CS
|  |  |  | Terminus point | San Juan Junction
Conditions | [5 empty] | minimum |  | normal |  |  | high |  |  | MAOP/max |  |  | Gas Characteristics
|  |  |  | Pressure (psig) | [9 empty] | 1202 | [5 empty] | H2O (lbs/MMcf) | 6
|  |  |  | Volume (MMcfd) |  | 1500 |  | 1705 |  |  | 1730 | [6 empty] | H2S
|  |  |  | Gas Quality(BTU, dry) |  | 985 |  | 1010 |  |  | 1016 |  |  | 1020 |  |  |  | CO2 |  |  | 2
other comp.-units
other comp.-units
Segment 1
| Length | 96.83 Miles | [5 empty] | Diameter | 36" | [5 empty] | Wall Thickness | .429" |  |  | Grade | 70000
|  |  | Class Location | [6 empty] | Protective Coating | [8 empty] | Terrain description
Segment 2
| Length | [6 empty] | Diameter | [6 empty] | Wall Thickness |  |  |  | Grade
|  |  | Class Location | [6 empty] | Protective Coating | [8 empty] | Terrain description
Segment 3
| Length | [6 empty] | Diameter | [6 empty] | Wall Thickness |  |  |  | Grade
|  |  | Class Location | [6 empty] | Protective Coating | [8 empty] | Terrain description
Segment 4
| Length | [6 empty] | Diameter | [6 empty] | Wall Thickness |  |  |  | Grade
|  |  | Class Location | [6 empty] | Protective Coating | [8 empty] | Terrain description
Connection Information: | [14 empty] | Number of connections required | 5
Description: |  |  | 1 at Bloomfield, 3 at the Mainline, and 1 at Bisti
Hot Tap | [5 empty] | Tee & side valve
Header pipe:
| Diameter | [5 empty] | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Branch pipe:
| Diameter | [5 empty] | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Description:
Hot Tap | [5 empty] | Tee & side valve
Header pipe:
| Diameter | [5 empty] | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Branch pipe:
| Diameter | [5 empty] | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Note on H8: NT: Should specify: - Nearest City/Zip Code, State(s) - County, Block, Quadrant, Section, RR Survey (TX) - County/Parish, Section, Township, Range (other states) - Area, Block (offshore) - Latitude/Longitude, Lambert Corrdinates (X,Y) - Use worksheet "Addt'l Info" if more space is needed. Attach maps or drawings in additional worksheet tabs provided. Drawings should be in common readable formats such as .tif, .jpg, or .bmp.

## Pipeline 2
Pipeline Facilities Design Parameters
Delivery: |  |  | Receipt: |  |  | Bidirectional:
System/Line No.: | [10 empty] | Size: | 36" | [6 empty] | Connection Mile Post:
Project Location(s): |  |  |  |  | San Juan Junction - Station #4 Suction
|  |  |  | Beginning point | San Juan Lateral Junction
|  |  |  | Terminus point | Station #2 Suction
Conditions | [5 empty] | minimum |  | normal |  |  | high |  |  | MAOP/max |  |  | Gas Characteristics
|  |  |  | Pressure (psig) | [9 empty] | 1008 | [5 empty] | H2O (lbs/MMcf) | 6
|  |  |  | Volume (MMcfd) |  | 950 |  | 2058 |  |  | 2075 | [6 empty] | H2S
|  |  |  | Gas Quality(BTU, dry) |  | 985 |  | 1010 |  |  | 1016 |  |  | 1020 |  |  |  | CO2 |  |  | 2
other comp.-units
other comp.-units
Segment 1
| Length | 43.9 | [5 empty] | Diameter | 36" | [5 empty] | Wall Thickness | 0.388" |  |  | Grade | 65000
|  |  | Class Location | [6 empty] | Protective Coating | [8 empty] | Terrain description
Segment 2
| Length | 85.5 | [5 empty] | Diameter | 36" | [5 empty] | Wall Thickness | 0.388" |  |  | Grade | 65000
|  |  | Class Location | [6 empty] | Protective Coating | [8 empty] | Terrain description
Segment 3
| Length | 59.11 | [5 empty] | Diameter | 36" | [5 empty] | Wall Thickness | 0.388" |  |  | Grade | 65000
|  |  | Class Location | [6 empty] | Protective Coating | [8 empty] | Terrain description
Segment 4
| Length | [6 empty] | Diameter | [6 empty] | Wall Thickness |  |  |  | Grade
|  |  | Class Location | [6 empty] | Protective Coating | [8 empty] | Terrain description
Connection Information: | [14 empty] | Number of connections required | 8
Description: |  |  | Install 2nd loop line to the mainline.
Hot Tap | [5 empty] | Tee & side valve
Header pipe:
| Diameter | [5 empty] | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Branch pipe:
| Diameter | [5 empty] | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Description:
Hot Tap | [5 empty] | Tee & side valve
Header pipe:
| Diameter | [5 empty] | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Branch pipe:
| Diameter | [5 empty] | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Note on H8: NT: Should specify: - Nearest City/Zip Code, State(s) - County, Block, Quadrant, Section, RR Survey (TX) - County/Parish, Section, Township, Range (other states) - Area, Block (offshore) - Latitude/Longitude, Lambert Corrdinates (X,Y) - Use worksheet "Addt'l Info" if more space is needed. Attach maps or drawings in additional worksheet tabs provided. Drawings should be in common readable formats such as .tif, .jpg, or .bmp.

## Pipeline 3
Pipeline Facilities Design Parameters
Delivery: |  |  | Receipt: |  |  | Bidirectional:
System/Line No.: | [10 empty] | Size: | 30" | [6 empty] | Connection Mile Post:
Project Location(s): |  |  |  |  | Station #15 discharge to Phoenix
|  |  |  | Beginning point | Station #15 discharge
|  |  |  | Terminus point | Phoenix - southwest side
Conditions | [5 empty] | minimum |  | normal |  |  | high |  |  | MAOP/max |  |  | Gas Characteristics
|  |  |  | Pressure (psig) |  | 750 |  | 960 |  |  | 975 |  |  | 1008 | [5 empty] | H2O (lbs/MMcf) | 6
|  |  |  | Volume (MMcfd) |  | 200 |  | 400 |  |  | 550 |  |  | 450 |  |  |  | H2S
|  |  |  | Gas Quality(BTU, dry) |  | 985 |  | 1010 |  |  | 1016 |  |  | 1020 |  |  |  | CO2 |  |  | 2
other comp.-units
other comp.-units
Segment 1
| Length | 126 | [5 empty] | Diameter | 36" | [5 empty] | Wall Thickness | .338" |  |  | Grade | 65000
|  |  | Class Location | [6 empty] | Protective Coating | [8 empty] | Terrain description
Segment 2
| Length | [6 empty] | Diameter | [6 empty] | Wall Thickness |  |  |  | Grade
|  |  | Class Location | [6 empty] | Protective Coating | [8 empty] | Terrain description
Segment 3
| Length | [6 empty] | Diameter | [6 empty] | Wall Thickness |  |  |  | Grade
|  |  | Class Location | [6 empty] | Protective Coating | [8 empty] | Terrain description
Segment 4
| Length | [6 empty] | Diameter | [6 empty] | Wall Thickness |  |  |  | Grade
|  |  | Class Location | [6 empty] | Protective Coating | [8 empty] | Terrain description
Connection Information: | [14 empty] | Number of connections required
Description:
Hot Tap | [5 empty] | Tee & side valve
Header pipe:
| Diameter | [5 empty] | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Branch pipe:
| Diameter | [5 empty] | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Description:
Hot Tap | [5 empty] | Tee & side valve
Header pipe:
| Diameter | [5 empty] | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Branch pipe:
| Diameter | [5 empty] | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Note on H8: NT: Should specify: - Nearest City/Zip Code, State(s) - County, Block, Quadrant, Section, RR Survey (TX) - County/Parish, Section, Township, Range (other states) - Area, Block (offshore) - Latitude/Longitude, Lambert Corrdinates (X,Y) - Use worksheet "Addt'l Info" if more space is needed. Attach maps or drawings in additional worksheet tabs provided. Drawings should be in common readable formats such as .tif, .jpg, or .bmp.

## Compression 1
Compression Facilities Design Parameters
1) Station Name/number |  |  |  |  | Station #4 - Klagetoh
System/Line No.: | [12 empty] | Connection Mile Post: | MP570.3
Project Location(s): |  |  | McKinley Co., NM
Station Type: |  | New |  |  |  |  | Modification |  |  |  |  | Mainline |  | Gathering
Station HP required |  |  | 25000 | [7 empty] | Number of units | 1 |  |  |  |  | Ambient Temp Range | -20 to 105 |  |  |  | Elev. | 7300
[8 empty] | MAOP |  | 1008 | [10 empty] | MAOP |  | 1008
Suction Conditions |  |  | minimum |  |  | normal |  |  | high |  |  | Discharge Conditions |  |  |  | minimum |  |  | normal |  |  | high
|  | Pressure (psig) | 760 |  |  | 780 |  |  | 810 | [5 empty] | Pressure (psig) | 950 |  |  | 972 |  |  | 1008
|  | Temperature (degF) |  | 65 |  |  | 83 |  |  | 85 |  |  |  |  | Temperature (degF) |  | 105 |  |  | 110 |  |  | 120
|  | Volume (MMcfd) | 950 |  |  | 2105 |  |  | 2120 | [5 empty] | Volume (MMcfd) | 950 |  |  | 2105 |  |  | 2120
|  | Gas Quality(BTU, dry) | 985 |  |  | 1010 |  |  | 1020 | [5 empty] | Gas Quality(BTU, dry) | 985 |  |  | 1010 |  |  | 1020
2) Station Name/number |  |  |  |  | Station #15
System/Line No.: | [12 empty] | Connection Mile Post: | MP235.2
Project Location(s): |  |  | Coconino Co., AZ
Station Type: |  | New |  |  |  |  | Modification |  |  |  |  | Mainline |  | Gathering
Station HP required |  |  | 25000 | [7 empty] | Number of units | 1 |  |  |  |  | Ambient Temp Range | -20 to 105 |  |  |  | Elev. | 5120
[8 empty] | MAOP |  | 1008 | [10 empty] | MAOP |  | 1008
Suction Conditions |  |  | minimum |  |  | normal |  |  | high |  |  | Discharge Conditions |  |  |  | minimum |  |  | normal |  |  | high
|  | Pressure (psig) | 725 |  |  | 788 |  |  | 820 | [5 empty] | Pressure (psig) | 900 |  |  | 969 |  |  | 1008
|  | Temperature (degF) |  | 75 |  |  | 92 |  |  | 95 |  |  |  |  | Temperature (degF) |  | 135 |  |  | 140 |  |  | 145
|  | Volume (MMcfd) | 0 |  |  | 2085 |  |  | 2100 | [5 empty] | Volume (MMcfd) | 0 |  |  | 2085 |  |  | 2100
|  | Gas Quality(BTU, dry) | 985 |  |  | 1010 |  |  | 1020 | [5 empty] | Gas Quality(BTU, dry) | 985 |  |  | 1010 |  |  | 1020
Connection Information: | [12 empty] | Number of connections required
Description:
Hot Taps | [6 empty] | Block, tee, side valves
Header pipe:
| Diameter |  |  |  |  | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Branch pipe:
| Diameter |  |  |  |  | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Description:
Hot Taps | [6 empty] | Block, tee, side valves
Header pipe:
| Diameter |  |  |  |  | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Branch pipe:
| Diameter |  |  |  |  | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP

## Compression 2
Compression Facilities Design Parameters
1) Station Name/number |  |  |  |  | Kingman CS
System/Line No.: | [12 empty] | Connection Mile Post: | MP155.4
Project Location(s): |  |  | Mohave Co., AZ
Station Type: |  | New |  |  |  |  | Modification |  |  |  |  | Mainline |  | Gathering
Station HP required |  |  | 30000 | [7 empty] | Number of units | 1 |  |  |  |  | Ambient Temp Range | 120 |  |  |  | Elev. | 2600
[8 empty] | MAOP |  | 1008 | [10 empty] | MAOP |  | 1008
Suction Conditions |  |  | minimum |  |  | normal |  |  | high |  |  | Discharge Conditions |  |  |  | minimum |  |  | normal |  |  | high
|  | Pressure (psig) | 640 |  |  | 650 |  |  | 675 | [5 empty] | Pressure (psig) | 940 |  |  | 955 |  |  | 975
|  | Temperature (degF) |  | 85 |  |  | 92 |  |  | 98 |  |  |  |  | Temperature (degF) |  | 140 |  |  | 150 |  |  | 165
|  | Volume (MMcfd) | 1350 |  |  | 1410 |  |  | 1450 | [5 empty] | Volume (MMcfd) | 1350 |  |  | 1410 |  |  | 1450
|  | Gas Quality(BTU, dry) | 985 |  |  | 1010 |  |  | 1020 | [5 empty] | Gas Quality(BTU, dry) | 985 |  |  | 1010 |  |  | 1020
2) Station Name/number |  |  |  |  | Standing Rock CS
System/Line No.: | [12 empty] | Connection Mile Post: | MP 67.6
Project Location(s): |  |  | McKinley Co., NM
Station Type: |  | New |  |  |  |  | Modification |  |  |  |  | Mainline |  | Gathering
Station HP required |  |  | 9500 | [7 empty] | Number of units | 1 |  |  |  |  | Ambient Temp Range | 110 |  |  |  | Elev. | 6250
[8 empty] | MAOP |  | 1202 | [10 empty] | MAOP |  | 1202
Suction Conditions |  |  | minimum |  |  | normal |  |  | high |  |  | Discharge Conditions |  |  |  | minimum |  |  | normal |  |  | high
|  | Pressure (psig) | 870 |  |  | 900 |  |  | 920 | [5 empty] | Pressure (psig) | 980 |  |  | 1003 |  |  | 1020
|  | Temperature (degF) |  | 82 |  |  | 85 |  |  | 88 |  |  |  |  | Temperature (degF) |  | 88 |  |  | 90 |  |  | 95
|  | Volume (MMcfd) | 1500 |  |  | 1705 |  |  | 1730 | [5 empty] | Volume (MMcfd) | 1500 |  |  | 1705 |  |  | 1730
|  | Gas Quality(BTU, dry) | 985 |  |  | 1000 |  |  | 1007 | [5 empty] | Gas Quality(BTU, dry) | 985 |  |  | 1000 |  |  | 1007
Connection Information: | [12 empty] | Number of connections required
Description:
Hot Taps | [6 empty] | Block, tee, side valves
Header pipe:
| Diameter |  |  |  |  | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Branch pipe:
| Diameter |  |  |  |  | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Description:
Hot Taps | [6 empty] | Block, tee, side valves
Header pipe:
| Diameter |  |  |  |  | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Branch pipe:
| Diameter |  |  |  |  | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP

## Compression 3
Compression Facilities Design Parameters
1) Station Name/number |  |  |  |  | Bloomfield Add unit 5
System/Line No.: | [12 empty] | Connection Mile Post: | MP00
Project Location(s): |  |  | San Juan Co., NM
Station Type: |  | New |  |  |  |  | Modification |  |  |  |  | Mainline |  | Gathering
Station HP required |  |  | 7000 | [7 empty] | Number of units | 1 |  |  |  |  | Ambient Temp Range | 110 |  |  |  | Elev. | 5580
[8 empty] | MAOP |  | 1202 | [10 empty] | MAOP |  | 1202
Suction Conditions |  |  | minimum |  |  | normal |  |  | high |  |  | Discharge Conditions |  |  |  | minimum |  |  | normal |  |  | high
|  | Pressure (psig) | 850 |  |  | 870 |  |  | 900 | [5 empty] | Pressure (psig) | 1050 |  |  | 1077 |  |  | 1195
|  | Temperature (degF) |  | 85 |  |  | 90 |  |  | 95 |  |  |  |  | Temperature (degF) |  | 130 |  |  | 138 |  |  | 145
|  | Volume (MMcfd) | 575 |  |  | 595 |  |  | 625 | [5 empty] | Volume (MMcfd) | 575 |  |  | 595 |  |  | 625
|  | Gas Quality(BTU, dry) | 985 |  |  | 1010 |  |  | 1016 | [5 empty] | Gas Quality(BTU, dry) | 985 |  |  | 1010 |  |  | 1016
2) Station Name/number |  |  |  |  | Gallup Compr. Mods
System/Line No.: | [12 empty] | Connection Mile Post: | MP 96.83
Project Location(s): |  |  | McKinley Co., NM
Station Type: |  | New |  |  |  |  | Modification |  |  |  |  | Mainline |  | Gathering
Station HP required |  |  | 10000 | [7 empty] | Number of units | 1 |  |  |  |  | Ambient Temp Range | 110 |  |  |  | Elev. | 6500
[8 empty] | MAOP |  | 1202 | [10 empty] | MAOP |  | 1202
Suction Conditions |  |  | minimum |  |  | normal |  |  | high |  |  | Discharge Conditions |  |  |  | minimum |  |  | normal |  |  | high
|  | Pressure (psig) | 825 |  |  | 872 |  |  | 885 | [5 empty] | Pressure (psig) | 930 |  |  | 950 |  |  | 980
|  | Temperature (degF) |  | 82 |  |  | 85 |  |  | 88 |  |  |  |  | Temperature (degF) |  | 98 |  |  | 102 |  |  | 106
|  | Volume (MMcfd) | 1500 |  |  | 1705 |  |  | 1730 | [5 empty] | Volume (MMcfd) | 1500 |  |  | 1705 |  |  | 1730
|  | Gas Quality(BTU, dry) | 985 |  |  | 1010 |  |  | 1016 | [5 empty] | Gas Quality(BTU, dry) | 985 |  |  | 1010 |  |  | 1016
Connection Information: | [12 empty] | Number of connections required
Description:
Hot Taps | [6 empty] | Block, tee, side valves
Header pipe:
| Diameter |  |  |  |  | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Branch pipe:
| Diameter |  |  |  |  | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Description:
Hot Taps | [6 empty] | Block, tee, side valves
Header pipe:
| Diameter |  |  |  |  | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP
Branch pipe:
| Diameter |  |  |  |  | Wall Thickness | [5 empty] | Grade | [5 empty] | MAOP

## Addt'l Info
Additional Information (General Information, Scope, etc.):

## Addt'l Info2
Additional Information (General Information, Scope, etc.):

## Dwgs-Maps
Insert drawing files or map files in this worksheet (use formats: .tif, .jpg, .bmp)

## Dwgs-Maps2
Insert drawing files or map files in this worksheet (use formats: .tif, .jpg, .bmp)

## Instructions
Origination Date: provided by the Requestor
Revision Date, Number & Estimate Level.: provided by Facility Planner
General Information: As much information possible is completed by the Requestor, the remaining information(and revisions, if necessary) is completed by the Facility Planner. The Request Number is generated by the Facility Planner. In some cases, Scope and other information discovered may be further refined or revised to provide more detail about the work required.
Design Parameters: As much information possible is completed by the Requestor. The Facility Planner may revise or provide additional design parameters as discovered.
Facilities: As much information possible is completed by the Requestor. The Facility Planner may revise or provide additional design parameters as discovered.
Notifications and Estimated Costs: provided by the Facility Planner
Comments: provided by either the Requestor or the Facility Planner

## List Box info
Pipeline Name | Cost Estimate Level | Other Component, Units
Units?
Transwestern Pipeline Company | Level A (+/-30%) | mole %
Northern Natural Gas Company | Level B (+/-10%) | ppm
Florida Gas Transmission |  | grs/100cf
EOTT | Type of Expenditure
Other, specify |  | Type of Power Req'd
Reimbursable-Expense
Type of Measurement | Reimbursable-Capital | Purchase
| Capital-Prepaid | Solar
EFM only | Capital-Enron | Generator
Orifice | Expense, O&M | Provided by others
Turbine | Other, specify
Ultrasonic |  | Other Equipment Required
Positive Displ. | Type of Regulatory Filing
Bi-directional |  | Chromatograph
| "Auxiliary Installations" Sec 2.55a | Continuous sampler
Type of Compression | "Like for Like" Sec 2.55b | Pipeline valves
| "On behalf Of" Sec 311 | Station valves
Gas driven - reciprocal | "Automatic or Prior Notice" Blanket | Moisture monitor
Gas driven - centrifugal | "Abandonment or Construction" Sec 7 | Quality monitor
Gas driven - rotary/screw | Other, specify | Actuator/Controller
Electric driven - centrifugal |  | Cathodic Protection
| Type of Piping Required | C.P. Monitor
Other Gas Treating Facilities |  | C.P.-Anode
| Tap only | C.P.-Rectifier
Separation | Tap and riser
Dehydration | Tap and linepipe | Communications
CO2 Extraction | Tap, linepipe & station
Amine | Tap & station | CPU
Gas Cooler | Station only | Transmitter(s)
Gas Heater |  | CPU & Xmtrs.
Other, specify | Measurement | SCADA-phone line
SCADA-satelite
Type of Regulation | EFM | SCADA-tower/radio
Charts
Pressure Cntrl | Index | Pipeline
Flow Cntrl
P. & F. Cntrl | Flange Ratings | Lateral/Branchline
P. Cntrl w/ monitor |  | Mainline
P. & F. Cntrl w/ monitor | ANSI 150# | Loopline
F. Cntrl w/ monitor | ANSI 300# | Replace/refurbish/retire
Relief Valve | ANSI 600# | Lowering/Reroute
P. Cntrl w/ Rlf. Vlv | ANSI 900#
P. & F. Cntrl w/ Rlf. Vlv. |  | ROW type
F. Cntrl w/ Rlf. Vlv. | Environmental
Sand
ROW costs | Estimate only | Rock
| Mitigation/Study Req'd | Wooded
Estimate only |  | Marsh
Due Diligence Req'd |  | Swamp
Pasture
Cultivated
Populated